## Contents
GIM Activity: Sep 01, 2026 to Sep 30, 2026
Table of Contents
Disclaimer and References | Disclaimer on the use of this report, and references to associated ERCOT Binding Documents ***Please read***
Acronyms | A list of the various acronyms used throughout the report
Summary | Tables that provide project aggregate counts and megawatt capacities by GIM phase and fuel type
Project Details - Large Gen | A table that list project details for Large Generators as defined in ERCOT Planning Guide Section 5.2.1(3); only include projects for which a Full Interconnection Study has been requested
Project Details - Small Gen | A table that list project details for Small Generators as defined in ERCOT Planning Guide 5.2.1(3); only include projects for which the Resource Registration form has been approved by ERCOT
GIM Trends | Charts and tables that show historical and projected interconnection study trends
Commissioning Update | A table listing project commissioning approval milestones met for the month: energization, synchronization, and commercial operations approval
Inactive Projects | A table listing Inactive projects
Cancellation Update | A table listing the projects cancelled for the month
Time of Report Run: Oct 1, 2026 8:00:45 AM

## Disclaimer and References
Generator Interconnection Status Report - Disclaimer
FOR PLANNING PURPOSES ONLY
This ERCOT Working Paper has been prepared for specific ERCOT and Market Participant purposes, and has been
developed from data provided by Interconnecting Entities and Transmission Service Providers that has been entered into the online RIOO system.
The data may contain errors or be obsolete depending on when the data was entered. ERCOT MAKES NO WARRANTY, EXPRESS
OR IMPLIED,INCLUDING ANY WARRANTY OF MERCHANTABILITY OR FITNESS FOR ANY PARTICULAR PURPOSE,
AND DISCLAIMS ANY AND ALL LIABILITY WITH RESPECT TO THE ACCURACY OF SAME OR THE FITNESS OR
APPROPRIATENESS OF SAME FOR ANY PARTICULAR USE. THIS ERCOT WORKING PAPER IS SUPPLIED WITH ALL FAULTS.
References
The links below provide more information on the ERCOT interconnection process:
http://www.ercot.com/mktrules/guides/planning/current
See the Resource Interconnection Handbook, available on ERCOT’s Resource Integration webpage:
http://www.ercot.com/services/rq/integration

## GRIMES COUNTY
GIM Project Details - Large Generators
INR | Project Name | GIM Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  |  | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | Economic Study Required | IA Signed |  | Air Permit | GHG Permit | Water Availability | Meets Planning | Meets All Planning |  | Construction Start | Construction End | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Change indicators: Proj Name, MW | Approval Date for | [6 empty] | Financial Security |  |  |  | Guide Section 6.9(1) | Guide Section 6.9 | Meets Planning Guide
[11 empty] | Size, COD, SFS/NtP, FIS Request, | Submission of Proof of | [6 empty] | and Notice to |  |  |  | Requirements for | Requirements for | QSA (Section 5.9)
[11 empty] | Status Change INA-to-PLN | Site Control | [6 empty] | Proceed Provided |  |  |  | Inclusion in Planning | Inclusion in Planning | Prerequisites
[23 empty] | Models | Models
19INR0085 | Blue Jay Solar | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 Iola 138kV | Grimes | NORTH | 2025-09-30 | SOL | PV | 141.05 |  | 2018-02-15 | 2017-05-30 | 2017-08-11 | 2018-02-15 | 2021-04-26 | No | 2020-10-26 | Yes | Not Required | Not Required | Not Required | 2020-12-02 | 2021-04-26 | 2021-04-29 |  |  | 2021-11-11 | 2022-06-28
21INR0538 | Blue Jay Solar II | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 Iola 138kV | Grimes | NORTH | 2025-10-31 | SOL | PV | 68.95 |  | 2018-02-15 | 2021-04-13 | 2021-04-14 |  | 2021-04-26 | No | 2020-10-26 | Yes |  |  | Not Required | 2020-12-02 | 2021-04-26 | 2021-04-29 |  |  | 2021-11-11 | 2021-11-19
24INR0172 | Smith Lake Solar DC | SS Completed, FIS Started, IA | Smith Lake Solar | TAP 345 KV 44645 SINGLETON - 44900 ZENITH Ckt #99 | Grimes | NORTH | 2028-12-29 | SOL | PV | 402 |  | 2022-11-30 | 2022-02-07 | 2022-05-06 | 2022-11-02 |  | Yes | 2025-12-30 | No |  |  | Not Required
25INR0045 | Smith Lake Storage DC | SS Completed, FIS Started, IA | Smith Lake Solar | Tap 345kV 44645 Singleton - 44900 Zenith Ckt #99 | Grimes | NORTH | 2028-12-28 | OTH | BA | 65 |  | 2022-11-30 | 2022-03-07 | 2022-05-06 | 2022-11-02 |  | Yes | 2025-12-30 | No
26INR0001 | Turin TxHSR TPSS HN-6 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | 8 Crutchfield 138kV | Grimes | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-10-22 | 2019-09-27 | 2021-04-28 | 2019-09-27 |  |  |  | No
26INR0004 | GRIMES SOLAR | SS Completed, FIS Started, No IA | CG Grimes County LLC | 40600 Roans Prairie 345kV | Grimes | NORTH | 2026-02-15 | SOL | PV | 153.45 |  | 2022-03-09 | 2022-03-14 | 2022-06-03 | 2022-03-07 |  |  |  | No |  |  | Not Required
26INR0200 | Vaughn Energy Storage | SS Completed, FIS Completed, No IA | Vaughn Battery Storage, LLC | 13 Keith 138kV | Grimes | NORTH | 2027-12-31 | OTH | BA | 200.6 |  | 2023-08-21 | 2023-08-21 | 2023-11-17 | 2023-08-20 | 2025-12-19 |  |  | No
26INR0285 | Hill Valley BESS | SS Completed, FIS Completed, IA | Hill Valley BESS, LLC | 345 kV Singleton (#44645) | Grimes | NORTH | 2028-07-15 | OTH | BA | 245.8 |  | 2023-11-09 | 2023-12-04 | 2024-03-01 | 2023-11-10 | 2024-12-03 |  | 2026-04-21 | No
26INR0324 | Misty Hollow BESS | SS Completed, FIS Completed, IA | Clear Fork BESS, LLC | 345 kV Singleton (#44645) | Grimes | NORTH | 2028-07-15 | OTH | BA | 245.8 |  | 2023-12-06 | 2023-12-20 | 2024-03-15 | 2023-12-06 | 2025-03-04 |  | 2025-12-04 | No | Not Required | Not Required
26INR0370 | Central Power Station | SS Completed, FIS Started, No IA | Hydra-Gen Energy Unlimited | 967 Gibbons Creek 345kV | Grimes | NORTH | 2027-05-01 | GAS | GT | 750 |  |  | 2024-03-22 | 2024-06-19 | 2025-01-14 |  |  |  | No
27INR0085 | Eagle Claw Energy Center | SS Completed, FIS Started, IA | Eagle Claw Energy Center, LLC | Singleton (Bus #44645) - Zenith (Bus #44900) Circuit #99 345 kV | Grimes | NORTH | 2028-03-31 | OTH | BA | 204.58 |  | 2023-09-28 | 2023-10-13 | 2024-01-10 | 2023-10-06 |  | Yes | 2025-09-15 | Yes | Not Required | Not Required |  | 2026-03-24
27INR0115 | Diamante BESS | SS Completed, FIS Completed, No IA | BESS DIAMANTE LLC | 40600 ROANS__POI_5 345kV | Grimes | NORTH | 2028-11-01 | OTH | BA | 513.68 |  | 2025-01-17 | 2024-02-27 | 2024-05-24 | 2024-11-21 | 2025-10-09 | No |  | No
27INR0190 | Millsing BESS | SS Completed, FIS Completed, No IA | Millsing BESS | 44645 CNP Singleton 345kV | Grimes | NORTH | 2028-10-15 | OTH | BA | 501.6 |  | 2024-02-02 | 2024-02-27 | 2024-05-24 | 2024-02-05 | 2024-10-08 |  |  | No
27INR0379 | Scrap Iron Solar | SS Completed, FIS Started, No IA | Energiekontor US Texas SP 15 LLC | Tap 138kV (#9) Bedias - (#25) North Zulch | Grimes | NORTH | 2028-09-01 | SOL | PV | 110.77 |  | 2025-05-02 | 2024-09-10 | 2024-12-06 | 2025-04-23 |  |  |  | No |  |  | Not Required
28INR0394 | Treehouse Solar | SS Completed, FIS Started, No IA | Treehouse Solar, LLC | Tap the 345 kV Jewett (#3390) - Singleton (#44645) line | Grimes | NORTH | 2028-11-13 | SOL | PV | 281.77 |  | 2025-07-11 | 2025-07-29 | 2025-10-26 | 2025-09-03 |  | Yes |  | No |  |  | Not Required
28INR0395 | Treehouse Storage | SS Completed, FIS Started, No IA | Treehouse Solar, LLC | Tap the 345 kV Jewett (#3390) - Singleton (#44645) line, ONCOR | Grimes | NORTH | 2028-11-13 | OTH | BA | 209.21 |  | 2025-07-07 | 2025-07-29 | 2025-10-26 | 2025-09-03 |  | Yes |  | No
29INR0333 | Tyler Rose Power Plant 1 | SS Completed, FIS Started, No IA | ProEnergy Services, LLC | Tap 345 kV Circuit 18 (#44920) Mission - (#967) Gibbons Creek | Grimes | NORTH | 2029-07-01 | GAS | GT | 597.36 |  | 2026-05-13 | 2026-05-13 | 2026-08-06 | 2026-05-13 |  |  |  | No
29INR0336 | Tyler Rose Power Plant 2 | SS Completed, FIS Started, No IA | ProEnergy Services, LLC | Tap 345 kV Circuit 18 (#44920) Mission - (#967) Gibbons Creek | Grimes | NORTH | 2029-12-01 | GAS | GT | 398.24 |  | 2026-05-13 | 2026-05-13 | 2026-08-07 | 2026-05-13 |  |  |  | No

## Acronyms
Acronyms
GIM = Generator Interconnection or Modification request
GINR = Generation Interconnection or Change Request
COD = Commercial Operation Date
SS = Security Screening Study
FIS = Full Interconnection Study
IA = Interconnection Agreement; can be either of the following:
- Standard Generation Interconnection Agreement (SGIA)
- Public financially binding agreement
- An official letter from a Municipally Owned Utility or Electric Cooperative signifying developer intent to build and operate generation facilities and
interconnect with the MOU or EC
POI = Point of lnterconnection
INR = Interconnection Request Number
TSP = Transmission Service Provider
NtP = Notice-to-Proceed given to the TSP for interconnection construction
CDR = Capacity, Demand and Reserves Report
SFS = Sufficient Financial Security provided to the TSP for construction of the interconnection facilities
QSA = Quarterly Stability Assessment
INA = Inactive status
PLN = Planned status
Fuel Types | Technology Types
BIO = Biomass | BA = Battery Energy Storage
COA = Coal | CC = Combined-Cycle
GAS = Gas | CE = Compressed Air Energy Storage
GEO = Geothermal | CP = Concentrated Solar Power
HYD = Hydrogen | EN = Energy Storage
NUC = Nuclear | FC = Fuel Cell
OIL = Fuel Oil | GT = Combustion (gas) Turbine, but not part of a Combined-Cycle
OTH = Other | HY = Hydroelectric Turbine
PET = Petcoke | IC = Internal Combustion Engine, eg. Reciprocating
SOL = Solar | OT = Other
WAT = Water | PV = Photovoltaic Solar
WIN = Wind | ST = Steam Turbine other than Combined-Cycle
WT = Wind Turbine

## Summary
Summary |  |  | Major GIM Milestone Status by Fuel/Technology Type, MW
Currently tracking 1874 generation interconnection or change requests as of Sep 30, 2026 |  |  | Includes only those (1) Large Generator projects for which a Screening Study has been requested, (2) Small Generators for which an interconnection request has been made, and (3) projects that are not Inactive
GENERATION INTERCONNECTION REQUESTS CURRENTLY UNDER STUDY |  |  | Fuel | Technology | SS Started | SS Started | SS Completed | SS Completed | SS Completed | SS Started | SS Started | SS Completed | SS Completed | SS Completed | Small Generator | Small Generator | TOTAL
Includes only those (1) Large Generator projects for which a Screening Study has been requested, |  |  | Type | Type | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | FIS Not Started | FIS Started | FIS Not Started | FIS Started | FIS Completed | Not Model Ready | Model Ready
(2) Small Generators for which an interconnection request has been made and |  |  |  |  | No IA | No IA | No IA | No IA | No IA | IA | IA | IA | IA | IA
and (3) projects that are not Inactive
Status of SS, FIS and IA | Project Count | % of Total | Gas | Combined-Cycle |  | 4993.62 | 1708 | 28600.49 | 34.5 |  |  |  | 6860.4 | 1371 | 9.9 | 9.3 | 43587.21
LARGE GENERATORS |  |  | Gas | Combustion Turbine | 173 | 2780.5 | 18 | 13096.22 | 736.5 |  |  |  | 3178.71 | 4227.46 |  |  | 24210.39
SS Started, FIS Not Started, No IA | 8 | 0.4269% | Gas | Internal Combustion Engine |  | 832.88 |  | 9411.03 |  |  |  |  | 678.11 | 925.38 | 19.98 | 19.89 | 11887.27
SS Started, FIS Started, No IA | 50 | 2.668% | Gas | Compressed Air Energy Storage
SS Completed, FIS Not Started, No IA | 41 | 2.188% | Gas | Steam Turbine |  |  |  | 1335 | [5 empty] | 14 |  |  | 1349
SS Completed, FIS Started, No IA | 1009 | 53.84% | Gas | Fuel Cell
SS Completed, FIS Completed, No IA | 110 | 5.87% | Gas | Total gas | 173 | 8607 | 1726 | 52442.74 | 771 |  |  |  | 10717.22 | 6537.84 | 29.88 | 29.19 | 81033.87
SS Started, FIS Not Started, IA | 0 | 0% | Coal
SS Started, FIS Started, IA | 0 | 0% | Wind |  | 1351.4 | 2460.03 |  | 25737.83 | 287.02 |  |  | 486.4 | 11157.32 | 8266.02 |  |  | 49746.02
SS Completed, FIS Not Started, IA | 5 | 0.2668% | Solar |  | 800 | 5075.55 | 4650.92 | 73972.9 | 5995.8 |  |  | 304.94 | 33353.34 | 30928.83 | 30.68 | 9.9 | 155122.86
SS Completed, FIS Started, IA | 268 | 14.3% | Biomass
SS Completed, FIS Completed, IA | 316 | 16.86% | Other | Battery | 900 | 1269.82 | 4139.61 | 106027.68 | 11608.45 |  |  | 132.98 | 18170.7 | 19834.3 | 282.49 | 213.58 | 162579.61
SMALL GENERATORS |  |  | Other* |  |  | 1370 | 930 | 2980.15 | [7 empty] | 19.9 | 5300.05
Not Model Ready* | 36 | 1.921% | TOTAL |  | 3224.4 | 18782.4 | 11446.53 | 261161.3 | 18662.27 |  |  | 924.32 | 73398.58 | 65566.99 | 343.05 | 272.57 | 453782.41
Model Ready* | 31 | 1.654% | * Other includes petroleum coke (pet coke), hydroelectric, fuel oil, nuclear, geothermal energy, other miscellaneous fuels reported by developers, and fuel cells that use fuels other than natural gas.
Total Interconnection Requests | 1874
Inactive (since last month) | 13
Cancelled (since last month) | 26
Capacity, MW
Total Capacity Under Study | 453782.41
Interconnection Agreements Executed | 141384.86
Inactive (since last month) | 2056.16
Inactive changed to Planned (since last month) | 1059.22
Inactive changed to Cancelled (since last month) | 230.34
Cancelled (since last month) | 5419.99
* "Not Model Ready" means that a Small Generator's data has not yet been loaded into the Network
Operations Model. "Model Ready" means that the data has been loaded into the NOM, and the Resource is
ready to begin the commissioning process.

## Project Details - Large Gen
GIM Project Details - Large Generators
NOTES:
Due to Protocol confidentiality provisions, only those projects for which a Full Interconnection Study has been requested are included.
Excludes projects that have a status of Inactive (status = INA).
The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or
negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.
The construction start date is the date physical on-site work of a significant nature (such as excavation for footings or foundations or pouring of concrete for foundations)
has begun and is on-going. Additionally, major equipment items (such as turbines or step-up transformers) are on-site, in route to the site, or being manufactured under a
binding contract with significant financial commitments. The construction end date is the date when all plant systems are ready for commissioning/startup activities. Note
that the reporting of Construction Start and End Dates will not begin until ERCOT's online GIM system is available to project developers for data entry.
Blank cells on Air Permit, GHG Permit and Water Availability indicate the emission permits/proof of water supplies are required but have not been obtained or reported to ERCOT yet.
A developer may split a project into two or more additional projects with different INR numbers during the interconnection request process. Due to current RIOO interface limitations,
the new projects do not inherit certain milestone dates entered for the original project. As a result, dates may be blank even though the milestones have been met.
A “1-1-1900” date is used to signify that an actual date for a project milestone is not available. This typically occurs for project data migrated from the legacy GINR database to the RIOO system.
Project Attributes | [10 empty] | Changes from Last Report | GIM Project Milestone Dates
INR | Project Name | GIM Study Phase | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) |  |  | Screening Study Started | Screening Study Complete | FIS Requested | FIS Approved | Economic Study Required | IA Signed |  | Air Permit | GHG Permit | Water Availability | Meets Planning | Meets All Planning |  | Construction Start | Construction End | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Change indicators: Proj Name, MW | Approval Date for | [6 empty] | Financial Security |  |  |  | Guide Section 6.9(1) | Guide Section 6.9 | Meets Planning Guide
[11 empty] | Size, COD, SFS/NtP, FIS Request, | Submission of Proof of | [6 empty] | and Notice to |  |  |  | Requirements for | Requirements for | QSA (Section 5.9)
[11 empty] | Status Change INA-to-PLN | Site Control | [6 empty] | Proceed Provided |  |  |  | Inclusion in Planning | Inclusion in Planning | Prerequisites
[23 empty] | Models | Models
22INR0541 | ALWEST BESS | SS Completed, FIS Started, No IA | Castleman Power | 3114 Paltalco 138kV | Anderson | NORTH | 2028-04-19 | OTH | BA | 208.63 |  | 2021-05-17 | 2021-08-24 | 2021-11-15 | 2021-06-03 |  |  |  | No
23INR0289 | Skull Creek Solar | SS Completed, FIS Completed, IA | Skull Creek Solar, LLC | Tap 138kV 3281 Tennessee Colony - 3499 Blackfoot Massey Lake Switch in TSP’s Pin Oak Switch - Long Lake Substation | Anderson | NORTH | 2027-06-30 | SOL | PV | 136.98 | COD | 2022-01-10 | 2021-05-28 | 2021-08-19 | 2021-12-16 | 2026-09-18 | No | 2024-05-20 | No | Not Required | Not Required | Not Required
23INR0439 | Lumen Farm Solar SLF | SS Completed, FIS Started, No IA | Neches Solar, LLC | Tap 138kV 3325 Blackburn Switch – 3272 Palestine | Anderson | NORTH | 2028-09-30 | SOL | PV | 201.04 |  | 2021-12-29 | 2022-01-06 | 2022-03-31 | 2021-12-29 |  | No |  | No |  |  | Not Required
24INR0450 | Lumen Farm BESS SLF | SS Completed, FIS Started, No IA | Neches Solar, LLC | Tap 138kV 3325 Blackburn Switch – 3272 Palestine | Anderson | NORTH | 2028-09-30 | OTH | BA | 0 |  | 2022-11-11 | 2022-11-15 | 2023-02-09 | 2022-10-28 |  | No |  | No
25INR0432 | Brotherton Storage | SS Completed, FIS Started, IA | BT Brotherton Storage, LLC | 6937 Tucker Sub 138kV | Anderson | NORTH | 2027-05-01 | OTH | BA | 176.13 |  | 2023-04-12 | 2023-04-19 | 2023-07-13 | 2023-04-12 |  | No | 2024-08-06 | Yes |  |  |  | 2025-09-15
28INR0094 | Pham BESS | SS Completed, FIS Not Started, IA | ASB1, LLC | Tap 138kV 3281 TENNCLNY_8 - 3499 BLACKFTAP_8 | Anderson | NORTH | 2028-09-18 | OTH | BA | 132.98 |  | 2024-08-30 | 2024-06-13 | 2024-09-10 |  |  |  | 2026-07-31 | Yes | Not Required | Not Required | 2026-08-11 | 2026-08-11
31INR0021 | Mule Deer Run Gas II | SS Completed, FIS Started, No IA | Anderson Energy Center, LLC | #3308 Pin Oak 345KV | Anderson | NORTH | 2032-07-01 | GAS | CC | 1263 |  | 2026-06-01 | 2026-06-04 | 2026-08-21 | 2026-06-01 |  |  |  | No
31INR0022 | Mule Deer Run Gas III | SS Completed, FIS Started, No IA | Anderson Energy Center, LLC | #3308 Pin Oak 345KV | Anderson | NORTH | 2032-07-01 | GAS | CC | 1263 |  | 2026-06-01 | 2026-06-04 | 2026-08-21 | 2026-06-01 |  |  |  | No
32INR0003 | Mule Deer Run Gas | SS Completed, FIS Started, No IA | Anderson Energy Center, LLC | #3308 Pin Oak 345KV | Anderson | NORTH | 2031-07-01 | GAS | CC | 1263 |  | 2025-11-05 | 2025-11-18 | 2026-01-19 | 2025-11-06 |  |  |  | No
19INR0103 | Rodeo Solar | SS Completed, FIS Started, IA | Core Solar SPV I, LLC | 138kV 11273 NELSON SWITCH | Andrews | WEST | 2026-11-30 | SOL | PV | 200 |  | 2018-02-19 | 2017-06-29 | 2017-08-04 | 2018-02-19 |  |  | 2019-08-20 | Yes | Not Required | Not Required | Not Required | 2021-03-10 | 2022-11-01
22INR0427 | BRP Kabru BESS | SS Completed, FIS Started, No IA | BRP Kabru BESS LLC | 1159 Andrew North - 11284 Blackbird 138kV | Andrews | WEST | 2028-12-01 | OTH | BA | 202.45 |  | 2020-09-28 | 2020-10-07 | 2020-12-28 | 2020-09-22 |  | No |  | No
23INR0104 | BRP Kamet BESS | SS Completed, FIS Started, No IA | BRP Kamet BESS LLC | Andrews North – McKenzie Draw Switch 138 kV | Andrews | WEST | 2025-12-01 | OTH | BA | 202.46 |  | 2020-09-28 | 2020-10-07 | 2020-12-30 | 2020-09-23 |  | No |  | No
23INR0278 | Tucana BESS | SS Completed, FIS Completed, No IA | BRP Tucana BESS LLC | 1157 Andrews County South 138kV | Andrews | WEST | 2028-03-01 | OTH | BA | 201.3 |  | 2021-06-01 | 2021-06-03 | 2021-08-19 | 2021-05-10 | 2025-06-18 | No |  | No
23INR0279 | Trivor BESS | SS Completed, FIS Started, No IA | BRP Trivor BESS LLC | 1272 Fullerton 138kV | Andrews | WEST | 2028-03-01 | OTH | BA | 205.46 |  | 2021-06-01 | 2021-06-03 | 2022-03-15 | 2021-05-10 |  | No |  | No
27INR0384 | Straight Spur Wind | SS Completed, FIS Started, No IA | ENGIE IR Holdings LLC | Tap 345 kV 23876 Clear Fork -11157 Gardenale Switch | Andrews | WEST | 2029-04-01 | WIN | WT | 247.4 |  | 2024-12-06 | 2024-12-19 | 2025-02-03 | 2024-12-06 |  |  |  | No |  |  | Not Required
27INR0385 | Straight Spur Solar | SS Completed, FIS Started, No IA | ENGIE IR Holdings LLC | Tap 345 kV ClearFork (Bus #23876) to Gardenale Switch (Bus #11157) | Andrews | WEST | 2029-04-01 | SOL | PV | 251.8 |  | 2024-10-17 | 2024-11-21 | 2025-02-18 | 2024-11-08 |  |  |  | No |  |  | Not Required
27INR0386 | Straight Spur Storage | SS Completed, FIS Started, No IA | ENGIE IR Holdings LLC | Tap 345kV ClearFork( Bus # 23876) to Gardenale Switch (Bus # 11157) | Andrews | WEST | 2029-04-01 | OTH | BA | 306.2 |  | 2024-11-14 | 2024-11-19 | 2025-02-18 | 2024-11-08 |  |  |  | No
30INR0135 | Blue Sage Wind | SS Started, FIS Started, No IA | CPV Blue Sage Wind, LLC | BUS #11270 - DOGHOUSE_5 - THE DOGHOUSE 345kV SUBSTATION | Andrews | WEST | 2030-04-23 | WIN | WT | 394.54 | MW Size COD | 2026-07-13 | 2026-07-22 |  | 2026-07-21 |  |  |  | No |  |  | Not Required
19INR0110 | Azalea Springs Solar | SS Completed, FIS Completed, IA | AZALEA SPRINGS SOLAR PARK LLC | tap 138kV Jim English – Lufkin Chipper Mill | Angelina | NORTH | 2026-11-01 | SOL | PV | 181 | COD | 2018-03-15 | 2017-07-26 | 2017-09-15 | 2018-03-15 | 2024-04-30 | No | 2023-09-14 | Yes | Not Required | Not Required | Not Required | 2024-05-01 | 2024-05-01 | 2024-05-01 |  |  | 2025-01-29 | 2025-02-11
24INR0174 | Solar Star North Herty Storage | SS Completed, FIS Started, No IA | Solar Star North Herty Storage, LLC | 3307 Redland Switch 138 kV | Angelina | NORTH | 2027-08-25 | OTH | BA | 125.9 |  | 2022-09-09 | 2022-02-21 | 2022-05-21 | 2022-08-15 |  |  |  | No
26INR0294 | Longleaf Power Station | SS Completed, FIS Started, No IA | WattBridge Texas Holdings, LLC | Redland Substation (# 3321) | Angelina | NORTH | 2029-03-31 | GAS | GT | 600 |  | 2023-10-04 | 2023-10-13 | 2024-01-09 | 2023-10-04 |  | No |  | No | Not Required | Not Required
27INR0247 | Sun Angel ESS | SS Completed, FIS Completed, No IA | Sun Angel ESS LLC | Tap 138kV LUFKINE East (#3326) - HERTY TAP (#3318) | Angelina | NORTH | 2028-09-21 | OTH | BA | 201.54 |  | 2024-06-03 | 2024-06-13 | 2024-08-07 | 2024-06-11 | 2026-09-01 | No |  | No
30INR0114 | Longleaf II Power Station | SS Completed, FIS Started, No IA | WattBridge Texas Holdings, LLC | 3321 Redland 345 kV | Angelina | NORTH | 2030-07-01 | GAS | GT | 600 |  | 2026-05-03 | 2026-05-11 | 2026-08-07 | 2026-04-20 |  |  |  | No
25INR0583 | Shannon Wind Repower | SS Completed, FIS Started, No IA | Shannon Wind, LLC | 1458 Cobb Switching Station 345 kV | Archer | WEST | 2027-09-15 | WIN | WT | 18.52 |  | 2024-02-26 | 2024-02-27 | 2024-05-31 | 2024-01-29 |  |  |  | No |  |  | Not Required
25INR0616 | Bobcat Bluff Storage SLF | SS Completed, FIS Completed, IA | Cub Storage LLC | 1475 Windthorst 138 kV | Archer | WEST | 2027-04-15 | OTH | BA | 0 |  | 2024-06-18 | 2024-02-27 | 2024-05-25 | 2024-06-12 | 2026-06-17 | No | 2026-01-12 | No |  |  |  | 2026-07-31 | 2026-07-31 | 2026-07-31
25INR0628 | Wichita Falls Energy Storage | SS Completed, FIS Started, No IA | Wichita Falls Energy Storage LLC | Tap 345kV 1422 Bowman - 1458 Cobb Switch | Archer | WEST | 2028-08-01 | OTH | BA | 202 |  | 2024-01-30 | 2024-02-26 | 2024-05-25 | 2024-02-14 |  |  |  | No | Not Required | Not Required
26INR0295 | Trinity Hills BESS SLF | SS Completed, FIS Started, No IA | Phoenix Battery Storage, LLC | To the 345 kV Garvey Road Switch (#17002) | Archer | WEST | 2028-01-24 | OTH | BA | 94 |  | 2023-11-13 | 2023-11-30 | 2024-02-26 | 2023-11-03 |  | No |  | No
27INR0279 | Red Hollow Renewable Energy BESS SLF | SS Completed, FIS Started, No IA | Red Hollow Renewable Energy LLC | Tap 345kV 1422 Bowman - 17002 Garvey Road | Archer | WEST | 2029-04-19 | OTH | BA | 0 |  | 2024-06-04 | 2024-06-13 | 2025-08-04 | 2024-06-04 |  |  |  | No
28INR0088 | Red Hollow Renewable Energy Solar SLF | SS Completed, FIS Started, No IA | Red Hollow Renewable Energy LLC | Tap 345kV (Bus# 1422) Bowman - (Bus# 17002) Garvey Road | Archer | WEST | 2029-04-19 | SOL | PV | 308.61 |  | 2024-06-04 | 2024-07-01 | 2024-10-04 | 2024-06-04 |  |  |  | No |  |  | Not Required
28INR0348 | Ringtail Energy Storage | SS Completed, FIS Started, No IA | PowerPulse LLC | Bus # 1446, Lake Wichita, 138 kV | Archer | WEST | 2028-12-15 | OTH | BA | 203.8 |  | 2025-04-15 | 2025-04-25 | 2025-07-22 | 2025-04-23 |  |  |  | No
23INR0637 | Goodnight Wind II | SS Completed, FIS Completed, IA | FGE Goodnight II, LLC | tap 345kV 23900 Alibates - 23914 Tule Canyon CKT2 | Armstrong | PANHANDLE | 2027-06-06 | WIN | WT | 261.1 |  | 2023-04-28 | 2023-04-19 | 2023-04-19 | 2023-05-01 | 2026-06-15 | No | 2019-08-18 | Yes | Not Required | Not Required | Not Required | 2023-05-01 | 2023-05-01 | 2026-07-31
25INR0586 | Zeus Armstrong Solar | SS Completed, FIS Started, No IA | Armstrong Solar, LLC | Tap 345KV 23900 AlLIBATES -23914 TULECNYN | Armstrong | PANHANDLE | 2028-04-17 | SOL | PV | 503.56 |  | 2024-08-01 | 2024-05-20 | 2024-06-19 | 2024-07-22 |  |  |  | No |  |  | Not Required |  |  |  | 2026-01-01 | 2027-03-01
25INR0587 | Zeus Armstrong BESS | SS Completed, FIS Started, No IA | Armstrong BESS, LLC | Tap 345KV 23900 ALIBATES - 23914 TULECNYN CKT1 & CKT2 | Armstrong | PANHANDLE | 2028-04-17 | OTH | BA | 1043.08 |  | 2024-08-12 | 2024-03-22 | 2024-06-19 | 2024-08-08 |  |  |  | No | [6 empty] | 2026-01-01 | 2027-03-01
27INR0443 | Serenity Wind | SS Completed, FIS Started, No IA | Serenity Wind, LLC | 23931 MIDPOINT SWITCH 345 kV | Armstrong | PANHANDLE | 2028-09-18 | WIN | WT | 473 |  | 2025-03-06 | 2025-03-24 | 2025-06-09 | 2025-03-07 |  | No |  | No |  |  | Not Required
28INR0215 | Complex Serenity Wind | SS Completed, FIS Started, No IA | Serenity Wind, LLC | Double tap 345 kV Alibates (bus# 23900) to Tule Canyon (bus# 23914) and Tule Canyon (bus# 23914) to Midpoint Switch (bus# 23931) | Armstrong | PANHANDLE | 2029-04-16 | WIN | WT | 971 |  | 2025-04-22 | 2025-06-05 | 2025-09-02 | 2025-04-30 |  |  |  | No |  |  | Not Required
21INR0391 | Grandslam Solar | SS Completed, FIS Started, IA | Grandslam Solar, L.L.C. | 5700 Miracle Lake 138kV | Atascosa | SOUTH | 2027-10-01 | SOL | PV | 121.89 |  | 2019-09-03 | 2019-07-29 | 2019-10-30 | 2019-07-26 |  |  | 2021-01-29 | No | Not Required | Not Required | Not Required
23INR0200 | Paradiso BESS | SS Completed, FIS Started, IA | VESI 13 | 8203 Pleasanton 138kV | Atascosa | SOUTH | 2028-03-15 | OTH | BA | 102.3 |  | 2021-09-03 | 2021-03-01 | 2021-05-13 | 2021-08-20 |  | No | 2025-04-18 | Yes | Not Required | Not Required
25INR0082 | Reis Solar | SS Completed, FIS Started, No IA | Greenalia Solar Power Reis LLC | Tapping into 138 kV line (5689) Choke Canyon AEP to (5902) San Miguel Gen | Atascosa | SOUTH | 2027-08-03 | SOL | PV | 105.48 |  | 2022-09-19 | 2022-06-02 | 2022-08-29 | 2022-09-09 |  |  |  | No |  |  | Not Required
26INR0654 | Great Hambino BESS | SS Completed, FIS Started, No IA | Atascosa BESS, LLC | #5700 Miracle Lake Substation 138kV | Atascosa | SOUTH | 2028-10-01 | OTH | BA | 122.98 | COD | 2025-09-10 | 2025-09-11 | 2025-11-12 | 2025-09-10 |  |  |  | No
27INR0305 | Kurtz Solar SLF | SS Completed, FIS Started, No IA | Kurtz Solar, LLC | Tap 69kV #8206 Charlotte - #8607 Jourdanton | Atascosa | SOUTH | 2029-05-31 | SOL | PV | 101.9 |  | 2024-08-29 | 2024-09-04 | 2024-12-02 | 2024-08-05 |  | No |  | No |  |  | Not Required
27INR0306 | Kurtz Storage SLF | SS Completed, FIS Started, No IA | Kurtz Storage, LLC | Tap 69kV #8206 Charlotte - #8607 Jourdanton | Atascosa | SOUTH | 2029-05-31 | OTH | BA | 0 |  | 2024-08-29 | 2024-09-04 | 2024-12-02 | 2024-08-26 |  | No |  | No
27INR0396 | Bluewind BESS | SS Completed, FIS Started, No IA | Bluewind Energy Center, LLC | 5713 Oaks Substation 138kV | Atascosa | SOUTH | 2029-07-02 | OTH | BA | 246.5 |  | 2025-04-22 | 2025-04-25 | 2025-07-22 | 2025-05-15 |  |  |  | No
28INR0208 | Strawberry Dunes Solar SLF | SS Completed, FIS Started, No IA | Strawberry Dunes LLC | Tap 138kV ROSSVILLESB8 (5718) to OAKSSW8 (5713) | Atascosa | SOUTH | 2028-06-30 | SOL | PV | 101.1 |  | 2024-12-23 | 2025-02-14 | 2025-05-12 | 2025-02-11 |  | No |  | No |  |  | Not Required
28INR0209 | Strawberry Dunes BESS SLF | SS Completed, FIS Started, No IA | Strawberry Dunes LLC | Tap 138kV ROSSVILLESB8 (5718) to OAKSSW8 (5713) | Atascosa | SOUTH | 2028-06-30 | OTH | BA | 0 |  | 2024-12-23 | 2025-02-14 | 2025-05-12 | 2025-02-11 |  | No |  | No
28INR0343 | Amphion Solar Phase 2 | SS Completed, FIS Started, No IA | Amphion Solar, LLC | TAP 345KV (#5709) Fowlerton - (#5901) SAN MIGUEL LINE Ckt-2 | Atascosa | SOUTH | 2029-05-15 | SOL | PV | 205.9 |  | 2025-03-28 | 2025-04-21 | 2025-07-19 | 2025-04-09 |  |  |  | No |  |  | Not Required
28INR0344 | Amphion Solar Phase 3 | SS Completed, FIS Started, No IA | Amphion Solar, LLC | TAP 345KV (#5709) Fowlerton - (#5901) SAN MIGUEL LINE Ckt-2 | Atascosa | SOUTH | 2029-11-15 | SOL | PV | 115.4 |  | 2025-03-28 | 2025-04-21 | 2025-07-19 | 2025-04-09 |  |  |  | No |  |  | Not Required
28INR0463 | Mutz Solar | SS Completed, FIS Started, No IA | AETS Development Holdings LLC | Tap 69 kV 5693 San Miguel Tap - 5698 North Calliham Sub | Atascosa | SOUTH | 2028-06-30 | SOL | PV | 72.82 |  | 2026-01-09 | 2026-01-13 | 2026-02-09 | 2026-01-06 |  | No |  | No |  |  | Not Required
29INR0050 | Amphion Solar Phase 1 | SS Completed, FIS Started, No IA | Amphion Solar, LLC | TAP 345KV (#5709) Fowlerton - (#5901) SAN MIGUEL LINE Ckt FOWRTN_SMIGL2 | Atascosa | SOUTH | 2028-09-01 | SOL | PV | 180.6 |  | 2024-10-10 | 2024-10-10 | 2025-01-07 | 2024-10-10 |  |  |  | No |  |  | Not Required
29INR0214 | Amphion Storage | SS Completed, FIS Started, No IA | Amphion Solar, LLC | TAP 345KV (#5709) Fowlerton - (#5901) SAN MIGUEL LINE Ckt-2 | Atascosa | SOUTH | 2029-05-15 | OTH | BA | 200 |  | 2026-02-03 | 2026-02-10 | 2026-03-26 | 2026-01-29 |  | No |  | No
26INR0229 | Pamplona Solar | SS Completed, FIS Completed, No IA | Karol Solar III | Tap 138 kV 44740 WALLIS_S65_8 - 44700 GEBHRT_X65B8 Ckt#65 | Austin | SOUTH | 2028-10-17 | SOL | PV | 42.38 |  | 2024-10-08 | 2023-08-14 | 2023-11-03 | 2024-06-18 | 2025-07-25 |  |  | No |  |  | Not Required
26INR0410 | Prost ESS | SS Completed, FIS Started, No IA | Prost ESS LLC | Tap 138kV L_PISEK_8_1Y (#7296) - L_WELCOM8_1Y(#7577) | Austin | SOUTH | 2028-09-08 | OTH | BA | 202.7 |  | 2024-02-12 | 2024-02-27 | 2024-05-20 | 2024-02-12 |  |  |  | No
26INR0427 | BremRaek BESS | SS Completed, FIS Started, No IA | BremRaek BESS | 7271 LCRA New Bremen 138 kV | Austin | SOUTH | 2027-11-14 | OTH | BA | 200.6 |  | 2024-02-29 | 2024-03-22 | 2024-06-19 | 2024-02-28 |  |  |  | No
26INR0466 | Symphony BESS | SS Completed, FIS Started, No IA | Symphony BESS, LLC | 46220 PETERS | Austin | SOUTH | 2028-07-01 | OTH | BA | 612 |  | 2025-01-28 | 2025-02-14 | 2025-04-22 | 2025-01-28 |  |  |  | No
26INR0519 | Sky Global West Houston | SS Completed, FIS Completed, IA | Sky Global Power Two, LLC | tap 138kV 44700 Gebhardt - 44740 Wallis circuit 65 | Austin | SOUTH | 2028-06-01 | GAS | IC | 324.58 | COD | 2024-05-29 | 2024-07-01 | 2024-10-04 | 2024-06-04 | 2025-03-12 | Yes | 2025-03-25 | No
27INR0252 | Parula Energy Center | SS Completed, FIS Started, No IA | Parula Energy Center | 7287 Bellville North 138kV | Austin | SOUTH | 2029-06-18 | OTH | BA | 250.95 | COD | 2024-05-10 | 2024-05-20 | 2024-08-15 | 2024-05-09 |  |  |  | No
28INR0061 | Sunrose Renewable Energy Solar SLF | SS Completed, FIS Completed, No IA | Sunrose Renewable Energy LLC | Tap 138kV #44740 WALLIS - #44700 GEBHRT | Austin | SOUTH | 2029-07-04 | SOL | PV | 309.88 |  | 2024-04-05 | 2024-04-09 | 2024-07-05 | 2024-03-29 | 2025-09-11 | No |  | No |  |  | Not Required
28INR0066 | Sunrose Renewable Energy Storage SLF | SS Completed, FIS Completed, No IA | Sunrose Renewable Energy LLC | Tap 138kV 44740 WALLIS - 44700 GEBHRT | Austin | SOUTH | 2029-07-04 | OTH | BA | 0 |  | 2024-03-19 | 2024-04-15 | 2024-07-05 | 2024-04-12 | 2025-09-11 | No |  | No
28INR0089 | EmberYork | SS Completed, FIS Completed, IA | EmberYork Energy Center | TAP 138kV WALLIS 44740 - GERBHRT 44700 | Austin | SOUTH | 2028-01-01 | GAS | GT | 900 |  | 2024-12-30 | 2024-08-29 | 2024-08-29 | 2024-12-11 | 2025-07-14 | Yes | 2025-12-12 | No
28INR0186 | Saddlehorn Energy Storage | SS Completed, FIS Started, No IA | Saddlehorn Energy Storage, LLC | Tap 138kV 7287 Bellville North - 7291 Highway 36 | Austin | SOUTH | 2028-11-01 | OTH | BA | 256.8 |  | 2024-11-25 | 2024-11-26 | 2025-02-18 | 2024-12-03 |  | No |  | No
28INR0226 | Pamplona Storage | SS Completed, FIS Completed, No IA | Karol Solar V | Tap 138 kV 44740 WALLIS_S65_8 - 44700 GEBHRT_X65B8 Ckt#65 | Austin | SOUTH | 2028-10-17 | OTH | BA | 153.88 |  | 2025-07-07 | 2024-12-19 | 2025-03-18 | 2025-06-25 | 2025-08-26 |  |  | No
28INR0265 | Agricola BESS | SS Completed, FIS Started, No IA | Agricola BESS LLC | Tap 138kV GEBHARDT (#44700) - Wallis (#44740) | Austin | SOUTH | 2029-05-31 | OTH | BA | 205.2 |  | 2025-01-24 | 2025-03-24 | 2025-06-09 | 2025-02-12 |  | No |  | No
29INR0041 | Homestead Power (TEF-Due Diligence) | SS Completed, FIS Started, No IA | Homestead Power LLC | 138 kV New Bremen #7271 | Austin | SOUTH | 2029-12-15 | GAS | GT | 260.3 |  | 2024-07-29 | 2024-07-30 | 2024-10-27 | 2024-07-29 |  |  |  | No
23INR0078 | Shaw Solar | SS Completed, FIS Completed, IA | Rio Lago Solar, LLC | Tap 138kV 7146 Verde Creek - 7438 Bandera | Bandera | SOUTH | 2026-10-16 | SOL | PV | 124.65 |  | 2021-05-21 | 2020-10-23 | 2021-01-12 | 2021-05-11 | 2025-03-12 | No | 2023-02-17 | Yes | Not Required | Not Required | Not Required | 2025-03-26 | 2025-04-30 | 2025-04-30 |  |  | 2026-06-04 | 2026-07-31
26INR0194 | Motif BESS II | SS Completed, FIS Started, No IA | Motif Storage, LLC | 7440 Tarpley 138kV | Bandera | SOUTH | 2029-02-19 | OTH | BA | 201.13 |  | 2024-11-04 | 2024-11-19 | 2025-02-18 | 2024-10-29 |  |  |  | No
25INR0422 | Waterloo Solar 1 | SS Completed, FIS Completed, IA | Waterloo Solar 1, LLC | Tap 345-kV 7040 Austrop to 7042 Zorn | Bastrop | SOUTH | 2027-12-01 | SOL | PV | 200.64 |  | 2023-04-18 | 2023-04-19 | 2023-07-12 | 2023-03-30 | 2026-09-18 | Yes | 2024-09-04 | No |  |  | Not Required
25INR0447 | Waterloo BESS 1 | SS Completed, FIS Started, IA | Waterloo BESS, LLC | Tap 345-kV 7040 Austrop to 7042 Zorn | Bastrop | SOUTH | 2028-12-15 | OTH | BA | 120 | COD | 2023-05-03 | 2023-05-15 | 2023-08-11 | 2023-05-03 |  | Yes | 2024-09-04 | No | Not Required | Not Required
26INR0045 | LUND STORAGE CENTER 1 | SS Completed, FIS Started, No IA | Lund Storage Center 1, LLC | TAP 138 KV LINE AND CREATE NEW BUS BETWEEN KIMBRO (7337) AND ELGIN SWITCH (3650) | Bastrop | SOUTH | 2029-10-31 | OTH | BA | 407.55 |  | 2023-05-26 | 2023-01-17 | 2023-04-14 | 2023-05-16 |  |  |  | No
26INR0261 | Bastrop Peaking Generators (TEF-Due Diligence) | SS Completed, FIS Started, IA | MPH Bastrop Peakers, LLC | 7048 L_GARFIE5_1Y 345kV | Bastrop | SOUTH | 2027-12-07 | GAS | GT | 1104 |  | 2024-04-09 | 2024-02-02 | 2024-05-01 | 2024-03-15 |  |  | 2025-12-19 | No
26INR0511 | Little Star Solar | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | #9043 CISTERN 345kV | Bastrop | SOUTH | 2027-12-31 | SOL | PV | 61.6 |  | 2024-06-20 | 2024-07-01 | 2024-09-23 | 2024-06-12 |  |  |  | No |  |  | Not Required
26INR0514 | Techne BESS | SS Completed, FIS Started, No IA | Techne BESS, LLC | 7560 RED ROCK 138kV | Bastrop | SOUTH | 2028-12-31 | OTH | BA | 202.7 |  | 2024-09-05 | 2024-09-10 | 2024-12-08 | 2024-09-05 |  |  |  | No
26INR0560 | Fort Worth Power Core Bastrop Gas Plant | SS Completed, FIS Started, No IA | Fort Worth Power Core LLC | Tap 345kV 7042 ZORN - 7040 AUSTROP | Bastrop | SOUTH | 2029-09-28 | GAS | CC | 506.38 |  | 2025-05-05 | 2025-05-27 | 2025-08-22 | 2025-04-30 |  |  |  | No | 2024-12-20 |  | 2025-11-19
29INR0166 | LOST PINES GAS RECIP | SS Completed, FIS Started, IA | LCRA | (#170174) LOST PINES 345 kV | Bastrop | SOUTH | 2033-06-01 | GAS | IC | 113.02 |  | 2025-06-27 | 2025-07-07 | 2025-09-30 | 2025-07-02 |  | Yes | 2025-12-26 | No
30INR0051 | Sim Gideon Combined Cycle | SS Completed, FIS Started, IA | LCRA | (#7310) SIM GIDEON 138 kV | Bastrop | SOUTH | 2030-12-15 | GAS | CC | 880 |  | 2025-06-12 | 2025-06-19 | 2025-09-17 | 2025-06-13 |  |  | 2025-12-19 | No
30INR0052 | Lost Pines Power Park | SS Completed, FIS Started, IA | LCRA | (#170174) LOST PINES 345 kV | Bastrop | SOUTH | 2033-06-01 | GAS | CC | 880 |  | 2025-06-06 | 2025-06-19 | 2025-09-17 | 2025-06-11 |  | Yes | 2025-12-26 | No
31INR0010 | LOST PINES GAS RECIP PHASE 2 | SS Completed, FIS Started, IA | LCRA | (#170174) LOST PINES 345 kV | Bastrop | SOUTH | 2033-06-01 | GAS | IC | 113.02 |  | 2025-06-27 | 2025-07-07 | 2025-09-30 | 2025-07-02 |  | Yes | 2025-12-26 | No
31INR0011 | SIM GIDEON GAS RICE | SS Completed, FIS Started, IA | LCRA | (#7310) SIM GIDEON 138 kV | Bastrop | SOUTH | 2031-05-10 | GAS | IC | 226.03 |  | 2025-07-03 | 2025-07-29 | 2025-10-26 | 2025-07-08 |  |  | 2025-12-19 | No
27INR0005 | Dundee East A Wind | SS Completed, FIS Started, IA | Felix 2, LLC | 345 kV Riley Substation (#6101); AEP | Baylor | WEST | 2027-12-31 | WIN | WT | 524 |  | 2022-12-28 | 2023-01-03 | 2023-03-30 | 2022-12-22 |  | Yes | 2025-02-21 | Yes | Not Required |  | Not Required | 2025-04-03
27INR0011 | Dundee East B Wind | SS Completed, FIS Started, IA | Felix 2, LLC | 345 kV Riley Substation (#6101); AEP | Baylor | WEST | 2027-12-31 | WIN | WT | 261.45 |  | 2023-01-06 | 2023-01-17 | 2023-04-14 | 2023-01-03 |  | Yes | 2025-02-21 | Yes | Not Required |  | Not Required | 2025-04-03
28INR0514 | Young Road Solar | SS Completed, FIS Started, No IA | reNRG TX 5 LLC | The POI B is TAP 69 KV LINE AND CREATE NEW BUS BETWEENWESTOVER (784) AND LAKE KEMP SWITCH (782) 69 KV SUB STATIONS. | Baylor | WEST | 2028-04-30 | SOL | PV | 101.7 |  | 2026-05-05 | 2026-05-11 | 2026-08-07 | 2026-05-01 |  |  |  | No |  |  | Not Required
29INR0198 | Velveteen Solar I | SS Completed, FIS Started, No IA | Velveteen Solar, LLC | Tap into 6076 FOXTAIL- 6100 OKLAUNION | Baylor | WEST | 2029-10-15 | SOL | PV | 502.2 |  | 2025-12-19 | 2025-12-23 | 2026-03-23 | 2025-12-19 |  |  |  | No |  |  | Not Required
29INR0225 | Velveteen Solar II | SS Completed, FIS Started, No IA | Velveteen Solar II, LLC | Tap into 6076 FOXTAIL- 6100 OKLAUNION | Baylor | WEST | 2029-12-15 | SOL | PV | 300.9 |  | 2025-12-19 | 2025-12-23 | 2026-03-23 | 2025-12-19 |  |  |  | No |  |  | Not Required
29INR0226 | Velveteen Solar III | SS Completed, FIS Started, No IA | Velveteen Solar III, LLC | Tap into 6076 FOXTAIL- 6100 OKLAUNION | Baylor | WEST | 2029-12-15 | SOL | PV | 200.7 |  | 2026-01-06 | 2026-01-13 | 2026-04-07 | 2025-12-09 |  | No |  | No |  |  | Not Required
20INR0129 | Foxtrot Wind | SS Completed, FIS Completed, IA | Lincoln Clean | AEP 88689 Tango 345kV station | Bee | SOUTH | 2026-12-31 | WIN | WT | 268.2 | COD |  | 2018-07-26 | 2018-09-14 | 2018-07-26 | 2021-07-30 | No | 2020-05-05 | Yes | Not Required | Not Required | Not Required | 2021-07-30 | 2021-07-30 | 2021-07-30 |  |  | 2022-02-23 | 2022-03-09
22INR0559 | Honeycomb Solar SLF | SS Completed, FIS Completed, IA | Honeycomb Solar, LLC | 69 kV Tynan Substation (#8107) | Bee | SOUTH | 2027-02-27 | SOL | PV | 61.4 | COD | 2021-10-26 | 2021-11-16 | 2022-01-17 | 2021-11-02 | 2025-03-28 | No | 2023-05-01 | Yes | Not Required | Not Required | Not Required | 2025-02-14 | 2025-07-25 | 2025-07-25
23INR0392 | Honeycomb Storage SLF | SS Completed, FIS Completed, IA | Honeycomb BESS, LLC | 69 kV Tynan Substation (#8107) | Bee | SOUTH | 2027-05-11 | OTH | BA | 0 |  | 2021-10-26 | 2021-11-16 | 2022-01-17 | 2021-11-02 | 2025-03-28 | No | 2023-05-01 | Yes | Not Required | Not Required |  | 2025-02-14 | 2025-07-25 | 2025-07-25
25INR0060 | Argenta Solar | SS Completed, FIS Started, IA | Charter Oak Solar, LLC | Tap 345kV 8689 Tango - 8606 Goddard | Bee | SOUTH | 2028-06-30 | SOL | PV | 310 |  | 2022-07-27 | 2022-06-27 | 2022-09-21 | 2022-07-14 |  |  | 2024-04-05 | Yes | Not Required | Not Required | Not Required | 2025-02-12
25INR0061 | Argenta Storage | SS Completed, FIS Started, IA | Charter Oak Storage, LLC | Tap 345kV 8689 Tango - 8606 Goddard | Bee | SOUTH | 2028-06-30 | OTH | BA | 192 |  | 2022-07-21 | 2022-06-27 | 2022-09-21 | 2022-07-13 |  | No | 2024-04-05 | Yes | Not Required | Not Required |  | 2025-02-12
25INR0394 | Orchard Ray BESS | SS Completed, FIS Started, No IA | Pettus BESS | 8590 Tuleta 138kV | Bee | SOUTH | 2027-05-01 | OTH | BA | 51.85 |  | 2023-05-22 | 2023-06-07 | 2023-09-01 | 2023-05-31 |  | No |  | No
26INR0134 | Myers Solar | SS Completed, FIS Started, No IA | BT Myers Solar, LLC | 8629 Baez 69 kV | Bee | SOUTH | 2028-05-22 | SOL | PV | 101.59 |  | 2023-06-13 | 2023-06-28 | 2023-09-20 | 2023-06-01 |  |  |  | No |  |  | Not Required
26INR0135 | Myers Storage | SS Completed, FIS Started, No IA | BT Myers Solar, LLC | 8629 Baez 69 kV | Bee | SOUTH | 2028-05-22 | OTH | BA | 75.96 |  | 2023-06-07 | 2023-06-28 | 2023-09-20 | 2023-06-01 |  |  |  | No
26INR0412 | BumbleBee Solar | SS Completed, FIS Started, No IA | BumbleBee Solar Farm LLC | Tap 345kV 5725 PawneeSW5 - 8689 Tango | Bee | SOUTH | 2031-03-01 | SOL | PV | 200.86 | COD | 2024-02-22 | 2024-02-27 | 2024-05-24 | 2024-02-26 |  |  |  | No |  |  | Not Required
27INR0083 | Spinner Energy Storage | SS Completed, FIS Completed, No IA | GCI Wolf Energy Storage, LLC | 8196 Poesta Substation 138kV | Bee | SOUTH | 2029-07-10 | OTH | BA | 125.63 |  | 2023-10-05 | 2023-10-13 | 2024-01-09 | 2023-09-27 | 2026-01-23 |  |  | No
27INR0372 | Abeja Solar Farm | SS Completed, FIS Started, IA | Abeja Solar Farm LLC | Tap 345kV 8012 PALADIO7A - 8689 TANGO7A | Bee | SOUTH | 2029-06-07 | SOL | PV | 200.84 | COD | 2024-12-09 | 2024-12-19 | 2025-02-20 | 2024-12-09 |  | Yes | 2025-12-16 | No |  |  | Not Required
28INR0485 | Sparta BESS | SS Completed, FIS Started, No IA | Sparta Storage Center | 88690 SPTPOI7A 345kV | Bee | SOUTH | 2029-12-31 | OTH | BA | 250.95 |  | 2026-08-04 | 2026-01-26 | 2026-04-24 |  |  | No |  | No
23INR0070 | Chillingham Solar | SS Completed, FIS Completed, IA | Chillingham Solar LLC | 3687 Bell County East 345kV | Bell | NORTH | 2026-10-31 | SOL | PV | 352.39 |  | 2020-09-02 | 2020-08-04 | 2020-10-28 | 2020-08-26 | 2024-01-26 | No | 2022-02-04 | Yes | Not Required | Not Required | Not Required | 2024-01-30 | 2024-01-30 | 2024-01-30 |  |  | 2024-08-19 | 2024-09-04
23INR0248 | Limewood Storage | SS Completed, FIS Started, IA | Limewood Bell Renewables LLC | 3420 Temple Pecan Creek 138kV | Bell | NORTH | 2028-12-29 | OTH | BA | 50 |  | 2021-11-03 | 2021-04-30 | 2021-07-22 | 2021-10-06 |  | No | 2023-02-22 | Yes | Not Required | Not Required |  | 2025-05-22
23INR0249 | Limewood Solar | SS Completed, FIS Completed, IA | Limewood Bell Renewables, LLC | 3420 Temple Pecan Creek 138kV | Bell | NORTH | 2026-12-29 | SOL | PV | 204.6 |  | 2021-11-03 | 2021-04-30 | 2021-07-22 | 2021-10-06 | 2025-03-14 | No | 2023-02-22 | Yes | Not Required | Not Required | Not Required | 2025-02-13 | 2025-05-01 | 2025-05-01 |  |  | 2026-08-10 | 2026-09-15
23INR0344 | Hermes Solar | SS Completed, FIS Completed, IA | Bell 1 Solar, LLC | Tap 345kV 3687 Bell County East Switch - 39950 TNP One Plant Ckt 2 | Bell | NORTH | 2026-06-12 | SOL | PV | 100.36 |  | 2022-06-14 | 2021-09-21 | 2021-12-09 | 2022-06-01 | 2024-04-19 | No | 2023-11-08 | Yes |  |  | Not Required | 2025-01-31 | 2025-01-31 | 2025-01-31 |  |  | 2026-02-23 | 2026-04-17
23INR0469 | Big Elm Storage | SS Completed, FIS Completed, IA | Big Elm Storage, LLC | 3404 Belfalls 345kV | Bell | NORTH | 2028-12-15 | OTH | BA | 120 |  | 2022-10-25 | 2022-04-18 | 2022-07-08 | 2022-10-11 | 2024-02-19 | No | 2024-05-10 | Yes |  |  |  | 2024-05-15
24INR0365 | Hermes Storage | SS Completed, FIS Completed, IA | Bell 1 Storage LLC | Tap 345kV 3687 Bell County East Switch - 39950 TNP One Plant Ckt 2 | Bell | NORTH | 2026-08-18 | OTH | BA | 100.42 |  | 2022-07-14 | 2022-07-18 | 2022-10-12 | 2022-06-30 | 2024-04-19 | No | 2023-11-08 | Yes |  |  |  | 2025-01-31 | 2025-01-31 | 2025-01-31 |  |  | 2026-03-03 | 2026-04-17
25INR0100 | Goldeneye BESS | SS Completed, FIS Completed, IA | Black Mountain Energy Storage II | 3423 KILLEEN Switch 138 KV | Bell | NORTH | 2028-05-15 | OTH | BA | 201.6 |  | 2022-08-03 | 2022-06-10 | 2022-09-06 | 2022-07-13 | 2023-08-18 | No | 2024-02-26 | No | Not Required | Not Required | 2025-10-02
25INR0281 | Cosper Solar | SS Completed, FIS Completed, IA | Gransolar Texas Twenty LLC | Tap 138kV 115 Ding Dong - 3630 Copperas Cove Tu | Bell | NORTH | 2027-11-12 | SOL | PV | 148.16 |  | 2023-06-13 | 2023-01-03 | 2023-03-30 | 2023-05-26 | 2024-11-01 |  | 2025-07-31 | Yes | Not Required | Not Required | Not Required | 2025-08-18
25INR0337 | Butcherbird Solar | SS Completed, FIS Completed, No IA | Butcherbird Solar, LLC | Tap 138 kV - Bell County #133 to Bartlett Switch #114 | Bell | NORTH | 2029-01-31 | SOL | PV | 116 |  | 2023-11-28 | 2023-12-18 | 2024-03-15 | 2023-12-06 | 2025-12-02 |  |  | No | Not Required | Not Required | Not Required
26INR0465 | Lavita BESS | SS Completed, FIS Started, No IA | Lavita BESS, LLC | Tap 345kV Temple Pecan Creek (3412) - Temple Switch (3414) 345kV ckt 2 | Bell | NORTH | 2028-07-01 | OTH | BA | 606 |  | 2024-06-03 | 2024-12-19 | 2025-02-20 | 2024-12-16 |  |  |  | No
26INR0614 | Bell County Leifester Storage | SS Completed, FIS Started, No IA | DM-BCRCML, LLC | Tap 138kV 3428 Killeen South – 13628 Founders Trail Sub | Bell | NORTH | 2029-09-17 | OTH | BA | 204.82 |  | 2024-11-14 | 2024-11-19 | 2025-02-18 | 2024-11-14 |  |  |  | No
26INR0615 | Bell County Morgan Storage | SS Completed, FIS Started, No IA | DM-BCTRM, LLC | To Tap 138 kV Trimmier Substation (Bus# 136) | Bell | NORTH | 2029-12-30 | OTH | BA | 256.27 |  | 2024-11-14 | 2024-11-19 | 2025-02-18 | 2024-11-14 |  |  |  | No
29INR0206 | Riviera Gas | SS Completed, FIS Started, No IA | BKV-BPP Power | Tap #3414 Temple Switch - #3780 Tower Switch 345kV DCKT Line | Bell | NORTH | 2030-06-14 | GAS | CC | 636.9 |  | 2025-10-30 | 2025-11-05 | 2026-01-19 | 2025-10-30 |  |  |  | No
22INR0423 | Quela BESS | SS Completed, FIS Started, No IA | BRP Quela BESS LLC | Tap 138kV 5110 J.T. Deely - 5294 Martinez | Bexar | SOUTH | 2027-12-01 | OTH | BA | 301.41 |  | 2020-09-25 | 2020-09-25 | 2020-12-16 | 2020-09-15 |  | No |  | No
23INR0207 | El Patrimonio Solar | SS Completed, FIS Completed, IA | Heritage Solar, LLC | tap 138kV 5429 Trumbo - 5260 Leon Creek | Bexar | SOUTH | 2027-04-29 | SOL | PV | 152.32 |  | 2022-03-02 | 2021-03-16 | 2021-05-28 | 2021-11-23 | 2024-10-17 | No | 2023-12-11 | Yes | Not Required | Not Required | Not Required | 2026-05-01 | 2026-05-01 | 2026-05-01
23INR0467 | Lavender Storage Project | SS Completed, FIS Started, IA | Lavender Storage Project LLC | Tap 138kV Deely (bus 5110) - Laredo (bus 5255) | Bexar | SOUTH | 2029-09-13 | OTH | BA | 231.9 |  | 2022-11-03 | 2022-02-28 | 2022-05-27 | 2022-10-21 |  | No | 2025-06-23 | No
23INR0479 | Taormina Storage | SS Completed, FIS Started, IA | Taormina Storage Project LLC | Tap 138kV VH Braunig (5025) to Valley Road 138kV (5465) | Bexar | SOUTH | 2029-05-26 | OTH | BA | 231.86 |  | 2022-11-08 | 2022-04-18 | 2022-07-15 | 2022-10-26 |  | No | 2025-04-14 | Yes | Not Required | Not Required |  | 2025-06-20
24INR0108 | Louisa Energy Storage | SS Completed, FIS Started, IA | VESI 49 LLC | 138 kV Helotes (#5200) | Bexar | SOUTH | 2029-03-12 | OTH | BA | 102.77 |  | 2021-11-16 | 2021-11-16 | 2022-01-17 | 2021-11-08 |  | No | 2025-02-27 | Yes | Not Required | Not Required
24INR0392 | Riverwalk BESS | SS Completed, FIS Started, IA | RWE Solar Developement, LLC | 5294 Martinez Substation 138kV | Bexar | SOUTH | 2027-10-01 | OTH | BA | 120 |  | 2022-07-14 | 2022-07-18 | 2022-10-14 | 2022-07-11 |  | No | 2026-08-18 | No | Not Required | Not Required
24INR0427 | CPS AvR CT1 Rotor Replacement | SS Completed, FIS Completed, No IA | CPS Energy | 5475 Braunig 345kV | Bexar | SOUTH | 2026-08-14 | GAS | CC | 11.3 | COD | 2022-08-30 | 2022-10-24 | 2023-01-20 | 2022-09-20 | 2023-04-18 |  |  | No | 2018-06-01 |  | 2023-04-21 | 2023-04-18 | 2023-04-18 | 2023-05-01 |  |  |  | 2023-12-04
25INR0346 | Cado Storage | SS Completed, FIS Completed, No IA | Cado Storage, LLC | Tap 138 kV Line from Braunig East (#5030) to Highland Hills (#5205) Ckt. 1 | Bexar | SOUTH | 2030-06-08 | OTH | BA | 205.51 |  | 2023-03-10 | 2023-03-13 | 2023-06-09 | 2023-03-07 | 2026-08-03 | No |  | No
25INR0531 | CPS Energy AvR1CT2 Rotor Replacement | SS Completed, FIS Completed, No IA | CPS Energy | 5475 Braunig 345kV | Bexar | SOUTH | 2026-08-14 | GAS | CC | 23.2 | COD | 2024-02-09 | 2023-10-13 | 2024-01-10 | 2024-01-26 | 2024-04-25 |  |  | No | 2028-03-20 |  | 2024-04-01 | 2024-04-01 | 2024-04-25 | 2024-05-01 |  |  |  | 2024-11-22
26INR0330 | Alamo City BESS | SS Completed, FIS Completed, IA | ALAMO CITY ESS LLC | Tap 138kV 5294 Martinez - 5110 JT Deely | Bexar | SOUTH | 2027-09-21 | OTH | BA | 128.2 |  | 2024-02-21 | 2024-02-27 | 2024-05-24 | 2024-02-13 | 2026-08-21 | No | 2025-05-22 | No | Not Required | Not Required | 2026-08-21
26INR0331 | RUSH ESS | SS Completed, FIS Started, No IA | OCI Solar Power LLC | Tap 345 kV 5231 HOWARD_5 – 5400 SPRUCE | Bexar | SOUTH | 2031-02-08 | OTH | BA | 201.27 |  | 2024-02-20 | 2023-11-30 | 2024-01-16 | 2024-02-12 |  |  |  | No
27INR0082 | Orbit Energy Storage | SS Completed, FIS Started, No IA | GCI Orbit Energy Storage, LLC | Tap 345 kV Calaveras Power Station (BUS #5400) to VON_ROSE (BUS #5475) | Bexar | SOUTH | 2027-06-01 | OTH | BA | 501.94 |  | 2023-11-28 | 2023-11-30 | 2024-02-29 | 2023-09-27 |  |  |  | No
27INR0180 | Otter BESS | SS Completed, FIS Started, No IA | GRS BESS TEXAS TEN, LLC | 5378 SHEPHERD RD 138kV | Bexar | SOUTH | 2029-09-15 | OTH | BA | 157.12 |  | 2024-02-01 | 2024-02-27 | 2024-05-20 | 2024-02-05 |  |  |  | No
27INR0294 | Bernice Energy Storage | SS Completed, FIS Started, No IA | Bernice Energy Storage LLC | 5135 ELMENDORF 138kV | Bexar | SOUTH | 2029-02-15 | OTH | BA | 402.8 |  | 2024-08-09 | 2024-09-04 | 2024-12-02 | 2024-08-12 |  |  |  | No
27INR0342 | Dorsey Road BESS | SS Completed, FIS Started, No IA | Horizon Energy Storage Greenfield Project Holdings LLC | Tap 138 kV Chavanea (5085) - Palo Alto (5330). | Bexar | SOUTH | 2029-08-31 | OTH | BA | 150.39 |  | 2025-02-04 | 2025-03-06 | 2025-06-03 | 2025-02-05 |  |  |  | No
27INR0393 | Ferdinand Grid BESS II | SS Completed, FIS Started, No IA | Coval Infrastructure DevCo LLC | 5260 Leon Creek 138kV | Bexar | SOUTH | 2027-12-01 | OTH | BA | 208.12 |  | 2024-10-14 | 2024-12-19 | 2025-03-04 | 2024-12-03 |  |  |  | No
28INR0020 | Caracara Energy Storage Center | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | Tap 138kV 5055 Cagnon - 5346 Potranco | Bexar | SOUTH | 2028-08-01 | OTH | BA | 203 |  | 2024-08-19 | 2024-05-09 | 2024-08-05 | 2024-08-05 |  |  |  | No
28INR0024 | Padua Grid BESS Unit 3 | SS Completed, FIS Completed, IA | Padua Grid 3, LLC | Tap #5395 O.W Sommer 138kV | Bexar | SOUTH | 2026-05-15 | OTH | BA | 201.35 |  | 2024-03-14 | 2024-03-22 | 2024-06-19 | 2024-03-01 | 2025-06-20 | No | 2025-03-07 | Yes | Not Required | Not Required |  | 2025-06-20 | 2025-07-17 | 2025-07-17 |  |  | 2026-06-12 | 2026-06-22
28INR0390 | Horsepower BESS | SS Completed, FIS Started, No IA | Horsepower BESS, LLC | POI is 138 kV Howard Substation (Bus# 5230) (SSWG bus name: HOWARD), NMMS station code: S1 | Bexar | SOUTH | 2028-01-31 | OTH | BA | 257.5 |  | 2025-12-14 | 2025-12-17 | 2026-02-23 | 2025-11-24 |  |  |  | No
28INR0474 | Mission Station Energy Storage I | SS Completed, FIS Started, No IA | Mission Station LLC | Tap 345kV (Bus #5400) SPRUCE – (Bus #5475) VON_ROSE Ckt 1; | Bexar | SOUTH | 2030-05-31 | OTH | BA | 375 |  | 2026-01-07 | 2026-02-10 | 2026-05-08 | 2026-02-04 |  | No |  | No
28INR0475 | Mission Station Energy Storage II | SS Completed, FIS Started, No IA | Mission Station LLC | Tap 345kV (Bus #5400) SPRUCE – (Bus #5231) HOWARD_5 Ckt 1 | Bexar | SOUTH | 2030-05-31 | OTH | BA | 375 |  | 2026-01-07 | 2026-02-10 | 2026-05-08 | 2026-02-04 |  | No |  | No
29INR0173 | Howard Road BESS | SS Completed, FIS Started, No IA | Project Fast Flow LLC | 5231 HOWARD RD 345 kV | Bexar | SOUTH | 2028-04-01 | OTH | BA | 617.63 |  | 2025-07-03 | 2025-07-29 | 2025-10-26 | 2025-07-16 |  |  |  | No
26INR0616 | Blanco County Behrends Storage | SS Completed, FIS Started, No IA | DM-BCB, LLC | #70482 Blanco Substation 138 kV - currently being upgraded | Blanco | SOUTH | 2029-12-30 | OTH | BA | 153.62 |  | 2024-12-13 | 2024-12-19 | 2025-03-17 | 2024-12-13 |  |  |  | No
25INR0439 | Stephens Ranch Wind Repower | SS Completed, FIS Started, No IA | Stephens Ranch Wind Energy, LLC | 59900 Long Draw 345 kV | Borden | WEST | 2027-11-01 | WIN | WT | 12.4 |  | 2023-06-07 | 2023-06-28 | 2023-09-20 | 2023-05-15 |  |  |  | Yes |  |  | Not Required
26INR0359 | Uva Creek Solar | SS Completed, FIS Started, IA | Grape Creek Solar, LLC | Muleshoe #59922 345 KV | Borden | WEST | 2028-08-25 | SOL | PV | 302.16 |  | 2023-12-18 | 2024-02-27 | 2024-05-20 | 2024-02-06 |  |  | 2024-10-30 | Yes | Not Required | Not Required | Not Required | 2026-04-07
26INR0621 | Juno 3 Solar | SS Completed, FIS Started, IA | Juno Solar 3 | #59916 Buck Canyon 345kV | Borden | WEST | 2027-11-30 | SOL | PV | 500 |  | 2025-03-18 | 2025-03-24 | 2025-06-09 | 2025-03-18 |  | Yes | 2025-07-01 | Yes |  |  | Not Required
26INR0636 | Lyra Storage | SS Completed, FIS Started, IA | JUNO BESS I | 345kV MULESHOE (#59922) | Borden | WEST | 2026-11-12 | OTH | BA | 500 |  |  | 2025-05-27 | 2025-08-23 | 2025-05-12 |  |  | 2025-08-13 | No
27INR0434 | Lyra Solar | SS Completed, FIS Started, IA | Juno Solar 4 | 345kV MULESHOE (#59922) | Borden | WEST | 2027-09-15 | SOL | PV | 500 |  | 2025-03-20 | 2025-03-24 | 2025-06-09 | 2025-03-20 |  | No | 2025-07-01 | Yes |  |  | Not Required
27INR0480 | Borden Dino Solar | SS Completed, FIS Started, No IA | Borden Dino Solar, LLC | 59905 FARADAY 345KV | Borden | WEST | 2028-07-01 | SOL | PV | 120.47 |  | 2025-03-06 | 2025-04-01 | 2025-06-09 | 2025-03-06 |  |  |  | No |  |  | Not Required
27INR0481 | Borden Dino BESS | SS Completed, FIS Started, No IA | Borden Dino Solar, LLC | 59905 FARADAY 345KV | Borden | WEST | 2028-07-01 | OTH | BA | 60.26 |  | 2025-03-06 | 2025-04-01 | 2025-06-09 | 2025-03-06 |  |  |  | No
27INR0499 | Draco Solar | SS Completed, FIS Started, No IA | Draco Solar LLC | Tap Long Draw (59900) – Faraday (59905) CKT 1 and LONGDRAW (59900) - GALVANI(59912) CKT 2 | Borden | WEST | 2027-08-19 | SOL | PV | 500 |  | 2025-03-31 | 2025-04-21 | 2025-07-19 | 2025-04-01 |  |  |  | No |  |  | Not Required
27INR0500 | Antila Solar | SS Completed, FIS Started, IA | Antila Solar LLC | #59916 Buck Canyon 345kV | Borden | WEST | 2027-11-30 | SOL | PV | 500 |  | 2025-04-01 | 2025-04-21 | 2025-07-19 | 2025-04-02 |  | Yes | 2025-08-13 | Yes |  |  | Not Required
28INR0176 | Gail Mountain Solar | SS Completed, FIS Started, IA | Gail Mountain Solar, LLC | Muleshoe (Bus #59922) 345 kV | Borden | WEST | 2028-08-25 | SOL | PV | 244.4 |  | 2024-10-22 | 2024-10-29 | 2025-01-14 | 2024-10-11 |  | No | 2025-12-30 | Yes | Not Required | Not Required | Not Required | 2026-03-24
28INR0297 | Magnet Solar | SS Completed, FIS Started, IA | HyFuels Big Spring Solar LLC | Faraday Substation 345kV - Bus #59905 | Borden | WEST | 2029-09-29 | SOL | PV | 503.09 | COD | 2025-05-05 | 2025-04-21 | 2025-07-19 | 2025-04-24 |  | No | 2025-12-11 | Yes |  |  | Not Required
28INR0298 | Magnet Storage | SS Completed, FIS Started, No IA | HyFuels Big Spring LLC | Faraday 345 kV Substation (#59905) | Borden | WEST | 2029-09-29 | OTH | BA | 426.7 | COD | 2025-10-07 | 2025-07-29 | 2025-10-22 | 2025-08-22 |  |  |  | No
29INR0131 | Caesar Solar | SS Completed, FIS Started, IA | Caesar Solar, LLC | 59916 Buck Canyon 345 kV | Borden | WEST | 2029-11-26 | SOL | PV | 181.6 | SFS/NtP | 2025-07-16 | 2025-07-29 | 2025-10-22 | 2025-07-07 |  | No | 2026-09-15 | Yes |  |  | Not Required
29INR0132 | Caesar Storage | SS Completed, FIS Started, IA | Caesar Solar, LLC | 59916 Buck Canyon 345 kV | Borden | WEST | 2029-11-26 | OTH | BA | 205.5 | SFS/NtP | 2025-07-16 | 2025-07-29 | 2025-10-22 | 2025-07-07 |  |  | 2026-09-15 | Yes
29INR0267 | Enfinity White Oak BESS | SS Completed, FIS Started, No IA | EG White Oak LLC | Tap 138kV Key (1307) to 138kV Gail (1308) | Borden | WEST | 2029-09-17 | OTH | BA | 200 |  | 2026-02-10 | 2026-02-25 | 2026-05-21 | 2026-02-17 |  |  |  | No
29INR0291 | Enfinity Post Oak Solar SLF | SS Completed, FIS Started, No IA | EG White Oak LLC | 345kV Muleshoe (59922) | Borden | WEST | 2029-12-18 | SOL | PV | 500 |  | 2026-03-13 | 2026-03-30 | 2026-06-25 | 2026-03-27 |  |  |  | No |  |  | Not Required
29INR0292 | Enfinity Post Oak Storage SLF | SS Completed, FIS Started, No IA | EG White Oak LLC | 345kV Muleshoe (59922) Transmission line | Borden | WEST | 2029-12-18 | OTH | BA | 0 |  | 2026-03-13 | 2026-03-30 | 2026-06-25 | 2026-03-27 |  |  |  | No
25INR0474 | Solheim Solar | SS Completed, FIS Completed, No IA | Solheim Solar, LLC | Meridian (Bus# 315) - Glen Rose (Bus #319) 69 kV | Bosque | NORTH | 2027-11-01 | SOL | PV | 108.68 |  | 2024-04-04 | 2023-08-14 | 2023-11-10 | 2024-03-21 | 2026-03-06 | No |  | No |  |  | Not Required
27INR0298 | Symank Solar | SS Completed, FIS Started, No IA | BT Symank Solar, LLC | Tap 69 kV 37470 TNOLSEN - 37520 TNSYCAMORE | Bosque | NORTH | 2027-12-15 | SOL | PV | 66.55 |  | 2024-10-29 | 2024-11-19 | 2025-02-14 | 2024-11-11 |  | No |  | No |  |  | Not Required
30INR0005 | Woodland Energy Storage | SS Completed, FIS Started, No IA | Woodland Energy Storage, LLC | 68040 Kopperl Substation 345kV | Bosque | NORTH | 2030-10-01 | OTH | BA | 207.6 |  | 2023-10-28 | 2023-12-18 | 2024-03-15 | 2023-10-23 |  |  |  | No
19INR0041 | Myrtle Solar | SS Completed, FIS Completed, IA | Myrtle Solar, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2027-06-21 | SOL | PV | 321.2 |  |  | 2017-03-15 | 2017-04-28 | 2017-05-09 | 2022-01-25 |  | 2019-11-13 | Yes | Not Required | Not Required | Not Required | 2019-11-30 | 2020-05-06 | 2022-02-01 |  |  | 2022-12-07 | 2022-12-20
19INR0134 | Cottonwood Bayou Solar | SS Completed, FIS Completed, IA | Cottonwood Bayou Solar, LLC | tap 138kV 42870 Liverpool - 43070 Petson | Brazoria | COASTAL | 2026-10-30 | SOL | PV | 351.4 | COD |  | 2017-09-22 | 2017-11-17 | 2018-02-15 | 2023-04-27 | No | 2019-11-13 | Yes | Not Required | Not Required | Not Required | 2023-04-27 | 2023-04-27 | 2023-04-27 |  |  | 2024-05-01 | 2024-05-29
20INR0248 | DAMAZO (Second Division) SOLAR | SS Completed, FIS Completed, IA | TX Gulf Solar 1 LLC | Tap 138 kV SANBER_POI_8 (Bus# 43110) to WEST COLUMBIA (Bus# 43380) Ckt 60 Line | Brazoria | COASTAL | 2025-12-31 | SOL | PV | 100.2 |  | 2019-08-06 | 2019-03-28 | 2019-06-18 | 2019-07-29 | 2022-10-28 | No | 2020-10-14 | Yes | Not Required | Not Required | Not Required | 2023-10-31 | 2023-10-31 | 2023-10-31 |  |  | 2024-10-08 | 2024-10-17
21INR0444 | Long Point Storage | SS Completed, FIS Started, IA | Long Point Storage, LLC | 138 KV (CEHE Sub) Tap Burke (42410) - Eagle Nest (42430) ckt 02 | Brazoria | COASTAL | 2027-12-30 | OTH | BA | 100.62 |  | 2020-09-17 | 2019-11-01 | 2020-02-05 | 2020-09-01 |  | No | 2023-08-28 | No | Not Required | Not Required
22INR0279 | Clutch City Solar Phase I | SS Completed, FIS Started, IA | HZ Solar I, LLC | tap 138kV 42960 Mustang Bayou – 42100 Hudson CKT #04 | Brazoria | COASTAL | 2028-07-01 | SOL | PV | 200.75 |  | 2020-03-16 | 2020-01-22 | 2020-04-08 | 2020-02-11 |  | No | 2022-09-30 | No | Not Required | Not Required | Not Required
23INR0054 | Tanglewood Solar | SS Completed, FIS Completed, IA | Brazoria Solar, LLC | 345kV Seabreeze Substation | Brazoria | COASTAL | 2026-09-30 | SOL | PV | 250.96 |  | 2021-01-15 | 2020-07-10 | 2020-09-28 | 2020-11-24 | 2024-06-03 | Yes | 2022-11-01 | Yes | Not Required | Not Required | Not Required | 2023-02-10 | 2024-11-07 | 2024-11-07 |  |  | 2025-08-05 | 2025-08-20
23INR0091 | Cascade Solar | SS Completed, FIS Completed, IA | Cascade Solar Energy, LLC | 43180 SAVANAH 345 kV | Brazoria | COASTAL | 2028-01-15 | SOL | PV | 171 |  | 2021-05-05 | 2021-02-09 | 2021-05-06 | 2021-04-28 | 2025-09-02 | No | 2023-04-17 | Yes | Not Required | Not Required | Not Required | 2023-12-07 | 2025-10-31 | 2025-10-31
23INR0150 | Cradle Solar | SS Completed, FIS Completed, IA | Cradle Solar LLC | tap 345kV 42500 Dow - 43035 Oasis ckt 18 | Brazoria | COASTAL | 2027-09-17 | SOL | PV | 200.85 |  | 2021-03-26 | 2021-02-04 | 2021-04-21 | 2021-03-15 | 2025-03-14 | No | 2023-03-15 | Yes |  |  | Not Required | 2025-02-12 | 2025-04-30 | 2025-04-30
23INR0194 | Pequin Energy Storage | SS Completed, FIS Started, No IA | Pequin Energy Storage, LLC | 39500 TN West Columbia 138kV | Brazoria | COASTAL | 2027-09-13 | OTH | BA | 103.4 |  | 2021-06-29 | 2021-01-25 | 2021-04-16 | 2021-06-14 |  |  |  | No
23INR0376 | Cascade Storage | SS Completed, FIS Started, No IA | Oyster Creek LLC | 345kV Oasis (43035) – Seabreeze circuit 27 | Brazoria | COASTAL | 2028-06-01 | OTH | BA | 250 |  | 2021-09-09 | 2021-09-09 | 2021-11-29 | 2021-09-09 |  |  |  | No
24INR0041 | Rock N' Roll Solar SLF | SS Completed, FIS Started, No IA | Rock N’ Roll Solar, LLC | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2027-08-30 | SOL | PV | 151.97 |  | 2022-02-10 | 2021-05-10 | 2021-07-30 | 2022-01-20 |  | No |  | No | Not Required | Not Required | Not Required
24INR0234 | Rock N' Roll Storage SLF | SS Completed, FIS Started, No IA | Rock N’ Roll Solar, LLC | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2028-08-01 | OTH | BA | 0 |  | 2022-02-10 | 2022-02-28 | 2022-05-27 | 2022-02-11 |  | No |  | No | Not Required | Not Required
24INR0235 | Rock N' Roll Storage Two | SS Completed, FIS Started, No IA | Rock N’ Roll Solar, LLC | tap 138kV 44600 Rosharon - 44531 Winmil | Brazoria | COASTAL | 2027-08-30 | OTH | BA | 206 |  | 2022-02-24 | 2022-02-28 | 2022-05-27 | 2022-02-11 |  | No |  | No | Not Required | Not Required
24INR0282 | Royal River BESS | SS Completed, FIS Completed, IA | Royal River LLC | Tap 138kV 42110 Angleton - 43381 West Columbia | Brazoria | COASTAL | 2028-06-30 | OTH | BA | 310.7 |  | 2023-02-08 | 2022-03-30 | 2022-06-27 | 2022-12-19 | 2025-10-09 | No | 2023-12-15 | Yes | Not Required | Not Required |  | 2026-07-15 | 2026-07-28
24INR0530 | Southside Energy | SS Completed, FIS Started, No IA | Southside Energy, LLC | Tap 138kV 42960 Mustang Bayou - 42100 HUDSON ckt 4 | Brazoria | COASTAL | 2028-12-31 | OTH | BA | 101.2 |  | 2023-11-01 | 2023-02-27 | 2023-05-26 | 2023-10-24 |  |  |  | No
24INR0570 | Marcus Energy Storage | SS Completed, FIS Completed, No IA | Marcus Energy Storage, LLC | Tap 138kV 39500 West Columbia Main - 110505 Sweeny Co-Gen LP Ckt 1 | Brazoria | COASTAL | 2027-09-01 | OTH | BA | 201.04 |  | 2023-10-31 | 2023-06-07 | 2023-09-01 | 2023-10-24 | 2024-09-30 |  |  | No
25INR0102 | Austin Bayou Solar | SS Completed, FIS Started, IA | Austin Bayou Solar, LLC | Tap 345 kV Savana 43180 to Seabreeze 43020 - Ckt 27 | Brazoria | COASTAL | 2027-06-01 | SOL | PV | 502.48 |  | 2022-08-15 | 2022-06-27 | 2022-09-21 | 2022-07-26 |  | No | 2023-11-15 | Yes |  |  | Not Required | 2025-02-12
25INR0103 | Elio BESS | SS Completed, FIS Completed, IA | Elio Energy LLC | 138 kV Weinbrenner Station (Bus #42990) | Brazoria | COASTAL | 2028-12-31 | OTH | BA | 205.28 | MW Size COD | 2023-05-19 | 2022-07-05 | 2022-10-01 | 2023-05-15 | 2024-10-31 |  | 2024-09-15 | Yes | Not Required | Not Required |  | 2025-02-12
25INR0170 | Pinewood Solar | SS Completed, FIS Started, IA | Brazoria Solar II, LLC | 43020 Seabreeze 345kV | Brazoria | COASTAL | 2028-02-29 | SOL | PV | 150.68 |  | 2023-07-03 | 2022-09-02 | 2022-11-30 | 2023-06-20 |  |  | 2025-05-08 | No |  |  | Not Required
25INR0235 | Austin Bayou Storage I | SS Completed, FIS Started, IA | Austin Bayou Solar, LLC | Tap 345 kV Savana 43180 to Seabreeze 43020 - Ckt 27 | Brazoria | COASTAL | 2027-06-01 | OTH | BA | 150.68 |  | 2023-03-02 | 2023-03-08 | 2023-06-05 | 2023-02-23 |  |  | 2025-02-14 | No | Not Required | Not Required
25INR0236 | Austin Bayou Storage II | SS Completed, FIS Started, IA | Austin Bayou Solar, LLC | Tap to CKT#27 from Savana (Bus# 43180) to Oasis (Bus# 43035) – 345 kV Line | Brazoria | COASTAL | 2027-06-01 | OTH | BA | 156.6 |  | 2023-03-02 | 2023-03-08 | 2023-06-05 | 2023-02-23 |  |  | 2025-02-14 | No | Not Required | Not Required
25INR0237 | Austin Bayou Storage III | SS Completed, FIS Started, IA | Austin Bayou Solar, LLC | Tap 345 kV Savana 43180 to Seabreeze 43020 - Ckt 27 | Brazoria | COASTAL | 2027-06-01 | OTH | BA | 156.6 |  | 2023-03-02 | 2023-03-08 | 2023-06-05 | 2023-02-23 |  |  | 2025-02-14 | No | Not Required | Not Required
25INR0330 | Clutch City Solar Phase II | SS Completed, FIS Started, IA | HZ SOLAR I, LLC | tap 138kV 42960 Mustang Bayou – 42100 Hudson CKT#04 | Brazoria | COASTAL | 2028-07-01 | SOL | PV | 251.27 |  | 2023-02-17 | 2023-02-20 | 2023-05-20 | 2023-02-10 |  |  | 2025-02-11 | No |  |  | Not Required
25INR0378 | Second Division Storage | SS Completed, FIS Started, No IA | Mound Creek Storage, LLC | Tap 138 kV SANBER_POI_8 (Bus# 43110) to WEST COLUMBIA (Bus# 43380) Ckt 60 Line | Brazoria | COASTAL | 2025-12-31 | OTH | BA | 0 |  | 2023-04-03 | 2023-04-19 | 2023-07-13 | 2023-03-15 |  |  |  | No
25INR0421 | Aldrin 138 BESS | SS Completed, FIS Completed, IA | Aldrin Energy Storage LLC | (Bus: 39015) North Alvin TNMP 138kV | Brazoria | COASTAL | 2028-03-01 | OTH | BA | 207 |  | 2023-05-02 | 2023-05-15 | 2023-08-11 | 2023-05-04 | 2025-08-22 | No | 2024-04-18 | Yes | Not Required | Not Required |  | 2024-05-06
25INR0425 | Aldrin 345 BESS | SS Completed, FIS Completed, IA | Aldrin Energy Storage LLC | (Bus: 43030) Meadow 345kV substation | Brazoria | COASTAL | 2028-03-01 | OTH | BA | 362 |  | 2023-05-10 | 2023-05-15 | 2023-08-11 | 2023-05-05 | 2025-04-21 | No | 2024-06-15 | Yes | Not Required | Not Required |  | 2025-02-12
25INR0458 | Surfside Energy Storage | SS Completed, FIS Started, No IA | Rocky Mountain Energy Holdings, LLC | Tap 138kV 42110 Angleton – 43150 Riwood ckt 82 | Brazoria | COASTAL | 2028-12-31 | OTH | BA | 50.34 |  | 2024-03-12 | 2023-07-19 | 2023-10-10 | 2024-02-28 |  |  |  | No | Not Required | Not Required
25INR0480 | Bell Creek BESS | SS Completed, FIS Completed, IA | BELL CREEK BESS, LLC | Tap 138kV 39500 West Colombia - 39703 FM524 | Brazoria | COASTAL | 2027-10-30 | OTH | BA | 200.9 |  | 2023-11-29 | 2023-06-28 | 2023-09-21 | 2023-11-17 | 2024-05-16 |  | 2024-11-14 | No
25INR0494 | Willow Beach Wind | SS Completed, FIS Completed, IA | Capital Wind, LLC | Tap 138 kV Bus# 42100 HUD_8 – Bus# 42960 MUSTNG_S04_8 138kV CKT# 4 | Brazoria | COASTAL | 2027-10-01 | WIN | WT | 202.33 |  | 2023-08-28 | 2023-10-13 | 2024-01-10 | 2023-09-20 | 2024-11-18 |  | 2025-06-16 | No |  |  | Not Required
25INR0550 | Friendswood Energy Storage | SS Completed, FIS Completed, No IA | Friendswood Energy Storage LLC | TAP 138kV 39010 HASTINGS - 38980 FRIENDSWOOD | Brazoria | COASTAL | 2028-03-30 | OTH | BA | 105.08 | COD | 2024-01-04 | 2024-02-02 | 2024-04-29 | 2024-01-17 | 2025-12-11 |  |  | No
25INR0554 | Dan Kearney BESS | SS Completed, FIS Completed, IA | Dan Kearney BESS LLC | 39703 TNFM524 138kV | Brazoria | COASTAL | 2029-02-28 | OTH | BA | 204.38 | COD | 2023-10-19 | 2024-01-11 | 2024-04-08 | 2024-01-03 | 2026-09-18 | No | 2024-10-18 | No
25INR0566 | Copano Bay Energy Storage | SS Completed, FIS Started, No IA | Copano Bay Energy Storage, LLC | Tap 138kV 42980 Nash - 44010 WA Parish Ckt 2 | Brazoria | COASTAL | 2027-12-31 | OTH | BA | 201.04 |  | 2023-10-22 | 2023-10-25 | 2024-01-22 | 2023-10-17 |  |  |  | No | Not Required | Not Required
26INR0117 | Oyster Creek Solar I SLF | SS Completed, FIS Started, No IA | Oyster Creek Solar 1, LLC | Tap 138kV 42110 Angleton - 42050 Clute | Brazoria | COASTAL | 2029-04-01 | SOL | PV | 0 |  | 2023-05-15 | 2023-06-28 | 2023-09-22 | 2023-06-15 |  | No |  | No |  |  | Not Required
26INR0118 | Oyster Creek Storage I SLF | SS Completed, FIS Started, No IA | Oyster Creek Solar 1, LLC | Tap 138kV 42110 Angleton - 42050 Clute | Brazoria | COASTAL | 2029-04-01 | OTH | BA | 0 |  | 2023-06-02 | 2023-06-28 | 2023-09-22 | 2023-06-20 |  | No |  | No
26INR0189 | Skipjack Energy Storage | SS Completed, FIS Started, IA | Skipper Energy Storage LLC | Tap 138 42980 Nash - 44010 W A Parish ckt #2 | Brazoria | COASTAL | 2028-02-28 | OTH | BA | 150.6 |  | 2023-07-17 | 2023-07-31 | 2023-10-27 | 2023-07-29 |  |  | 2024-08-13 | Yes |  |  |  | 2025-02-24
26INR0226 | First Capitol BESS | SS Completed, FIS Started, IA | First Capitol BESS, LLC | Tap 138kV West Columbia Main (39500) - Sweeny Cogen (110505) | Brazoria | COASTAL | 2027-11-01 | OTH | BA | 257.48 |  | 2023-09-25 | 2023-10-04 | 2023-12-14 | 2023-09-22 |  | No | 2025-05-15 | Yes | Not Required | Not Required |  | 2025-02-12
26INR0314 | Brazos River BESS | SS Completed, FIS Started, IA | Brazos River BESS LLC | Tap 138kV 39530 West Colombia LOCAL TNP - 39560 ANGLETON TNP | Brazoria | COASTAL | 2027-10-30 | OTH | BA | 180.36 |  | 2024-05-31 | 2023-10-04 | 2024-01-01 | 2024-05-24 |  |  | 2025-05-24 | No | Not Required | Not Required
26INR0374 | Cobra Clean Energy Center | SS Completed, FIS Started, No IA | Cobra Clean Energy Center LLC | looped on circuit 04 between Mustang Bayou (#42960) and Hudson (#42100) | Brazoria | COASTAL | 2027-10-08 | OTH | BA | 100.4 |  | 2024-07-09 | 2024-02-02 | 2024-05-01 | 2024-07-02 |  | No |  | No
26INR0408 | Liatris Flexible Gas | SS Completed, FIS Started, IA | Stone Creek Peaker LLC | Tap 138 kV (42980) Nash - (44010) WA Parish CKT02 | Brazoria | COASTAL | 2029-02-01 | GAS | GT | 204.71 |  | 2024-02-06 | 2024-03-22 | 2024-06-19 | 2024-03-06 |  | No | 2025-11-01 | Yes | 2024-05-22 | 2024-05-22 | 2026-02-18 | 2026-02-18
26INR0417 | GAMAY ENERGY STORAGE | SS Completed, FIS Started, IA | GAMAY ENERGY STORAGE LLC | Tap 138 kV Line from TNFM524 (39703) to West Columbia Main (39500), in Brazoria County. | Brazoria | COASTAL | 2028-01-01 | OTH | BA | 418.6 |  | 2024-01-30 | 2024-02-07 | 2024-04-30 | 2024-01-26 |  |  | 2025-05-27 | No | Not Required | Not Required
26INR0497 | Rosharon BESS | SS Completed, FIS Completed, No IA | Rosharon BESS LLC | 138 kV 42570 Archer (ACH) | Brazoria | COASTAL | 2028-06-30 | OTH | BA | 120 |  | 2025-01-07 | 2024-04-09 | 2024-07-05 | 2024-12-27 | 2026-01-14 | Yes |  | No
26INR0551 | Hastings Park BESS | SS Completed, FIS Completed, IA | Brazos Roots BESS, LLC | 39010 138kV HASTINGS | Brazoria | COASTAL | 2028-02-27 | OTH | BA | 256.34 | COD | 2024-08-02 | 2024-08-16 | 2024-11-01 | 2024-08-09 | 2025-03-21 |  | 2025-08-13 | No
27INR0061 | Hecate Energy Orem Wind | SS Completed, FIS Started, No IA | Hecate Energy LLC | 42530 Jones Creek 345kV | Brazoria | COASTAL | 2030-06-01 | WIN | WT | 1542 |  | 2024-06-27 | 2023-06-28 | 2023-09-22 | 2024-06-14 21:31 |  |  |  | No |  |  | Not Required
27INR0095 | Bulldog Power (TEF - Due Diligence) | SS Completed, FIS Completed, No IA | Bulldog Power LLC | 39703 TNMP FM524 Substation 138kV | Brazoria | COASTAL | 2027-12-18 | GAS | GT | 311 |  | 2023-11-13 | 2023-11-14 | 2024-02-08 | 2023-11-08 | 2026-03-20 | No |  | No
27INR0096 | Rubicon Power BESS | SS Completed, FIS Started, No IA | Rubicon Power LLC | 39703 TNMP FM524 138kV | Brazoria | COASTAL | 2027-12-31 | OTH | BA | 301.38 |  | 2023-11-13 | 2023-11-14 | 2024-02-08 | 2023-11-08 |  | No |  | No
27INR0209 | Goby Energy Center | SS Completed, FIS Started, No IA | Goby Energy Center | Tap 138kV line 44390 Karsten - 44721 Thompsons | Brazoria | COASTAL | 2029-09-07 | OTH | BA | 200.65 | COD | 2024-05-01 | 2024-05-20 | 2024-08-15 | 2024-05-07 |  |  |  | No
27INR0449 | Gulf Prairie Solar | SS Completed, FIS Started, No IA | Gulf Prairie Energy LLC | (CEHESub) looped either 1) on 138 kV circuit 82 between RIWOOD (#43150) and Angleton (#42110), or 2) on 345 kV circuit 18 between DOW (#42500) and Huizache (#46640) | Brazoria | COASTAL | 2028-12-01 | SOL | PV | 202.17 |  | 2025-05-29 | 2025-06-19 | 2025-09-16 | 2025-01-22 |  | Yes |  | No |  |  | Not Required
27INR0611 | Bodkin BESS SLF | SS Completed, FIS Started, No IA | Bodkin BESS, LLC | The 138kV Danbury Dab DANBUR_POI_8 (BUS#42875) Station | Brazoria | COASTAL | 2027-12-01 | OTH | BA | 0 |  | 2026-03-23 | 2026-04-02 | 2026-06-30 | 2026-03-23 |  | No |  | No | Not Required | Not Required
27INR0636 | Myrtle Solar Repower | SS Completed, FIS Completed, No IA | Myrtle Solar, LLC | 42110 Angleton 138kV | Brazoria | COASTAL | 2027-06-21 | SOL | PV | 314.27 | FIS Request | 2026-09-10 | 2026-09-10 |  | 2026-09-10 | 2026-09-15 |  |  | No |  |  | Not Required
28INR0295 | Margay Energy Storage | SS Completed, FIS Completed, IA | PowerPulse LLC | Tap 138kV 42750 Mykawa - 48353 Telephone Ckt 06 | Brazoria | COASTAL | 2029-04-10 | OTH | BA | 101.3 |  | 2025-01-29 | 2025-02-25 | 2025-05-20 | 2025-02-24 | 2025-11-13 |  | 2025-12-26 | No
28INR0448 | Gulf Prairie BESS | SS Completed, FIS Started, No IA | Gulf Prairie Energy LLC | (CEHESub) looped either 1) on 138 kV circuit 82 between RIWOOD (#43150) and Angleton (#42110), or 2) on 345 kV circuit 18 between DOW (#42500) and Huizache (#46640) | Brazoria | COASTAL | 2028-12-01 | OTH | BA | 207.78 |  | 2025-09-16 | 2025-09-22 | 2025-12-12 | 2025-09-03 |  | Yes |  | No
29INR0174 | Palisade BESS | SS Completed, FIS Started, No IA | Flexen USA LLC | Hoffman (42810) - Lake Jackson (42880) 138 kV line | Brazoria | COASTAL | 2029-10-01 | OTH | BA | 153.5 |  | 2025-09-23 | 2025-09-23 | 2025-12-23 | 2025-09-23 |  | No |  | No
30INR0073 | Bulldog Power II | SS Completed, FIS Started, No IA | Bulldog Power II LLC | 39703 TNMP FM524 Substation 138kV | Brazoria | COASTAL | 2030-09-30 | GAS | GT | 311 |  | 2025-11-25 | 2025-12-16 | 2026-02-04 | 2025-12-12 |  | No |  | No
25INR0347 | Cadet Storage | SS Completed, FIS Started, No IA | TX BESS 5, LLC | Tap 69kV 32864 BRYN_ATK69 to 32873 BRYN SHADY | Brazos | NORTH | 2029-07-28 | OTH | BA | 104.42 |  |  | 2023-05-22 | 2023-08-18 | 2023-04-24 |  |  |  | No
28INR0530 | Wickson Creek Gas | SS Completed, FIS Started, No IA | Wickson Creek Center, LLC | Jack Creek Station 345 kV (#975) | Brazos | NORTH | 2028-10-01 | GAS | GT | 1022.08 |  | 2026-06-08 | 2026-06-12 | 2026-09-04 | 2026-06-04 |  |  |  | No
28INR0271 | Three Ranches Solar | SS Completed, FIS Started, No IA | Three Ranches Energy LLC | TAP 138kV #6680 Alamitto Creek - #60444 Hayter Ranch | Brewster | WEST | 2029-12-01 | SOL | PV | 125.53 |  | 2025-02-10 | 2025-02-14 | 2025-05-12 | 2025-01-22 |  | No |  | No |  |  | Not Required
29INR0170 | Three Ranches BESS | SS Completed, FIS Started, No IA | Three Ranches Energy LLC | TAP 138kV #6680 Alamitto Creek - #60444 Hayter Ranch | Brewster | WEST | 2029-12-01 | OTH | BA | 103.37 |  | 2025-08-22 | 2025-08-21 | 2025-11-10 | 2025-08-29 |  | No |  | No
23INR0330 | BRP Snowdon BESS | SS Completed, FIS Started, No IA | BRP SNOWDON BESS LLC | 23914 Tule Canyon Substation 345kV | Briscoe | PANHANDLE | 2028-12-01 | OTH | BA | 410.94 |  | 2021-09-15 | 2021-09-15 | 2021-11-29 | 2021-09-08 |  |  |  | No
28INR0023 | Silverton Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap 345kV 23914 Tule Canyon - 79001 Cross_W1 | Briscoe | PANHANDLE | 2029-07-01 | SOL | PV | 410 |  | 2024-04-01 | 2023-12-04 | 2024-03-01 | 2024-03-18 21:54 |  |  |  | No |  |  | Not Required
29INR0030 | Commodus Solar | SS Completed, FIS Started, No IA | IP Blackwell, LLC | Tap 345kV 23914 Tule Canyon - 23900 Alibates | Briscoe | PANHANDLE | 2029-07-30 | SOL | PV | 502.1 |  | 2024-07-17 | 2024-07-22 | 2024-10-17 | 2024-07-11 |  |  |  | No |  |  | Not Required
29INR0031 | Commodus Wind | SS Completed, FIS Started, No IA | IP Blackwell, LLC | tap 345kV 23914 Tule Canyon - 23900 Alibates | Briscoe | PANHANDLE | 2029-07-30 | WIN | WT | 641.4 |  | 2024-07-17 | 2024-07-22 | 2024-10-17 | 2024-07-11 |  |  |  | No |  |  | Not Required
29INR0397 | Black Mountain Briscoe Gas | SS Started, FIS Started, No IA | Black Mountain Power LLC | ‎23914, Tule Canyon Substation, 345 kV | Briscoe | PANHANDLE | 2029-09-28 | GAS | CC | 495.32 | FIS Request | 2026-09-14 | 2026-09-18 |  | 2026-09-15 |  |  |  | No
23INR0087 | Kinenos Solar | SS Completed, FIS Started, No IA | Encino del Sol Energy, LLC | tap 345kV 8905 North Edinburg - 8455 Lon Hill | Brooks | SOUTH | 2029-12-31 | SOL | PV | 203.17 |  | 2020-08-28 | 2020-12-22 | 2021-03-10 | 2020-12-03 |  | No |  | No |  |  | Not Required
27INR0400 | Reforzar BESS 1 | SS Completed, FIS Completed, No IA | Tempus Power management LLC | 345 kV 80078 Reforzar | Brooks | SOUTH | 2028-04-13 | OTH | BA | 207.6 |  | 2024-09-30 | 2024-12-19 | 2025-03-17 | 2024-11-05 | 2026-06-18 | No |  | No
27INR0401 | Reforzar Bess 2 | SS Completed, FIS Started, No IA | Tempus Power management LLC | 345 kV 80078 Reforzar | Brooks | SOUTH | 2028-04-13 | OTH | BA | 207.6 |  | 2024-11-14 | 2024-12-19 | 2025-03-17 | 2024-10-10 |  | No |  | No
28INR0059 | Verily Solar (FKA Cuello De Cuero Solar) | SS Completed, FIS Started, No IA | Verily Solar, LLC | 80078 Reforzar Switch Station 345kV | Brooks | SOUTH | 2029-07-01 | SOL | PV | 261 |  | 2024-02-29 | 2024-03-22 | 2024-06-19 | 2024-03-06 |  |  |  | No |  |  | Not Required
19INR0075 | Horseshoe Bend Solar | SS Completed, FIS Started, No IA | Clenera | 1444 Brown 345kV | Brown | NORTH | 2028-02-20 | SOL | PV | 301.1 |  | 2018-02-09 | 2017-06-23 | 2017-08-07 | 2018-02-09 |  | No |  | No | Not Required | Not Required | Not Required
21INR0294 | Mountaineer Solar | SS Completed, FIS Started, No IA | Mustang Mountaineer Solar LLC | 1444 Brown 345 kV | Brown | NORTH | 2029-09-01 | SOL | PV | 329.26 |  | 2019-12-11 | 2019-04-16 | 2019-06-11 | 2019-12-08 |  |  |  | No | Not Required | Not Required | Not Required
24INR0331 | Chisme Storage | SS Completed, FIS Completed, No IA | Blue Heron Solar, LLC | Tap 345 kV 1444 BROWN SWITCH - 3424 BUCKHORN SWITCH | Brown | NORTH | 2027-04-13 | OTH | BA | 150.7 |  | 2023-01-11 | 2023-01-17 | 2023-04-14 | 2023-01-11 | 2026-06-23 | No |  | Yes | Not Required | Not Required | 2025-09-15 | 2025-09-15 | 2026-07-31 | 2026-07-31
24INR0333 | Chisme Solar | SS Completed, FIS Completed, No IA | Blue Heron Solar, LLC | Tap 345 kV 1444 BROWN SWITCH - 3424 BUCKHORN SWITCH | Brown | NORTH | 2027-04-13 | SOL | PV | 147 |  | 2023-01-11 | 2023-01-17 | 2023-04-14 | 2023-01-11 | 2026-06-23 |  |  | Yes | Not Required | Not Required | Not Required | 2025-09-16 | 2026-07-31 | 2026-07-31
24INR0544 | Wetzel BESS | SS Completed, FIS Started, No IA | Brown ESS, LLC | Tap 138kV 1654 Zephyr – 1655 Brownwood Switch | Brown | NORTH | 2028-09-09 | OTH | BA | 185.57 |  | 2023-03-14 | 2023-03-27 | 2023-06-20 | 2023-03-15 |  | No |  | No
27INR0291 | Nouveau BESS | SS Completed, FIS Started, No IA | RamZ BESS, LLC | 1444 Brown Switch - 3348 Russell Gap 345 kV Line | Brown | NORTH | 2027-12-15 | OTH | BA | 256.1 |  | 2024-07-31 | 2024-08-16 | 2024-01-08 | 2024-07-31 |  |  |  | No
27INR0432 | Coyote Ridge BESS | SS Completed, FIS Started, No IA | Grenergy USA | 292 Holder 138 kV | Brown | NORTH | 2027-10-06 | OTH | BA | 111.06 |  | 2025-01-16 | 2025-01-28 | 2025-04-17 | 2025-01-15 |  |  |  | No
28INR0166 | Brookesmith Storage | SS Completed, FIS Started, No IA | Brookesmith Storage LLC | Tap Brown Switch #1444 – Russell Gap Switch #3348 | Brown | NORTH | 2029-05-07 | OTH | BA | 351 |  | 2025-03-12 | 2025-04-01 | 2025-06-25 | 2025-05-21 |  |  |  | No
28INR0269 | Soluce Bravo Solar | SS Completed, FIS Started, No IA | BNPB1, LLC | tap 345kV 1444 BROWN - 11441 CORN TRAIL SW CKT2 | Brown | NORTH | 2029-09-17 | SOL | PV | 80.82 |  | 2025-10-29 | 2025-01-13 | 2025-04-08 |  |  |  |  | No |  |  | Not Required
28INR0270 | Soluce Bravo Storage | SS Completed, FIS Started, No IA | BNPB1, LLC | tap 345kV 1444 BROWN - 11441 CORN TRAIL SW CKT2 | Brown | NORTH | 2029-09-17 | OTH | BA | 302.62 |  | 2025-10-29 | 2025-01-13 | 2025-04-08 |  |  |  |  | No
30INR0111 | Tradition BESS | SS Completed, FIS Started, No IA | Horizon Energy Storage Greenfield Project Holdings LLC | 32878 Greens Prairie 138kV | Burleson | SOUTH | 2030-04-30 | OTH | BA | 150.36 |  | 2026-08-03 | 2026-05-26 | 2026-08-21 | 2026-07-17 |  |  |  | No
24INR0313 | Backbone Creek BESS | SS Completed, FIS Completed, IA | Backbone Creek BESS LLC | 7351 STARCKE 138kV | Burnet | SOUTH | 2026-12-01 | OTH | BA | 124.1 |  | 2022-05-09 | 2022-04-18 | 2022-07-08 | 2022-04-27 | 2025-09-08 | No | 2023-12-22 | Yes |  |  |  | 2023-12-22 | 2025-10-29 | 2025-10-29 |  |  | 2026-09-04 | 2026-09-21
26INR0499 | Mineral Springs BESS | SS Completed, FIS Started, No IA | Burnet County LLC | 7065 DOBVI 138kV | Burnet | SOUTH | 2027-11-02 | OTH | BA | 104 |  | 2024-12-16 | 2024-06-03 | 2024-08-30 | 2024-10-21 |  |  |  | No
27INR0124 | RedSun Solar | SS Completed, FIS Completed, IA | Redsun Solar Project LLC | Tap 138kV 7100 Burnet - 7529 Bertram | Burnet | SOUTH | 2028-08-28 | SOL | PV | 82.55 |  | 2023-11-28 | 2023-12-04 | 2024-03-01 | 2023-11-28 | 2025-07-29 | No | 2025-09-25 | No |  |  | Not Required
27INR0125 | RedSun BESS | SS Completed, FIS Completed, No IA | Redsun Solar Project LLC | Existing Line from Substation Name: Burnet (PSSE#7100) to Substation Name: Bertram (PSSE#7520) | Burnet | SOUTH | 2028-08-28 | OTH | BA | 84.04 |  | 2023-11-27 | 2023-12-04 | 2024-03-01 | 2023-11-21 | 2025-07-29 | No |  | No
20INR0245 | Volunteer Storage | SS Completed, FIS Started, No IA | Blackjack Storage LLC | 7216 Lockhart 138kV | Caldwell | SOUTH | 2028-02-29 | OTH | BA | 50.6 |  | 2019-01-16 | 2019-01-15 | 2019-07-02 | 2019-03-15 |  |  |  | No | Not Required | Not Required
22INR0473 | TAIN SOLAR | SS Completed, FIS Started, No IA | Abei Energy Green VII LLC | tap 138kV 7216 Lockhart - 7224 Luling City | Caldwell | SOUTH | 2027-10-27 | SOL | PV | 37.54 |  | 2021-11-02 | 2020-12-03 | 2021-02-17 | 2021-10-20 |  |  |  | No |  |  | Not Required
23INR0135 | Elbus BESS | SS Completed, FIS Started, No IA | BRP Elbus BESS LLC | 9075 Lytton 138kV | Caldwell | SOUTH | 2028-06-01 | OTH | BA | 200.99 |  | 2020-11-30 | 2020-12-03 | 2021-02-18 | 2020-11-25 |  |  |  | No
23INR0503 | Ardesia Storage | SS Completed, FIS Started, No IA | Ardesia Storage Project LLC | Tap 138kV 7325 Mendoza - 7216 Lockhart | Caldwell | SOUTH | 2030-03-29 | OTH | BA | 100 |  | 2022-08-29 | 2022-06-10 | 2022-09-06 | 2022-07-22 |  |  |  | No
25INR0129 | Demeter Solar | SS Completed, FIS Started, No IA | Demeter Solar, LLC | Tap 138kV 7224 LULING - 7216 LOCKHART | Caldwell | SOUTH | 2029-06-01 | SOL | PV | 88 |  | 2023-03-17 | 2022-08-05 | 2022-11-01 | 2023-03-10 |  |  |  | No |  |  | Not Required
25INR0130 | Demeter Storage | SS Completed, FIS Started, No IA | Demeter Solar, LLC | Tap 138kV 7224 LULING - 7216 Lockhart | Caldwell | SOUTH | 2029-06-01 | OTH | BA | 65 |  | 2023-03-17 | 2022-08-05 | 2022-11-01 | 2023-03-10 |  |  |  | No
26INR0523 | Demeter Storage 2 | SS Completed, FIS Started, No IA | Demeter Solar, LLC | Tap 138kV 7224 LULING - 7216 Lockhart | Caldwell | SOUTH | 2029-06-01 | OTH | BA | 138 |  | 2024-09-17 | 2024-10-01 | 2024-12-30 | 2024-09-19 |  |  |  | No
27INR0478 | Metro BESS | SS Completed, FIS Started, No IA | Metro BESS LLC | 138 kV LYTTON8 (9075) | Caldwell | SOUTH | 2030-12-07 | OTH | BA | 200.71 |  | 2025-02-22 | 2025-02-25 | 2025-05-20 | 2025-02-24 |  |  |  | No
27INR0584 | Lytton Springs Solar | SS Completed, FIS Started, No IA | SMT Lytton Springs LLC | Lytton Springs (#9074) – Fayette Plant (#7055) 345 kV Line | Caldwell | SOUTH | 2028-12-01 | SOL | PV | 55.3 |  | 2025-12-01 | 2025-12-02 | 2026-01-19 | 2025-11-26 |  |  |  | No | Not Required | Not Required | Not Required
27INR0585 | Lytton Springs BESS | SS Completed, FIS Started, No IA | SMT Lytton Springs LLC | Lytton Springs (#9074) – Fayette Plant (#7055) 345 kV Line | Caldwell | SOUTH | 2028-12-01 | OTH | BA | 76.4 |  | 2025-12-01 | 2025-12-02 | 2026-01-19 | 2025-11-26 |  |  |  | No | Not Required | Not Required
29INR0167 | Big Watt Power Austin-1 | SS Completed, FIS Started, No IA | Big Watt Power Austin-1 LLC | Tapping the 345 kV Double circuit Line: Zorn (Bus# 7042) - Lytton Springs (Bus# 9074) and Zorn (Bus# 7042) - Austrop (Bus# 7040). | Caldwell | SOUTH | 2028-11-15 | GAS | CC | 448.98 | COD | 2025-09-26 | 2025-10-03 | 2025-11-14 | 2025-09-26 |  |  |  | No
29INR0176 | SCHNEIDER GAS RICE | SS Completed, FIS Started, IA | LCRA | Double Tap 345kV #7042 Zorn - #7040 Austrop and #7042 Zorn - #9074 Lytton Springs | Caldwell | SOUTH | 2032-12-14 | GAS | IC | 113.02 | COD | 2025-07-22 | 2025-07-29 | 2025-10-26 | 2025-07-25 |  |  | 2025-12-19 | No
29INR0340 | Bobcat Generating Station | SS Completed, FIS Started, No IA | Critical Grid Solutions Bobcat, LLC | Between (7042) ZORN & (9074) LYTTON SPRINGS Substations on ONCOR 345kV. | Caldwell | SOUTH | 2029-11-01 | GAS | IC | 450 |  | 2026-06-22 | 2026-06-24 | 2026-09-19 | 2026-06-22 |  |  |  | No
30INR0031 | Caldwell County Energy Center | SS Completed, FIS Started, No IA | Caldwell County Energy Center, LLC | #7051 Misty Substation 345kV | Caldwell | SOUTH | 2030-04-30 | GAS | CC | 1500 |  |  | 2025-02-03 | 2025-05-03 | 2025-10-29 |  | No |  | No
30INR0054 | SCHNEIDER COMBINED CYCLE | SS Completed, FIS Started, IA | LCRA | Double Tap 345kV #7042 Zorn - #7040 Austrop and #7042 Zorn - #9074 Lytton Springs | Caldwell | SOUTH | 2033-05-10 | GAS | CC | 880 | COD | 2025-07-22 | 2025-07-29 | 2025-10-26 | 2025-07-25 |  |  | 2025-12-19 | No
31INR0013 | SCHNEIDER GAS RICE PHASE 2 | SS Completed, FIS Started, IA | LCRA | Double Tap 345kV #7042 Zorn - #7040 Austrop and #7042 Zorn - #9074 Lytton Springs | Caldwell | SOUTH | 2032-12-14 | GAS | IC | 113.02 | COD | 2025-07-22 | 2025-07-29 | 2025-10-26 | 2025-07-25 |  |  | 2025-12-19 | No
20INR0266 | Tres Bahias Solar | SS Completed, FIS Completed, IA | Tres Bahias Solar Power LLC | 8140 Joslin 138kV | Calhoun | COASTAL | 2026-08-31 | SOL | PV | 195 |  | 2019-06-03 | 2019-03-26 | 2019-06-11 | 2019-06-03 | 2022-01-21 |  | 2020-08-07 | Yes | Not Required | Not Required | Not Required | 2020-10-07 | 2022-12-20 | 2023-01-30 |  |  | 2023-06-26 | 2023-09-12
23INR0123 | Vaca Storage | SS Completed, FIS Started, No IA | Long Mount Storage, LLC | 138kV 8723 Cangrejo | Calhoun | COASTAL | 2029-07-01 | OTH | BA | 101 |  | 2022-06-01 | 2021-03-26 | 2021-06-14 | 2022-05-11 |  | No |  | No | Not Required | Not Required
26INR0019 | HyFuels Green Lake Solar | SS Completed, FIS Started, No IA | HyFuels Green Lake Solar LLC | Dokmai 138kV Substation (bus #80090) | Calhoun | COASTAL | 2027-12-01 | SOL | PV | 347 |  | 2023-06-09 | 2022-09-27 | 2022-12-22 | 2023-06-13 |  |  |  | No |  |  | Not Required
27INR0466 | Wolfram Storage | SS Completed, FIS Started, No IA | Nova Clean Energy, LLC | Dokmai 138kV Substation (bus #80090) | Calhoun | COASTAL | 2027-12-01 | OTH | BA | 206.6 |  | 2025-04-04 | 2025-05-19 | 2025-08-15 | 2025-05-02 |  |  |  | No
20INR0083 | Baird North Wind | SS Completed, FIS Completed, IA | BMP Wind, LLC | 68008 Latimer 345kV | Callahan | WEST | 2026-12-31 | WIN | WT | 340 |  |  | 2018-05-04 | 2018-06-12 | 2018-08-20 | 2020-10-30 | No | 2019-05-31 | Yes | Not Required | Not Required | Not Required | 2019-07-19 | 2020-10-30 | 2020-11-01 |  |  | 2021-08-09 | 2021-08-20
22INR0262 | Sequoia II Solar | SS Completed, FIS Completed, IA | ENBRIDGE SOLAR SEQUOIA II LLC | 68051 Reata 345kV | Callahan | WEST | 2027-01-28 | SOL | PV | 417.47 | COD | 2020-09-02 | 2020-01-22 | 2020-04-08 | 2020-08-27 | 2026-03-16 | No | 2023-08-29 | Yes | Not Required | Not Required | Not Required | 2025-09-22 | 2026-04-28 | 2026-04-28
25INR0446 | Guitar BESS | SS Completed, FIS Started, No IA | Guitar BESS LLC | Tap 138kV 6275 ABEAST4A - 6670 PUTN4C | Callahan | WEST | 2027-12-31 | OTH | BA | 204.79 |  | 2024-04-15 | 2023-05-15 | 2023-08-11 | 2024-04-03 |  |  |  | No
28INR0245 | Hittson Creek Solar | SS Completed, FIS Started, No IA | 174 Power Global Properties | Tapping the two 345 kV Lines: Sam Line Reactor (Bus# 68005) - Reata (Bus# 68051) and Latimer (Bus# 68008) - Reata (Bus# 68051). | Callahan | WEST | 2028-12-15 | SOL | PV | 402.93 |  | 2024-12-17 | 2024-12-19 | 2025-03-18 | 2024-12-18 |  |  |  | No |  |  | Not Required
28INR0246 | Hittson Creek BESS | SS Completed, FIS Started, No IA | 174 Power Global Properties | Tapping the two 345 kV Lines: Sam Line Reactor (Bus# 68005) - Reata (Bus# 68051) and Latimer (Bus# 68008) - Reata (Bus# 68051). | Callahan | WEST | 2028-12-15 | OTH | BA | 205.38 |  | 2024-12-17 | 2024-12-19 | 2025-03-18 | 2024-12-18 |  |  |  | No
20INR0086 | Arroyo Solar | SS Completed, FIS Started, IA | BT Cantwell Solar, LLC | 345 KV Tap #8318 Rio Hondo - #8317 La Palma | Cameron | COASTAL | 2028-02-22 | SOL | PV | 100 |  | 2018-10-10 | 2018-05-09 | 2018-07-09 | 2018-10-10 |  | No | 2021-09-28 | Yes | Not Required | Not Required | Not Required | 2025-08-05
22INR0401 | Eval Storage | SS Completed, FIS Started, IA | Hecate Grid East Valley Storage LLC | 80229 Cavazos 138kV | Cameron | COASTAL | 2029-04-30 | OTH | BA | 251.85 |  | 2020-12-29 | 2020-10-23 | 2021-01-12 | 2020-11-03 |  | No | 2022-02-03 | Yes | Not Required | Not Required |  | 2025-02-14
22INR0469 | Harper Energy Storage | SS Completed, FIS Started, No IA | VESI 31 LLC | Tap 138kV 8314 La Palma - 80229 Villa Cavazos | Cameron | COASTAL | 2028-09-15 | OTH | BA | 82.42 |  | 2022-02-10 | 2021-12-03 | 2022-03-01 | 2022-01-27 |  |  |  | No
22INR0480 | Pachanga Wind | SS Completed, FIS Started, No IA | Pachanga Wind LLC | tap 345kV 5966 Palmito - 80137 Stewart Rd | Cameron | COASTAL | 2030-04-08 | WIN | WT | 300 |  | 2021-06-28 | 2021-02-09 | 2021-05-06 | 2021-04-05 |  |  |  | No |  |  | Not Required
23INR0066 | Accalia Point Solar | SS Completed, FIS Started, No IA | Accalia Point Solar LLC | Tap 345kV 8383 North Edingburg – 79501 Kingfisher | Cameron | COASTAL | 2029-05-31 | SOL | PV | 190.5 |  | 2021-02-10 | 2020-10-23 | 2021-01-12 | 2021-01-27 |  | No |  | No |  |  | Not Required
24INR0306 | Arroyo Storage | SS Completed, FIS Completed, IA | BT Cantwell Solar, LLC | Tap 345kV 8318 Rio Hondo - 8317 La Palma (New Gulch Substation ) | Cameron | COASTAL | 2026-10-23 | OTH | BA | 183.76 |  | 2022-05-03 | 2022-05-10 | 2022-08-05 | 2022-04-26 | 2024-04-30 |  | 2022-08-10 | Yes |  |  |  | 2024-06-24 | 2024-06-24 | 2024-10-29 |  |  | 2025-12-08 | 2026-06-25
24INR0319 | Burro Loco Energy Storage | SS Completed, FIS Started, No IA | VESI | 8626 Resaca 69kV | Cameron | COASTAL | 2028-09-15 | OTH | BA | 25.14 |  | 2022-07-14 | 2022-07-18 | 2022-10-14 | 2022-07-08 |  |  |  | No | Not Required | Not Required
24INR0572 | Megacharge BESS | SS Completed, FIS Started, No IA | SMT Harlingen III LLC | 8320 WEST HARLINGEN 69kV | Cameron | COASTAL | 2028-07-01 | OTH | BA | 110 |  | 2023-06-27 | 2023-06-28 | 2023-09-20 | 2023-06-26 |  |  |  | No
25INR0270 | Harryoung Solar | SS Completed, FIS Started, No IA | Gransolar Texas Four LLC | Tap 8319 Rio Hondo - SOUTH SANTA ROSA: 8359, 138kV | Cameron | COASTAL | 2028-05-15 | SOL | PV | 190.01 |  | 2023-11-02 | 2022-11-23 | 2023-02-17 | 2023-08-14 |  |  |  | No | Not Required | Not Required | Not Required
25INR0385 | Bobcat Cameron BESS | SS Completed, FIS Started, No IA | Bobcat BESS, LLC | 5764 East Rio Hondo Substation 138kV | Cameron | COASTAL | 2027-12-31 | OTH | BA | 200.78 |  | 2023-04-06 | 2023-04-19 | 2023-07-14 | 2023-04-11 |  |  |  | No
25INR0552 | HarryoungBESS | SS Completed, FIS Started, No IA | Gransolar Texas Four LLC | 8319 Rio Hondo sub 138kV | Cameron | COASTAL | 2028-05-15 | OTH | BA | 190.01 |  | 2023-09-26 | 2023-10-04 | 2023-12-19 | 2023-09-19 |  |  |  | No | Not Required | Not Required
26INR0008 | Puerto Del Sol 1 | SS Completed, FIS Started, No IA | PUERTO DEL SOL, LLC | Tap 345kV 79500 Palmito - 79501 King Fisher Ckt 1 | Cameron | COASTAL | 2026-12-31 | SOL | PV | 213.8 |  | 2023-01-20 | 2022-05-16 | 2022-08-13 | 2023-01-13 16:05 |  |  |  | No | Not Required | Not Required | Not Required
26INR0181 | Solar Star Frontier BESS | SS Completed, FIS Started, No IA | Solar Star Frontier BESS, LLC | 8656 Luna 138kV | Cameron | COASTAL | 2029-02-27 | OTH | BA | 101.02 |  | 2023-12-23 | 2023-06-28 | 2023-09-22 | 2023-12-18 |  | No |  | No | Not Required | Not Required
26INR0461 | Rio Hondo BESS | SS Completed, FIS Started, No IA | SBESS TX25 LLC | Tap 138kV #80309 Las Pulgas - #8319 Rio Hondo | Cameron | COASTAL | 2028-06-30 | OTH | BA | 200.78 |  | 2024-04-18 | 2024-05-09 | 2024-08-05 | 2024-04-18 |  | No |  | No
26INR0515 | Rio Grand Valley Element Fuels Power | SS Completed, FIS Started, No IA | Element H2Gen, LLC | Tap 138kV 59450 Waterport Substation - 5789 Southmost Sub | Cameron | COASTAL | 2028-12-05 | HYD | OT | 79.63 |  | 2025-04-14 | 2024-06-13 | 2024-09-10 | 2025-03-03 |  |  |  | No
26INR0640 | Amberjack2 BESS | SS Completed, FIS Started, No IA | Hunt Energy Network, LLC | 79501 KINGFISHER 345KV | Cameron | COASTAL | 2028-04-03 | OTH | BA | 180 |  | 2024-12-26 | 2025-01-28 | 2025-05-03 | 2025-01-06 |  |  |  | No
27INR0002 | Puerto Del Sol 2 | SS Completed, FIS Started, No IA | PUERTO DEL SOL, LLC | Tap 345kV 79500 Palmito - 79501 King Fisher Ckt 1 | Cameron | COASTAL | 2027-12-31 | SOL | PV | 213.8 |  | 2023-03-28 | 2022-05-16 | 2022-08-13 | 2023-01-30 17:14 |  |  |  | No |  |  | Not Required
27INR0084 | Aegle Power | SS Completed, FIS Started, No IA | Aegle Power LLC | (#79501) Kingfisher 345 kV | Cameron | COASTAL | 2027-07-30 | GAS | CC | 1536.4 |  | 2024-07-03 | 2024-07-22 | 2024-10-17 | 2024-07-03 |  |  |  | No
27INR0399 | Resaca Oasis Storage | SS Completed, FIS Completed, IA | Resaca Oasis Storage, LLC | # 79601 Stillman Substation 138 kV | Cameron | COASTAL | 2028-09-20 | OTH | BA | 200.7 |  | 2024-12-03 | 2024-12-12 | 2025-03-03 | 2024-11-22 | 2025-10-10 | No | 2025-05-22 | Yes | Not Required | Not Required | 2025-09-15 | 2025-06-03
28INR0397 | Ouroboros Grid BESS 1 | SS Completed, FIS Started, No IA | Ouroboros Grid BESS Unit 1 | POIB: #88337 Chalybe 345 kV (expansion of the #8735 Chalybe 138 kV – to be connected by double circuit line to #79500 Palmito 345 kV) | Cameron | COASTAL | 2028-06-01 | OTH | BA | 200.82 |  | 2026-01-20 | 2025-07-29 | 2025-10-22 |  |  |  |  | No
28INR0398 | Ouroboros Grid BESS 2 | SS Completed, FIS Started, No IA | Ouroboros Grid BESS Unit 2 | 88337 Chalybe 345 kV | Cameron | COASTAL | 2028-06-01 | OTH | BA | 200.81 |  | 2026-01-20 | 2025-07-29 | 2025-10-22 |  |  |  |  | No
28INR0403 | Ouroboros Grid BESS 3 | SS Completed, FIS Started, No IA | Ouroboros Grid BESS Unit 3 | 88337 Chalybe 345 kV | Cameron | COASTAL | 2028-06-01 | OTH | BA | 200.72 |  | 2026-01-22 | 2025-07-29 | 2025-10-22 |  |  |  |  | No
28INR0427 | Ouroboros Grid BESS 4 | SS Completed, FIS Started, No IA | Ouroboros Grid BESS Unit 4 | 79500 Palmito 345kV | Cameron | COASTAL | 2029-06-01 | OTH | BA | 201.14 |  | 2026-03-19 | 2025-08-18 | 2025-11-21 |  |  |  |  | No
28INR0428 | Ouroboros Grid BESS 5 | SS Completed, FIS Started, No IA | Ouroboros Grid BESS Unit 5 | 79500 Palmito 345KV | Cameron | COASTAL | 2029-06-01 | OTH | BA | 200.96 |  | 2026-03-19 | 2025-08-18 | 2025-11-21 |  |  |  |  | No
28INR0429 | Ouroboros Grid BESS 6 | SS Completed, FIS Started, No IA | Ouroboros Grid BESS Unit 6 | 79500 Palmito 345KV | Cameron | COASTAL | 2029-06-01 | OTH | BA | 200.94 |  | 2026-03-19 | 2025-08-18 | 2025-11-21 |  |  |  |  | No
23INR0283 | Kota Battery | SS Completed, FIS Started, No IA | Kota Storage, LLC | 23900 Alibates 345kV | Carson | PANHANDLE | 2028-10-31 | OTH | BA | 200.8 |  | 2021-06-02 | 2021-06-07 | 2021-08-27 | 2021-06-02 |  |  |  | No
27INR0022 | Panhandle Flagship Solar 1 | SS Completed, FIS Started, IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005) | Carson | PANHANDLE | 2031-06-30 | SOL | PV | 439.4 |  | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-02-23 |  | Yes | 2025-08-28 | No |  |  | Not Required
27INR0025 | Panhandle Flagship Storage | SS Completed, FIS Started, IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005) | Carson | PANHANDLE | 2031-06-30 | OTH | BA | 371.7 |  | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-02-23 |  | Yes | 2025-08-28 | No |  |  | 2026-01-30
27INR0140 | Kingsmill Wind SLF | SS Completed, FIS Started, IA | Kingsmill Wind, LLC | 79005 Railhead 345kV | Carson | PANHANDLE | 2029-09-01 | WIN | WT | 606.3 |  | 2025-03-18 | 2024-01-11 | 2024-04-08 | 2024-10-08 |  |  | 2025-12-18 | No |  |  | Not Required
16INR0049 | Nazareth Solar | SS Completed, FIS Completed, IA | TX Nazareth Solar, LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala C2 | Castro | PANHANDLE | 2027-08-31 | SOL | PV | 203 |  | 2014-07-07 | 2014-06-19 | 2014-07-25 | 2014-07-01 | 2025-07-29 | No | 2026-03-05 | Yes | Not Required | Not Required | Not Required | 2024-03-22
20INR0050 | Castro Solar | SS Completed, FIS Started, IA | Castro Solar One, LLC | 23912 Ogallala 345kV | Castro | PANHANDLE | 2029-04-18 | SOL | PV | 224.67 | COD | 2018-05-15 | 2018-02-08 | 2018-04-09 | 2018-05-15 |  | No | 2020-11-30 | No | Not Required | Not Required | Not Required
23INR0015 | Scarlet Solar | SS Completed, FIS Started, No IA | Innovative Solar 416, LLC | tap 345kV 23912 Ogallala - 23910 Windmill | Castro | PANHANDLE | 2025-08-26 | SOL | PV | 180 |  | 2020-09-16 | 2019-12-11 | 2020-03-06 | 2020-08-31 |  |  |  | No |  |  | Not Required
25INR0460 | Acker BESS | SS Completed, FIS Started, IA | Ogallala BESS LLC | 23912 Ogallala 345 kV | Castro | PANHANDLE | 2029-04-17 | OTH | BA | 301.04 |  | 2023-05-26 | 2023-06-07 | 2023-09-01 | 2023-05-09 |  |  | 2025-04-21 | No | Not Required | Not Required
27INR0143 | Ogalalla Storage | SS Completed, FIS Started, No IA | Hecate Energy Ogalalla Solar LLC | 23912 OGALLALA_5 345kV | Castro | PANHANDLE | 2028-04-15 | OTH | BA | 251.6 |  | 2024-04-24 | 2024-01-03 | 2024-03-25 | 2024-04-19 |  |  |  | No
29INR0034 | Cavell Solar | SS Completed, FIS Started, No IA | IP Cavell, LLC | Tap 345kV 23910 Windmill - 23912 Ogallala Ckt 1 | Castro | PANHANDLE | 2029-07-30 | SOL | PV | 502.1 |  | 2024-07-03 | 2024-07-22 | 2024-10-17 | 2024-06-28 |  | No |  | No |  |  | Not Required
29INR0035 | Cavell Wind | SS Completed, FIS Started, No IA | IP Cavell, LLC | tap 345kV 23910 Windmill - 23912 Ogallala Ckt 1 | Castro | PANHANDLE | 2029-07-30 | WIN | WT | 641.2 |  | 2024-07-03 | 2024-07-22 | 2024-10-17 | 2024-07-03 |  | No |  | No |  |  | Not Required
23INR0029 | Cedar Bayou 5 (TEF - Due Diligence) | SS Completed, FIS Completed, IA | NRG Cedar Bayou 5 LLC | 40000 Cedar Bayou 345kV | Chambers | HOUSTON | 2028-03-31 | GAS | GT | 697 | COD | 2020-03-31 | 2020-03-26 | 2020-06-04 | 2020-03-18 | 2025-05-30 | No | 2022-01-10 | Yes | 2021-03-17 | 2021-03-17 | 2024-06-07 | 2025-02-12
23INR0425 | Coneflower Storage Project | SS Completed, FIS Completed, IA | Coneflower Storage Project LLC | 40855 JORDON 138 kV | Chambers | HOUSTON | 2028-02-28 | OTH | BA | 170.85 |  | 2022-07-11 | 2021-12-20 | 2022-03-11 | 2022-07-06 | 2026-03-19 | No | 2024-03-25 | Yes | Not Required | Not Required |  | 2024-04-11
24INR0285 | APV Plumwood Storage | SS Completed, FIS Started, IA | APV Lonestar Energy LLC | Tap 138kV 40171 Baytown - 40015Cedar Bayou Plant | Chambers | HOUSTON | 2029-10-01 | OTH | BA | 200.82 |  | 2022-03-18 | 2022-03-30 | 2022-06-26 | 2022-03-22 |  | No | 2024-09-03 | No | Not Required | Not Required
18INR0009 | Eagle Pines Gas | SS Completed, FIS Started, No IA | FGE Power | tap 345kV 3109 Stryker - 3123 Trinidad | Cherokee | NORTH | 2028-10-30 | GAS | CC | 1173.5 |  | 2015-03-24 | 2015-03-30 | 2015-06-23 | 2015-04-29 |  |  |  | No | 2017-02-14 | 2015-11-04 |  |  |  |  | 2026-01-30 | 2028-08-14
23INR0324 | Lumberjack Storage | SS Completed, FIS Started, IA | EDP Renewables North America LLC | 138 kV Tap 3110 Stryker Creek - 3147 Troup | Cherokee | NORTH | 2029-11-01 | OTH | BA | 50.94 |  | 2022-04-20 | 2021-08-12 | 2021-10-29 | 2022-04-06 |  | No | 2024-03-20 | No | Not Required | Not Required
25INR0414 | Rogers Creek BESS | SS Completed, FIS Started, No IA | Dialville BESS | Tap 138 KV DailVille (3160) - Neches Pump (3296) | Cherokee | NORTH | 2029-04-17 | OTH | BA | 100.33 |  | 2023-05-03 | 2023-05-15 | 2023-08-11 | 2023-05-03 |  | No |  | No
21INR0455 | Independence Trail Storage | SS Completed, FIS Started, No IA | KCE TX 16, LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2028-01-01 | OTH | BA | 100 |  | 2019-11-11 | 2019-12-03 | 2020-02-24 | 2019-10-22 |  |  |  | No | Not Required | Not Required
25INR0515 | Fagus Storage SLF | SS Completed, FIS Started, No IA | Greenalia Energy Storage MISAE II LLC | 60501 Tesla 345kV | Childress | PANHANDLE | 2026-09-01 | OTH | BA | 0 |  | 2023-10-19 | 2023-10-25 | 2024-01-22 | 2023-09-22 |  |  |  | No
26INR0524 | Fagus Solar Park 3 SLF | SS Completed, FIS Completed, IA | Greenalia Solar Power Misae III, LLC | 60501 Tesla 345 kV | Childress | PANHANDLE | 2027-06-28 | SOL | PV | 169.59 |  |  | 2024-06-03 | 2018-07-06 | 2024-05-30 | 2026-06-23 | No | 2019-02-21 | Yes | Not Required | Not Required | Not Required | 2024-12-19
23INR0228 | Hiru Solar | SS Completed, FIS Started, No IA | Hecate Energy Hazel LLC | Tap 345kV 6111 Riley - 1730 West Krum ckt 1 | Clay | WEST | 2029-04-01 | SOL | PV | 603.7 |  | 2021-09-08 | 2021-04-21 | 2021-07-14 | 2021-08-30 |  | No |  | No | Not Required | Not Required | Not Required
24INR0444 | Hiru Storage | SS Completed, FIS Started, No IA | Hecate Energy Hazel LLC | Tap 345kV 6111 Riley - 1730 West Krum ckt 1 | Clay | WEST | 2029-04-01 | OTH | BA | 503.6 |  | 2023-12-22 | 2022-11-15 | 2023-02-10 | 2023-08-19 00:08 |  |  |  | No
25INR0097 | Soleil Solar | SS Completed, FIS Started, IA | Soleil Solar, LLC | Tap 345 kV 1730 Krum West Switch - 6111 Riley ckt 2 | Clay | WEST | 2028-12-28 | SOL | PV | 451.69 |  | 2022-08-31 | 2022-09-02 | 2022-11-29 | 2022-08-26 |  |  | 2025-05-09 | Yes |  |  | Not Required
26INR0612 | Clay County Yang Storage | SS Completed, FIS Started, No IA | DM-CCY, LLC | 1458 Cobb Switching Station 345 kV | Clay | WEST | 2029-04-16 | OTH | BA | 307.51 | MW Size | 2024-12-20 | 2024-12-26 | 2025-03-19 | 2024-12-20 |  |  |  | No
21INR0253 | Ulysses Solar | SS Completed, FIS Completed, IA | BNB Tennyson Solar LLC | 60072 Odysseus Substation 345 kV | Coke | WEST | 2027-03-17 | SOL | PV | 151.2 | COD | 2019-05-14 | 2019-01-25 | 2019-04-05 | 2019-05-10 | 2025-12-15 | No | 2022-10-03 | Yes | Not Required | Not Required | Not Required | 2022-12-05 | 2026-01-21 | 2026-01-21 |  |  | 2026-09-18
25INR0135 | Hayrick BESS | SS Completed, FIS Completed, No IA | Gransolar Texas Five LLC | 6351 Nicole 138kV | Coke | WEST | 2028-03-15 | OTH | BA | 113.9 |  | 2023-05-31 | 2022-08-16 | 2022-11-11 | 2023-05-18 | 2025-12-15 | No |  | No
26INR0218 | Fort Chadbourne Cattle BESS | SS Completed, FIS Started, No IA | Fort Chadbourne BESS | 6324 Fort Chadbourne 138 kv | Coke | WEST | 2027-06-29 | OTH | BA | 50.23 |  | 2023-08-14 | 2023-08-21 | 2023-11-06 | 2023-07-31 |  |  |  | No
27INR0453 | Roboman Solar | SS Completed, FIS Started, No IA | Roboman Solar, LLC | Tap 345 kV (#76009) Twin Buttes – (#76090) Divide Ckt 1 | Coke | WEST | 2029-07-01 | SOL | PV | 272.6 |  | 2025-06-26 | 2025-07-07 | 2025-09-30 | 2025-06-26 |  |  |  | No | Not Required | Not Required | Not Required
28INR0155 | Coke BESS | SS Completed, FIS Started, No IA | Coke ESS, LLC | 76090 Divide Switchyard 345kV | Coke | WEST | 2028-04-10 | OTH | BA | 220.3 |  | 2024-09-24 | 2024-10-01 | 2024-12-09 | 2024-09-27 |  |  |  | No
23INR0086 | Hanson Solar | SS Completed, FIS Completed, IA | Hanson Solar, LLC | tap 345kV 1444 Brown - 11406 Central Bluff | Coleman | WEST | 2027-08-17 | SOL | PV | 398.83 |  | 2021-03-30 | 2020-10-23 | 2021-02-02 | 2021-03-25 | 2026-03-26 |  | 2023-09-20 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2026-07-29 | 2026-07-29
23INR0794 | Invictus Energy Storage | SS Completed, FIS Started, No IA | GSA Land Holdings | 6390 FIREROCK4A 138kV | Coleman | WEST | 2028-05-31 | OTH | BA | 140.53 |  | 2024-06-21 | 2024-01-03 | 2024-03-28 | 2024-06-11 |  |  |  | No
28INR0469 | Paintbrush PV1 | SS Completed, FIS Started, No IA | Renew Development HoldCo LLC | Tap 345kV 1444 Brown Switch – 60040 Bluff Creek Switch & 1444 Brown Switch – 11406 Central Bluff Switch | Coleman | WEST | 2030-05-15 | SOL | PV | 251.5 |  | 2025-11-23 | 2025-12-02 | 2026-01-19 | 2025-11-13 |  |  |  | No |  |  | Not Required
28INR0470 | Paintbrush PV2 | SS Completed, FIS Started, No IA | Renew Development HoldCo LLC | Tap 345kV 1444 Brown Switch – 60040 Bluff Creek Switch & 1444 Brown Switch – 11406 Central Bluff Switch | Coleman | WEST | 2030-05-15 | SOL | PV | 251.5 |  | 2025-11-23 | 2025-12-02 | 2026-01-19 | 2025-11-13 |  |  |  | No |  |  | Not Required
29INR0220 | Paintbrush PV3 | SS Completed, FIS Started, No IA | Renew Development HoldCo LLC | Tap 345kV 1444 Brown Switch – 60040 Bluff Creek Switch & 1444 Brown Switch – 11406 Central Bluff Switch | Coleman | WEST | 2030-10-15 | SOL | PV | 251.5 |  | 2025-11-23 | 2025-12-02 | 2026-01-19 | 2025-11-13 |  |  |  | No |  |  | Not Required
29INR0221 | Paintbrush PV4 | SS Completed, FIS Started, No IA | Renew Development HoldCo LLC | Tap 345kV 1444 Brown Switch – 60040 Bluff Creek Switch & 1444 Brown Switch – 11406 Central Bluff Switch | Coleman | WEST | 2030-10-15 | SOL | PV | 251.5 |  | 2025-11-23 | 2025-12-02 | 2026-01-19 | 2025-11-13 |  |  |  | No |  |  | Not Required
29INR0222 | Paintbrush BESS1 | SS Completed, FIS Started, No IA | Renew Development HoldCo LLC | Tap 345kV 1444 Brown Switch – 60040 Bluff Creek Switch & 1444 Brown Switch – 11406 Central Bluff Switch | Coleman | WEST | 2030-10-15 | OTH | BA | 201.31 |  | 2025-11-23 | 2026-01-13 | 2026-04-07 | 2025-12-10 |  | No |  | No
24INR0274 | Bufflehead BESS | SS Completed, FIS Completed, IA | Boxcar Energy Storage, LLC | 2475 Lavon Switch 138kV | Collin | NORTH | 2027-02-15 | OTH | BA | 153.77 |  | 2022-02-25 | 2022-03-07 | 2022-06-02 | 2022-02-28 | 2026-02-27 |  | 2024-04-10 | No | Not Required | Not Required |  | 2026-04-27 | 2026-04-27 | 2026-04-27
25INR0101 | Drake BESS | SS Completed, FIS Completed, IA | Mallard Energy Storage LLC | #833 Wylie Switch 138kV | Collin | NORTH | 2027-01-29 | OTH | BA | 257.3 |  | 2022-06-22 | 2022-06-02 | 2022-08-29 | 2022-06-17 | 2025-06-18 | No | 2025-05-06 | Yes | Not Required | Not Required |  | 2025-07-16 | 2025-07-17 | 2025-07-17
25INR0238 | Little Ridge Storage | SS Completed, FIS Started, No IA | TX BESS B LLC | Tap 138kV Swindell (812) - Olinger (818) | Collin | NORTH | 2027-09-01 | OTH | BA | 252 |  | 2023-05-04 | 2023-05-15 | 2023-08-11 | 2023-04-25 |  |  |  | No
25INR0391 | Purple Sage BESS 1 | SS Completed, FIS Completed, IA | Purple Sage, LLC | Anna 345 kV Bus# 2373. | Collin | NORTH | 2028-02-12 | OTH | BA | 156 |  | 2023-03-07 | 2023-03-08 | 2023-06-05 | 2023-03-07 | 2024-03-20 | No | 2024-10-11 | Yes | Not Required | Not Required |  | 2025-02-13
25INR0392 | Purple Sage BESS 2 | SS Completed, FIS Completed, IA | Purple Sage, LLC | Anna 345 kV Bus# 2373 | Collin | NORTH | 2028-02-12 | OTH | BA | 156 |  | 2023-03-07 | 2023-03-08 | 2023-06-05 | 2023-03-07 | 2024-03-20 | No | 2024-10-11 | Yes | Not Required | Not Required |  | 2025-02-13
25INR0186 | Moonlight Sonata BESS | SS Completed, FIS Started, No IA | Samsung Solar Energy 2, LLC | Altair (78118) – Nada (78103) 138KV | Colorado | SOUTH | 2028-07-01 | OTH | BA | 201.08 |  | 2023-07-01 | 2022-09-27 | 2022-12-22 | 2023-06-20 |  |  |  | No
25INR0402 | Driet BESS | SS Completed, FIS Started, IA | Driet BESS LLC | 7254 WEIMAR8 138kV | Colorado | SOUTH | 2028-06-20 | OTH | BA | 150.52 |  | 2023-05-22 | 2023-06-07 | 2023-09-01 | 2023-05-31 |  |  | 2025-12-23 | No
26INR0259 | Cottontail Energy Center | SS Completed, FIS Started, No IA | Cottontail Energy Center, LLC | 7258 Glidden Substation 138kV | Colorado | SOUTH | 2027-10-19 | OTH | BA | 200.85 |  | 2023-10-05 | 2023-10-25 | 2024-01-22 | 2023-10-17 |  |  |  | No
27INR0147 | Paloma Energy Center | SS Completed, FIS Started, No IA | Harrison Street Development, LLC | Tap 138 kV 57640 Rock Island - 57639 Sheridan | Colorado | SOUTH | 2027-12-31 | SOL | PV | 193.8 |  | 2024-01-08 | 2024-02-07 | 2024-05-01 | 2024-01-09 |  |  |  | No | Not Required | Not Required | Not Required
27INR0148 | Paloma Energy Center BESS | SS Completed, FIS Started, No IA | Harrison Street Development, LLC | Tap 138kV 57640 Rock Island - 57639 Sheridan | Colorado | SOUTH | 2027-12-31 | OTH | BA | 53.6 |  | 2024-01-22 | 2024-02-07 | 2024-05-01 | 2024-01-22 |  |  |  | No
27INR0321 | Rock Island Generating (TEF -Due Diligence) | SS Completed, FIS Completed, IA | Kerrville Public Utility Board Public Facility Corporation | 57640 Rock Island 138 kV | Colorado | SOUTH | 2027-06-01 | GAS | IC | 121.8 |  | 2024-07-15 | 2024-07-22 | 2024-10-08 | 2024-07-11 | 2025-03-21 |  | 2025-03-17 | Yes | 2024-08-01 | Not Required | 2025-05-05 | 2025-08-04 |  | 2026-08-03
27INR0555 | Montezuma Storage | SS Completed, FIS Started, No IA | Montezuma Storage LLC | L_GLIDDE8_1Y; Bus number - 7258 138KV | Colorado | SOUTH | 2030-10-16 | OTH | BA | 183.88 |  | 2025-09-15 | 2025-09-22 | 2025-12-02 | 2025-09-04 |  |  |  | No | Not Required | Not Required
28INR0321 | Altair Energy Storage | SS Completed, FIS Started, No IA | Altair Energy Storage | Tap on 138 kV ALTAIR (bus# 78118) to STAFFORD HILL (bus# 78520) | Colorado | SOUTH | 2030-03-31 | OTH | BA | 201.76 |  | 2025-04-14 | 2025-04-21 | 2025-07-19 | 2025-03-31 |  |  |  | No
29INR0085 | Firefly Fields Solar | SS Completed, FIS Started, No IA | Firefly Fields Energy Center LLC | Tap 138 kV <57640> <Rock Island> - <7258> <Glidden> | Colorado | SOUTH | 2028-09-30 | SOL | PV | 100.52 |  | 2025-01-06 | 2025-01-13 | 2025-04-08 | 2024-12-09 |  |  |  | No |  |  | Not Required
29INR0123 | Firefly Fields Storage | SS Completed, FIS Started, No IA | Firefly Fields Energy Center LLC | Tap 138 kV 57640 Rock Island to 7258 Glidden | Colorado | SOUTH | 2028-09-30 | OTH | BA | 156.52 |  | 2025-03-17 | 2025-03-24 | 2025-06-19 | 2025-03-19 |  |  |  | No
30INR0045 | Radiant Plains Energy Center BESS | SS Completed, FIS Started, No IA | Adapture Solar Development | Tap 138-kV Weimar (7254) to Schulenburg (7252) | Colorado | SOUTH | 2029-12-27 | OTH | BA | 100 |  | 2025-11-04 | 2025-06-12 | 2025-09-04 |  |  |  |  | No
32INR0002 | Radiant Plains Energy Center Solar | SS Completed, FIS Started, No IA | Adapture Solar Development | Tap 138-kV Weimar (7254) to Schulenburg (7252) | Colorado | SOUTH | 2029-12-27 | SOL | PV | 100 |  | 2025-11-04 | 2025-06-12 | 2025-09-04 |  |  |  |  | No |  |  | Not Required
28INR0436 | Englehardt BESS | SS Completed, FIS Started, No IA | Comal BESS LLC | River Oaks (7173) | Comal | SOUTH | 2027-09-01 | OTH | BA | 200.51 |  | 2025-08-26 | 2025-09-22 | 2025-12-02 | 2025-09-19 |  |  |  | No
29INR0242 | Enfinity Redbud Storage | SS Completed, FIS Started, No IA | EG Redbud LLC | 345kV Hays Energy (7043) - 345kV Bergheim (7770) | Comal | SOUTH | 2029-12-18 | OTH | BA | 516.05 |  | 2026-01-06 | 2026-02-10 | 2026-05-08 | 2026-02-06 |  | No |  | No
30INR0112 | Short River BESS | SS Started, FIS Started, No IA | Horizon Energy Storage Greenfield Project Holdings LLC | 7456 LOP3378 138kV | Comal | SOUTH | 2030-04-30 | OTH | BA | 150.36 |  | 2026-06-03 | 2026-07-08 |  | 2026-07-07 |  |  |  | No
22INR0220 | Lamkin Solar | SS Completed, FIS Completed, IA | Commanche Solar, LLC | tap 69kV 258 Hamilton - 273 Gustine | Comanche | NORTH | 2027-11-08 | SOL | PV | 101.5 | COD | 2020-05-11 | 2019-06-24 | 2019-09-18 | 2020-03-13 | 2022-07-11 |  | 2025-03-06 | Yes | Not Required | Not Required | Not Required | 2025-04-23
22INR0237 | Dragan Solar | SS Completed, FIS Started, No IA | Hecate Comanche Solar LLC | 1440 Comanche 345kV | Comanche | NORTH | 2027-09-15 | SOL | PV | 411 |  | 2019-11-11 | 2019-11-11 | 2020-02-17 | 2019-08-23 |  | No |  | No |  |  | Not Required
22INR0400 | Dragan Storage | SS Completed, FIS Started, No IA | Hecate Grid Dragan Storage LLC | 1440 Comanche 345kV | Comanche | NORTH | 2030-03-31 | OTH | BA | 408.3 |  | 2020-10-02 | 2020-08-21 | 2020-11-04 | 2020-08-13 |  |  |  | No
23INR0359 | Crios BESS | SS Completed, FIS Started, No IA | BRP Crios BESS LLC | Tap 138 kV 1649 HASSE_P8 - 1684 SABANA_8 | Comanche | NORTH | 2028-03-01 | OTH | BA | 205.46 |  | 2021-10-18 | 2021-10-18 | 2022-01-07 | 2021-09-30 |  |  |  | No
24INR0157 | Merope BESS | SS Completed, FIS Started, No IA | BRP Merope BESS LLC | 345 kV Corn Trail Switch Substation (#11441) | Comanche | NORTH | 2028-03-01 | OTH | BA | 402.44 |  | 2021-12-13 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  | No |  | No
27INR0049 | Darkwood Solar | SS Completed, FIS Completed, IA | Mustang Creek Solar, LLC | Tap 345KV 1900 Comanche Peak to 1440 Comanche SS | Comanche | NORTH | 2027-09-20 | SOL | PV | 152.02 |  | 2023-11-09 | 2023-06-28 | 2023-09-01 | 2023-11-09 | 2026-09-17 |  | 2025-11-05 | Yes |  |  | Not Required
27INR0050 | Darkwood BESS | SS Completed, FIS Completed, IA | Mustang Creek Solar, LLC | Tap 345KV 1900 Comanche Peak - 1440 Comanche Switch | Comanche | NORTH | 2028-07-01 | OTH | BA | 150.5 |  | 2023-11-09 | 2023-06-07 | 2023-09-01 | 2023-10-31 | 2025-07-29 |  | 2025-11-05 | Yes
27INR0365 | Comanche BESS | SS Completed, FIS Completed, IA | ENERGOS BESS | #1440 Comanche Switching Station 345kV | Comanche | NORTH | 2029-05-07 | OTH | BA | 614.4 |  | 2024-12-06 | 2024-12-06 | 2025-02-18 | 2024-11-05 | 2026-02-10 | No | 2026-03-20 | No
25INR0174 | Concho Pearl Solar | SS Completed, FIS Started, IA | Concho Pearl Solar, LLC | Tap 345kV 76009 Twin Buttes - 7077 Amos Creek | Concho | WEST | 2028-01-09 | SOL | PV | 171.9 |  | 2022-12-05 | 2022-12-07 | 2023-03-06 | 2022-11-30 |  |  | 2024-07-22 | No | Not Required | Not Required | Not Required
25INR0175 | Concho Pearl Storage | SS Completed, FIS Started, IA | Concho Pearl Solar, LLC | Tap 345kV 76009 Twin Buttes - 7077 Amos Creek | Concho | WEST | 2028-01-09 | OTH | BA | 162.4 |  | 2022-12-08 | 2022-12-15 | 2023-03-13 | 2022-12-07 |  |  | 2024-07-22 | No | Not Required | Not Required | 2025-09-15
25INR0225 | Lucy Solar | SS Completed, FIS Completed, IA | Concho County Solar 1 LLC | Tap 345kV 7077 Amos Creek - 6444 San Angelo Red Creek and 7077 Amos Creek - 76009 Twin Buttes | Concho | WEST | 2027-06-30 | SOL | PV | 352.21 |  | 2023-06-15 | 2023-06-28 | 2023-09-20 | 2023-06-08 | 2026-06-08 | Yes | 2024-05-29 | Yes | Not Required | Not Required | Not Required | 2026-07-15 | 2026-07-15 | 2026-08-03
26INR0255 | Operation Sunshine | SS Completed, FIS Started, IA | Duck Creek Solar, LLC | 7077 Amos Creek 345kV | Concho | WEST | 2029-04-01 | SOL | PV | 603.2 |  | 2023-09-29 | 2023-11-14 | 2024-02-09 | 2023-09-27 |  |  | 2025-08-27 | Yes |  |  | Not Required | 2025-09-11
26INR0357 | Operation Sunshine Storage | SS Completed, FIS Started, IA | Duck Creek Storage, LLC | 7077 Amos Creek 345kV | Concho | WEST | 2029-04-01 | OTH | BA | 409.8 |  | 2024-01-17 | 2024-02-02 | 2024-02-09 | 2024-01-18 |  |  | 2025-08-27 | Yes | Not Required | Not Required |  | 2025-09-11
27INR0108 | Paint Rock Wind | SS Completed, FIS Started, IA | Paint Rock Wind, LLC | Amos Creek (7077) – Bow Wood (76006) | Concho | WEST | 2028-10-01 | WIN | WT | 379.18 |  | 2023-12-06 | 2024-01-03 | 2024-03-29 | 2023-12-11 |  |  | 2026-08-24 | No | Not Required | Not Required | Not Required
28INR0358 | Cherry Sage Solar 1 SLF | SS Completed, FIS Started, No IA | Cherry Sage Solar 1 LLC | (#60423) TREADWELL 138kV. | Concho | WEST | 2029-02-23 | SOL | PV | 142.51 |  | 2025-04-15 | 2025-04-25 | 2025-07-23 | 2025-04-22 |  | No |  | No |  |  | Not Required
29INR0139 | Trail Ranch Solar 1 | SS Completed, FIS Started, No IA | Aurora Solar LLC | Tap 345KV #6444 Red Creek - #7077 AMOS Creek | Concho | WEST | 2029-12-01 | SOL | PV | 301.9 |  | 2026-08-03 | 2025-11-18 | 2026-01-19 | 2026-07-16 |  |  |  | No |  |  | Not Required
29INR0272 | Trail Ranch Solar 2 | SS Completed, FIS Started, No IA | Aurora Solar LLC | Tap 345 kV 6444 Red Creek -7077 Amos Creek | Concho | WEST | 2029-12-01 | SOL | PV | 132.85 | FIS Request |  | 2026-01-14 | 2026-03-25 | 2026-09-17 10:47 |  | No |  | No |  |  | Not Required
20INR0033 | WILDWIND | SS Completed, FIS Completed, IA | Wildcat Creek | tap 345kV 1730 KrumW - 2373 Anna | Cooke | NORTH | 2026-04-15 | WIN | WT | 180.08 |  | 2018-06-14 | 2017-10-18 | 2017-12-11 | 2018-06-14 | 2019-11-25 | No | 2020-02-21 | Yes | Not Required | Not Required | Not Required | 2020-03-23 | 2020-04-30 | 2020-04-30 |  |  | 2020-12-22 | 2021-02-10
24INR0198 | Two Forks BESS | SS Completed, FIS Started, IA | Two Forks LLC | 684 SPRING 138kV | Cooke | NORTH | 2028-08-01 | OTH | BA | 309.8 | COD | 2022-10-23 | 2022-01-28 | 2022-04-26 | 2022-10-13 |  | No | 2024-05-03 | Yes | Not Required | Not Required |  | 2024-05-06
24INR0239 | Trojan BESS SLF | SS Completed, FIS Started, No IA | Trojan BESS | 11735 Cedar Elm Switch 345kV | Cooke | NORTH | 2029-07-01 | OTH | BA | 0 |  | 2022-05-17 | 2022-06-02 | 2022-08-30 | 2022-04-19 |  |  |  | No
26INR0219 | Mountain Springs BESS | SS Completed, FIS Completed, No IA | Mountain Springs BESS | 704 Mountain Springs 138 kV | Cooke | NORTH | 2029-04-01 | OTH | BA | 150.52 |  | 2023-09-25 | 2023-10-04 | 2023-12-30 | 2023-09-21 | 2025-06-05 | No |  | No
28INR0328 | 18-ALPHA BESS | SS Completed, FIS Started, No IA | SCOUT ENERGY MANAGEMENT, LLC | To the 138 kV Valley View Substation, ( Bus No.691) | Cooke | NORTH | 2028-02-01 | OTH | BA | 307.4 |  | 2025-04-04 | 2025-04-21 | 2025-07-19 | 2025-04-04 |  |  |  | No
20INR0246 | Ryan Energy Storage | SS Completed, FIS Completed, IA | Ryan Storage LLC | 37580 TNPancake 69kV | Coryell | NORTH | 2026-12-12 | OTH | BA | 51.6 |  | 2019-02-08 | 2019-01-15 | 2019-04-05 | 2019-03-15 | 2025-09-16 | No | 2021-02-18 | Yes | Not Required | Not Required |  | 2022-08-03 | 2026-01-27 | 2026-01-27
25INR0177 | Triangle Ranch Alpha | SS Completed, FIS Started, No IA | Triangle Ranch Wind | Edith Clark 345 kV (#60500) | Cottle | WEST | 2029-07-01 | WIN | WT | 301.74 |  | 2022-10-04 | 2022-10-06 | 2022-12-29 | 2022-09-15 |  |  |  | No |  |  | Not Required
25INR0178 | Triangle Ranch Bravo | SS Completed, FIS Started, No IA | Triangle Ranch Wind | Edith Clark 345 kV (#60500) | Cottle | WEST | 2028-07-01 | WIN | WT | 200.22 |  | 2022-10-04 | 2022-10-06 | 2022-12-29 | 2022-09-15 |  |  |  | No |  |  | Not Required
28INR0267 | Soluce Cotton Solar | SS Completed, FIS Started, No IA | CTPB1, LLC | Tap 345kV 59904 COTTONWOOD - 60500 EDITH CLARKE | Cottle | WEST | 2029-08-13 | SOL | PV | 202.91 |  | 2025-07-16 | 2025-02-14 | 2025-05-12 |  |  | Yes |  | No |  |  | Not Required
28INR0268 | Soluce Cotton Storage | SS Completed, FIS Started, No IA | CTPB1,LLC | Tap 345kV 59904 COTTONWOOD - 60500 EDITH CLARKE | Cottle | WEST | 2029-08-13 | OTH | BA | 201.54 |  | 2025-07-16 | 2025-02-14 | 2025-05-12 |  |  | Yes |  | No
20INR0143 | Tri-X Solar 1 SLF | SS Completed, FIS Started, IA | Crane I Solar Electric, LLC | 138 kV Soda Lake (#76026) | Crane | WEST | 2028-10-30 | SOL | PV | 201.5 |  | 2020-09-08 | 2016-11-07 | 2016-11-08 | 2017-02-10 |  | No | 2026-08-21 | No | Not Required | Not Required | Not Required
22INR0385 | BRP Pictor BESS | SS Completed, FIS Started, No IA | BRP Pictor BESS LLC | 60400 Lynx 138kV | Crane | WEST | 2029-12-31 | OTH | BA | 201.07 | COD | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  | No |  | No
23INR0074 | BRP Ampato BESS | SS Completed, FIS Started, No IA | BRP Ampato BESS LLC | 10002 NS Crane Switch 138kV | Crane | WEST | 2027-12-01 | OTH | BA | 121.56 |  | 2020-08-26 | 2020-08-04 | 2020-10-28 | 2020-08-24 |  |  |  | No
23INR0080 | Soda Lake Solar 2 SLF | SS Completed, FIS Started, IA | Crane II Solar Electric, LLC | 138 kV Soda Lake (#76026) | Crane | WEST | 2028-10-30 | SOL | PV | 201.74 |  | 2020-09-08 | 2020-09-11 | 2020-11-30 | 2020-08-24 |  |  | 2022-03-23 | No |  |  | Not Required
23INR0308 | Fowler Ranch Storage | SS Completed, FIS Started, No IA | Crane BESS, LLC | 76025 Castle Mountain 138kV | Crane | WEST | 2027-09-30 | OTH | BA | 26.07 | COD | 2022-06-03 | 2021-06-21 | 2021-09-07 | 2022-05-18 |  |  |  | No
24INR0383 | Soda Lake BESS 2 SLF | SS Completed, FIS Started, IA | Crane II Solar Electric, LLC | 138 kV Soda Lake (#76026) | Crane | WEST | 2028-10-30 | OTH | BA | 205.35 |  | 2022-08-03 | 2022-09-02 | 2022-11-29 | 2022-08-09 |  |  | 2026-08-21 | No
26INR0110 | Western Flats Solar | SS Completed, FIS Started, No IA | Hecate Energy Point Mountain Solar Facility 1 LLC | Tap 138 kV 76615 Crane -76635 King Mountain; POI is 7.85 miles from Crane. | Crane | WEST | 2028-11-01 | SOL | PV | 410.2 |  | 2023-11-17 | 2023-04-07 | 2023-07-05 | 2023-09-11 |  |  |  | No |  |  | Not Required
26INR0188 | Western Flats Storage | SS Completed, FIS Started, No IA | Hecate Energy Point Mountain Solar Facility 1 LLC | Tap 138 kV 76615 Crane -76635 King Mountain | Crane | WEST | 2028-11-01 | OTH | BA | 410.7 |  | 2025-01-17 | 2024-04-09 | 2024-07-05 | 2025-01-07 |  |  |  | No
28INR0389 | Tri-X BESS 1 SLF | SS Completed, FIS Started, IA | Crane I Solar Electric, LLC | 138 kV Soda Lake (#76026) | Crane | WEST | 2028-10-30 | OTH | BA | 205.3 |  | 2025-08-05 | 2025-08-18 | 2025-11-10 | 2025-08-06 |  |  | 2026-08-21 | No
29INR0013 | Cattle Drive Solar | SS Completed, FIS Started, IA | Cattle Drive Solar, LLC | 76000 North McCamey 345kV | Crane | WEST | 2028-12-31 | SOL | PV | 307 | COD | 2024-06-13 | 2024-06-13 | 2024-09-10 | 2024-06-13 |  |  | 2025-12-29 | No |  |  | Not Required
29INR0279 | Tierra Loma Solar | SS Completed, FIS Started, No IA | Tierra Loma Solar, LLC | Tap 345 kV #18668 ROCK DRAW - #76000 NORTH MCCAMEY ckt 1 | Crane | WEST | 2029-09-01 | SOL | PV | 250 |  | 2026-02-17 | 2026-02-19 | 2026-05-15 | 2026-02-18 |  | No |  | No |  |  | Not Required
29INR0280 | Tierra Loma Storage | SS Completed, FIS Started, No IA | Tierra Loma Solar, LLC | Tap 345 kV #18668 ROCK DRAW - #76000 NORTH MCCAMEY ckt 1 | Crane | WEST | 2029-09-01 | OTH | BA | 200 |  | 2026-02-17 | 2026-02-19 | 2026-05-15 | 2026-02-18 |  | No |  | No
16INR0104 | Big Sampson Wind | SS Completed, FIS Completed, IA | Big Sampson Wind Project, LLC | tap 345kV 76015 Cedar Canyon - 7053 Noelke | Crockett | WEST | 2026-09-01 | WIN | WT | 265.4 |  |  | 2015-05-11 | 2015-06-17 | 2015-05-11 | 2024-10-30 | Yes | 2019-11-08 | Yes | Not Required | Not Required | Not Required | 2024-10-31 | 2024-11-04 | 2024-11-04 |  |  | 2025-06-04 | 2025-06-16
22INR0455 | Blue Sky Sol | SS Completed, FIS Started, IA | Blue Sky Solar LLC | 6562 Friends Ranch 138kV | Crockett | WEST | 2027-12-31 | SOL | PV | 101.2 |  | 2020-12-09 | 2020-12-03 | 2021-02-16 | 2020-11-10 |  | No | 2022-02-01 | Yes | Not Required | Not Required | Not Required | 2022-02-07 | 2023-07-31 | 2023-07-31
24INR0442 | Midnight Sun Energy Storage | SS Completed, FIS Started, IA | Midnight Sun Energy Storage, LLC | 6601 Rio Pecos 138kV | Crockett | WEST | 2028-06-29 | OTH | BA | 523.86 |  | 2022-12-05 | 2022-12-07 | 2023-03-04 | 2022-11-18 |  | No | 2025-07-14 | Yes |  |  |  | 2025-07-29
25INR0216 | Blue Sky Storage SLF | SS Completed, FIS Started, No IA | UKA North America, LLC | 138 kV Friend Ranch (Bus# 6562) | Crockett | WEST | 2028-06-30 | OTH | BA | 0 |  | 2022-10-17 | 2022-10-24 | 2023-01-22 | 2022-10-14 |  |  |  | No
25INR0489 | Ranchero BESS | SS Completed, FIS Started, No IA | Ranchero Battery Facility, LLC | 7053 Noelke 345 kV | Crockett | WEST | 2028-04-30 | OTH | BA | 150 |  | 2024-04-25 | 2023-06-28 | 2023-09-22 | 2024-04-03 |  |  |  | No
26INR0365 | BLACK BEAR SOLAR | SS Completed, FIS Started, No IA | ESCONDIDO DRAW RESOURCES, LLC | #6564 ILLN4A 138 KV | Crockett | WEST | 2028-06-01 | SOL | PV | 102.9 |  | 2024-06-19 | 2023-12-04 | 2024-03-04 | 2024-05-17 |  | No |  | No |  |  | Not Required
26INR0366 | BLACK BEAR BESS | SS Completed, FIS Started, No IA | ESCONDIDO DRAW RESOURCES, LLC | #6564 ILLN4A 138kV | Crockett | WEST | 2028-06-01 | OTH | BA | 51.2 |  | 2024-06-19 | 2023-12-04 | 2024-03-04 | 2024-05-17 |  | No |  | No
29INR0073 | Oasis wind | SS Started, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | 6562 Friend Ranch Station 138kV | Crockett | WEST | 2030-07-01 | WIN | WT | 350 | MW Size | 2026-07-16 | 2026-07-22 |  | 2026-07-16 |  |  |  | No |  |  | Not Required
29INR0184 | Gridline Solar | SS Completed, FIS Started, No IA | Big Lake Ranch LLC | 76005 Schneeman Draw LCRA | Crockett | WEST | 2029-07-01 | SOL | PV | 400 |  | 2025-07-31 | 2025-08-18 | 2025-11-10 | 2025-07-31 |  |  |  | No |  |  | Not Required
26INR0647 | Wake Wind Energy Repower | SS Completed, FIS Completed, IA | WAKE WIND ENERGY | 59904 Cottonwood 345 | Crosby | PANHANDLE | 2027-06-04 | WIN | WT | 252.5 | COD | 2025-04-04 | 2025-04-21 | 2025-07-15 | 2025-04-17 | 2026-06-16 |  | 2014-02-28 | No |  |  | Not Required | 2026-08-03 | 2026-08-03 | 2026-08-03
22INR0454 | Wallace Solar | SS Completed, FIS Completed, IA | Delaware Ranch Solar, LLC | Delaware River SW (11112) | Culberson | WEST | 2027-05-14 | SOL | PV | 36 |  | 2020-11-04 | 2020-12-22 | 2021-03-10 | 2020-12-17 | 2026-03-18 | No | 2022-02-07 | Yes | Not Required | Not Required | Not Required | 2026-03-18 | 2026-04-22 | 2026-04-22
27INR0074 | Desert Hill Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings | Tap 138kV El Capitan (#10179) - Black River (#1096). | Culberson | WEST | 2030-07-01 | SOL | PV | 250.5 |  | 2026-04-07 | 2024-01-11 | 2024-04-05 | 2026-04-02 |  |  |  | No |  |  | Not Required
27INR0334 | Buffalo Jump Wind | SS Completed, FIS Started, No IA | BOULEVARD ASSOCIATES, LLC | 1097 Culberson 345 KV | Culberson | WEST | 2029-07-01 | WIN | WT | 740 |  | 2025-10-28 | 2025-11-05 | 2025-12-07 | 2025-10-29 |  |  |  | No |  |  | Not Required
28INR0520 | SunRustler Solar | SS Started, FIS Started, No IA | SunRustler Solar | 11082 MAVRKDRW_8 138kV | Culberson | WEST | 2028-06-15 | SOL | PV | 301.49 | FIS Request | 2026-09-23 |  |  | 2026-09-23 |  |  |  | No |  |  | Not Required
25INR0006 | Atlanta TxHSR TPSS DS-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2429 Watermill E - 3083 Wilmer | Dallas | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-10-11 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  |  |  | No | Not Required | Not Required
27INR0457 | watermelon 1 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2024-12-13 | 2025-01-13 | 2025-04-08 | 2025-01-06 |  |  |  | No | Not Required | Not Required
27INR0458 | watermelon 2 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2024-12-16 | 2025-01-13 | 2025-04-08 | 2025-01-06 |  |  |  | No | Not Required | Not Required
27INR0459 | watermelon 3 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. 1.6 miles from 2427 WATMLL_W5 | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2024-12-16 | 2025-01-13 | 2025-04-08 | 2025-01-06 |  |  |  | No | Not Required | Not Required
27INR0460 | watermelon 4 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2024-12-16 | 2025-01-13 | 2025-04-08 | 2025-01-06 |  |  |  | No | Not Required | Not Required
28INR0255 | watermelon 5 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2025-02-06 | 2025-02-14 | 2025-05-12 | 2025-02-06 |  |  |  | No | Not Required | Not Required
28INR0256 | watermelon 6 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2025-02-06 | 2025-02-14 | 2025-05-12 | 2025-02-06 |  |  |  | No | Not Required | Not Required
28INR0257 | watermelon 7 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2025-02-06 | 2025-02-14 | 2025-05-12 | 2025-02-06 |  |  |  | No | Not Required | Not Required
28INR0258 | watermelon 8 energy storage | SS Completed, FIS Started, No IA | Tempus power management LLC | Tap on 2427 WATMLL_W5 345.00 - 2432 TRICRN1_5 345.00 345kV line ckt 1. | Dallas | NORTH | 2029-03-01 | OTH | BA | 102.1 |  | 2025-02-06 | 2025-02-14 | 2025-05-12 | 2025-02-06 |  |  |  | No | Not Required | Not Required
21INR0022 | Red Holly Solar | SS Completed, FIS Started, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2029-09-30 | SOL | PV | 260 |  |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  | No | 2020-10-19 | No | Not Required | Not Required | Not Required
21INR0029 | Red Holly Storage 1 | SS Completed, FIS Started, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2028-05-30 | OTH | BA | 50 |  |  | 2018-07-11 | 2018-08-16 | 2018-07-11 |  |  | 2020-10-19 | No | Not Required | Not Required
21INR0033 | Red Holly Storage | SS Completed, FIS Started, IA | GreenGo Energy | tap 345kV 59900 Longdraw - 79641 Farmland | Dawson | WEST | 2028-05-30 | OTH | BA | 50 |  |  | 2018-09-27 | 2018-12-18 | 2018-12-11 |  | No | 2020-10-19 | No | Not Required | Not Required
26INR0530 | Longview Wind | SS Completed, FIS Started, IA | Longview Wind, LLC | Venturi (Bus #59923) | Dawson | WEST | 2028-12-01 | WIN | WT | 352.6 | Status Change INA-to-PLN | 2025-09-17 | 2025-09-22 | 2025-12-02 | 2025-09-05 |  |  | 2025-12-16 | Yes | Not Required | Not Required | Not Required | 2026-01-09
27INR0474 | Fivemile Wind | SS Completed, FIS Started, No IA | 180 Wind LLC | Tap 138kV Lamesa 138kv (10008) to Jim Payne 138kV (18880) | Dawson | WEST | 2029-09-23 | WIN | WT | 282.3 |  | 2025-04-25 | 2025-04-25 | 2025-07-22 | 2025-04-25 |  |  |  | No |  |  | Not Required
27INR0501 | Mesquite Creek Windpower Repower | SS Completed, FIS Started, No IA | Mesquite Creek Wind LLC | <59900><Long Draw><345> | Dawson | WEST | 2027-12-31 | WIN | WT | 214.2 | MW Size | 2025-04-28 | 2025-04-29 | 2025-07-26 | 2025-04-28 |  | No |  | No |  |  | Not Required
29INR0255 | Los Toros Energy Center Solar SLF | SS Completed, FIS Started, No IA | Los Toros Energy Center, LLC | Tap 1167 Mustang_8 to 11206 Dillion_P8 138 kV | Dawson | WEST | 2030-03-31 | SOL | PV | 401.56 |  | 2026-02-24 | 2026-02-25 | 2026-05-22 | 2026-02-20 |  |  |  | No | Not Required | Not Required | Not Required
29INR0271 | Los Toros Energy Center Storage SLF | SS Completed, FIS Started, No IA | Los Toros Energy Center, LLC | Tap 1167 Mustang_8 to 11206 Dillion_P8 138 kV | Dawson | WEST | 2030-03-31 | OTH | BA | 0 |  | 2026-02-19 | 2026-02-26 | 2026-05-22 | 2026-02-25 |  |  |  | No | Not Required | Not Required
20INR0255 | Renegade Project | SS Completed, FIS Started, IA | Renegade Renewable LLC | Tap 345kV 23910 Windmill - 23906 AJ Swope | Deaf Smith | PANHANDLE | 2028-01-15 | SOL | PV | 515.66 |  | 2019-04-01 | 2019-02-26 | 2019-05-17 | 2019-02-07 |  |  | 2021-01-04 | Yes | Not Required | Not Required | Not Required | 2024-04-30 |  |  | 2026-03-01 | 2027-12-09
23INR0056 | Caliche Mound Solar | SS Completed, FIS Completed, IA | CIG DS1 LLC | Mule Deer Switch 23921 (tap 345kV 23906 AJSwope - 23910 Windmill) | Deaf Smith | PANHANDLE | 2027-10-26 | SOL | PV | 406.6 |  | 2020-08-27 | 2020-07-24 | 2020-09-08 | 2020-07-07 | 2026-09-17 |  | 2023-10-12 | Yes |  |  | Not Required | 2025-02-12
24INR0134 | BRP Hemera BESS | SS Completed, FIS Started, No IA | BRP Hemera BESS LLC | 345 kV Deaf Smith Substation (#23908, Oncor) | Deaf Smith | PANHANDLE | 2029-12-01 | OTH | BA | 206.96 |  | 2021-12-20 | 2021-12-29 | 2022-03-25 | 2021-12-14 |  |  |  | No
24INR0200 | White Tail Solar | SS Completed, FIS Started, No IA | Mule Deer Solar LLC | Tap 345kV Windmill (23910) – AJ Swope (23906) | Deaf Smith | PANHANDLE | 2028-12-29 | SOL | PV | 226.8 | COD | 2022-11-09 | 2022-02-07 | 2022-05-07 | 2022-10-21 |  |  |  | No |  |  | Not Required
29INR0003 | Aurelius Solar | SS Completed, FIS Completed, IA | IP Roman, LLC | 23908 Deaf Smith station 345 kV | Deaf Smith | PANHANDLE | 2028-06-30 | SOL | PV | 1124.24 |  | 2023-07-13 | 2023-07-18 | 2023-10-15 | 2023-07-13 | 2025-09-22 | Yes | 2025-10-09 | Yes |  |  | Not Required | 2026-03-17
29INR0004 | Aurelius Wind | SS Completed, FIS Completed, IA | IP Roman Wind, LLC | 23908 Deaf Smith station 345 kV | Deaf Smith | PANHANDLE | 2028-06-30 | WIN | WT | 621.6 |  | 2023-07-13 | 2023-08-14 | 2023-11-06 | 2023-08-07 | 2025-09-22 | Yes | 2025-10-09 | Yes |  |  | Not Required | 2026-03-17
29INR0009 | Aurelius 2 Solar | SS Completed, FIS Started, IA | IP Roman, LLC | 23908 Deaf Smith station 345 kV. This INR has a 600 MW PUN load at the medium voltage side of the MPTs for a total of 1800 MW PUN load (refer to the substation SLD). | Deaf Smith | PANHANDLE | 2028-09-30 | SOL | PV | 445.4 |  | 2023-11-28 | 2023-12-04 | 2024-03-01 | 2023-11-30 |  |  | 2026-07-10 | Yes |  |  | Not Required | 2026-07-13
29INR0010 | Aurelius 2 Wind | SS Completed, FIS Started, No IA | IP Roman Wind II, LLC | 23908 Deaf Smith station 345kV | Deaf Smith | PANHANDLE | 2028-09-30 | WIN | WT | 621.6 |  | 2023-11-28 | 2023-12-04 | 2024-03-01 | 2023-11-30 |  |  |  | No |  |  | Not Required
29INR0011 | Aurelius 3 Solar | SS Completed, FIS Started, No IA | IP Roman III, LLC | 23908 Deaf Smith station 345 kV. This INR has a 600 MW PUN load at the medium voltage side of the MPTs for a total of 1800 MW PUN load (refer to the substation SLD). | Deaf Smith | PANHANDLE | 2030-06-30 | SOL | PV | 445.4 | COD | 2023-11-20 | 2023-12-04 | 2024-03-01 | 2023-11-30 |  |  |  | No |  |  | Not Required
29INR0012 | Aurelius 3 Wind | SS Completed, FIS Started, No IA | IP Roman III, LLC | 23908 Deaf Smith station 345kV | Deaf Smith | PANHANDLE | 2030-06-30 | WIN | WT | 497.3 | MW Size COD | 2023-11-28 | 2023-12-04 | 2024-03-01 | 2023-11-30 |  |  |  | No |  |  | Not Required
29INR0361 | Aurelius 3 Natural Gas | SS Completed, FIS Started, No IA | IP Roman III Gas, LLC | 23908 Deaf Smith station 345 kV | Deaf Smith | PANHANDLE | 2030-06-30 | GAS | IC | 1275 | COD | 2026-06-24 | 2026-06-29 | 2026-09-20 | 2026-06-25 |  |  |  | No
24INR0136 | Eagle Springs Storage | SS Completed, FIS Completed, IA | Eagle Springs BESS LLC | Tap Lake Creek Substation (#6835) – Enloe Switching station (#6834) 138 kV Line | Delta | NORTH | 2027-03-29 | OTH | BA | 33.94 | COD | 2022-06-20 | 2021-10-18 | 2022-01-12 | 2022-06-13 | 2025-09-17 | No | 2024-04-17 | Yes | Not Required | Not Required |  | 2025-10-30 | 2025-10-30 | 2025-10-30
24INR0137 | Eagle Springs Solar | SS Completed, FIS Completed, IA | Eagle Springs Solar, LLC | Tap Lake Creek Substation (#6835) – Enloe Switching station (#6834) 138 kV Line | Delta | NORTH | 2027-03-29 | SOL | PV | 77.21 | COD | 2022-06-20 | 2021-10-18 | 2022-01-12 | 2022-06-13 | 2025-09-17 | No | 2024-04-17 | Yes | Not Required | Not Required | Not Required | 2025-10-30 | 2025-10-30 | 2025-10-30
25INR0227 | SERENGETI SOLAR | SS Completed, FIS Completed, IA | Abei Energy Green XIV LLC | Tap 138kV Enloe Tap (bus# 11806) – Delta sub (bus# 1802) | Delta | NORTH | 2028-09-18 | SOL | PV | 76.18 | SFS/NtP | 2022-11-08 | 2022-12-07 | 2023-03-06 | 2022-11-18 | 2026-04-03 | No | 2025-12-30 | Yes |  |  | Not Required | 2026-09-21
28INR0454 | Oakley BESS | SS Completed, FIS Started, No IA | Oakley BESS LLC | Tap 138 kV 612 BLUHORSE– 684 SPRING | Denton | NORTH | 2028-09-08 | OTH | BA | 200.96 |  | 2025-10-02 | 2025-10-06 | 2025-11-16 | 2025-10-01 |  |  |  | No
22INR0251 | Shaula I Solar | SS Completed, FIS Started, IA | Shaula Energy Project, LLC | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | DeWitt | SOUTH | 2028-06-15 | SOL | PV | 205.2 |  | 2019-11-27 | 2019-12-03 | 2020-03-08 | 2019-11-20 |  | No | 2022-02-16 | Yes |  |  | Not Required | 2023-03-27
22INR0267 | Shaula II Solar | SS Completed, FIS Started, IA | Shaula Energy Project II, LLC | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | DeWitt | SOUTH | 2028-06-15 | SOL | PV | 205.2 |  | 2019-12-27 | 2019-12-18 | 2020-03-12 | 2019-12-18 |  | No | 2022-04-27 | Yes |  |  | Not Required | 2023-03-27
23INR0009 | Shaula III Solar | SS Completed, FIS Started, No IA | Shaula Energy Project III, LLC | tap 345kV 5133 Elm Creek - 5915 SO TEX ckt 1 | DeWitt | SOUTH | 2025-12-24 | SOL | PV | 205.2 |  | 2020-01-13 | 2019-12-18 | 2020-03-11 | 2019-12-18 |  |  |  | No |  |  | Not Required
24INR0555 | Shaula I BESS | SS Completed, FIS Started, No IA | Shaula Energy Project LLC | 5380 Shaula 345kV | DeWitt | SOUTH | 2028-06-01 | OTH | BA | 205.77 |  | 2023-05-19 | 2023-07-10 | 2023-10-05 | 2023-07-03 |  |  |  | No
26INR0328 | Yorktown BESS | SS Completed, FIS Started, No IA | Navitas Energy LLC | (#78575) LCRA Yorktown 138 kV | DeWitt | SOUTH | 2028-12-16 | OTH | BA | 150.49 |  | 2023-10-18 | 2023-10-25 | 2024-01-22 | 2023-10-10 |  |  |  | No
23INR0089 | Donegal Solar | SS Completed, FIS Started, IA | HE-Cottonwood Solar LLC | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2028-11-01 | SOL | PV | 201.57 |  | 2020-10-08 | 2020-10-07 | 2020-12-28 | 2020-09-11 |  |  | 2022-07-25 | Yes | Not Required | Not Required | Not Required | 2025-05-14
25INR0165 | Timberlakes Solar | SS Completed, FIS Started, No IA | Donegalsol | 59904 Cottonwood 345kV | Dickens | PANHANDLE | 2028-11-15 | SOL | PV | 200.71 |  | 2022-08-26 | 2022-11-07 | 2023-02-03 | 2022-09-02 |  |  |  | No |  |  | Not Required
25INR0172 | Wolf Spring Solar | SS Completed, FIS Completed, IA | Wolf Spring Solar, LLC | Tap 345kV 59904 Cotton Wood - 23922 White River Ckt 1 | Dickens | PANHANDLE | 2028-08-25 | SOL | PV | 195.8 |  | 2022-12-05 | 2022-12-07 | 2023-03-06 | 2022-11-30 | 2026-01-09 | No | 2024-08-14 | No | Not Required | Not Required | Not Required
25INR0173 | Wolf Spring Storage | SS Completed, FIS Completed, IA | Wolf Spring Solar, LLC | Tap 345kV 59904 Cotton Wood - 23922 White River Ckt 1 | Dickens | PANHANDLE | 2028-08-25 | OTH | BA | 202.7 |  | 2022-12-05 | 2022-12-15 | 2023-03-13 | 2022-12-07 | 2026-01-09 | No | 2024-08-14 | No | Not Required | Not Required | 2025-09-15
27INR0195 | CORUSCANT BESS | SS Completed, FIS Started, No IA | AEU Battery Project III LLC | Tap 345kV 59904 COTTONWOOD - 60500 EDITHCLA7A | Dickens | PANHANDLE | 2027-04-18 | OTH | BA | 417.79 |  | 2024-02-12 | 2024-02-27 | 2024-05-20 | 2024-02-06 |  | Yes |  | No
28INR0169 | Sanders Hollow Energy Center | SS Completed, FIS Not Started, IA | Sanders Hollow Energy Center, LLC | Tap 345 kV 59904 Cottonwood (W_CW_345) - 60500 Edith Clarke (EDITHCLA7A) CKT 01 | Dickens | PANHANDLE | 2029-06-23 | WIN | WT | 292.6 |  | 2025-07-09 | 2024-10-29 | 2025-01-27 |  |  |  | 2026-06-09 | No |  |  | Not Required
28INR0288 | Outrider BESS | SS Completed, FIS Started, IA | Sanders Hollow Energy Center, LLC | Tap 345 kV 59904 Cottonwood (W_CW_345) - 60500 Edith Clarke (EDITHCLA7A) CKT. Approximately distance from the POI to Cottonwood Substation is 11.13 miles and to Edith Clarke Substation 77.6 miles. | Dickens | PANHANDLE | 2029-06-26 | OTH | BA | 302 |  | 2025-09-10 | 2025-06-05 | 2025-08-29 | 2025-09-03 |  |  | 2026-06-09 | No
29INR0192 | Spurland Solar I | SS Completed, FIS Started, IA | Spurland Solar I | 59908 Nova Prime 345 345kV | Dickens | PANHANDLE | 2028-12-30 | SOL | PV | 302.1 |  | 2025-10-28 | 2025-11-05 | 2026-01-12 | 2025-10-23 |  |  | 2026-08-06 | Yes |  |  | Not Required | 2026-08-27
29INR0195 | Spurland Solar II | SS Completed, FIS Started, IA | Spurland Solar II | 59908 Nova Prime 345 345kV | Dickens | PANHANDLE | 2028-12-30 | SOL | PV | 201.6 |  | 2025-10-28 | 2025-11-05 | 2026-01-12 | 2025-10-23 |  |  | 2026-08-06 | No |  |  | Not Required
23INR0164 | Steppe Reserve Storage | SS Completed, FIS Started, No IA | KCE TX 25, LLC | 8283 Asherton 138 kV | Dimmit | SOUTH | 2028-01-01 | OTH | BA | 51.9 |  | 2021-01-08 | 2021-01-25 | 2021-04-16 | 2020-12-29 |  |  |  | No
25INR0133 | Rose Quartz BESS | SS Completed, FIS Completed, IA | Rose Quartz BESS, LLC | Tap 138kV 8283 Asherton - 8613 Bigwells | Dimmit | SOUTH | 2026-12-01 | OTH | BA | 101.41 |  | 2022-10-27 | 2022-09-02 | 2022-11-30 | 2022-10-14 | 2025-04-23 | No | 2026-07-28 | No | Not Required | Not Required
26INR0356 | Saluga Ranch Storage | SS Completed, FIS Started, No IA | Saluga Ranch Energy, LLC | Asherton 8283 - Big wells 8613 -138 kV | Dimmit | SOUTH | 2027-08-25 | OTH | BA | 125.4 |  | 2024-01-08 | 2024-02-02 | 2024-04-29 | 2024-01-08 |  |  |  | No
26INR0555 | Desert Palm BESS | SS Completed, FIS Started, IA | Desert Palm BESS, LLC | 78280 Bevo Substation 138 kV | Dimmit | SOUTH | 2028-09-01 | OTH | BA | 201.3 |  | 2024-08-07 | 2024-08-16 | 2024-11-13 | 2024-08-08 |  |  | 2026-07-24 | No
26INR0556 | Wintergarden BESS | SS Completed, FIS Started, No IA | Wintergarden BESS LLC | 8970 Catarina 138 kV | Dimmit | SOUTH | 2028-06-30 | OTH | BA | 201.2 |  | 2024-08-13 | 2024-08-16 | 2024-10-08 | 2024-08-07 |  | No |  | No
27INR0208 | Sugarloaf BESS | SS Completed, FIS Started, No IA | Sugarloaf Clean Energy LLC | (#80481) PILONCIL4 138KV | Dimmit | SOUTH | 2028-01-31 | OTH | BA | 100.6 |  | 2024-03-04 | 2024-03-22 | 2024-06-19 | 2024-03-11 |  | No |  | No
27INR0330 | Wild Horse Desert Solar | SS Completed, FIS Completed, No IA | Wild Horse Desert Solar, LLC | Tap 138kV 8613 Big Well - 8212 Dilley Switch | Dimmit | SOUTH | 2028-07-01 | SOL | PV | 120 |  | 2024-12-10 | 2024-12-19 | 2025-02-20 | 2024-12-06 | 2026-09-14 | No |  | No | Not Required | Not Required | Not Required
27INR0331 | Wild Horse Desert Storage | SS Completed, FIS Started, No IA | Wild Horse Desert Solar, LLC | Tap 138kV 8613 Big Well - 8212 Dilley Switch | Dimmit | SOUTH | 2028-07-01 | OTH | BA | 90.3 |  | 2024-12-05 | 2024-12-19 | 2025-02-20 | 2024-12-06 |  | No |  | No | Not Required | Not Required | 2025-09-15
27INR0373 | Velado Solar SLF | SS Completed, FIS Started, No IA | Velado Solar, LLC | Tap 138kV 78281 Dimmit - 8274 Conoco Chittam | Dimmit | SOUTH | 2028-09-14 | SOL | PV | 115.2 |  | 2024-11-07 | 2024-11-19 | 2025-02-14 | 2024-11-07 |  |  |  | No |  |  | Not Required
27INR0374 | Velado Storage SLF | SS Completed, FIS Started, No IA | Velado Solar, LLC | Tap 138kv 78281 Dimmit - 8274 Conoco Chittam. | Dimmit | SOUTH | 2028-09-14 | OTH | BA | 115.2 |  | 2024-11-05 | 2024-11-19 | 2025-02-14 | 2024-11-05 |  |  |  | No
29INR0107 | 7L Solar SLF | SS Completed, FIS Started, No IA | 7L Solar, LLC | Tap 69kV 5870 Brundage - 5868 Big Wells | Dimmit | SOUTH | 2029-11-13 | SOL | PV | 71.6 |  | 2025-09-15 | 2025-09-22 | 2025-12-12 | 2025-09-12 |  |  |  | No |  |  | Not Required
29INR0108 | 7L Storage SLF | SS Completed, FIS Started, No IA | 7L Solar, LLC | Tap 69kV 5870 Brundage - 5868 Big Wells | Dimmit | SOUTH | 2029-11-13 | OTH | BA | 0 |  | 2025-09-16 | 2025-09-22 | 2025-12-12 | 2025-09-12 |  |  |  | No
26INR0391 | Jumping Cactus Storage | SS Completed, FIS Started, No IA | Dove Wing Energy Center, LLC | 138 kV Zenaida Bus# 80043 | Duval | SOUTH | 2029-09-30 | OTH | BA | 125.32 |  | 2024-01-03 | 2024-01-11 | 2024-03-19 | 2023-12-19 |  |  |  | No
26INR0393 | Dove Wing Storage | SS Completed, FIS Started, No IA | Dove Wing Energy Center, LLC | 138 kV Zenaida Bus# 80043 | Duval | SOUTH | 2029-09-30 | OTH | BA | 122.21 |  | 2024-01-13 | 2024-02-07 | 2024-04-29 | 2024-01-05 |  |  |  | No
27INR0150 | Cielo Vista Solar | SS Completed, FIS Started, No IA | Cielo Vista Solar, LLC | Tap 345kV Bus #5901 Miguel5 - Bus #80079 Cruce7A Ckt 1 | Duval | SOUTH | 2029-03-30 | SOL | PV | 503.34 |  | 2025-03-26 | 2025-04-21 | 2025-07-18 | 2025-04-14 |  |  |  | No |  |  | Not Required
28INR0040 | Black Hawk Solar | SS Completed, FIS Started, No IA | ACE DevCo NC, LLC | San Miguel (5901) - Cruce (80079) double circuit transmission line. Requesting interconnection to both lines on the double circuit. This is a planned double circuit with ISD of 2027. | Duval | SOUTH | 2030-12-31 | SOL | PV | 251.34 |  | 2024-11-26 | 2024-02-27 | 2024-05-24 | 2024-11-21 |  |  |  | No |  |  | Not Required
28INR0168 | Guajillo Wind | SS Completed, FIS Started, No IA | Guajillo Wind LLC | Tap 345 kV 80079 Cruce - 5901 San Miguel CKT 01 | Duval | SOUTH | 2028-09-01 | WIN | WT | 199.9 |  | 2024-12-11 | 2024-12-19 | 2025-03-18 | 2024-12-10 |  |  |  | No |  |  | Not Required
28INR0229 | Allthorn Solar | SS Completed, FIS Started, No IA | ALLTHORN SOLAR, LLC | Tap 138 kV BRUNI4A (#8297) - CRESTONI4A (#8695) | Duval | SOUTH | 2029-01-15 | SOL | PV | 231.5 |  | 2024-12-17 | 2025-02-14 | 2025-05-13 | 2025-02-03 |  |  |  | No |  |  | Not Required
28INR0230 | Allthorn BESS | SS Completed, FIS Started, No IA | ALLTHORN SOLAR, LLC | Tap 138 kV BRUNI44A (#8297) - CRESTONI4A (#8695) | Duval | SOUTH | 2029-01-15 | OTH | BA | 205.2 |  | 2024-12-17 | 2025-02-14 | 2025-05-13 | 2025-02-03 |  |  |  | No
28INR0325 | Cielo Vista Power Gas Plant | SS Completed, FIS Started, No IA | Cielo Vista Power, LLC | Tap 345kV Bus #5901 Miguel5 - Bus #80079 Cruce7A Ckt 1 | Duval | SOUTH | 2029-03-30 | GAS | IC | 343.8 | COD | 2025-07-29 | 2025-08-18 | 2025-10-13 | 2025-08-13 |  |  |  | No
28INR0497 | Cielo Vista Power II | SS Started, FIS Started, No IA | Cielo Vista Power II, LLC | TAP 345 kV BUS # 5901 MIGUEL5 - BUS #80280 CRUCE SM 7A Ckt-1 | Duval | SOUTH | 2029-03-30 | GAS | IC | 350.38 | COD | 2026-04-16 | 2026-07-06 |  | 2026-07-01 |  |  |  | No
29INR0115 | Cielo Vista Storage | SS Completed, FIS Started, No IA | Cielo Vista Storage, LLC | Tap 345kV Bus #5901 Miguel5 - Bus #80079 Cruce7A Ckt 1 | Duval | SOUTH | 2029-03-30 | OTH | BA | 310.8 |  | 2025-03-18 | 2025-04-21 | 2025-07-18 | 2025-03-25 |  |  |  | No
29INR0124 | Apricot Sun Solar | SS Completed, FIS Started, No IA | Apricot Sun Energy Center, LLC | Tap 80079 (Cruce) - 5901 (San Miguel) 345 kV Ckt 1 | Duval | SOUTH | 2029-09-30 | SOL | PV | 200.84 |  | 2025-03-26 | 2025-04-01 | 2025-06-25 | 2025-03-30 |  |  |  | No |  |  | Not Required
29INR0125 | Apricot Sun Storage | SS Completed, FIS Started, No IA | Apricot Sun Energy Center, LLC | Tap 80079 (Cruce) - 5901 (San Miguel) 345 kV Ckt 1 | Duval | SOUTH | 2029-09-30 | OTH | BA | 200.84 |  | 2025-03-26 | 2025-04-01 | 2025-06-25 | 2025-03-30 |  |  |  | No
29INR0146 | Estrella Dorada Wind | SS Completed, FIS Started, No IA | Estrella Dorada Wind Farm, LLC | Tap 345 kV 80079 Cruce - 5901 San Miguel Ckt 2 | Duval | SOUTH | 2029-07-13 | WIN | WT | 306 |  | 2025-07-16 | 2025-07-21 | 2025-09-30 | 2025-07-17 |  |  |  | No |  |  | Not Required
29INR0160 | Cazadores Solar | SS Completed, FIS Started, No IA | OCI Energy LLC | Tap 345 kV (80079) CRUCE7A – (5901) MIGUEL5 CKT 2 | Duval | SOUTH | 2029-04-10 | SOL | PV | 301.62 |  | 2025-06-16 | 2025-07-07 | 2025-10-01 | 2025-06-20 |  |  |  | No |  |  | Not Required
18INR0064 | Silver Star repower | SS Completed, FIS Completed, IA | Silver Star I Power Partners, LLC | 1642 Flat Creek 138kV | Eastland | NORTH | 2026-12-31 | WIN | WT | -7.2 | COD | 2017-07-06 | 2017-04-05 | 2017-05-08 | 2017-07-06 | 2018-04-26 | No | 2018-10-16 | Yes | Not Required | Not Required | Not Required | 2019-10-23 | 2019-10-23 | 2019-10-28 |  |  |  | 2020-07-28
21INR0546 | Anchor Wind III | SS Completed, FIS Completed, IA | RANCHLAND WIND PROJECT LLC | 345 kV Aspire Station (68011) | Eastland | NORTH | 2025-12-29 | WIN | WT | 16 |  | 2019-06-26 | 2021-12-03 | 2022-03-01 |  | 2021-04-30 | No | 2020-11-30 | Yes | Not Required | Not Required | Not Required | 2020-12-02 | 2021-04-30 | 2021-04-30 |  |  | 2021-11-29 | 2022-12-13
23INR0538 | Roadrunner Crossing BESS SLF | SS Completed, FIS Completed, IA | Roadrunner Crossing BESS | 68051 Reata 354kV | Eastland | NORTH | 2026-08-30 | OTH | BA | 0 |  | 2022-10-23 | 2022-11-15 | 2023-02-10 | 2022-10-28 | 2025-03-18 |  | 2025-02-15 | Yes | Not Required | Not Required | 2025-04-25 | 2025-04-28 | 2025-05-30 | 2025-04-28 |  |  | 2025-11-14 | 2025-12-10
26INR0467 | Basketflower Storage | SS Completed, FIS Completed, No IA | Basketflower Solar, LLC | Tap 138kV Risingstar (285) - Nimrod (289) | Eastland | NORTH | 2027-12-31 | OTH | BA | 92 |  | 2024-10-24 | 2024-10-29 | 2025-01-14 | 2024-10-25 | 2026-03-26 | No |  | No
26INR0468 | Basketflower Solar | SS Completed, FIS Completed, No IA | Basketflower Solar, LLC | Tap 138kV Risingstar (285) - Nimrod (289) | Eastland | NORTH | 2027-12-31 | SOL | PV | 183 |  | 2024-10-24 | 2024-10-29 | 2025-01-14 | 2024-10-24 | 2026-03-26 | No |  | No |  |  | Not Required
26INR0602 | Damia Storage | SS Completed, FIS Started, No IA | Damia Solar, LLC | Tap 138kV 6317 Cisco - 3545 MTNBRANCH_8 | Eastland | NORTH | 2028-07-01 | OTH | BA | 153 |  | 2025-03-30 | 2025-04-01 | 2025-06-25 | 2025-03-18 |  | No |  | No
26INR0603 | Damia Solar | SS Completed, FIS Started, No IA | Damia Solar, LLC | Tap 138kV 6317 Cisco - 3545 MTNBRANCH_8 | Eastland | NORTH | 2028-07-01 | SOL | PV | 306 |  | 2025-03-30 | 2025-04-01 | 2025-06-25 | 2025-03-18 |  | No |  | No |  |  | Not Required
26INR0726 | Roadrunner Crossing Wind (Uprate) | SS Completed, FIS Completed, No IA | Roadrunner Wind, LLC | 68051 Reata 345kV | Eastland | NORTH | 2027-06-30 | WIN | WT | 7.32 |  | 2025-12-04 | 2025-12-23 | 2026-02-05 | 2025-12-10 | 2026-06-09 | No |  | Yes | Not Required | Not Required | Not Required | 2026-07-30 | 2026-07-30 | 2026-08-03
28INR0195 | Star Grass Renewable Energy Solar SLF | SS Completed, FIS Started, No IA | Star Grass Renewable Energy LLC | Tap 138kV 6310 Putnam - 3378 Carbon_8 | Eastland | NORTH | 2029-09-14 | SOL | PV | 150 |  | 2025-01-13 | 2025-02-14 | 2025-05-12 | 2024-12-30 |  |  |  | No |  |  | Not Required
28INR0197 | Star Grass Renewable Energy Storage SLF | SS Completed, FIS Started, No IA | Star Grass Renewable Energy LLC | Tap 138kV 6310 Putnam - 3378 Carbon_8 | Eastland | NORTH | 2029-09-14 | OTH | BA | 0 |  | 2025-01-13 | 2025-02-14 | 2025-05-12 | 2024-12-30 |  |  |  | No
29INR0274 | Richardson McClung Ranch Solar | SS Completed, FIS Started, No IA | Rising Star Energy Center, LLC | 33285 Rising Star 138 kV | Eastland | NORTH | 2029-11-30 | SOL | PV | 251.95 |  | 2026-06-30 | 2026-01-28 | 2026-02-09 | 2026-05-06 |  | No |  | No |  |  | Not Required
29INR0275 | Richardson McClung Ranch BESS | SS Completed, FIS Started, No IA | Rising Star Energy Center, LLC | 33285 Rising Star 138 kV | Eastland | NORTH | 2029-11-30 | OTH | BA | 205.49 |  | 2026-05-12 | 2026-01-26 | 2026-02-09 | 2026-05-06 |  | No |  | No
21INR0265 | Sisters Solar | SS Completed, FIS Completed, IA | Oberon Solar LLC | tapping the 345 kV line connecting Moss Switch (Bus# 1018) to Wolf Switching Station (Bus# 11010) | Ector | WEST | 2028-09-23 | SOL | PV | 100.51 |  | 2019-02-28 | 2019-02-28 | 2019-03-29 | 2019-02-20 | 2025-06-20 | Yes | 2025-07-01 | Yes | Not Required | Not Required | Not Required | 2025-09-18
21INR0268 | Greyhound Solar | SS Completed, FIS Completed, IA | Rockhound Solar 2, LLC dba "Greyhound Solar" | Tap 345kV 11010 Wolf - 1018 Moss | Ector | WEST | 2026-06-30 | SOL | PV | 335.45 |  | 2019-03-14 | 2019-03-28 | 2019-06-05 | 2019-03-21 | 2024-10-31 | No | 2022-01-15 | Yes | Not Required | Not Required | Not Required | 2024-11-04 | 2024-11-04 | 2024-11-04 |  |  | 2025-11-26 | 2026-04-24
22INR0218 | Velociraptor Solar I | SS Completed, FIS Started, No IA | Velociraptor Solar I, LLC | #10012 METEOR 5 Substation 345kV | Ector | WEST | 2029-12-01 | SOL | PV | 241.67 |  | 2019-05-23 | 2019-05-14 | 2019-08-05 | 2019-05-10 |  |  |  | No | Not Required | Not Required | Not Required
23INR0471 | Ophelia Solar | SS Completed, FIS Started, No IA | Ophelia Solar | Tap 138 kV Raceway Switch #18663 - Shin Oak POD #11128 | Ector | WEST | 2028-09-19 | SOL | PV | 110.5 |  | 2022-08-15 | 2022-09-02 | 2022-11-29 | 2022-08-01 |  |  |  | No |  |  | Not Required
25INR0140 | Seragio BESS | SS Completed, FIS Completed, No IA | Seragio BESS, LLC | 11140 ECTRCNTYN_8 138kV | Ector | WEST | 2028-04-30 | OTH | BA | 201.13 |  | 2022-12-27 | 2022-09-15 | 2022-12-13 | 2022-12-29 | 2026-04-14 | No |  | No
25INR0301 | Van Zandt Energy Storage | SS Completed, FIS Completed, IA | Rocky Mountain Energy Holdings, LLC | 1027 Odessa EHV Switch 138 kV | Ector | WEST | 2027-05-15 | OTH | BA | 256 |  | 2023-03-21 | 2023-06-07 | 2023-09-01 | 2023-04-05 | 2024-11-18 | No | 2025-03-03 | No
26INR0273 | Momentum Hazy Jane BESS | SS Completed, FIS Started, No IA | MOMENTUM HAZY JANE, LLC | Tap 138kV 1102 Judkins - 1110 Edward | Ector | WEST | 2028-02-26 | OTH | BA | 125.5 |  | 2024-08-21 | 2023-11-14 | 2024-02-09 | 2024-08-08 |  |  |  | No
26INR0287 | Firebird BESS | SS Completed, FIS Started, No IA | TX BESS 6, LLC | Tap 138kV #1099 Southwestern Portland Tap - #1052 Rexall | Ector | WEST | 2029-06-29 | OTH | BA | 102.65 |  | 2023-10-31 | 2023-11-14 | 2024-02-09 | 2023-10-31 |  |  |  | No | Not Required | Not Required
27INR0421 | M-Bar Solar I | SS Completed, FIS Completed, No IA | M-Bar Energy I, LLC | 1141 Holt Switch Substation 138kV | Ector | WEST | 2028-09-18 | SOL | PV | 30.21 |  | 2024-12-13 | 2024-12-19 | 2025-03-17 | 2024-12-13 | 2026-08-25 | No |  | No |  |  | Not Required
27INR0422 | M-Bar BESS I | SS Completed, FIS Started, No IA | M-Bar Energy I, LLC | 1141 Holt Switch Substation 138 kV | Ector | WEST | 2028-09-18 | OTH | BA | 82.1 |  | 2024-12-13 | 2024-12-19 | 2025-03-17 | 2024-12-13 |  | No |  | No
27INR0493 | Velociraptor BESS I | SS Completed, FIS Started, No IA | Velociraptor BESS I, LLC | 10012 METEOR_5 Substation 345kV | Ector | WEST | 2029-12-01 | OTH | BA | 246 |  | 2025-05-15 | 2025-05-27 | 2025-08-23 | 2025-05-07 |  |  |  | No
27INR0570 | Sisters Solar - Phase 2 | SS Started, FIS Started, No IA | Oberon Solar IV, LLC | 10009 McGee 345 kV | Ector | WEST | 2028-09-23 | SOL | PV | 201.51 |  | 2026-07-14 | 2026-07-22 |  | 2026-07-22 |  |  |  | No |  |  | Not Required
28INR0177 | Sisters Solar II | SS Completed, FIS Completed, No IA | Oberon Solar III, LLC | tap 345kV 11010 Wolf Switching Station - 10012 Meteor | Ector | WEST | 2028-12-15 | SOL | PV | 205.54 |  | 2024-10-18 | 2024-10-21 | 2025-01-10 | 2024-10-18 | 2026-03-27 | No |  | No |  |  | Not Required
28INR0205 | Gypsum Plains Solar | SS Completed, FIS Started, No IA | Gypsum Plains Solar, LLC | Tap 345kv line Wolf BUS# 11010 - Reiter BUS#18544 | Ector | WEST | 2029-06-21 | SOL | PV | 503.12 |  | 2025-05-28 | 2025-06-05 | 2025-09-02 | 2025-05-29 |  |  |  | No |  |  | Not Required
28INR0217 | Gypsum Plains Storage | SS Completed, FIS Started, No IA | Gypsum Plains Solar, LLC | Tap 345kv 11010 Wolf - 18544 Reiter | Ector | WEST | 2029-06-21 | OTH | BA | 211.14 |  | 2024-12-30 | 2025-01-31 | 2025-04-18 | 2025-01-24 |  |  |  | No
28INR0227 | GPlains Solar | SS Completed, FIS Started, No IA | Gypsum Plains Solar, LLC | Tap 138kV #1013 WOLFSS_8 - #1103 SANDHLTA_8 | Ector | WEST | 2029-06-21 | SOL | PV | 151.29 |  | 2025-03-27 | 2025-04-21 | 2025-07-19 | 2025-04-08 |  |  |  | No |  |  | Not Required
28INR0228 | GPlains Storage | SS Completed, FIS Started, No IA | Gypsum Plains Solar, LLC | Tap 138kV WOLFSS_8 (1013) - SANDHLTA_8 (1103) | Ector | WEST | 2029-06-21 | OTH | BA | 51.27 |  | 2025-03-27 | 2025-04-21 | 2025-07-19 | 2025-04-11 |  |  |  | No
28INR0322 | Velociraptor Solar II | SS Completed, FIS Started, No IA | Velociraptor Solar II, LLC | Tap Wolf (#11010) - Reiter Switch (#18544) Ckt1 345KV | Ector | WEST | 2029-12-01 | SOL | PV | 241.81 |  | 2025-05-20 | 2025-05-27 | 2025-08-23 | 2025-05-12 |  |  |  | No |  |  | Not Required
28INR0323 | Velociraptor BESS II | SS Completed, FIS Started, No IA | Velociraptor BESS II, LLC | Tap Wolf (#11010) - Reiter Switch (#18544) Ckt1 345KV | Ector | WEST | 2029-12-01 | OTH | BA | 246.12 |  | 2025-05-15 | 2025-05-27 | 2025-08-23 | 2025-05-07 |  |  |  | No
30INR0141 | Jackrabbit Flats Solar | SS Started, FIS Started, No IA | Jackrabbit Flats Solar LLC | Tap 345 kV 1185 Midland County NW - 1018 Moss | Ector | WEST | 2030-06-29 | SOL | PV | 401.33 |  | 2026-07-07 | 2026-07-22 |  | 2026-07-16 |  |  |  | No |  |  | Not Required
21INR0362 | Oystercatcher Solar | SS Completed, FIS Completed, IA | Oystercatcher Solar, LLC | tap 345kV 1906 Venus - 68091 Navarro | Ellis | NORTH | 2027-01-29 | SOL | PV | 198.43 |  | 2020-01-15 | 2019-05-30 | 2019-08-07 | 2019-12-20 | 2025-11-13 | Yes | 2021-08-20 | No | Not Required | Not Required | Not Required | 2026-01-09 | 2026-01-29 | 2026-01-29 |  |  | 2026-09-02
21INR0534 | Midlothian Unit 2 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1939 Midlothian ELP 345kV | Ellis | NORTH | 2028-06-03 | GAS | GT | 18 | COD | 2021-04-28 | 2021-01-25 | 2021-04-30 | 2021-02-08 |  |  |  | No
22INR0523 | Midlothian 4 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1940 Midlothian ANP 345kV | Ellis | NORTH | 2028-06-03 | GAS | GT | 18 | COD | 2021-04-28 | 2021-04-26 | 2021-07-28 | 2021-04-21 |  |  |  | No
22INR0543 | Midlothian Unit 3 repower | SS Completed, FIS Started, No IA | MIDLOTHIAN ENERGY, LLC | 1940 Midlothian ELP 345kV | Ellis | NORTH | 2028-06-03 | GAS | GT | 18 | COD | 2021-05-21 | 2021-05-24 | 2021-08-06 | 2021-05-11 |  |  |  | No
23INR0216 | Venus Mill Storage | SS Completed, FIS Started, IA | AIH Texas Acquisitions, LLC | 138 kV Tap #442 Rail Port - #1905 Griffith | Ellis | NORTH | 2027-12-31 | OTH | BA | 100.8 |  | 2022-02-11 | 2022-03-14 | 2022-06-09 | 2022-03-04 |  | No | 2025-12-24 | No | Not Required | Not Required
24INR0178 | Cumulus Grid BESS | SS Completed, FIS Completed, IA | Cumulus Grid, LLC | 1906 Venus Switch Substation 345kV | Ellis | NORTH | 2028-01-01 | OTH | BA | 210.74 |  | 2022-11-01 | 2022-03-14 | 2022-04-18 | 2022-10-18 | 2025-01-27 |  | 2025-06-03 | Yes | Not Required | Not Required |  | 2026-03-24
25INR0005 | Tokyo TxHSR TPSS EW-1 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 2241 Ennis W - 2321 Waxahachie | Ellis | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-09-13 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  |  |  | No | Not Required | Not Required
25INR0495 | Dolomite Storage | SS Completed, FIS Started, No IA | BT Wilson Storage, LLC | 218 Rockett 69kV | Ellis | NORTH | 2026-12-01 | OTH | BA | 125.7 |  | 2023-08-15 | 2023-09-08 | 2023-12-04 | 2023-08-22 |  | No |  | No | Not Required | Not Required
26INR0241 | Sol Marina SLF Energy Center | SS Completed, FIS Completed, IA | Sol Marina Energy Center, LLC | Tap 345kV Stainback Switch (bus# 2217) – Big Onion Switch (bus# 2466) | Ellis | NORTH | 2027-10-29 | SOL | PV | 171.09 |  | 2023-10-17 | 2023-10-25 | 2024-01-22 | 2023-09-07 | 2026-09-17 | No | 2025-04-25 | Yes | Not Required | Not Required | Not Required | 2025-07-29
27INR0219 | Galaxy Solar | SS Completed, FIS Started, No IA | Galaxy Solar, LLC | Stainback Switch (bus #2217) - Elrod Switch (bus #3159) | Ellis | NORTH | 2028-10-30 | SOL | PV | 177.32 |  | 2024-08-22 | 2024-03-22 | 2024-06-19 | 2024-08-16 |  | No |  | No |  |  | Not Required
27INR0220 | Galaxy Storage | SS Completed, FIS Started, No IA | Galaxy Solar, LLC | Stainback Switch (bus #2217) - Elrod Switch (bus #3159) | Ellis | NORTH | 2028-10-30 | OTH | BA | 155 |  | 2024-08-22 | 2024-03-22 | 2024-06-19 | 2024-08-16 |  | No |  | No
27INR0417 | Bluebonnet Trail Solar | SS Completed, FIS Completed, No IA | Bluebonnet trail solar LLC | Tap 345 kV (#2427) WATMLL_W5 - (#2466) BIGONION_5 | Ellis | NORTH | 2028-09-19 | SOL | PV | 150.9 |  | 2024-12-18 | 2024-12-19 | 2025-03-17 | 2024-12-13 | 2026-07-30 | Yes |  | No |  |  | Not Required
27INR0469 | Kickstart Energy Storage I | SS Completed, FIS Started, No IA | Kickstart Infrastructure LLC | Tap 345 kV 1907 Venus Switch - 3383 BYNUM_5 | Ellis | NORTH | 2029-09-30 | OTH | BA | 1.44 |  | 2025-03-06 | 2025-03-24 | 2025-06-09 | 2025-03-12 |  |  |  | No
27INR0470 | Kickstart Energy Storage II | SS Completed, FIS Started, No IA | Kickstart Infrastructure LLC | Tap 345 kV 1907 Venus Switch - 3383 BYNUM_5 | Ellis | NORTH | 2029-09-30 | OTH | BA | 1.44 |  | 2025-03-06 | 2025-03-24 | 2025-06-09 | 2025-03-12 |  |  |  | No
27INR0471 | Kickstart Energy Storage III | SS Completed, FIS Started, No IA | Kickstart Infrastructure LLC | Tap 345 kV #1906 VENUS_S5 to #68091 NAVARRO | Ellis | NORTH | 2029-09-30 | OTH | BA | 1.44 |  | 2025-03-06 | 2025-03-24 | 2025-06-09 | 2025-03-10 |  |  |  | No
27INR0472 | Kickstart Energy Storage IV | SS Completed, FIS Started, No IA | Kickstart Infrastructure LLC | Tap 345 kV #1906 VENUS_S5 to #68091 NAVARRO | Ellis | NORTH | 2029-09-30 | OTH | BA | 1.44 |  | 2025-03-06 | 2025-03-24 | 2025-06-09 | 2025-03-10 |  |  |  | No
28INR0100 | Digital Ranch Gas | SS Started, FIS Started, No IA | MCV 1 LLC | #1906 Venus Switch 345 kV | Ellis | NORTH | 2030-04-15 | GAS | IC | 378 | COD | 2026-06-30 | 2026-07-06 |  | 2026-06-26 |  |  |  | No
28INR0355 | Galaxy I Solar | SS Completed, FIS Started, No IA | Galaxy Solar, LLC | Stainback Switch (bus #2217) - Elrod Switch (bus #3159) | Ellis | NORTH | 2028-10-30 | SOL | PV | 99.42 |  | 2025-07-22 | 2025-04-21 | 2025-07-19 | 2025-07-16 |  | No |  | No |  |  | Not Required
28INR0385 | Galaxy Solar 2 | SS Completed, FIS Started, No IA | Galaxy Solar 2, LLC | 3/4-Breaker Ring Bus at 345kV Venus Switch (#1907) BKR 4920 - Navarro Switch (LST) (#68091) BKR 3B3134/3B3127 | Ellis | NORTH | 2029-10-30 | SOL | PV | 301.64 |  | 2025-06-12 | 2025-06-19 | 2025-09-17 | 2025-09-03 |  |  |  | No |  |  | Not Required
28INR0387 | Galaxy Storage 2 | SS Completed, FIS Started, No IA | Galaxy Solar 2, LLC | 3/4-Breaker Ring Bus at 345kV Venus Switch (#1907) BKR 4920 - Navarro Switch (LST) (#68091) BKR 3B3134/3B3127 | Ellis | NORTH | 2029-10-30 | OTH | BA | 201.87 |  | 2025-09-10 | 2025-06-19 | 2025-09-17 | 2025-09-03 |  |  |  | No
28INR0495 | Old Alma Road Solar | SS Started, FIS Started, No IA | Wildcat Renewables, LLC | 2326 ENNS_SE_8 138kV | Ellis | NORTH | 2028-10-31 | SOL | PV | 20.06 |  | 2026-09-01 | 2026-09-04 |  | 2026-08-26 |  |  |  | No |  |  | Not Required
28INR0529 | Victory Ellis–BESS | SS Completed, FIS Started, No IA | Victory Ellis, LLC | Tap 345kV Nimbus (2249) – Big Onion (2466) & Stainback (2217) – Elrod Switch (3159) DCKT | Ellis | NORTH | 2030-09-28 | OTH | BA | 452.99 |  | 2026-06-23 | 2026-07-10 | 2026-08-18 | 2026-06-26 |  |  |  | No
28INR0531 | Crape Myrtle Solar | SS Started, FIS Started, No IA | Crape Myrtle Solar LLC | Tap 345 kV 2255 OLDCNTRY_5 - 3376 NOTUS_5 | Ellis | NORTH | 2030-04-15 | SOL | PV | 140.69 |  | 2026-06-30 | 2026-07-06 |  | 2026-06-17 |  |  |  | No |  |  | Not Required
29INR0196 | Two Step Solar | SS Completed, FIS Started, No IA | Two Step Solar, LLC | Tap 345kV 1907 Venus - 68091 Navarro | Ellis | NORTH | 2029-09-17 | SOL | PV | 401.62 |  | 2025-12-03 | 2025-12-17 | 2026-02-04 | 2025-11-12 |  | No |  | No |  |  | Not Required
29INR0217 | Kickstart Energy Storage V | SS Completed, FIS Started, No IA | Kickstart Infrastructure LLC | 345 KV Venus 1906 to Fort Smith 3389 | Ellis | NORTH | 2029-12-31 | OTH | BA | 999 |  | 2025-11-18 | 2025-11-24 | 2026-01-19 | 2025-11-21 |  |  |  | No
29INR0218 | Kickstart Energy Storage VI | SS Completed, FIS Started, No IA | Kickstart Infrastructure LLC | 345 KV Venus 1907 to Navarro 68091 | Ellis | NORTH | 2029-12-31 | OTH | BA | 1026.2 |  | 2025-11-10 | 2025-12-17 | 2026-02-23 | 2025-11-21 |  |  |  | No
29INR0264 | Victory Ellis – Gas | SS Completed, FIS Started, No IA | Victory Ellis, LLC | Tap 345kV Nimbus (2249) – Big Onion (2466) & Stainback (2217) – Elrod Switch (3159) DCKT | Ellis | NORTH | 2030-09-28 | GAS | GT | 465.92 |  | 2026-04-14 | 2026-07-08 | 2026-08-18 | 2026-04-24 |  |  |  | No
23INR0202 | Erath County Solar | SS Completed, FIS Started, IA | Erath County Solar, LLC | tap 345kV 68020 Romney1E - 68030 KopperlW | Erath | NORTH | 2029-01-31 | SOL | PV | 207.4 |  | 2021-01-20 | 2021-03-08 | 2021-05-28 | 2021-03-06 |  | Yes | 2023-06-01 | Yes |  |  | Not Required | 2025-02-12
25INR0661 | McCrae Energy Storage | SS Completed, FIS Completed, IA | McCrae Energy Storage, LLC | Tap 345 kV 1900 COMCHPKW_5 - 1440 COMCHESS1_5 | Erath | NORTH | 2028-09-25 | OTH | BA | 306.35 |  | 2024-04-29 | 2024-05-20 | 2024-08-13 | 2024-05-01 | 2026-02-17 | No | 2025-12-30 | No
28INR0290 | Field Marshal Storage | SS Completed, FIS Started, No IA | Field Marshal Storage LLC | Dublin (1636) - Fullhouse (1652) 138kV | Erath | NORTH | 2029-05-07 | OTH | BA | 150.8 |  | 2025-03-11 | 2025-03-24 | 2025-06-09 | 2025-03-20 |  |  |  | No
20INR0106 | Wang Solar SLF | SS Completed, FIS Started, No IA | BT Yixin Solar, LLC | tap 345kV 3409 LakeCr1 - 3414 TempSS | Falls | NORTH | 2029-01-31 | SOL | PV | 144.6 | COD | 2018-08-29 | 2018-06-14 | 2018-08-13 | 2018-08-29 |  | No |  | No | Not Required | Not Required | Not Required
20INR0205 | Roseland Solar | SS Completed, FIS Completed, IA | Enel Green Power Roseland Solar, LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2026-10-05 | SOL | PV | 254 | COD | 2018-11-05 | 2018-11-30 | 2019-02-04 | 2019-02-04 | 2021-10-25 | No | 2020-12-10 | Yes | Not Required | Not Required | Not Required | 2021-08-18 | 2021-11-01 | 2021-10-25 |  |  | 2022-06-07 | 2022-09-26
22INR0506 | Roseland Solar II | SS Completed, FIS Completed, IA | Enel Green Power Roseland Solar, LLC | tap 345kV 3390 Jewett - 3399 Ratsnake | Falls | NORTH | 2026-10-05 | SOL | PV | 254 | COD | 2018-11-05 | 2021-10-05 | 2019-02-04 |  | 2021-10-25 |  | 2020-12-10 | Yes | Not Required | Not Required | Not Required | 2021-10-26 | 2021-10-26 | 2021-10-26 |  |  | 2022-06-07 | 2022-09-26
22INR0514 | Wang Storage SLF | SS Completed, FIS Started, No IA | BT Yixin Solar, LLC | tap 345kV 3409 LakeCr1 - 3414 TempSS | Falls | NORTH | 2029-01-31 | OTH | BA | 0 | COD | 2021-06-09 | 2022-11-07 | 2023-02-03 | 2022-09-23 |  | No |  | No
24INR0040 | Rosebud Solar SLF | SS Completed, FIS Completed, No IA | Rosebud Solar, LLC | Tap 69kV 67 BAGGINS - 69 BARCLAY | Falls | NORTH | 2028-01-15 | SOL | PV | 130 |  | 2022-01-12 | 2021-04-13 | 2021-07-06 | 2022-01-10 | 2025-10-20 |  |  | No |  |  | Not Required
25INR0297 | RIVERBEND SOLAR SLF | SS Completed, FIS Started, No IA | Riverbend Renewables, LLC | TAP 345 KV LINE FROM TRADINGHOUSE (#3405) TO TEMPLE PECAN CREEK (#3412) SUBSTATIONS | Falls | NORTH | 2027-12-31 | SOL | PV | 301.6 |  | 2023-02-13 | 2023-03-08 | 2023-06-05 | 2023-03-03 |  |  |  | No |  |  | Not Required
25INR0311 | RIVERBEND STORAGE SLF | SS Completed, FIS Completed, No IA | Riverbend Renewables, LLC | TAP 345 KV LINE FROM TRADINGHOUSE (#3405) TO TEMPLE PECAN CREEK (#3412) SUBSTATIONS | Falls | NORTH | 2027-12-31 | OTH | BA | 0 |  | 2023-02-13 | 2023-03-08 | 2023-06-05 | 2023-03-03 | 2024-07-23 |  |  | No
25INR0341 | Rosebud Storage SLF | SS Completed, FIS Completed, No IA | Rosebud Storage, LLC | Tap 69 kV 67 BAGGINS - 69 BARCLAY | Falls | NORTH | 2028-01-15 | OTH | BA | 0 |  | 2024-01-05 | 2023-03-09 | 2023-06-05 | 2023-12-04 | 2025-10-20 |  |  | No
25INR0440 | Bronc Rodeo Solar Project | SS Completed, FIS Started, No IA | Energiekontor US Texas SP 16 LLC | Tap 138 kV Line from Temple Pecan Creek (#3420) to the Cow Bayou Switch (#3385) | Falls | NORTH | 2029-04-16 | SOL | PV | 105.7 |  | 2023-09-19 | 2023-05-03 | 2023-07-28 | 2023-09-12 |  |  |  | No | Not Required | Not Required | Not Required
28INR0147 | Fallstone Solar SLF | SS Completed, FIS Started, No IA | Fallstone Solar, LLC | Tap 69kV 3588 Groesbeck - 3637 Otto Junction | Falls | NORTH | 2028-09-21 | SOL | PV | 60.55 |  | 2024-11-08 | 2024-12-19 | 2025-03-18 | 2024-12-04 |  |  |  | No |  |  | Not Required
28INR0149 | Fallstone Storage SLF | SS Completed, FIS Started, No IA | Fallstone Solar, LLC | Tap 69kV 3588 Groesbeck - 3637 Otto Junction | Falls | NORTH | 2028-09-21 | OTH | BA | 0 |  | 2024-11-08 | 2024-12-19 | 2025-03-18 | 2024-12-04 |  |  |  | No
28INR0262 | Pasture Rose Wind | SS Completed, FIS Started, No IA | Pasture Rose, LLC | TAP 345KV BUS 3721 STRANGER SW - 3711 BALE_S5 | Falls | NORTH | 2029-06-07 | WIN | WT | 198.7 |  | 2025-02-05 | 2025-03-24 | 2025-06-09 | 2025-04-01 |  |  |  | No |  |  | Not Required
29INR0105 | Falls County Storage | SS Completed, FIS Started, No IA | Aurora Solar LLC | 3711 BALSW 345kV | Falls | NORTH | 2029-10-01 | OTH | BA | 60 |  | 2026-01-27 | 2025-04-29 | 2025-07-26 | 2026-01-14 |  |  |  | No
27INR0145 | Steelhead Energy Storage | SS Completed, FIS Started, No IA | GRS BESS TEXAS SEVEN, LLC | Tap 1593 BONHAM_P8 to Allens Creek 1835 138kV | Fannin | NORTH | 2029-04-30 | OTH | BA | 192.1 |  | 2023-12-17 | 2024-02-07 | 2024-04-29 | 2024-01-04 |  |  |  | No | Not Required | Not Required
28INR0286 | 2 Cedar Wind | SS Completed, FIS Started, No IA | SunWR, LLC | Tap 345kV 1729 Valley South – Anna Switch 2373 | Fannin | NORTH | 2028-05-02 | WIN | WT | 180 |  | 2026-03-31 | 2025-07-07 | 2025-09-30 | 2026-03-26 |  |  |  | No |  |  | Not Required
29INR0191 | Black Mountain Fannin Gas | SS Completed, FIS Started, No IA | Black Mountain Power LLC | 345 KV #1729 Valley South | Fannin | NORTH | 2030-04-26 | GAS | CC | 990.59 |  | 2026-05-27 | 2026-06-04 | 2026-08-28 | 2026-05-14 |  |  |  | No
25INR0189 | Staccato BESS | SS Completed, FIS Completed, IA | Staccato Storage, LLC | 138kV WARDA #7312. | Fayette | SOUTH | 2027-05-28 | OTH | BA | 201.8 |  | 2023-01-05 | 2022-11-07 | 2023-02-03 | 2022-12-15 | 2026-03-11 | No | 2024-08-27 | Yes | Not Required | Not Required |  | 2026-05-01 | 2026-05-01 | 2026-05-01
25INR0512 | Monument Hill Solar | SS Completed, FIS Started, IA | RWE Solar Development, LLC | Tap 345kV 7055 Fayette - 9074 Lytton Springs | Fayette | SOUTH | 2029-06-30 | SOL | PV | 200 |  | 2023-07-31 | 2023-10-13 | 2024-01-10 | 2023-08-23 |  |  | 2025-12-22 | No |  |  | Not Required
28INR0150 | South Tripoint BESS | SS Completed, FIS Started, No IA | South Triangle Energy, LLC | 7286 L_FAYETT8_1Y 138kV | Fayette | SOUTH | 2030-05-30 | OTH | BA | 204.5 |  | 2025-09-19 | 2024-12-19 | 2025-03-12 |  |  |  |  | No
29INR0249 | Lightcycle Energy Storage | SS Completed, FIS Started, No IA | Lightcycle Energy Storage LLC | 9073 HOLMAN 345 kV | Fayette | SOUTH | 2030-03-01 | OTH | BA | 409.69 |  | 2026-01-09 | 2026-01-13 | 2026-04-06 | 2026-01-09 |  | No |  | No | Not Required | Not Required
19INR0080 | Whitehorse Wind | SS Completed, FIS Completed, IA | MESQUITE STAR SPECIAL LLC | 68001 Clayton 345kV | Fisher | WEST | 2026-12-31 | WIN | WT | 418.9 |  |  | 2017-06-23 | 2017-08-07 | 2018-02-16 | 2019-01-22 | No | 2018-12-05 | Yes | Not Required | Not Required | Not Required | 2019-03-12 | 2019-04-02 | 2019-05-01 |  |  | 2019-12-12 | 2019-12-27
21INR0031 | Indigo Solar | SS Completed, FIS Started, IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2027-09-17 | SOL | PV | 150 |  | 2019-05-16 | 2018-09-27 | 2018-11-20 | 2019-05-15 |  | No | 2020-09-15 | Yes | Not Required | Not Required | Not Required | 2025-02-12
24INR0496 | Indigo Storage | SS Completed, FIS Started, IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2027-09-17 | OTH | BA | 60 |  | 2023-10-16 | 2022-12-15 | 2023-03-13 | 2023-08-28 |  | No | 2026-03-27 | Yes
25INR0528 | Indigo Storage 2 | SS Completed, FIS Started, IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2027-09-17 | OTH | BA | 60 |  | 2024-06-12 | 2023-09-22 | 2023-12-20 | 2024-06-06 |  | No | 2026-03-27 | Yes
25INR0529 | Indigo Storage 3 | SS Completed, FIS Started, IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2027-09-17 | OTH | BA | 60 |  | 2024-08-23 | 2023-11-14 | 2024-02-09 | 2024-06-06 |  | No | 2026-03-27 | Yes
25INR0530 | Indigo Storage 4 | SS Completed, FIS Started, IA | Innovative Solar 245, LLC | tap 345 kV 68001 Claytonville – 68004 Phantom Hill Circuit 2 | Fisher | WEST | 2027-09-17 | OTH | BA | 60 |  | 2024-06-26 | 2023-10-25 | 2024-01-22 | 2024-06-06 |  | No | 2026-03-27 | Yes
25INR0547 | Indigo solar 2 | SS Completed, FIS Started, No IA | Indigo Solar 2 | Tap 345KV 68001 Clayton 345KV -68000 WShack Ckt 2 | Fisher | WEST | 2027-07-15 | SOL | PV | 180 |  | 2024-08-23 | 2023-10-04 | 2023-12-22 | 2024-08-13 |  |  |  | No |  |  | Not Required
25INR0632 | Jenna Eco-Electric Solar | SS Completed, FIS Completed, No IA | Clean Energy Holdings, LLC | Tap 345 kV 1048 Tonkawa Switch - 1430 Graham SES | Fisher | WEST | 2029-04-16 | SOL | PV | 576.3 |  | 2024-05-17 | 2024-05-20 | 2024-08-13 | 2024-05-17 | 2026-04-02 | Yes |  | No |  |  | Not Required
28INR0067 | Indigo Solar 3 | SS Completed, FIS Started, No IA | Indigo solar 3 | Tap Line Segment Tankawa (Bus #1048) to Graham (Bus #1430) | Fisher | WEST | 2028-11-01 | SOL | PV | 800 |  |  | 2024-10-29 | 2025-01-25 | 2025-07-15 |  |  |  | No |  |  | Not Required
28INR0415 | Alkali Creek Wind | SS Completed, FIS Started, No IA | Alkali Creek Wind, LLC | Tap 345 kV BUS #1048 Tonkawa - BUS #11050 Dusty Road | Fisher | WEST | 2028-12-01 | WIN | WT | 474.4 |  | 2025-07-31 | 2025-08-18 | 2025-11-10 | 2025-07-31 |  |  |  | No |  |  | Not Required
28INR0456 | Brazos Energy Security | SS Completed, FIS Started, No IA | Golden Spread Electric | Tap 345 kV (Bus #1048) Tonkawa Switch – (Bus #11050) Dusty Road | Fisher | WEST | 2030-09-22 | GAS | CC | 3000 | FIS Request | 2026-09-29 | 2025-10-21 | 2026-01-06 | 2026-09-16 |  |  |  | No
28INR0478 | Alkali Creek Wind 2 | SS Completed, FIS Started, No IA | Alkali Creek Wind, LLC | Tap 345 kV BUS #1048 Tonkawa - BUS #11050 Dusty Road | Fisher | WEST | 2028-12-01 | WIN | WT | 250.3 |  | 2025-12-12 | 2025-12-17 | 2026-02-23 | 2025-11-20 |  |  |  | No |  |  | Not Required
29INR0399 | Rugged Prairie Wind | SS Started, FIS Started, No IA | Rugged Prairie Wind, LLC | Tap 345kV BUS #11305 Dermott- BUS #60706 Kirchhef | Fisher | WEST | 2029-12-01 | WIN | WT | 294.14 | FIS Request | 2026-09-29 | 2026-09-30 |  | 2026-09-18 |  |  |  | No |  |  | Not Required
23INR0140 | Seine BESS | SS Completed, FIS Completed, IA | BRP Seine BESS LLC | 60500 Edith Clarke 345kV | Foard | WEST | 2027-10-01 | OTH | BA | 308.88 |  | 2020-11-30 | 2020-12-03 | 2021-02-19 | 2020-11-27 | 2026-09-01 | No | 2024-12-01 | Yes | Not Required | Not Required |  | 2026-03-24
28INR0476 | Pease River Solar | SS Completed, FIS Started, No IA | Pease River Solar LLC | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B | Foard | WEST | 2029-06-30 | SOL | PV | 276.35 |  | 2025-11-25 | 2025-12-02 | 2025-12-15 | 2025-11-17 |  | Yes |  | No | Not Required | Not Required | Not Required
28INR0535 | Daisy Solar | SS Started, FIS Started, No IA | Daisy Solar LLC | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B | Foard | WEST | 2029-06-30 | SOL | PV | 200.92 |  | 2026-07-01 | 2026-07-06 |  | 2026-06-30 |  |  |  | No | Not Required | Not Required | Not Required
29INR0148 | Big Field Solar | SS Completed, FIS Started, No IA | Big Field Solar Energy LLC | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B | Foard | WEST | 2029-12-31 | SOL | PV | 506.17 |  | 2025-09-16 | 2025-06-11 | 2025-09-04 |  |  | Yes |  | No |  |  | Not Required
29INR0326 | Montgomery Ranch 2 Wind | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | 60059 Penumbra 345-kV | Foard | WEST | 2030-06-02 | WIN | WT | 301.5 |  | 2026-05-05 | 2026-05-11 | 2026-08-07 | 2026-05-08 |  |  |  | No |  |  | Not Required
24INR0405 | Crowned Heron BESS | SS Completed, FIS Completed, IA | RWE Renewables | WA Parish 345 kV Bus #44000 | Fort Bend | HOUSTON | 2026-10-02 | OTH | BA | 154.2 |  | 2022-07-14 | 2022-07-18 | 2022-10-14 | 2022-07-12 | 2023-05-17 |  | 2023-06-26 | Yes | Not Required | Not Required |  | 2024-05-01 | 2024-05-01 | 2024-05-01 |  |  | 2025-12-08 | 2026-01-21
24INR0493 | Crowned Heron BESS 2 | SS Completed, FIS Completed, IA | RWE Renewables | WA Parish 345 kV Bus #44000 | Fort Bend | HOUSTON | 2026-10-02 | OTH | BA | 154.2 |  | 2022-11-22 | 2022-11-23 | 2023-02-17 | 2022-11-15 | 2024-01-28 | No | 2024-08-20 | Yes |  |  |  | 2024-10-10 | 2024-11-04 | 2024-11-04 |  |  | 2026-01-27 | 2026-04-06
25INR0242 | Pato Blanco Storage | SS Completed, FIS Completed, No IA | TX BESS 4, LLC | Tap 138 kV 44010 W A Parish - 42980 NASH___S02_8 | Fort Bend | HOUSTON | 2028-12-15 | OTH | BA | 71.34 |  | 2023-04-25 | 2023-05-15 | 2023-08-11 | 2023-04-24 | 2025-09-12 |  |  | No
25INR0372 | Elan BESS | SS Completed, FIS Completed, No IA | Elan BESS, LLC | 42380 Needville 138kV | Fort Bend | HOUSTON | 2026-12-31 | OTH | BA | 202.65 |  | 2023-03-01 | 2023-03-08 | 2023-06-05 | 2023-02-15 | 2024-03-21 |  |  | No
26INR0201 | Rock Rose BESS | SS Completed, FIS Completed, IA | Rock Rose Energy Storage LLC | 44070 Whaley 345 kV | Fort Bend | HOUSTON | 2027-03-19 | OTH | BA | 208.5 |  | 2023-03-21 | 2023-09-22 | 2023-12-14 | 2023-09-08 | 2026-03-18 | No | 2024-06-15 | Yes | Not Required | Not Required | 2025-11-12 | 2025-11-13 | 2026-05-26 | 2026-05-01
26INR0375 | Avalon BESS | SS Completed, FIS Completed, IA | Avalon BESS, LLC | Tapping the 345 kV Line from Smithers (Bus# 44650) to Bellaire (Bus# 47000). | Fort Bend | HOUSTON | 2026-12-01 | OTH | BA | 522.12 |  | 2023-12-06 | 2023-12-20 | 2024-03-08 | 2023-11-30 | 2024-05-20 | Yes | 2024-12-17 | No | Not Required | Not Required
26INR0525 | Bypass BESS II | SS Completed, FIS Started, No IA | Bypass BESS II LLC | 44000 Wa Parish 345 kV | Fort Bend | HOUSTON | 2028-04-30 | OTH | BA | 205.86 |  | 2024-11-04 | 2024-11-19 | 2025-02-18 | 2024-10-23 |  | Yes |  | No
27INR0142 | UNICORN BESS | SS Completed, FIS Started, No IA | Unicorn Energies | Tap 138 kV Wa Parish (#44015) - Crabb River Road Line (#44170) Line; CNP | Fort Bend | HOUSTON | 2027-09-01 | OTH | BA | 278.98 |  | 2024-01-05 | 2024-01-11 | 2024-04-05 | 2024-01-05 |  |  |  | No
27INR0627 | Redbird BESS | SS Completed, FIS Started, No IA | Redbird BESS, LLC | 44090 Cedar Creek 345kV | Fort Bend | HOUSTON | 2029-03-01 | OTH | BA | 100 |  | 2026-07-27 | 2026-05-13 | 2026-08-07 | 2026-07-22 |  |  |  | No
29INR0145 | Elysium Energy Center BESS | SS Completed, FIS Started, No IA | Adapture Solar Development | 44030 Arcola 138 kV | Fort Bend | HOUSTON | 2030-01-17 | OTH | BA | 100 |  | 2026-01-20 | 2025-04-21 | 2025-07-19 |  |  |  |  | No
24INR0150 | Lupinus Solar 1 | SS Completed, FIS Completed, IA | Lupinus Solar, LLC | Tap 345 kV 11699 Woodard Switch - 1695 Monticello SES | Franklin | NORTH | 2027-09-13 | SOL | PV | 162.31 |  | 2022-05-23 | 2021-12-08 | 2022-03-04 | 2022-05-11 | 2026-09-17 | No | 2025-06-26 | Yes |  |  | Not Required | 2025-08-05
24INR0153 | Lupinus Storage 1 | SS Completed, FIS Completed, No IA | Lupinus Solar, LLC | Tap 345 kV 11699 Woodard Switch - 1695 Monticello SES | Franklin | NORTH | 2027-09-13 | OTH | BA | 84.01 |  | 2022-05-23 | 2021-12-13 | 2022-03-10 | 2022-05-11 | 2026-09-17 | No |  | Yes |  |  |  | 2025-09-22
24INR0154 | Lupinus Solar 2 | SS Completed, FIS Completed, IA | Lupinus Solar 2, LLC | Hagansport Switch (old Monticello Tap bus# 1794) | Franklin | NORTH | 2027-04-03 | SOL | PV | 242.31 |  | 2022-05-23 | 2021-12-13 | 2022-03-10 | 2022-05-11 | 2026-03-17 | No | 2025-03-04 | Yes | Not Required | Not Required | Not Required | 2026-04-22 | 2026-04-22 | 2026-04-09
24INR0155 | Lupinus Storage 2 | SS Completed, FIS Completed, IA | Lupinus Solar 2, LLC | Hagansport Switch (old Monticello Tap bus# 1794) | Franklin | NORTH | 2027-04-03 | OTH | BA | 124.55 |  | 2022-06-03 | 2021-12-13 | 2022-03-10 | 2022-05-11 | 2026-03-17 | No | 2025-03-04 | Yes | Not Required | Not Required |  | 2026-04-22 | 2026-04-22 | 2026-04-09
25INR0504 | Lazy Frog Solar SLF | SS Completed, FIS Completed, No IA | Lazy Frog Solar, LLC | 11688 Thorn Tree Switch 345kV | Franklin | NORTH | 2028-04-17 | SOL | PV | 100.4 |  | 2024-05-15 | 2023-09-22 | 2023-12-14 | 2024-05-10 | 2025-10-28 | No |  | No |  |  | Not Required
25INR0506 | Lazy Frog Storage SLF | SS Completed, FIS Completed, No IA | Lazy Frog Solar, LLC | 11688 Thorn Tree Switch 345kV | Franklin | NORTH | 2028-04-17 | OTH | BA | 0 |  | 2024-05-15 | 2023-09-22 | 2023-12-14 | 2024-05-10 | 2025-10-28 | No |  | No
30INR0071 | Prairie Ridge (Gas - CC) | SS Completed, FIS Started, No IA | Tenaska Power Generation, LLC | Tap 345 kV 11699 Woodard – 1695 Monticello | Franklin | NORTH | 2032-06-01 | GAS | CC | 1660.4 |  | 2025-11-18 | 2025-12-01 | 2026-01-19 | 2025-11-26 |  | No |  | No
24INR0117 | Utley Solar | SS Completed, FIS Started, IA | Palmera Solar Development, LLC | Tap 345kV 3381 Big Brown Switch - 3391 Jewett | Freestone | NORTH | 2028-05-11 | SOL | PV | 221.78 |  | 2022-03-23 | 2021-09-07 | 2021-11-29 | 2022-03-09 |  |  | 2025-12-18 | Yes |  |  | Not Required
24INR0269 | Bar Candela Solar SLF | SS Completed, FIS Started, IA | Bar Candela Solar Project LLC | Long Lake Sub (Bus 3280) – Long Lake Tap Switch (Bus 3279) | Freestone | NORTH | 2029-05-16 | SOL | PV | 200.3 | COD | 2022-12-16 | 2022-03-21 | 2022-06-13 | 2022-12-06 |  | No | 2025-05-06 | No |  |  | Not Required
24INR0271 | Bar Candela Storage SLF | SS Completed, FIS Started, IA | Bar Candela Storage Project LLC | Long Lake Sub (Bus 3280) – Long Lake Tap Switch (Bus 3279) | Freestone | NORTH | 2029-05-16 | OTH | BA | 0 | COD | 2022-12-16 | 2022-03-21 | 2022-06-13 | 2022-12-05 |  | No | 2025-05-06 | No | Not Required | Not Required
24INR0289 | Ratcliff Solar | SS Completed, FIS Started, No IA | Greenalia Solar Power Ratcliff | Tap 138kV 3279 Long Lake Tap Switch - 3280 Long Lake | Freestone | NORTH | 2029-04-07 | SOL | PV | 85.74 |  | 2022-08-22 | 2022-06-27 | 2022-09-23 | 2022-08-17 |  |  |  | No |  |  | Not Required
24INR0532 | Timber Cove Solar SLF | SS Completed, FIS Started, No IA | Freestone Solar, LLC | Tap 138 kV 212 Winkler - 3510 Pin Oak | Freestone | NORTH | 2027-06-01 | SOL | PV | 100.5 |  | 2023-05-02 | 2023-05-22 | 2023-08-17 | 2023-05-17 |  |  |  | No |  |  | Not Required
25INR0168 | Piedra Solar | SS Completed, FIS Completed, IA | Piedra Solar, LLC | Tap 345-kV line Navarro (68091) – Limestone (46020)) | Freestone | NORTH | 2027-01-15 | SOL | PV | 281.7 |  | 2023-03-09 | 2022-09-02 | 2022-11-30 | 2023-03-07 | 2025-09-17 | No | 2024-07-02 | Yes | Not Required |  | Not Required | 2025-09-17 | 2025-10-30 | 2025-10-31 |  |  | 2026-07-27 | 2026-08-26
25INR0169 | Piedra BESS | SS Completed, FIS Completed, IA | Piedra Solar, LLC | Tap 345-kV line Navarro (68091) – Limestone (46020) | Freestone | NORTH | 2027-12-01 | OTH | BA | 103.65 |  | 2023-03-08 | 2022-09-02 | 2022-11-30 | 2023-03-07 | 2025-09-18 |  | 2024-07-02 | Yes | Not Required |  | 2025-09-19 | 2025-09-18
26INR0033 | Fairway Storage | SS Completed, FIS Started, IA | Fairway Storage LLC | Tap 138kV 3503 FAIRWPOD_8 - 196 FAIRFIELD | Freestone | NORTH | 2027-09-24 | OTH | BA | 120.3 |  | 2023-02-17 | 2022-11-07 | 2023-02-04 | 2023-02-15 |  | No | 2025-08-11 | Yes | Not Required |  |  | 2026-03-09
26INR0082 | Amerada Solar | SS Completed, FIS Started, No IA | Amerada Solar, LLC | Tap 345kV 3133 RICHLND2_5 - 3381 BIGBRNW_5 | Freestone | NORTH | 2028-12-30 | SOL | PV | 301.57 |  | 2023-05-12 | 2023-05-15 | 2023-08-11 | 2023-04-28 |  |  |  | No |  |  | Not Required
26INR0084 | Amerada Storage | SS Completed, FIS Started, No IA | Amerada Solar, LLC | Tap 345kV 3133 RICHLND2_5 - 3381 BIGBRNW_5 | Freestone | NORTH | 2028-07-21 | OTH | BA | 150.78 |  | 2023-05-10 | 2023-05-15 | 2023-08-11 | 2023-04-28 |  |  |  | No
26INR0098 | Douie Solar | SS Completed, FIS Completed, IA | Buffalo Spring Solar LLC | Tap 138 kV 3501 Sea way Teague - 3394 Jewett | Freestone | NORTH | 2028-04-18 | SOL | PV | 221.2 |  | 2023-05-09 | 2023-05-15 | 2023-08-11 | 2023-05-12 | 2025-07-07 |  | 2026-03-08 | Yes | Not Required | Not Required | Not Required | 2026-04-13
26INR0394 | Timber Cove Storage SLF | SS Completed, FIS Started, No IA | Freestone Solar, LLC | Tap 138 kV 212 Winkler - 3510 Pin Oak | Freestone | NORTH | 2027-06-01 | OTH | BA | 0 |  | 2024-01-04 | 2024-01-11 | 2024-04-08 | 2023-12-18 |  |  |  | No
27INR0186 | Silver Dollar Solar | SS Completed, FIS Started, No IA | Silver Dollar Solar Project, LLC | Tap 345 kV Big Brown 3380 to Navarro 68091 ckt#2 | Freestone | NORTH | 2029-10-31 | SOL | PV | 301.9 | COD | 2024-05-21 | 2024-06-03 | 2024-08-29 | 2024-05-13 |  |  |  | No |  |  | Not Required
27INR0187 | Silver Dollar Storage | SS Completed, FIS Started, No IA | Silver Dollar Solar Project, LLC | Tap 345 kV Big Brown 3380 to Navarro 68091 ckt#2 | Freestone | NORTH | 2029-10-31 | OTH | BA | 153.1 | COD | 2024-05-21 | 2024-06-03 | 2024-08-29 | 2024-05-13 |  |  |  | No
27INR0316 | Avant Prairie BESS | SS Completed, FIS Completed, No IA | Avant Prairie ESS LLC | Tap 345kV BIGBRNE (#3380) - JEWETT (#3390) CKT 1 | Freestone | NORTH | 2029-04-16 | OTH | BA | 201.72 |  | 2024-09-03 | 2024-09-04 | 2024-12-02 | 2024-09-02 | 2026-09-01 | Yes |  | No
27INR0651 | Three Canes Gas P1 | SS Started, FIS Started, No IA | CleanAI, LLC | #3344 Tarantula Switching Station | Freestone | NORTH | 2027-11-30 | GAS | IC | 0 |  | 2026-07-02 | 2026-07-06 |  | 2026-06-26 |  |  |  | No
27INR0652 | Three Canes Gas P2 | SS Started, FIS Started, No IA | CleanAI, LLC | Tap on the 345 kV Outlaw Switch (bus #3386) to Limestone Plant Station (bus #46020) Transmission Line | Freestone | NORTH | 2027-11-30 | GAS | IC | 0 |  | 2026-07-02 | 2026-07-06 |  | 2026-06-26 |  |  |  | No
28INR0055 | Freestone Battery Storage Project | SS Completed, FIS Started, No IA | Freestone Power Generation, LLC | 3134 RICHLAND CHAMBERS 345kV (PSS/E Bus Name: RICHLND1_5) | Freestone | NORTH | 2028-12-16 | OTH | BA | 210.5 |  | 2025-01-24 | 2024-02-07 | 2024-04-30 | 2025-01-17 22:00 |  |  |  | No
28INR0080 | Turtle Rock Storage | SS Completed, FIS Started, No IA | Turtle Rock Energy Center, LLC | Tap 138 kV 13501 Clayhill to 13681 Reed | Freestone | NORTH | 2028-07-02 | OTH | BA | 135.59 |  | 2024-05-07 | 2024-05-09 | 2024-08-05 | 2024-05-08 |  |  |  | No
29INR0119 | Simsboro Storage | SS Completed, FIS Started, No IA | Simsboro Storage LLC | Tap Outlaw (3386) – Limestone (46020) | Freestone | NORTH | 2029-03-31 | OTH | BA | 301.6 |  | 2025-05-09 | 2025-06-11 | 2025-09-04 | 2025-05-21 |  |  |  | No
29INR0150 | Jewett Energy Center 1 Gas | SS Completed, FIS Started, IA | Jewett Energy Center LLC | Tap #3391 JEWETT_N5 - #46020 LMEST_POI_5 and Tap #3390 JEWETT_S5 - #46020 LMEST_POI_5 | Freestone | NORTH | 2029-11-01 | GAS | CC | 1274 |  | 2025-10-10 | 2025-10-21 | 2025-11-19 | 2025-10-14 |  |  | 2026-07-15 | No
29INR0298 | BM Freestone Energy Center | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II | Loop Big Brown E to Navarro Ckt 1(PTI#3380-68091) and Big Brown W to Tarantulla Ckt 1 (PTI#3381-3344) at 31.813367° -96.147730° | Freestone | NORTH | 2029-09-20 | GAS | CC | 990.6 |  | 2026-02-12 | 2026-02-25 | 2026-05-21 | 2026-02-11 |  |  |  | No
21INR0483 | Morrow Lake Storage | SS Completed, FIS Started, No IA | Morrow Lake Storage, LLC | Morrow Lake Switch 138kV (5896) | Frio | SOUTH | 2028-09-30 | OTH | BA | 201.13 |  | 2020-11-10 | 2020-02-07 | 2020-04-30 | 2020-10-26 |  |  |  | No
27INR0362 | Hamlet Solar SLF | SS Completed, FIS Started, No IA | Hamlet Solar, LLC | Tap 138kV #5895 PEARSALL - #5827 MOORE | Frio | SOUTH | 2029-09-04 | SOL | PV | 201 |  | 2024-11-04 | 2024-11-19 | 2025-02-14 | 2024-11-04 |  | No |  | No |  |  | Not Required
27INR0363 | Hamlet Storage SLF | SS Completed, FIS Started, No IA | Hamlet Solar, LLC | Tap 138kV #5895 PEARSALL -#5827 MOORE | Frio | SOUTH | 2029-09-04 | OTH | BA | 201 |  | 2024-11-04 | 2024-11-19 | 2025-02-14 | 2024-11-04 |  |  |  | No
28INR0411 | Black Creek BESS | SS Completed, FIS Started, No IA | Francitas Renewables LLC | New tap between line Bigfoot4A (8221) - MooreSw8 (5827) | Frio | SOUTH | 2029-03-20 | OTH | BA | 120 |  | 2026-04-20 | 2025-07-29 | 2025-10-13 | 2026-04-09 |  |  |  | No
28INR0461 | Dilley Solar | SS Completed, FIS Started, No IA | AETS Development Holdings LLC | Tap 138 kV 8212 DILLEY SWITCH AEP - 8613 BIG WELLS | Frio | SOUTH | 2028-06-30 | SOL | PV | 200.7 |  | 2025-12-19 | 2025-12-23 | 2026-03-23 | 2025-12-19 |  |  |  | No |  |  | Not Required
21INR0012 | Air Products GCA | SS Completed, FIS Completed, IA | Air Products | 39140 TNTxCityMain 69kV (Will be upgraded to 138kV) | Galveston | HOUSTON | 2025-12-31 | GAS | ST | 14 |  | 2019-03-26 | 2018-06-07 | 2018-08-01 |  | 2023-03-10 |  | 2020-08-07 | Yes | Not Required | Not Required | 2020-03-31 | 2023-03-13 | 2023-03-13 | 2023-03-13 |  |  | 2023-11-07 | 2024-07-10
23INR0290 | Zeya BESS | SS Completed, FIS Started, IA | BRP Zeya BESS LLC | 38740 Heights 138kV | Galveston | HOUSTON | 2027-12-01 | OTH | BA | 255.33 |  | 2021-06-02 | 2021-05-31 | 2022-03-09 | 2021-05-20 |  | No | 2023-01-20 | Yes | Not Required | Not Required |  | 2025-02-12
23INR0485 | Hacienda Storage | SS Completed, FIS Started, No IA | Galveston Energy Storage LLC | 38745 Attwater 138kV | Galveston | HOUSTON | 2027-12-01 | OTH | BA | 205.8 |  | 2022-04-20 | 2022-05-10 | 2022-08-06 | 2022-04-04 |  |  |  | No
24INR0281 | Red Egret BESS | SS Completed, FIS Completed, IA | Red Egret LLC | 38820 FREEWAY PARK 138KV | Galveston | HOUSTON | 2027-11-17 | OTH | BA | 310.58 |  | 2022-10-23 | 2022-03-14 | 2022-06-09 | 2022-10-13 | 2025-08-21 | No | 2023-06-07 | Yes | Not Required | Not Required |  | 2023-08-08 | 2024-08-13 | 2025-10-14
25INR0262 | Shepard Energy Storage | SS Completed, FIS Completed, IA | Shepard Energy Storage LLC | # 38900 Hidden Lakes - # 42015 PHR 138 KV | Galveston | HOUSTON | 2028-06-30 | OTH | BA | 256.79 |  | 2022-12-02 | 2022-12-15 | 2023-03-11 | 2022-12-09 | 2026-03-19 | No | 2024-01-17 | Yes | Not Required | Not Required |  | 2025-02-12
25INR0310 | IEP Blackhawk | SS Completed, FIS Started, No IA | IEP Texas Verde II, llc | 38740 Heights Substation 138kV | Galveston | HOUSTON | 2026-12-01 | OTH | BA | 100 |  | 2023-04-04 | 2023-04-07 | 2023-07-05 | 2023-03-08 |  |  |  | No
26INR0340 | SOUTHERN SELECT ENERGY STORAGE | SS Completed, FIS Completed, IA | SOUTHERN SELECT ENERGY STORAGE LLC | Bus Name: TNHEIGHTS_1 Bus Number: 38740 | Galveston | HOUSTON | 2027-05-24 | OTH | BA | 204.85 |  | 2023-10-16 | 2023-10-25 | 2024-01-22 | 2023-10-12 | 2026-04-20 |  | 2025-05-09 | Yes | Not Required | Not Required |  | 2026-07-31 | 2026-07-31 | 2026-07-31
28INR0465 | Valcrest BESS | SS Completed, FIS Started, No IA | Flexen USA LLC | tap 138 kV 43500 WEBSTR_B138A - 48403 W_GALV01TP_8 | Galveston | HOUSTON | 2028-12-31 | OTH | BA | 154.25 |  | 2025-11-26 | 2025-12-17 | 2026-02-05 | 2025-12-02 |  | No |  | No
28INR0490 | Vertus Energy Storage 2 | SS Completed, FIS Started, No IA | Vertus Energy Storage 2 LLC | 38830 TNMAINLAND1 138 KV | Galveston | HOUSTON | 2028-02-15 | OTH | BA | 204.93 |  | 2026-01-21 | 2026-01-26 | 2026-04-17 | 2026-01-21 |  | No |  | No
30INR0003 | Hecate Energy Jamaica Wind | SS Completed, FIS Started, No IA | Hecate Energy LLC | 42000 P. H. Robinson 345kV | Galveston | HOUSTON | 2030-06-01 | WIN | WT | 1029.39 |  |  | 2023-06-28 | 2023-09-25 | 2024-06-14 18:19 |  |  |  | No |  |  | Not Required
24INR0514 | Rogers Draw BESS | SS Completed, FIS Completed, IA | ROGERS DRAW ENERGY STORAGE, LLC | 7751 Headwaters substation 138kV | Gillespie | SOUTH | 2030-07-31 | OTH | BA | 148.61 |  | 2023-01-10 | 2023-01-03 | 2023-03-30 | 2023-01-09 | 2025-09-10 | No | 2024-02-28 | Yes | Not Required | Not Required |  | 2025-10-28 | 2025-10-28 | 2025-10-28
25INR0353 | Marshall Spring Solar | SS Completed, FIS Started, IA | Marshall Springs Solar, LLC | New POI station between 7132 L_GILLES8_1Y - 7126 L_FERGUS8_1Y 138kV line and 7132 L_GILLES8_1Y - 7128 L_HORSBA8_1Y 138kV line, then loop in both lines into the new POI station. | Gillespie | SOUTH | 2028-12-20 | SOL | PV | 150 |  | 2023-10-04 | 2023-02-20 | 2023-05-18 | 2023-09-27 |  |  | 2025-12-26 | No |  |  | Not Required
25INR0354 | Marshall Spring Storage | SS Completed, FIS Started, IA | Marshall Springs Storage, LLC | New POI station between 7132 L_GILLES8_1Y - 7126 L_FERGUS8_1Y 138kV line and 7132 L_GILLES8_1Y - 7128 L_HORSBA8_1Y 138kV line, then loop in both lines into the new POI station. | Gillespie | SOUTH | 2028-12-20 | OTH | BA | 150 |  | 2023-10-04 | 2023-02-20 | 2023-05-18 | 2023-09-27 |  |  | 2025-12-26 | No
15INR0064b | Harald (BearKat Wind B) | SS Completed, FIS Completed, IA | McCrae Wind Energy II, LLC | 59903 Bearkat 345kV | Glasscock | WEST | 2026-12-03 | WIN | WT | 162.1 |  |  | 2013-11-27 | 2014-01-27 | 2014-04-15 | 2017-09-27 | No | 2018-05-30 | Yes | Not Required | Not Required | Not Required | 2018-05-30 | 2018-09-19 | 2019-01-22 |  |  | 2020-02-10 | 2020-05-12
24INR0578 | Panther Creek 1 Repower | SS Completed, FIS Completed, No IA | Panther Creek Wind Farm I&II, LLC | 1058 Longshore 345kV | Glasscock | WEST | 2026-12-31 | WIN | WT | 11 |  | 2023-06-27 | 2023-06-28 | 2023-09-21 | 2023-06-21 | 2024-05-03 |  |  | Yes | Not Required | Not Required | Not Required | 2024-06-21 | 2024-06-21 | 2024-05-06 |  |  |  | 2024-10-02
24INR0582 | Panther Creek 2 Repower | SS Completed, FIS Completed, No IA | Panther Creek Wind Farm I&II, LLC | Longshore 345kV [Bus# 1058] | Glasscock | WEST | 2026-12-31 | WIN | WT | 8 |  | 2023-06-27 | 2023-06-28 | 2023-09-21 | 2023-06-27 | 2024-05-03 |  |  | Yes | Not Required | Not Required | Not Required | 2024-06-21 | 2024-06-21 | 2024-05-06 |  |  |  | 2024-10-02
25INR0138 | Champaign BESS | SS Completed, FIS Completed, IA | Champaign BESS, LLC | Tap 138kV Shaw POD (18664) – Desert Wind Sub (11283) new station Potterson Lake Switch | Glasscock | WEST | 2028-03-31 | OTH | BA | 201.13 |  | 2022-12-30 | 2022-09-21 | 2022-12-19 | 2022-12-29 | 2024-08-13 | No | 2025-07-31 | Yes
25INR0142 | Sagewood BESS | SS Completed, FIS Started, No IA | Sagewood BESS, LLC | tap McDonald Road Switch (1333) – Pastores Switch (10121) ckt 1 | Glasscock | WEST | 2028-03-31 | OTH | BA | 100.57 |  | 2022-12-30 | 2022-09-21 | 2022-12-19 | 2022-12-29 |  | No |  | No
25INR0578 | Forest Creek Wind Repower | SS Completed, FIS Completed, IA | Forest Creek Wind Farm, LLC | Mcdonald 138 kV (Bus #: 1333) | Glasscock | WEST | 2026-12-31 | WIN | WT | 125.1 |  | 2023-11-15 | 2024-01-11 | 2024-04-05 | 2023-12-08 | 2024-12-10 |  | 2005-11-17 | Yes |  |  | Not Required | 2025-01-24 | 2025-01-24 | 2025-01-24 |  |  | 2025-07-28 | 2025-08-27
25INR0608 | Proteus London-Leigh Solar SLF | SS Completed, FIS Started, No IA | London Leigh Solar, LLC | 345kV Bernoulli (bus # 59907) | Glasscock | WEST | 2028-09-30 | SOL | PV | 600 |  | 2024-01-08 | 2024-03-22 | 2024-06-19 | 2024-02-19 |  | Yes |  | No |  |  | Not Required
25INR0609 | Proteus London-Leigh Storage SLF | SS Completed, FIS Started, No IA | London Leigh Solar, LLC | Bernoulli (bus # 59907) | Glasscock | WEST | 2028-09-30 | OTH | BA | 0 |  | 2024-01-08 | 2024-02-27 | 2024-04-19 | 2023-12-22 |  | Yes |  | No
26INR0355 | Pleiades Storage | SS Completed, FIS Completed, No IA | Pleiades Storage, LLC | Tap 138kV Einstein 23852 - 10043 St. Lawrence | Glasscock | WEST | 2029-09-22 | OTH | BA | 205.5 |  | 2024-03-06 | 2024-03-22 | 2024-06-19 | 2024-02-23 | 2025-01-17 | No |  | No | [6 empty] | 2028-05-22 | 2029-09-22
26INR0447 | Honey Mesquite Wind Farm | SS Completed, FIS Completed, IA | Honey Mesquite Wind Farm , LLC | 59902 Sand Bluff 345kV | Glasscock | WEST | 2026-12-30 | WIN | WT | 173.95 |  | 2024-03-06 | 2024-03-22 | 2024-06-19 | 2024-03-11 | 2025-09-11 | No | 2024-09-10 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2025-10-20 | 2025-10-27 |  |  | 2026-08-03 | 2026-08-20
26INR0452 | Cannibal Draw Solar | SS Completed, FIS Started, IA | Cannibal Draw Solar, LLC | Sand_Bluff 345 kV (59902) | Glasscock | WEST | 2028-04-10 | SOL | PV | 149.5 |  | 2024-06-26 | 2024-07-01 | 2024-09-27 | 2024-06-10 |  | No | 2025-01-17 | Yes | Not Required | Not Required | Not Required | 2025-02-12
26INR0453 | Cannibal Draw Storage | SS Completed, FIS Started, IA | Cannibal Draw Solar, LLC | Sand_Bluff 345 kV (59902) | Glasscock | WEST | 2028-04-10 | OTH | BA | 98.6 |  | 2024-06-26 | 2024-07-01 | 2024-09-27 | 2024-06-10 |  | No | 2025-01-17 | Yes | Not Required | Not Required | 2025-09-15 | 2025-02-12
26INR0573 | Cummins BESS | SS Completed, FIS Started, No IA | RWE Solar Development, LLC | 1333 MCDONALD 138kV | Glasscock | WEST | 2028-06-30 | OTH | BA | 200.89 |  | 2024-09-10 | 2024-10-01 | 2024-11-12 | 2024-09-16 |  |  |  | No
27INR0355 | Gardner Draw Solar | SS Completed, FIS Completed, IA | RWE Clean Energy Development, LLC | 59902 Sand Bluff 345kV | Glasscock | WEST | 2028-06-01 | SOL | PV | 309.5 | COD SFS/NtP | 2024-09-26 | 2024-10-01 | 2024-12-30 | 2024-09-25 | 2026-09-16 | Yes | 2025-08-07 | Yes |  |  | Not Required
27INR0371 | Feather Dalea BESS | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | 59902 Sand_Bluff 345kV | Glasscock | WEST | 2027-07-02 | OTH | BA | 200 |  | 2024-09-16 | 2024-10-01 | 2024-12-09 | 2024-09-24 |  |  |  | No
27INR0383 | Windjammer Windpower | SS Completed, FIS Started, IA | Windjammer Windpower, LLC | tap 345kV 59902 Sand Bluff Wind Farm - 59907 Bernoulli | Glasscock | WEST | 2028-12-31 | WIN | WT | 244.06 |  | 2024-12-20 | 2024-09-10 | 2024-12-06 | 2024-12-12 |  | Yes | 2025-12-03 | Yes | Not Required | Not Required | Not Required | 2026-01-06
29INR0040 | Gusty Windpower | SS Completed, FIS Started, IA | Gusty Windpower, LLC | Tap 345kV 59903 Bearkat - 1058 Longshore_5; Anemone 345 kV Station | Glasscock | WEST | 2028-12-31 | WIN | WT | 248.9 |  | 2024-09-12 | 2024-07-30 | 2024-10-27 | 2024-08-20 |  | No | 2025-12-03 | Yes | Not Required | Not Required | Not Required | 2026-03-25
30INR0080 | Indigo Quill Gas | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | 59902 SAND_BLUFF 345KV | Glasscock | WEST | 2028-12-29 | GAS | GT | 370.08 |  | 2026-02-24 | 2026-03-10 | 2026-06-04 | 2026-03-04 |  | No |  | No
21INR0223 | Tulsita Solar | SS Completed, FIS Completed, IA | Ray Ranch Solar LLC | Tap 138kV 8590 Tuleta - 8595 Euler | Goliad | SOUTH | 2026-09-15 | SOL | PV | 256.2 |  | 2019-05-20 | 2018-12-05 | 2019-02-21 | 2019-05-17 | 2024-03-01 | No | 2022-09-19 | Yes | Not Required | Not Required | Not Required | 2022-10-03 | 2024-02-02 | 2024-04-30 |  |  | 2024-10-22 | 2024-10-30
24INR0065 | Keys Hollow Solar Phase II SLF | SS Completed, FIS Completed, IA | Keys Hollow Solar, LLC | 345kV Tap 8164 Coleto Creek - 8673 RAPTOR7A | Goliad | SOUTH | 2028-03-10 | SOL | PV | 200.85 |  | 2021-08-25 | 2021-06-17 | 2021-09-01 | 2021-07-29 | 2026-09-02 | No | 2024-10-29 | Yes | Not Required | Not Required | Not Required
24INR0066 | Keys Hollow Storage Phase II SLF | SS Completed, FIS Started, IA | Keys Hollow Solar, LLC | 345kV Tap 8164 Coleto Creek - 8673 RAPTOR7A | Goliad | SOUTH | 2028-03-10 | OTH | BA | 0 |  | 2022-01-20 | 2021-06-17 | 2021-09-01 | 2022-01-10 |  | No | 2024-10-29 | Yes | Not Required | Not Required
24INR0067 | KEYS HOLLOW SOLAR SLF | SS Completed, FIS Completed, IA | Keys Hollow Solar, LLC | TAP 345 KV LINE FROM COLETO 8164 - RAPTOR7A 8673 | Goliad | SOUTH | 2028-03-10 | SOL | PV | 200.85 |  | 2022-03-10 | 2021-06-17 | 2021-09-01 | 2022-03-04 | 2026-09-02 | No | 2024-10-29 | Yes |  |  | Not Required
24INR0068 | KEYS HOLLOW STORAGE SLF | SS Completed, FIS Started, IA | Keys Hollow Solar, LLC | TAP 345 KV LINE FROM COLETO 8164 - RAPTOR7A 8673 | Goliad | SOUTH | 2028-03-10 | OTH | BA | 0 |  | 2022-03-10 | 2021-06-17 | 2021-09-01 | 2022-03-04 |  | No | 2024-10-29 | Yes
26INR0664 | Coleto Creek - Fuel Change Only | SS Completed, FIS Started, No IA | COLETO CREEK POWER LLC | 8162 Coleto Creek 138kV | Goliad | SOUTH | 2026-12-15 | GAS | ST | 655 |  | 2025-06-02 | 2025-04-21 | 2025-07-19 | 2025-05-21 |  |  |  | No
27INR0144 | Angel City Solar | SS Completed, FIS Started, No IA | Angel City Energy Center, LLC | Coleto Creek (# 8164) AEP – Pawnee (#5725) STEC, 25.9 miles from Coleto Creek, 28.2 miles from Pawnee Sub. POI co-ordinates: 28.755, -97.583 | Goliad | SOUTH | 2029-09-30 | SOL | PV | 221.02 |  | 2024-01-22 | 2024-02-07 | 2024-04-30 | 2024-01-23 |  |  |  | No |  |  | Not Required
27INR0149 | Diablo Campo Storage | SS Completed, FIS Started, No IA | Diablo Campo Energy Center, LLC | The Coleto Greek (#8164) to Pawnee Switching Station (#5725) ; LCRA | Goliad | SOUTH | 2029-09-30 | OTH | BA | 313.54 |  | 2024-01-23 | 2024-02-07 | 2024-04-29 | 2024-01-23 |  |  |  | No
27INR0248 | Double A Solar SLF | SS Completed, FIS Started, No IA | Double A Solar, LLC | Tap 69kV 5678 Schroeder - 5675 Big Oak | Goliad | SOUTH | 2028-05-31 | SOL | PV | 132.6 |  | 2024-05-14 | 2024-06-13 | 2024-08-07 | 2024-05-30 |  |  |  | No |  |  | Not Required
27INR0257 | Double A Storage SLF | SS Completed, FIS Started, No IA | Double A Storage, LLC | Tap 69kV 5678 Schroeder - 5675 Big Oak | Goliad | SOUTH | 2028-05-31 | OTH | BA | 0 |  | 2024-06-10 | 2024-06-13 | 2024-08-07 | 2024-05-30 |  |  |  | No
28INR0303 | Kuy Creek Solar 1 SLF | SS Completed, FIS Started, No IA | Kuy Creek Solar 1 LLC | Tap Coleto Creek (Bus # 8162) - Victoria (Bus# 8172) 138 kV CKT 1 | Goliad | SOUTH | 2029-03-20 | SOL | PV | 234.87 |  | 2025-02-18 | 2025-04-21 | 2025-06-18 | 2025-03-03 |  | Yes |  | No |  |  | Not Required
28INR0304 | Kuy Creek Storage 1 SLF | SS Completed, FIS Started, No IA | Kuy Creek Storage 1 LLC | Tap - Coleto Creek (Bus # 8162) - Victoria (Bus# 8172) 138 kV CKT 1 | Goliad | SOUTH | 2029-03-20 | OTH | BA | 151.46 |  | 2025-02-18 | 2025-03-24 | 2025-06-18 | 2025-03-03 |  | Yes |  | No
23INR0231 | Hoke Solar | SS Completed, FIS Completed, IA | Hoke Solar Project, LLC | tap 138kV 7595 Deer Creek - 7621 Nixon | Gonzales | SOUTH | 2027-07-05 | SOL | PV | 95.29 |  | 2021-04-28 | 2021-04-22 | 2021-07-14 | 2021-04-22 | 2026-07-17 | No | 2022-04-25 | Yes | Not Required | Not Required | Not Required | 2025-09-08 | 2026-07-27 | 2026-08-01
23INR0232 | Hoke Storage | SS Completed, FIS Completed, IA | Hoke Solar Project, LLC | tap 138kV 7595 Deer Creek - 7621 Nixon | Gonzales | SOUTH | 2027-07-05 | OTH | BA | 33.17 |  | 2021-04-28 | 2021-04-22 | 2021-07-14 | 2021-04-22 | 2026-07-17 | No | 2022-04-25 | Yes | Not Required | Not Required | 2026-04-20 | 2026-03-25 | 2026-07-27 | 2026-08-01
24INR0440 | Starling Solar | SS Completed, FIS Started, IA | Starling Solar, LLC | 138-kV Birdhouse (7255) Starling Solar Phase II is a an addition of 42.24MW to the 23INR0035 (solar) filed in 2020. 23INR0181 (storage) was filed in 2021. | Gonzales | SOUTH | 2028-01-28 | SOL | PV | 144.6 |  | 2023-06-21 | 2022-10-06 | 2022-12-28 | 2023-06-16 |  | No | 2026-02-17 | No |  |  | Not Required
25INR0010 | Nockenut Springs Solar 3 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Gonzales | SOUTH | 2029-06-05 | SOL | PV | 201.4 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  |  |  | No |  |  | Not Required
25INR0193 | Nockenut Springs Solar 4 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | The 345 kV Elm Creek - South Texas Project Line (Bus #5133 - #5915) | Gonzales | SOUTH | 2029-06-05 | SOL | PV | 201.15 |  | 2022-09-13 | 2022-09-15 | 2022-12-13 | 2022-08-31 |  |  |  | No |  |  | Not Required
25INR0280 | Nockenut Springs Solar 5 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | Tap 345 kV 5133 Elm Creek - 5915 South Texas Project | Gonzales | SOUTH | 2029-06-05 | SOL | PV | 201.15 |  | 2023-01-24 | 2023-02-09 | 2023-05-08 | 2023-01-27 |  |  |  | No |  |  | Not Required
29INR0063 | Columbine Wind | SS Completed, FIS Started, No IA | Wilson Wind LLC | TAP 345KV BUS #5380 SHAULA- BUS #5133 ELM CREEK | Gonzales | SOUTH | 2029-09-01 | WIN | WT | 295 |  | 2025-02-18 | 2025-02-25 | 2025-05-20 | 2025-02-18 |  |  |  | No |  |  | Not Required
25INR0080 | Meitner Solar | SS Completed, FIS Started, IA | IP Meitner, LLC | 345 kV Gray (Bus# 79000) | Gray | PANHANDLE | 2028-06-08 | SOL | PV | 702.64 |  | 2022-07-26 | 2022-08-05 | 2022-11-01 | 2022-07-27 |  | Yes | 2024-01-31 | No |  |  | Not Required
26INR0113 | Meitner Wind | SS Completed, FIS Started, IA | IP Meitner, LLC | 79000 Gray Substation 345kV | Gray | PANHANDLE | 2028-05-24 | WIN | WT | 709 |  | 2023-07-13 | 2023-07-18 | 2023-10-15 | 2023-06-29 |  |  | 2024-04-19 | No |  |  | Not Required
29INR0103 | Meitner 2 Wind | SS Completed, FIS Started, No IA | IP Meitner, LLC | 79000 Gray Substation 345kV | Gray | PANHANDLE | 2028-06-30 | WIN | WT | 709.1 |  | 2025-05-02 | 2025-06-05 | 2025-09-02 | 2025-04-18 |  |  |  | No |  |  | Not Required
26INR0300 | Whitewright Solar 2 | SS Completed, FIS Started, No IA | SunWR, LLC | Tap 345kV 1729 Valley South – Anna Switch 2373 | Grayson | NORTH | 2028-05-02 | SOL | PV | 301.69 |  | 2023-11-07 | 2023-12-18 | 2024-03-15 | 2023-11-07 |  |  |  | No |  |  | Not Required
26INR0605 | White Bright BESS | SS Completed, FIS Started, No IA | VLN, LLC | Tap 345kV 1729 Valley South – Anna Switch 2373 | Grayson | NORTH | 2029-04-16 | OTH | BA | 313.69 |  | 2025-03-12 | 2025-03-21 | 2025-06-17 | 2024-11-13 |  |  |  | No
27INR0234 | Lima Solar Project | SS Completed, FIS Started, IA | Industrial Lima Project, LLC | Tap 138 kV Haggerty Switch (12677) to Van Al (1754) 138kV | Grayson | NORTH | 2029-03-01 | SOL | PV | 101.3 |  | 2024-04-16 | 2024-05-09 | 2024-08-05 | 2024-04-17 |  |  | 2026-09-02 | No |  |  | Not Required
28INR0108 | RAYBURN ENERGY STATION II Gas (TEF-Due Diligence) | SS Completed, FIS Started, IA | Rayburn Country Electric Cooperative, Inc. | Double Tap 138 kV Haggerty (12677) - Progress Park (#12678) & Haggerty - Winding Oaks Switch | Grayson | NORTH | 2028-02-26 | GAS | GT | 570 |  | 2025-01-02 | 2025-01-13 | 2025-04-08 | 2025-01-02 |  | Yes | 2025-12-22 | Yes | 2026-03-31 | 2026-03-31 | 2026-06-02 | 2026-06-02 | 2026-08-25
19INR0085 | Blue Jay Solar | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 Iola 138kV | Grimes | NORTH | 2025-09-30 | SOL | PV | 141.05 |  | 2018-02-15 | 2017-05-30 | 2017-08-11 | 2018-02-15 | 2021-04-26 | No | 2020-10-26 | Yes | Not Required | Not Required | Not Required | 2020-12-02 | 2021-04-26 | 2021-04-29 |  |  | 2021-11-11 | 2022-06-28
21INR0538 | Blue Jay Solar II | SS Completed, FIS Completed, IA | Blue Jay Solar I, LLC | 4 Iola 138kV | Grimes | NORTH | 2025-10-31 | SOL | PV | 68.95 |  | 2018-02-15 | 2021-04-13 | 2021-04-14 |  | 2021-04-26 | No | 2020-10-26 | Yes |  |  | Not Required | 2020-12-02 | 2021-04-26 | 2021-04-29 |  |  | 2021-11-11 | 2021-11-19
24INR0172 | Smith Lake Solar DC | SS Completed, FIS Started, IA | Smith Lake Solar | TAP 345 KV 44645 SINGLETON - 44900 ZENITH Ckt #99 | Grimes | NORTH | 2028-12-29 | SOL | PV | 402 |  | 2022-11-30 | 2022-02-07 | 2022-05-06 | 2022-11-02 |  | Yes | 2025-12-30 | No |  |  | Not Required
25INR0045 | Smith Lake Storage DC | SS Completed, FIS Started, IA | Smith Lake Solar | Tap 345kV 44645 Singleton - 44900 Zenith Ckt #99 | Grimes | NORTH | 2028-12-28 | OTH | BA | 65 |  | 2022-11-30 | 2022-03-07 | 2022-05-06 | 2022-11-02 |  | Yes | 2025-12-30 | No
26INR0001 | Turin TxHSR TPSS HN-6 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | 8 Crutchfield 138kV | Grimes | NORTH | 2028-07-15 | OTH | OT | 50 |  | 2019-10-22 | 2019-09-27 | 2021-04-28 | 2019-09-27 |  |  |  | No
26INR0004 | GRIMES SOLAR | SS Completed, FIS Started, No IA | CG Grimes County LLC | 40600 Roans Prairie 345kV | Grimes | NORTH | 2026-02-15 | SOL | PV | 153.45 |  | 2022-03-09 | 2022-03-14 | 2022-06-03 | 2022-03-07 |  |  |  | No |  |  | Not Required
26INR0200 | Vaughn Energy Storage | SS Completed, FIS Completed, No IA | Vaughn Battery Storage, LLC | 13 Keith 138kV | Grimes | NORTH | 2027-12-31 | OTH | BA | 200.6 |  | 2023-08-21 | 2023-08-21 | 2023-11-17 | 2023-08-20 | 2025-12-19 |  |  | No
26INR0285 | Hill Valley BESS | SS Completed, FIS Completed, IA | Hill Valley BESS, LLC | 345 kV Singleton (#44645) | Grimes | NORTH | 2028-07-15 | OTH | BA | 245.8 |  | 2023-11-09 | 2023-12-04 | 2024-03-01 | 2023-11-10 | 2024-12-03 |  | 2026-04-21 | No
26INR0324 | Misty Hollow BESS | SS Completed, FIS Completed, IA | Clear Fork BESS, LLC | 345 kV Singleton (#44645) | Grimes | NORTH | 2028-07-15 | OTH | BA | 245.8 |  | 2023-12-06 | 2023-12-20 | 2024-03-15 | 2023-12-06 | 2025-03-04 |  | 2025-12-04 | No | Not Required | Not Required
26INR0370 | Central Power Station | SS Completed, FIS Started, No IA | Hydra-Gen Energy Unlimited | 967 Gibbons Creek 345kV | Grimes | NORTH | 2027-05-01 | GAS | GT | 750 |  |  | 2024-03-22 | 2024-06-19 | 2025-01-14 |  |  |  | No
27INR0085 | Eagle Claw Energy Center | SS Completed, FIS Started, IA | Eagle Claw Energy Center, LLC | Singleton (Bus #44645) - Zenith (Bus #44900) Circuit #99 345 kV | Grimes | NORTH | 2028-03-31 | OTH | BA | 204.58 |  | 2023-09-28 | 2023-10-13 | 2024-01-10 | 2023-10-06 |  | Yes | 2025-09-15 | Yes | Not Required | Not Required |  | 2026-03-24
27INR0115 | Diamante BESS | SS Completed, FIS Completed, No IA | BESS DIAMANTE LLC | 40600 ROANS__POI_5 345kV | Grimes | NORTH | 2028-11-01 | OTH | BA | 513.68 |  | 2025-01-17 | 2024-02-27 | 2024-05-24 | 2024-11-21 | 2025-10-09 | No |  | No
27INR0190 | Millsing BESS | SS Completed, FIS Completed, No IA | Millsing BESS | 44645 CNP Singleton 345kV | Grimes | NORTH | 2028-10-15 | OTH | BA | 501.6 |  | 2024-02-02 | 2024-02-27 | 2024-05-24 | 2024-02-05 | 2024-10-08 |  |  | No
27INR0379 | Scrap Iron Solar | SS Completed, FIS Started, No IA | Energiekontor US Texas SP 15 LLC | Tap 138kV (#9) Bedias - (#25) North Zulch | Grimes | NORTH | 2028-09-01 | SOL | PV | 110.77 |  | 2025-05-02 | 2024-09-10 | 2024-12-06 | 2025-04-23 |  |  |  | No |  |  | Not Required
28INR0394 | Treehouse Solar | SS Completed, FIS Started, No IA | Treehouse Solar, LLC | Tap the 345 kV Jewett (#3390) - Singleton (#44645) line | Grimes | NORTH | 2028-11-13 | SOL | PV | 281.77 |  | 2025-07-11 | 2025-07-29 | 2025-10-26 | 2025-09-03 |  | Yes |  | No |  |  | Not Required
28INR0395 | Treehouse Storage | SS Completed, FIS Started, No IA | Treehouse Solar, LLC | Tap the 345 kV Jewett (#3390) - Singleton (#44645) line, ONCOR | Grimes | NORTH | 2028-11-13 | OTH | BA | 209.21 |  | 2025-07-07 | 2025-07-29 | 2025-10-26 | 2025-09-03 |  | Yes |  | No
29INR0333 | Tyler Rose Power Plant 1 | SS Completed, FIS Started, No IA | ProEnergy Services, LLC | Tap 345 kV Circuit 18 (#44920) Mission - (#967) Gibbons Creek | Grimes | NORTH | 2029-07-01 | GAS | GT | 597.36 |  | 2026-05-13 | 2026-05-13 | 2026-08-06 | 2026-05-13 |  |  |  | No
29INR0336 | Tyler Rose Power Plant 2 | SS Completed, FIS Started, No IA | ProEnergy Services, LLC | Tap 345 kV Circuit 18 (#44920) Mission - (#967) Gibbons Creek | Grimes | NORTH | 2029-12-01 | GAS | GT | 398.24 |  | 2026-05-13 | 2026-05-13 | 2026-08-07 | 2026-05-13 |  |  |  | No
23INR0088 | Nockenut Springs Solar 1 | SS Completed, FIS Completed, IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Guadalupe | SOUTH | 2029-06-05 | SOL | PV | 203.17 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 | 2025-07-07 | Yes | 2023-11-17 | Yes |  |  | Not Required
24INR0007 | Nockenut Springs Solar 2 | SS Completed, FIS Started, IA | Pecan Springs Energy, LLC | tap 345kV 5133 Elm Creek - 5915 STP ckt 1 | Guadalupe | SOUTH | 2029-06-05 | SOL | PV | 203.26 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  | Yes | 2023-11-17 | Yes |  |  | Not Required
24INR0115 | Aster Solar | SS Completed, FIS Started, No IA | Aster Solar | 7042 Zorn 345kV | Guadalupe | SOUTH | 2029-06-01 | SOL | PV | 160.5 |  | 2022-06-16 | 2021-09-21 | 2021-12-09 | 2022-05-24 |  | No |  | No |  |  | Not Required
24INR0145 | Calpine Guadalupe Peakers | SS Completed, FIS Started, No IA | Guadalupe Peaking Energy Center, LLC | 7044 Marion 345kV | Guadalupe | SOUTH | 2030-05-30 | GAS | GT | 450 |  | 2021-10-26 | 2021-11-15 | 2022-02-11 | 2021-10-18 |  |  |  | No
24INR0287 | Rockridge Solar | SS Completed, FIS Started, IA | Magnolia Solar Development, LLC | 7225 Hickory Forest 138kV | Guadalupe | SOUTH | 2028-06-27 | SOL | PV | 211.2 |  | 2022-08-10 | 2022-04-18 | 2022-07-12 | 2022-08-03 |  |  | 2025-03-14 | No | Not Required | Not Required | Not Required
27INR0093 | Guadalupe Battery Storage Project | SS Completed, FIS Started, No IA | Guadalupe Power Partners, LP | # 7044 Marion 345kV | Guadalupe | SOUTH | 2030-05-30 | OTH | BA | 210.5 |  | 2024-12-02 | 2023-11-14 | 2024-02-08 | 2024-10-22 |  |  |  | No
27INR0117 | Roble BESS | SS Completed, FIS Started, No IA | Flexen USA LLC | 7180 L_ZORN__8_1Y 138kV | Guadalupe | SOUTH | 2028-12-01 | OTH | BA | 154.3 |  | 2025-06-17 | 2024-08-16 | 2024-11-14 | 2025-06-02 |  |  |  | No
28INR0391 | Ruedrich BESS | SS Completed, FIS Started, No IA | Ruedrich BESS | LINE TAP OF CIBOLO (7608) AND McQUEENEY (7606) | Guadalupe | SOUTH | 2028-11-09 | OTH | BA | 200.58 |  | 2025-06-11 | 2025-06-19 | 2025-09-17 | 2025-06-12 |  |  |  | No
28INR0532 | Alpha Power Phase 1 | SS Started, FIS Started, No IA | Palomino Alpha, LLC | 345kV 7042 Zorn Substation | Guadalupe | SOUTH | 2028-12-31 | GAS | GT | 400.1 |  | 2026-07-08 | 2026-07-10 |  | 2026-07-01 |  |  |  | No
29INR0211 | Enfinity Juniper Storage | SS Completed, FIS Started, No IA | EG Juniper LLC | Hickory Forest (7225) | Guadalupe | SOUTH | 2029-12-18 | OTH | BA | 261.08 |  | 2026-01-06 | 2026-02-05 | 2026-05-01 | 2026-02-05 |  | No |  | No
29INR0363 | Alpha Power Phase 2 | SS Started, FIS Started, No IA | Palomino Alpha, LLC | 345kV 7042 Zorn Substation | Guadalupe | SOUTH | 2029-12-31 | GAS | GT | 400.1 |  | 2026-07-08 | 2026-07-10 |  | 2026-07-01 |  |  |  | No
30INR0143 | Alpha Power Phase 3 | SS Started, FIS Started, No IA | Palomino Alpha, LLC | 345kV 7042 Zorn Substation | Guadalupe | SOUTH | 2030-12-31 | GAS | GT | 400.1 |  | 2026-07-08 | 2026-07-10 |  | 2026-07-01 |  |  |  | No
31INR0025 | Alpha Power Phase 4 | SS Started, FIS Started, No IA | Palomino Alpha, LLC | 345kV 7042 Zorn Substation | Guadalupe | SOUTH | 2031-12-31 | GAS | GT | 400.1 |  | 2026-07-08 | 2026-07-10 |  | 2026-07-01 |  |  |  | No
32INR0007 | Alpha Power Phase 5 | SS Started, FIS Started, No IA | Palomino Alpha, LLC | 345kV 7042 Zorn Substation | Guadalupe | SOUTH | 2032-12-31 | GAS | GT | 400.1 |  | 2026-07-08 | 2026-07-10 |  | 2026-07-01 |  |  |  | No
22INR0330 | Old Aqueduct Batt | SS Completed, FIS Started, No IA | Old Aqueduct LLC | 23920 Blackwater 345kV | Hale | PANHANDLE | 2030-03-01 | OTH | BA | 300.96 |  | 2020-07-24 | 2020-05-01 | 2020-07-13 | 2020-06-29 |  |  |  | No
22INR0462 | Old Aqueduct Solar | SS Completed, FIS Started, No IA | Old Aqueduct Solar | 23920 Blackwater 345kV | Hale | PANHANDLE | 2028-06-01 | SOL | PV | 511.63 |  | 2021-07-09 | 2020-12-03 | 2021-02-19 | 2021-06-29 |  |  |  | No |  |  | Not Required
27INR0181 | Elk Unit 4 | SS Completed, FIS Completed, IA | Golden Spread Electric Cooperative, Inc. | 141607 AEEC_5 | Hale | PANHANDLE | 2027-02-28 | GAS | GT | 210 |  | 2024-03-04 | 2024-04-09 | 2024-07-05 | 2024-03-19 | 2025-07-16 |  | 2025-12-30 | Yes | 2025-08-14 | 2025-08-14 | 2026-07-29 | 2026-07-29 | 2026-07-29 | 2026-08-03
28INR0498 | Old Aqueduct BESS II | SS Completed, FIS Started, No IA | Tempus Power Management LLC | 23920 BLKWTRDR_5 345kV | Hale | PANHANDLE | 2030-03-01 | OTH | BA | 300.96 |  | 2026-03-09 | 2026-03-10 | 2026-06-04 | 2026-03-05 |  |  |  | No
29INR0175 | Black Mountain Hale Gas | SS Completed, FIS Started, No IA | Fort Worth Power Core LLC | 345 kV Blackwater Draw Switch (#23920) | Hale | PANHANDLE | 2030-04-16 | GAS | CC | 990.6 |  | 2025-08-26 | 2025-08-27 | 2025-11-18 | 2025-08-28 |  |  |  | No
23INR0055 | Tabor Solar | SS Completed, FIS Started, No IA | Quanah Solar LLC | Tap 345kV 60504 Tesla - 61001 Jim Treece | Hardeman | WEST | 2027-04-16 | SOL | PV | 506.4 |  | 2020-08-31 | 2020-09-02 | 2020-11-19 | 2020-07-07 |  | No |  | No |  |  | Not Required
23INR0233 | Earthwise Solar | SS Completed, FIS Started, No IA | Quanah Solar 2 | Tap 345kV 60504 Tesla - 61001 Jim Treece | Hardeman | WEST | 2028-12-31 | SOL | PV | 370.5 |  | 2022-02-23 | 2022-03-14 | 2022-06-09 | 2022-02-25 |  |  |  | No | Not Required | Not Required | Not Required
26INR0171 | Lazy U Solar 1 | SS Completed, FIS Started, No IA | Lazy U Solar 1 | Tap 345kV 60505 EDITHCLA7B - 60501 TESLA7A ckt2 | Hardeman | WEST | 2029-06-30 | SOL | PV | 252 |  | 2023-08-07 | 2023-08-21 | 2023-11-02 | 2023-08-09 |  | Yes |  | No |  |  | Not Required
26INR0172 | Lazy U Solar 2 | SS Completed, FIS Started, No IA | Lazy U Solar 2 | Tap 345kV 60505 EDITHCLA7B - 60501 TESLA7A CKT2 | Hardeman | WEST | 2029-06-30 | SOL | PV | 252 |  | 2023-08-14 | 2023-08-21 | 2023-11-02 | 2023-08-15 |  | Yes |  | No |  |  | Not Required
26INR0173 | Juniper Ridge BESS 1 | SS Completed, FIS Started, No IA | Lazy U ESS 1 | Tap EDITHCLA7B [60505] -- TESLA7A [60501] 345kV ckt2 | Hardeman | WEST | 2029-06-30 | OTH | BA | 251.5 |  | 2023-08-03 | 2023-09-08 | 2023-12-04 | 2023-08-16 |  | Yes |  | No
26INR0174 | Juniper Ridge BESS 2 | SS Completed, FIS Started, No IA | Lazy U ESS 2 | Tap EDITHCLA7B [60505] -- TESLA7A [60501] ckt2 | Hardeman | WEST | 2029-06-30 | OTH | BA | 251.5 |  | 2023-08-16 | 2023-08-21 | 2023-11-02 | 2023-08-16 |  | Yes |  | No
26INR0496 | Hardeman BESS | SS Completed, FIS Started, No IA | Quanah BESS LLC | 6050 PAUL 138kV | Hardeman | WEST | 2028-06-30 | OTH | BA | 104 |  | 2024-12-06 | 2024-05-09 | 2024-08-05 | 2024-11-11 |  | No |  | No
27INR0063 | Supra Wind | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings, LLC | Tap #6101 Riley 7A to #60505 Edithcla 7B 345kV | Hardeman | WEST | 2027-12-23 | WIN | WT | 205.86 |  | 2023-07-05 | 2023-07-10 | 2023-10-05 | 2023-06-29 |  |  |  | No |  |  | Not Required
22INR0546 | Enchanted Rock NEWPP | SS Completed, FIS Completed, IA | Generate ER-NG, LLC | 40475 Deusen 138kV | Harris | HOUSTON | 2026-02-28 | GAS | IC | 30 |  | 2022-12-01 | 2021-11-10 | 2022-01-17 | 2022-07-13 | 2024-04-19 | No | 2024-04-30 | Yes | 2024-04-25 | Not Required | 2024-04-30 | 2024-05-01 | 2024-05-01 | 2024-05-01
22INR0558 | Callisto II Energy Center | SS Completed, FIS Completed, IA | Callisto II Energy Center LLC | 47150 HO Clarke 138kV | Harris | HOUSTON | 2026-12-17 | OTH | BA | 203.2 | COD | 2021-10-07 | 2021-10-07 | 2021-12-08 | 2021-09-29 | 2025-08-21 | No | 2023-12-11 | Yes | Not Required | Not Required | 2025-10-22 | 2025-02-12 | 2025-09-11 | 2025-10-23
23INR0040 | Dori BQ Solar | SS Completed, FIS Started, IA | Sunnyside Energy, LLC | tap 138kV 47210 Holmes – 42680 Garden Villas | Harris | HOUSTON | 2027-08-30 | SOL | PV | 50.42 |  | 2021-02-10 | 2020-06-09 | 2020-08-18 | 2021-01-29 |  | No | 2022-12-01 | No | Not Required | Not Required | Not Required
23INR0126 | Sigma Storage | SS Completed, FIS Started, No IA | AES Distributed Energy, Inc | 40460 Deepwater 138kV | Harris | HOUSTON | 2029-10-01 | OTH | BA | 408.4 |  | 2022-02-17 | 2021-05-11 | 2021-07-30 | 2022-02-04 |  | No |  | No | [6 empty] | 2028-05-01 | 2029-05-01
23INR0127 | Beacon Storage | SS Completed, FIS Started, No IA | AES Distributed Energy, Inc | 40450 Deepwater 345kV | Harris | HOUSTON | 2029-10-01 | OTH | BA | 408.7 |  | 2022-03-23 | 2021-05-05 | 2021-07-27 | 2022-02-28 |  | No |  | No | [6 empty] | 2028-05-01 | 2029-05-01
23INR0382 | Outer Loop BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II | 40700 Greens Bayou 345kV | Harris | HOUSTON | 2027-12-06 | OTH | BA | 201.2 |  | 2022-05-02 | 2021-09-29 | 2021-12-06 | 2022-04-19 |  | No |  | No
24INR0073 | Hyacinth Storage | SS Completed, FIS Started, No IA | Hyacinth Storage, LLC | 46500 Tomball 345 kV | Harris | HOUSTON | 2030-12-25 | OTH | BA | 103.05 |  | 2022-04-02 | 2021-07-02 | 2021-09-22 | 2022-03-21 |  |  |  | No
24INR0081 | SANJAC BESS | SS Completed, FIS Started, No IA | Castleman Power | 40270 Riverside 138kV | Harris | HOUSTON | 2027-04-04 | OTH | BA | 202.37 |  | 2021-07-08 | 2021-07-08 | 2021-09-28 | 2021-07-08 |  |  |  | No
24INR0196 | Dori BQ BESS | SS Completed, FIS Started, IA | Sunnyside Energy LLC | 138kV line Holmes (#47210) - Garden Villas (#42680); CNP | Harris | HOUSTON | 2027-08-30 | OTH | BA | 154 |  | 2022-01-05 | 2022-02-07 | 2022-05-06 | 2022-01-19 |  | No | 2023-05-31 | No | Not Required | Not Required
24INR0410 | NRG Greens Bayou 6 (TEF-Due Diligence) | SS Completed, FIS Completed, IA | NRG Greens Bayou 6 LLC | Position 1/0 PSSE 40710, Greens Bayou Substation, 138 kV | Harris | HOUSTON | 2028-05-01 | GAS | GT | 445 |  | 2022-07-21 | 2022-08-16 | 2022-11-11 | 2022-07-21 | 2025-08-14 |  | 2025-02-07 | Yes | 2023-09-15 | 2023-09-15 | 2024-06-26 | 2026-07-01 | 2026-08-24
24INR0413 | Furay Battery Energy Storage System | SS Completed, FIS Started, No IA | Blue Topaz 1, LLC | Tap 138kV 45660 Jonte substation – 46332 Scenic Woods Tapping both radial lines. | Harris | HOUSTON | 2028-09-30 | OTH | BA | 304 |  | 2022-08-31 | 2022-09-02 | 2022-11-29 | 2022-09-01 |  | No |  | No | Not Required | Not Required
24INR0419 | High Plains Storage | SS Completed, FIS Started, No IA | ROBP Holdings, LLC | 45880 Hockley 138kV | Harris | HOUSTON | 2028-05-30 | OTH | BA | 157.7 |  | 2022-08-18 | 2022-09-02 | 2022-11-29 | 2022-08-18 |  |  |  | No | Not Required | Not Required
24INR0500 | Claire BESS | SS Completed, FIS Started, No IA | BRP Blue Topaz 3, LLC | 40011 Cedar Bayou 138kV | Harris | HOUSTON | 2027-12-17 | OTH | BA | 406.01 |  | 2023-01-30 | 2023-02-09 | 2023-05-08 | 2023-01-30 |  |  |  | No
24INR0584 | Kegans BESS (Houston IV BESS) | SS Completed, FIS Completed, IA | SMT Houston IV LLC | 44140 CLODINE 138kV | Harris | HOUSTON | 2026-09-05 | OTH | BA | 164.6 |  | 2023-06-30 | 2023-07-10 | 2023-10-05 | 2023-06-27 | 2025-07-01 | No | 2024-11-07 | Yes | Not Required |  | 2025-09-18 | 2025-02-12 | 2025-10-28 | 2025-10-28 |  |  | 2026-05-06 | 2026-06-08
25INR0002 | Barcelona TxHSR TPSS HN-4 | SS Completed, FIS Started, No IA | Texas Central Rail Holdings, LLC | tap 138kV 45885 HocklyC - 46220 Peters | Harris | HOUSTON | 2028-07-15 | OTH | OT | 50 |  | 2019-10-11 | 2019-01-30 | 2019-04-17 | 2019-08-09 |  | No |  | No | Not Required | Not Required
25INR0420 | Houston BESS | SS Completed, FIS Completed, No IA | SMT Houston | Tap 138 kV LAUDER (#46002) - RITTENHOUSE (#46282) ckt 95 | Harris | HOUSTON | 2028-01-01 | OTH | BA | 227.9 |  | 2023-03-31 | 2023-04-07 | 2023-07-03 | 2023-03-28 | 2024-04-04 |  |  | No
25INR0434 | Bluegill BESS | SS Completed, FIS Started, No IA | Bluegill BESS, LLC | Tap 138 kV 40130 Atascocita - 40690 East Gate | Harris | HOUSTON | 2028-10-31 | OTH | BA | 251 | COD | 2023-06-07 | 2023-06-28 | 2023-09-21 | 2023-05-18 |  | No |  | No
26INR0317 | Pinnacle Point Energy Storage | SS Completed, FIS Completed, No IA | GCI Pinnacle Point, LLC | Tap Highlands (Bus # 40812) - HANEY ( BUS # 40790) 138 kV | Harris | HOUSTON | 2029-07-10 | OTH | BA | 101.3 |  | 2023-11-07 | 2023-11-14 | 2024-01-08 | 2023-11-08 | 2025-11-10 | Yes |  | No | Not Required | Not Required
26INR0341 | Megamouth Energy Storage | SS Completed, FIS Completed, IA | GCI Megamouth, LLC | 42750 Mykawa 138 kV | Harris | HOUSTON | 2028-12-31 | OTH | BA | 101.3 | Status Change INA-to-PLN | 2024-03-11 | 2024-03-22 | 2024-06-19 | 2024-03-11 | 2024-09-17 |  | 2025-11-18 | No
26INR0343 | Stinger Energy Storage | SS Completed, FIS Started, No IA | Stinger Energy Storage LLC | Tap Atascocita 138kV Substation (Bus # 40130) - Lake Houston (Bus #40820) | Harris | HOUSTON | 2028-03-01 | OTH | BA | 200.8 |  | 2023-11-02 | 2023-11-14 | 2024-01-08 | 2023-11-02 |  |  |  | No
26INR0345 | NET Power Demonstration plant | SS Completed, FIS Completed, No IA | NET Power LLC | 42360 Mirage POI 8 138kV | Harris | HOUSTON | 2027-08-21 | GAS | GT | 25.5 |  | 2024-09-03 | 2023-12-20 | 2024-03-08 | 2024-09-03 | 2025-07-10 |  |  | No
26INR0503 | Rex Storage | SS Completed, FIS Started, No IA | Rex BESS, LLC | Tap 138 kV 48096 El Dorado - 43610 Scarsdale CKT 92 | Harris | HOUSTON | 2028-10-30 | OTH | BA | 256.4 | COD | 2024-06-05 | 2024-06-13 | 2024-08-07 | 2024-06-04 |  |  |  | No
26INR0545 | Knight Airport BESS I | SS Completed, FIS Started, No IA | Airport Storage I LLC | Tap 138kV 48126 Gulfgate - 48199 Knight 06 and 42680 Garden Villas - 42770 Ashville 06 | Harris | HOUSTON | 2027-10-15 | OTH | BA | 522.46 |  | 2024-08-07 | 2024-08-16 | 2024-11-13 | 2024-08-08 |  |  |  | No
26INR0546 | Hobby BESS I | SS Completed, FIS Completed, No IA | Airport Storage II LLC | Double Tap 138kV 42680 Garden Villas – 48250 Hall & 42680 Garden Villas – 48013 Chocolate Bayou | Harris | HOUSTON | 2027-10-15 | OTH | BA | 602.56 |  | 2024-08-06 | 2024-09-04 | 2024-12-03 | 2024-08-15 | 2026-01-20 |  |  | No
26INR0548 | Burnet Bay Storage | SS Completed, FIS Completed, No IA | TOCE TX BESS 4, LLC | tap 138kV 40390 Crosby - 40790 Haney | Harris | HOUSTON | 2029-06-01 | OTH | BA | 207.83 |  | 2024-08-27 | 2024-09-10 | 2024-12-08 | 2024-08-29 | 2026-02-17 | No |  | No
26INR0590 | Callisto ID Energy Center | SS Completed, FIS Started, No IA | Tempus Power management LLC | 47170 (H_O_C__B138) 138kV | Harris | HOUSTON | 2028-06-01 | OTH | BA | 100 |  | 2024-09-10 | 2024-10-01 | 2024-11-13 | 2024-09-10 |  |  |  | No
27INR0245 | Pez Rojo BESS | SS Completed, FIS Started, IA | Pez Rojo BESS, LLC | Tap 138 kV #40260 Chamon - #40912 King | Harris | HOUSTON | 2029-02-01 | OTH | BA | 217.23 |  | 2024-06-26 | 2024-07-01 | 2024-09-23 | 2024-06-14 |  | No | 2026-05-01 | No
27INR0436 | Coati Energy Storage | SS Completed, FIS Started, No IA | PowerPulse LLC | Bus # 40830, Humble, 138 kV | Harris | HOUSTON | 2029-06-15 | OTH | BA | 202.8 |  | 2025-05-28 | 2024-12-19 | 2025-03-17 | 2025-05-21 |  |  |  | No
28INR0074 | Massey Storage | SS Completed, FIS Completed, No IA | Massey Storage, LLC | Tap 138kV Chevron_NewSub(#99300) and Cedar Bayou Tap(#48065) circuit 84 | Harris | HOUSTON | 2028-01-03 | OTH | BA | 102.86 |  | 2024-07-23 | 2024-07-30 | 2024-10-25 | 2024-07-23 | 2025-12-12 | No |  | No
28INR0154 | Pamela Heights I | SS Completed, FIS Completed, IA | Pamela heights I Energy Center LLC | #47150 HOC 138kV | Harris | HOUSTON | 2026-12-18 | OTH | BA | 101.65 |  | 2024-09-03 | 2024-09-10 | 2024-12-03 | 2024-09-09 | 2025-08-15 | No | 2025-10-07 | Yes | Not Required | Not Required | 2025-10-22 | 2025-10-28 | 2025-10-28 | 2025-10-23
29INR0245 | Texas Deepwater BESS | SS Completed, FIS Started, No IA | TDWP Partners LLC | #40881 Parkes Substation 138 kV | Harris | HOUSTON | 2029-03-05 | OTH | BA | 313.29 |  | 2026-02-10 | 2026-02-13 | 2026-05-13 | 2026-02-10 |  | No |  | No
20INR0012 | Lueders Solar | SS Completed, FIS Started, No IA | Innovative Solar 75 | Tap 138kV 6161 Paint Creek - 6200 Ft Phantom | Haskell | WEST | 2029-12-31 | SOL | PV | 40 |  |  | 2017-07-11 | 2017-08-28 | 2017-10-20 |  | No |  | No | Not Required | Not Required | Not Required
21INR0207 | Quantum Solar | SS Completed, FIS Completed, IA | IP QUANTUM II, LLC | 60089 Kilby Station 345kV | Haskell | WEST | 2026-09-01 | SOL | PV | 321.66 |  | 2018-11-07 | 2018-09-27 | 2018-11-14 | 2018-11-07 | 2025-06-16 | No | 2023-10-26 | Yes | Not Required | Not Required | Not Required | 2025-08-04 | 2025-08-04 | 2025-08-04 |  |  | 2026-03-06 | 2026-04-10
22INR0374 | Inertia Solar | SS Completed, FIS Started, IA | Inertia Solar Project, LLC | tap 345kV 60515 Clear Crossing - 6104 Smoky Hill | Haskell | WEST | 2029-03-31 | SOL | PV | 202.39 |  | 2020-10-26 | 2021-02-02 | 2021-02-02 | 2020-10-13 |  |  | 2023-05-10 | Yes | Not Required | Not Required | Not Required | 2021-10-08
23INR0031 | Solace Solar | SS Completed, FIS Completed, IA | IP QUANTUM, LLC. | tap 345kV 1430 Graham - 1048 Tonkawas | Haskell | WEST | 2026-09-01 | SOL | PV | 321.64 |  | 2020-04-21 | 2020-04-22 | 2020-07-09 | 2020-04-03 | 2023-10-26 | No | 2024-01-30 | Yes | Not Required | Not Required | Not Required | 2024-06-07 | 2025-07-25 | 2025-07-24 |  |  | 2026-01-30 | 2026-03-03
23INR0059 | Briggs Solar | SS Completed, FIS Started, IA | IP Quantum III, LLC | tap 345kV 60515 Clear Crossing - 60507 Pendulo | Haskell | WEST | 2028-04-15 | SOL | PV | 323.7 |  | 2021-03-15 | 2020-08-04 | 2020-10-28 | 2021-03-04 |  |  | 2025-03-15 | Yes | Not Required | Not Required | Not Required | 2025-03-24
24INR0058 | Briggs Storage | SS Completed, FIS Started, IA | IP Quantum III, LLC | tap 345kV 60515 Clear Crossing - 60507 Pendulo | Haskell | WEST | 2028-04-15 | OTH | BA | 336 |  | 2022-03-18 | 2021-05-31 | 2021-08-18 | 2022-03-04 |  |  | 2025-03-15 | Yes | Not Required | Not Required |  | 2025-03-24
24INR0125 | Grasshopper Solar | SS Completed, FIS Started, No IA | Grasshopper Solar LLC | Smoky Hill 345kV Sub (Bus #6104) Locational coordinates : 33.34414; 99.624637 | Haskell | WEST | 2028-10-01 | SOL | PV | 407.68 |  | 2021-09-28 | 2021-09-28 | 2021-12-09 | 2021-09-22 |  |  |  | No |  |  | Not Required
24INR0291 | Rubicon Alpha Wind | SS Completed, FIS Completed, IA | Throckmorton Wind, LLC | 60507 pendulo7A 345kV | Haskell | WEST | 2027-07-31 | WIN | WT | 222.6 |  | 2022-03-28 | 2022-05-10 | 2022-08-06 | 2022-04-15 | 2026-03-13 |  | 2024-05-08 | Yes | Not Required | Not Required | Not Required | 2025-02-13 | 2026-04-30 | 2026-04-30
26INR0146 | DMF Sagerton Solar SLF | SS Completed, FIS Started, No IA | Double Mountain Fork LLC | Tap 138kV 6158 Aspermont – 6161 Paint Creek | Haskell | WEST | 2028-12-15 | SOL | PV | 125.5 |  | 2023-07-23 | 2023-07-31 | 2023-10-27 | 2023-07-24 |  |  |  | No |  |  | Not Required
26INR0148 | DMF Sagerton Storage SLF | SS Completed, FIS Started, No IA | Double Mountain Fork LLC | Tap 138kV 6158 Aspermont – 6161 Paint Creek | Haskell | WEST | 2028-12-15 | OTH | BA | 0 |  | 2023-07-23 | 2023-07-31 | 2023-10-27 | 2023-07-20 |  |  |  | No
26INR0309 | Solace Storage | SS Completed, FIS Completed, IA | IP Quantum BESS, LLC | tap 345kV 1430 Graham - 1048 Tonkawas | Haskell | WEST | 2026-09-01 | OTH | BA | 321.79 |  | 2024-02-27 | 2024-03-22 | 2024-06-19 | 2024-02-22 | 2025-06-09 | No | 2025-03-21 | Yes | Not Required | Not Required |  | 2025-07-24 | 2025-07-24 | 2025-07-24 |  |  | 2026-01-30 | 2026-03-03
26INR0310 | Quantum Storage | SS Completed, FIS Completed, IA | IP Quantum II BESS, LLC | 60089 Kilby Switching Station 345kV | Haskell | WEST | 2026-09-01 | OTH | BA | 321.75 |  | 2024-02-28 | 2024-03-22 | 2024-06-19 | 2024-02-22 | 2025-06-16 | No | 2023-10-26 | Yes | Not Required | Not Required |  | 2025-08-04 | 2025-08-04 | 2025-08-04 |  |  | 2026-03-26 | 2026-04-10
26INR0501 | Rolling Plains BESS | SS Completed, FIS Started, No IA | Haskell County BESS LLC | 6104 SMOKY HILL 345kV | Haskell | WEST | 2028-06-30 | OTH | BA | 120 |  | 2024-11-15 | 2024-08-16 | 2024-09-13 | 2024-10-21 |  | No |  | No
26INR0521 | Millers Branch Solar III | SS Completed, FIS Completed, IA | Miller's Branch Solar LLC | Tap 345kV 60703 Gauss - 60514 Clear Crossing (60712 QUASAR) | Haskell | WEST | 2026-10-01 | SOL | PV | 133 |  | 2025-01-30 | 2024-08-16 | 2024-11-04 | 2025-01-30 | 2024-12-09 |  | 2021-06-14 | Yes | Not Required | Not Required | Not Required | 2025-05-14 | 2026-01-27 | 2026-01-27 |  |  | 2026-05-26 | 2026-07-10
27INR0217 | Journey Solar | SS Completed, FIS Started, No IA | Journey Solar, LLC | Tap 138kV Paint Creek 6161 - Aspermont 6158 | Haskell | WEST | 2027-09-14 | SOL | PV | 124.7 |  | 2024-03-13 | 2024-03-29 | 2024-06-19 | 2024-03-14 |  |  |  | No |  |  | Not Required
28INR0408 | Max 4 Wind | SS Completed, FIS Started, No IA | Lake Creek Wind, LLC | Tap 345 kV Gauss7D (Bus# 60703) to Quasar7A (Bus# 60712) Transmission Line | Haskell | WEST | 2029-08-31 | WIN | WT | 352.6 |  | 2025-07-16 | 2025-07-29 | 2025-10-06 | 2025-07-16 |  |  |  | No |  |  | Not Required
28INR0433 | Blue Spring Solar | SS Completed, FIS Started, No IA | Flat Creek Solar, LLC | #60515 Clear Crossing 345 kV | Haskell | WEST | 2028-10-28 | SOL | PV | 301 |  | 2025-08-28 | 2025-10-03 | 2025-11-14 | 2025-09-22 |  |  |  | No | Not Required | Not Required | Not Required
21INR0527 | Hays Energy Unit 3 Repower | SS Completed, FIS Started, No IA | HAYS ENERGY, LLC | 7043 Hays 345kV | Hays | SOUTH | 2028-07-01 | GAS | GT | 18 | COD | 2021-02-09 | 2020-10-07 | 2020-12-30 | 2021-02-05 |  |  |  | No | 2020-11-05
22INR0586 | Hays Energy Unit 2 Repower | SS Completed, FIS Started, No IA | HAYS ENERGY, LLC | 7043 Haysen 345kV | Hays | SOUTH | 2028-07-01 | GAS | GT | 18 | COD | 2022-12-01 | 2022-02-21 | 2022-05-21 | 2022-11-15 |  |  |  | No
24INR0387 | PaleAle BESS | SS Completed, FIS Completed, No IA | Momentum Energy Storage Partners,LLC | Tap 138 kV Bus 7506 L_CEDAVA8_1Y - Bus 7507 L_FRIEND8_1Y | Hays | SOUTH | 2027-04-15 | OTH | BA | 75.38 |  | 2022-12-13 | 2022-07-18 | 2022-10-14 | 2022-12-06 | 2026-04-13 | No |  | No
25INR0694 | Hays Energy Unit 1 Repower | SS Completed, FIS Started, No IA | HAYS ENERGY, LLC | 7043 Hays Energy 345kV | Hays | SOUTH | 2028-07-01 | GAS | GT | 18 | COD | 2026-01-12 | 2024-10-18 | 2025-01-15 | 2026-01-06 |  |  |  | No
25INR0695 | Hays Energy Unit 4 Repower | SS Completed, FIS Started, No IA | HAYS ENERGY, LLC | 7043 Hays Energy 345kV | Hays | SOUTH | 2028-07-01 | GAS | GT | 18 | COD | 2026-01-12 | 2024-10-29 | 2025-01-15 | 2026-01-06 |  | No |  | No
23INR0464 | Sloan Storage | SS Completed, FIS Started, No IA | Sloan Energy Storage LLC | 3179 Pauline 138kV | Henderson | NORTH | 2026-03-27 | OTH | BA | 200.9 |  | 2022-07-13 | 2022-02-21 | 2022-05-21 | 2022-06-29 |  |  |  | No | Not Required | Not Required
24INR0355 | Anatole Renewable Energy Storage | SS Completed, FIS Completed, IA | Anatole Renewable Energy LLC | (Bus# 6951) Eustace Southeast 138kV Substation (owned by Rayburn Electric Cooperative) | Henderson | NORTH | 2027-06-30 | OTH | BA | 207.82 |  | 2022-12-14 | 2022-06-02 | 2022-08-30 | 2022-12-02 | 2026-09-21 | No | 2024-05-10 | Yes | Not Required |  |  | 2025-02-12 |  |  | 2026-06-01 | 2027-04-01
27INR0014 | Kit Fox Storage | SS Completed, FIS Started, No IA | Kit Fox Storage, LLC | Walton Switch (6899) 138KV | Henderson | NORTH | 2029-07-01 | OTH | BA | 153.6 |  | 2023-03-08 | 2023-03-13 | 2023-06-09 | 2023-03-10 |  | No |  | No
27INR0198 | Musgravite Solar | SS Completed, FIS Completed, IA | Solex Ridge, LLC | Tap 138 kV (6855) Coffee - (6849) New York. | Henderson | NORTH | 2027-11-01 | SOL | PV | 100.6 |  | 2024-03-01 | 2024-03-22 | 2024-06-19 | 2024-03-06 | 2025-10-06 | No | 2025-05-20 | Yes |  |  | Not Required
28INR0029 | Old Fiddler Energy Storage | SS Completed, FIS Started, No IA | Old Fiddler Energy Storage LLC | 3233 Foggle Switch 138 kV | Henderson | NORTH | 2029-04-16 | OTH | BA | 224.55 |  | 2025-06-19 | 2024-01-11 | 2024-04-08 |  |  |  |  | No
28INR0075 | Wild Paw Storage | SS Completed, FIS Started, No IA | Wild Paw Energy Center, LLC | Tap 345kV 3124 Trinidad - 3130 Forest Grove | Henderson | NORTH | 2028-09-30 | OTH | BA | 301.17 | MW Size | 2024-05-07 | 2024-05-09 | 2024-08-05 | 2024-05-07 |  | Yes |  | No
19INR0055 | Monte Cristo II Wind | SS Completed, FIS Started, IA | Monte Cristo Windpower II, LLC | 8574 Pomelo 345kV | Hidalgo | SOUTH | 2028-12-31 | WIN | WT | 233.9 |  | 2017-07-28 | 2017-04-11 | 2017-05-03 | 2017-07-28 |  | No | 2025-12-19 | Yes | Not Required | Not Required | Not Required | 2026-06-30
22INR0387 | Val Vista Grid BESS 1 | SS Completed, FIS Started, IA | Val Vista Grid, LLC | Tap 345kV 8383 North Edinburg - 80137 Stewart Road | Hidalgo | SOUTH | 2029-03-30 | OTH | BA | 209.32 |  | 2020-08-04 | 2020-08-04 | 2020-10-16 | 2020-07-21 |  | Yes | 2025-12-31 | No
23INR0456 | Bronze Quinta Storage | SS Completed, FIS Started, No IA | KCE TX 28, LLC | S_MCALLN 8371 (S. McAllen 138kV Substation) | Hidalgo | SOUTH | 2028-01-01 | OTH | BA | 103.51 |  | 2022-01-12 | 2022-01-13 | 2022-04-11 | 2022-01-11 |  |  |  | No | Not Required | Not Required
23INR0462 | Palladium Storage | SS Completed, FIS Started, No IA | Palladium Energy Storage LLC | Tap 138 kV 8656 Luna - 8033 Pantera | Hidalgo | SOUTH | 2028-06-30 | OTH | BA | 156.33 |  |  | 2022-02-28 | 2022-05-27 | 2022-01-21 |  |  |  | No
23INR0480 | Camellia Storage | SS Completed, FIS Started, No IA | Camellia Storage Project LLC | Tap 138 kV 8358 NORTH MERCEDES - 8327 HARLINGEN 138 kV | Hidalgo | SOUTH | 2028-06-30 | OTH | BA | 90.76 |  | 2022-07-12 | 2022-07-05 | 2022-10-01 | 2022-07-06 |  |  |  | No | Not Required | Not Required
24INR0102 | Val Vista Grid BESS 2 | SS Completed, FIS Started, IA | Val Vista Grid, LLC | Tap 345kV 8383 North Edinburg - 80137 Stewart Road | Hidalgo | SOUTH | 2029-03-30 | OTH | BA | 210.56 |  | 2021-09-30 | 2021-10-01 | 2021-12-09 | 2021-10-01 |  | Yes | 2025-12-31 | No | Not Required | Not Required
24INR0447 | PSE Chihuahua TX Storage | SS Completed, FIS Completed, No IA | PureSky Development Inc | Tap 138kV 8392 Bates – 8394 Liston | Hidalgo | SOUTH | 2028-06-30 | OTH | BA | 200 |  | 2023-09-25 | 2022-12-07 | 2023-03-06 | 2023-09-15 | 2025-10-16 | No |  | No | Not Required | Not Required
24INR0448 | PSE Minnesota TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | Tap 138kV 8372 North Pharr – 8906 North Alamo | Hidalgo | SOUTH | 2028-06-30 | OTH | BA | 94 |  | 2023-08-21 | 2022-11-15 | 2023-02-09 | 2023-08-09 |  |  |  | No | Not Required | Not Required
24INR0449 | PSE Richardson TX Storage | SS Completed, FIS Completed, No IA | PureSky Development Inc. | TAP 138KV 8374 SOUTH EAST EDINBURG - 8029 CLOSNER | Hidalgo | SOUTH | 2028-06-30 | OTH | BA | 100 |  | 2023-09-28 | 2022-12-07 | 2023-03-06 | 2023-09-15 | 2026-02-17 |  |  | No | Not Required | Not Required
24INR0491 | Gunnar BESS | SS Completed, FIS Completed, IA | Gunnar Reliability Project LLC | 8029 CLOSNER4A 138kV | Hidalgo | SOUTH | 2026-11-25 | OTH | BA | 154.75 | COD | 2023-02-01 | 2023-02-09 | 2023-05-05 | 2023-01-30 | 2025-09-11 | No | 2023-09-22 | Yes | Not Required | Not Required |  | 2024-05-06 | 2025-10-29 | 2025-10-31 |  |  | 2026-08-28 | 2026-09-08
25INR0039 | Borderland ESC | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | tap 138kV 8380 NEDIN4A – 8632 NMCALLEN4C | Hidalgo | SOUTH | 2028-11-30 | OTH | BA | 200 |  | 2022-02-08 | 2022-02-21 | 2022-05-22 | 2022-02-08 |  |  |  | No
25INR0040 | McMEXICO STORAGE | SS Completed, FIS Started, No IA | FRESH AIR ENERGY II, LLC | 8644 Trade Zone 138kV | Hidalgo | SOUTH | 2028-11-30 | OTH | BA | 201.9 |  | 2022-01-28 | 2022-02-28 | 2022-05-27 | 2022-02-15 |  | No |  | No | Not Required | Not Required
25INR0192 | Palmvalley Storage | SS Completed, FIS Started, No IA | Palm Valley BESS LLC | Frontera (#8980) | Hidalgo | SOUTH | 2027-05-01 | OTH | BA | 100 |  | 2022-08-26 | 2022-09-27 | 2022-12-21 | 2022-09-16 |  |  |  | No
25INR0239 | Big Five Storage | SS Completed, FIS Started, No IA | TX BESS 3 LLC | Tap 138kV (5784) Redgtss - (8380) Nedina | Hidalgo | SOUTH | 2028-01-15 | OTH | BA | 102.18 |  | 2023-05-24 | 2023-05-26 | 2023-08-17 | 2023-05-22 |  |  |  | No | [6 empty] | 2027-07-01 | 2027-09-06
25INR0376 | Hawkins BESS | SS Completed, FIS Started, No IA | BRP BLUE TOPAZ 7, LLC | 85005 ELGATO4A 138 kV | Hidalgo | SOUTH | 2028-01-16 | OTH | BA | 150.43 |  | 2023-04-19 | 2023-05-03 | 2023-07-28 | 2023-04-19 |  |  |  | No
26INR0442 | Donna BESS | SS Completed, FIS Started, No IA | Donna Solar LLC | Tap 345 kV 80137 Stewart Road - 8383 North Edinburg | Hidalgo | SOUTH | 2029-02-22 | OTH | BA | 53.91 |  | 2024-11-20 | 2024-03-22 | 2024-06-19 | 2024-11-06 |  | Yes |  | No | Not Required | Not Required
26INR0443 | Sullivan Solar | SS Completed, FIS Started, No IA | Sullivan Solar LLC | Tap 138kV 8798 La Grulla - 8355 Goodwin | Hidalgo | SOUTH | 2029-02-25 | SOL | PV | 170.68 |  | 2024-11-12 | 2024-03-22 | 2024-06-19 | 2024-11-06 |  |  |  | No |  |  | Not Required
26INR0444 | Sullivan BESS | SS Completed, FIS Started, No IA | Sullivan Solar LLC | Tap 138kV 8798 La Grulla - 8355 Goodwin | Hidalgo | SOUTH | 2029-02-25 | OTH | BA | 72.19 |  | 2024-11-12 | 2024-03-22 | 2024-06-19 | 2024-11-06 |  |  |  | No
27INR0205 | Donna Solar | SS Completed, FIS Started, No IA | Donna Solar LLC | Tap 345 kV (80137) Stewart Road - (8383) North Edinburg CKT ID#01 | Hidalgo | SOUTH | 2029-02-22 | SOL | PV | 168.13 |  | 2024-11-26 | 2024-03-22 | 2024-06-19 | 2024-11-06 |  | Yes |  | No |  |  | Not Required
27INR0232 | Anawa La Solar | SS Completed, FIS Started, No IA | Anawa La Solar LLC | TAP 138 KV 8394 LISTON - 8392 BATES | Hidalgo | SOUTH | 2027-08-31 | SOL | PV | 93.3 |  | 2024-04-29 | 2024-03-29 | 2024-06-19 | 2024-04-15 |  | No |  | No |  |  | Not Required
27INR0233 | Anawa La BESS | SS Completed, FIS Started, No IA | Anawa La Solar LLC | Tap 138KV 8394 Liston- 8392 Bates | Hidalgo | SOUTH | 2027-08-31 | OTH | BA | 103.7 |  | 2024-04-29 | 2024-03-22 | 2024-06-19 | 2024-04-15 |  | No |  | No
27INR0338 | Billie Storage | SS Completed, FIS Started, No IA | Weslaco Storage LLC | Tap 138kV 8357 North Weslaco – 8358 North Mercedes | Hidalgo | SOUTH | 2029-09-02 | OTH | BA | 83.75 |  | 2025-05-02 | 2024-07-30 | 2024-10-27 |  |  |  |  | No
28INR0247 | Eligius BESS | SS Completed, FIS Started, No IA | Eligius Storage LLC | tap 138kV Liston (#8394) – JL Bates (#8392) line, AEP | Hidalgo | SOUTH | 2028-11-28 | OTH | BA | 174.66 |  | 2025-02-17 | 2025-02-25 | 2025-05-20 | 2025-02-18 |  | No |  | No
28INR0524 | Anawa La Gas | SS Completed, FIS Started, No IA | Anawa La Solar LLC | Liston 138 KV to Bates 138 KV | Hidalgo | SOUTH | 2028-12-30 | GAS | CC | 250 | MW Size | 2026-06-18 | 2026-06-24 | 2026-09-19 | 2026-06-10 |  |  |  | No
21INR0258 | Mercury Storage SLF | SS Completed, FIS Started, No IA | Mercury Storage, LLC | 68092 Liberty Station 345kV | Hill | NORTH | 2029-07-01 | OTH | BA | 0 |  | 2019-02-07 | 2019-02-14 | 2019-05-03 | 2019-02-07 |  |  |  | No | Not Required | Not Required
22INR0499 | Aquilla Lake 3 Wind | SS Completed, FIS Completed, IA | Aquilla Lake 3 Wind | tap 345 kV 68040 Kopperl to 68091 Navarro | Hill | NORTH | 2026-11-20 | WIN | WT | 297.4 |  | 2021-03-05 | 2021-03-08 | 2021-05-28 | 2021-02-18 | 2025-09-10 | Yes | 2024-01-24 | Yes | Not Required |  | Not Required | 2025-09-10 | 2025-09-10 | 2025-10-30 |  |  | 2026-07-02 | 2026-07-14
24INR0023 | Compadre Solar | SS Completed, FIS Completed, IA | Hill Solar I, LLC | tap 345kV 68090 Sam Switch - 1907 Venus | Hill | NORTH | 2026-10-31 | SOL | PV | 405.7 | COD | 2021-03-29 | 2021-03-16 | 2021-05-28 | 2021-03-08 | 2024-01-31 | No | 2022-11-12 | Yes | Not Required | Not Required | Not Required | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  | 2024-10-30 | 2024-11-13
24INR0106 | Payne Battlecreek | SS Completed, FIS Started, IA | Gransolar Texas Ten, LLC | tap 138kV 213 Haney - 3515 Hubbard | Hill | NORTH | 2027-08-25 | SOL | PV | 84.99 |  | 2022-03-23 | 2021-08-12 | 2021-10-29 | 2022-03-10 |  | No | 2024-02-23 | No | Not Required | Not Required | Not Required
24INR0124 | High Noon Solar | SS Completed, FIS Started, IA | High Noon Solar Project, LLC | Tap 138kV 445 Yates - 444 Covington | Hill | NORTH | 2028-05-09 | SOL | PV | 182 |  | 2021-11-02 | 2021-11-03 | 2021-12-29 | 2021-11-02 |  |  | 2024-05-03 | Yes | Not Required | Not Required | Not Required | 2025-02-12
24INR0126 | High Noon Storage | SS Completed, FIS Started, IA | High Noon Solar Project, LLC | Tap 138kV 445 Yates - 444 Covington | Hill | NORTH | 2028-05-09 | OTH | BA | 94 |  | 2021-11-02 | 2021-11-03 | 2021-12-29 | 2021-11-02 |  |  | 2024-05-08 | Yes | Not Required | Not Required |  | 2025-02-12
24INR0407 | Mercury Solar III | SS Completed, FIS Started, IA | Mercury Solar | 68092 Liberty Station 345kV | Hill | NORTH | 2029-04-01 | SOL | PV | 203.5 |  | 2022-08-02 | 2022-08-16 | 2022-11-11 | 2022-08-03 |  | Yes | 2025-12-12 | Yes |  |  | Not Required
25INR0046 | Blue Skies BESS | SS Completed, FIS Started, IA | ACTX BESS Project LLC | 68090 SAM SW 345kV | Hill | NORTH | 2028-04-01 | OTH | BA | 306.26 |  | 2022-04-02 | 2022-05-10 | 2022-08-06 | 2022-04-15 |  |  | 2024-06-20 | Yes |  |  |  | 2025-02-12
25INR0122 | Vial BESS | SS Completed, FIS Started, IA | Gransolar Texas Eleven LLC | Chatt(234) - Pecan Street (3352) 138kV | Hill | NORTH | 2027-09-15 | OTH | BA | 135.18 |  | 2023-04-03 | 2022-07-05 | 2022-10-01 | 2023-03-29 |  | No | 2025-08-04 | Yes | Not Required | Not Required | 2025-08-18 | 2025-08-28
25INR0166 | Compadre Solar II | SS Completed, FIS Completed, IA | Hill Solar II, LLC | Tap 345kV 68090 Sam Switch – 3389 Fort Smith | Hill | NORTH | 2026-12-31 | SOL | PV | 201.4 | COD | 2023-03-17 | 2022-09-15 | 2022-12-13 | 2023-03-07 | 2025-06-16 |  | 2024-12-24 | Yes |  |  | Not Required | 2025-03-04 | 2025-12-16 | 2025-12-16 |  |  | 2026-04-27 | 2026-07-16
25INR0229 | OCI Cobb Creek Solar | SS Completed, FIS Completed, IA | Hillsboro Solar Project LLC | tap 345kV 1907 Venus - 68090 Sam Sw | Hill | NORTH | 2027-12-31 | SOL | PV | 203.1 |  | 2022-11-11 | 2022-11-15 | 2023-02-09 | 2022-11-09 | 2024-05-06 | No | 2024-07-24 | Yes | Not Required | Not Required | Not Required | 2025-06-11
25INR0233 | OCI Cobb Creek ESS | SS Completed, FIS Completed, IA | Hillsboro Solar Project LLC | tap 345kV 1907 Venus - 68090 Sam Sw | Hill | NORTH | 2028-12-31 | OTH | BA | 201.6 |  | 2022-11-17 | 2022-12-07 | 2023-03-04 | 2022-11-23 | 2024-05-06 | No | 2024-07-24 | Yes | Not Required |  |  | 2025-06-11
26INR0313 | Edens Solar | SS Completed, FIS Started, No IA | Hill PV, LLC | Tap 69kV 3532 Itasca - 3523 Hillsboro | Hill | NORTH | 2028-04-09 | SOL | PV | 70.75 |  | 2023-10-18 | 2023-10-25 | 2024-01-22 | 2023-10-20 |  |  |  | No |  |  | Not Required
26INR0402 | HILLBORO BESS | SS Completed, FIS Started, No IA | Abei Energy Green XI LLC | Tap 138kV Ash Creek Switch (Bus #3473) – Revolution Switch (Bus #3387) | Hill | NORTH | 2028-09-21 | OTH | BA | 130.9 |  | 2025-05-28 | 2024-02-27 | 2024-05-24 | 2024-11-14 |  |  |  | No
27INR0312 | HILLBORO WIND | SS Completed, FIS Started, No IA | Abei Energy Green XI LLC | Tap 138kV Ash Creek Switch (Bus #3473) – Revolution Switch (Bus #3387) | Hill | NORTH | 2028-09-21 | WIN | WT | 33.2 |  | 2025-04-04 | 2024-07-01 | 2024-09-24 | 2024-11-19 |  |  |  | No |  |  | Not Required
27INR0646 | Files BESS SLF | SS Started, FIS Started, No IA | Files BESS | Fort Smith Switch (#3389) 345 kV | Hill | NORTH | 2029-11-07 | OTH | BA | 34 | COD | 2026-07-20 | 2026-07-22 |  | 2026-07-03 |  |  |  | No | Not Required | Not Required
28INR0404 | Penelope Solar | SS Completed, FIS Started, No IA | Ash Creek Project LLC | New sub in the 234 Chatt - 3473 Ash Creek 138kV line | Hill | NORTH | 2029-09-24 | SOL | PV | 97.8 |  | 2026-02-02 | 2025-07-21 | 2025-10-02 | 2026-01-28 |  |  |  | No | Not Required | Not Required | Not Required
28INR0472 | Seven Angels Energy Storage I | SS Completed, FIS Started, No IA | Seven Angels Infrastructure LLC | 68090 Sam Switch Bus 345kV | Hill | NORTH | 2028-12-31 | OTH | BA | 514 |  | 2025-11-04 | 2025-11-05 | 2026-01-12 | 2025-11-04 |  | No |  | No
28INR0473 | Seven Angels Energy Storage II | SS Completed, FIS Started, No IA | Seven Angels Infrastructure LLC | 68090 Sam Switch Bus 345kV | Hill | NORTH | 2028-12-31 | OTH | BA | 514 |  | 2025-11-04 | 2025-11-05 | 2026-01-12 | 2025-11-04 |  | No |  | No
29INR0158 | NRG Prairie Energy Center | SS Completed, FIS Started, No IA | NRG Prairie Energy Center LLC | Tap #1907 Venus Switch – #3389 Fort Smith Switch 345 kV | Hill | NORTH | 2030-12-31 | GAS | CC | 1253 |  | 2026-03-26 | 2026-04-02 | 2026-06-30 | 2026-03-25 |  |  |  | No
33INR0005 | Bullock Gas | SS Completed, FIS Started, No IA | Bullock Data Center, LLC | BULLOCK 345 KV STATION (Bus# 68096) | Hill | NORTH | 2032-07-01 | GAS | CC | 1400 |  | 2026-06-04 | 2026-06-12 | 2026-07-29 | 2026-05-22 |  |  |  | No
33INR0006 | Liberty Thermal Energy Center | SS Completed, FIS Started, No IA | Liberty Data Center I, LLC | LIBERTY 345 KV STATION (Bus# 68092) | Hill | NORTH | 2032-07-01 | GAS | CC | 1400 |  | 2026-06-08 | 2026-06-12 | 2026-07-29 | 2026-06-08 |  |  |  | No
24INR0567 | Wolf Hollow III | SS Completed, FIS Started, No IA | Wolf Hollow II Power LLC | 1877 Mitchell Bend 345KV | Hood | NORTH | 2027-05-31 | GAS | GT | 306.32 |  | 2023-05-18 | 2023-06-07 | 2023-09-01 | 2023-05-30 |  |  |  | No
25INR0231 | Apache Hill BESS | SS Completed, FIS Completed, IA | APACHE HILL ENERGY CENTER | 363 Hood 138kV | Hood | NORTH | 2026-10-31 | OTH | BA | 201.15 |  | 2022-10-25 | 2022-11-07 | 2023-02-03 | 2022-10-25 | 2026-03-10 | No | 2024-06-26 | Yes | Not Required | Not Required |  | 2024-07-17 | 2026-05-01 | 2026-05-01 |  |  | 2026-09-18
27INR0285 | Rain Lily Storage 1 | SS Completed, FIS Started, IA | Rain Lily Storage One, LLC | Tap 138kV #350 ABBYBEND - #363 HOOD | Hood | NORTH | 2028-10-15 | OTH | BA | 105.6 | SFS/NtP | 2024-06-04 | 2025-02-25 | 2025-05-13 | 2025-01-10 |  |  | 2026-09-16 | Yes
27INR0288 | Rain Lily Solar 1 | SS Completed, FIS Started, IA | Rain Lily Solar 1 LLC | Tap 138kV #350 ABBYBEND - #363 HOOD | Hood | NORTH | 2028-10-15 | SOL | PV | 147.76 | SFS/NtP | 2024-06-04 | 2025-02-25 | 2025-05-13 | 2025-01-10 |  |  | 2026-09-16 | Yes |  |  | Not Required
20INR0203 | Pine Forest Solar | SS Completed, FIS Completed, IA | Pine Forest Solar I, LLC | Monticello Switch – Allen Switch 345 kV Line | Hopkins | NORTH | 2027-02-01 | SOL | PV | 301.51 | COD | 2019-03-26 | 2018-10-04 | 2018-11-20 |  | 2024-12-18 | No | 2020-07-29 | Yes | Not Required | Not Required | Not Required | 2024-05-22 | 2025-01-28 | 2025-01-28 |  |  | 2025-06-03 | 2025-07-03
23INR0229 | CH Solterra LLC | SS Completed, FIS Started, No IA | CH Solterra LLC | Tap 138kV 11796 White Oak POI - 11797 Brinker POI | Hopkins | NORTH | 2027-05-31 | SOL | PV | 143 |  | 2021-03-17 | 2021-03-19 | 2021-06-11 | 2021-03-18 |  | No |  | No | Not Required | Not Required | Not Required
23INR0494 | Cartwheel BESS 1 | SS Completed, FIS Completed, IA | Cartwheel BESS, LLC | Tap 345kV 1697 Sulphur Springs Switch – 2464 Cash Switch | Hopkins | NORTH | 2026-12-31 | OTH | BA | 154.2 |  | 2022-05-20 | 2022-06-02 | 2022-08-30 | 2022-05-10 | 2024-04-12 |  | 2023-11-10 | Yes |  |  |  | 2024-11-04 | 2024-11-04 | 2024-10-30 |  |  | 2025-06-26 | 2025-09-10
23INR0495 | Cartwheel BESS 2 | SS Completed, FIS Started, No IA | RWE Renewables | Tap 345kV 1697 Sulphur Springs Switch – 2464 Cash Switch | Hopkins | NORTH | 2028-06-15 | OTH | BA | 156.91 |  | 2022-05-20 | 2022-06-02 | 2022-08-30 | 2022-05-10 |  |  |  | No
24INR0326 | Blarney Solar | SS Completed, FIS Completed, IA | Blarney Solar Project LLC | 138 kV Ridgeway Switch | Hopkins | NORTH | 2027-10-01 | SOL | PV | 81.46 |  | 2022-04-20 | 2022-07-05 | 2022-10-01 | 2022-04-21 | 2026-09-17 | No | 2024-04-22 | No |  |  | Not Required
25INR0204 | Cedar Range Solar | SS Completed, FIS Completed, IA | Cedar Range, LLC | “Sweet Tea” 345 kV switchyard that taps the Allen Switch – Stouts Creek 345 kV Line | Hopkins | NORTH | 2027-09-17 | SOL | PV | 150.64 |  | 2023-03-06 | 2022-09-21 | 2022-12-19 | 2022-11-03 | 2026-09-17 | No | 2025-07-02 | No |  |  | Not Required
26INR0304 | JUNIPERUSSS | SS Completed, FIS Started, No IA | BLUE STONE RENEWABLE XXI LLC | Tap 345kV Cash Switch (bus# 2464) - Sandy Ranch Switch (bus# 2621) | Hopkins | NORTH | 2029-07-09 | SOL | PV | 80.33 |  | 2024-01-05 | 2024-01-11 | 2024-04-08 | 2024-01-04 |  |  |  | No | Not Required | Not Required | Not Required
26INR0409 | Lucky 7 Solar | SS Completed, FIS Completed, IA | Lucky 7 Solar Farm LLC | Tap 345kV 2621 Sandy Ranch Switch - 2464 CASH SWITCH | Hopkins | NORTH | 2027-09-20 | SOL | PV | 101.35 |  | 2024-03-06 | 2024-03-22 | 2024-06-19 | 2024-02-29 | 2026-08-28 | No | 2025-08-13 | Yes | Not Required |  | Not Required
27INR0097 | JUNIPERUS BESS | SS Completed, FIS Started, No IA | BLUE STONE RENEWABLE XXI LLC | Tap 345kV Cash Switch (bus# 2464) - Sandy Ranch Switch (bus# 2621) | Hopkins | NORTH | 2029-07-09 | OTH | BA | 169.6 |  | 2024-08-05 | 2023-10-30 | 2024-01-26 | 2024-07-24 |  |  |  | No
27INR0451 | Dairyland Storage | SS Completed, FIS Started, No IA | ENGIE IR Holdings LLC | To 345 kV Birthright Station (#11684) | Hopkins | NORTH | 2029-04-30 | OTH | BA | 301.8 |  | 2025-04-07 | 2025-04-21 | 2025-07-18 | 2025-02-04 |  |  |  | No
29INR0056 | Palomino Solar | SS Completed, FIS Started, No IA | Palomino Renewables | Tap 345kV 1695 Monticello - 1697 Sulphur Springs | Hopkins | NORTH | 2028-12-31 | SOL | PV | 301.2 |  | 2025-04-28 | 2024-10-18 | 2025-01-13 | 2025-04-09 |  |  |  | No |  |  | Not Required
29INR0057 | Palomino Storage | SS Completed, FIS Started, No IA | Palomino Renewables | Tap 345kV 1695 Monticello - 1697 Sulphur Springs | Hopkins | NORTH | 2029-05-01 | OTH | BA | 155.1 |  | 2025-04-28 | 2024-11-19 | 2025-01-13 | 2025-04-09 |  |  |  | No
29INR0189 | Project Alpha Solar | SS Completed, FIS Started, No IA | SGE Alpha Energy LLC | 138 kV COOPER LAKE PUMP TAP bus# 1822 ---- 138 KV #1814 SULPHUR SPRINGS | Hopkins | NORTH | 2029-09-24 | SOL | PV | 121.95 |  | 2026-02-05 | 2025-09-09 | 2025-12-11 | 2026-01-28 |  |  |  | No |  |  | Not Required
24INR0412 | Camino Ranch Solar SLF | SS Completed, FIS Completed, IA | Camino Ranch Solar Project LLC | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | Houston | NORTH | 2028-12-09 | SOL | PV | 296.42 |  | 2023-07-01 | 2022-10-06 | 2023-01-03 | 2023-06-22 | 2026-05-08 | No | 2025-12-31 | No |  |  | Not Required
24INR0420 | Camino Ranch Storage SLF | SS Completed, FIS Completed, IA | Camino Solar Ranch, LLC | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | Houston | NORTH | 2028-12-09 | OTH | BA | 298.06 |  | 2023-07-04 | 2022-10-18 | 2023-01-03 | 2023-06-22 | 2026-05-08 | No | 2025-12-31 | No
26INR0176 | Dionysus Solar | SS Completed, FIS Started, IA | Dionysus Solar, LLC | Tap 138kV 6733 Mustang Prairie - 6732 Latexo | Houston | NORTH | 2028-12-15 | SOL | PV | 153.26 | COD | 2023-06-14 | 2023-06-28 | 2023-09-22 | 2023-06-05 |  |  | 2026-07-31 | No |  |  | Not Required
26INR0177 | Dionysus Storage | SS Completed, FIS Started, IA | Dionysus Solar, LLC | Tap 138kV 6733 Mustang Prairie - 6732 Latexo | Houston | NORTH | 2028-12-15 | OTH | BA | 77.28 | COD | 2023-06-14 | 2023-06-28 | 2023-09-22 | 2023-06-05 |  |  | 2026-07-31 | No
26INR0256 | Camino Ranch Solar 2 SLF | SS Completed, FIS Completed, IA | Camino Ranch Solar Project LLC | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | Houston | NORTH | 2028-12-09 | SOL | PV | 237.21 |  | 2023-09-05 | 2024-02-27 | 2024-05-24 | 2024-01-10 | 2026-05-08 | No | 2025-12-31 | No |  |  | Not Required
26INR0257 | Camino Ranch Storage 2 SLF | SS Completed, FIS Completed, IA | Camino Ranch Solar LLC | Tap to Jim English (#3351) – Flat Branch (#3345) 138kV | Houston | NORTH | 2028-12-09 | OTH | BA | 238.45 |  | 2023-08-23 | 2024-02-02 | 2024-04-29 | 2023-10-12 | 2026-05-08 | No | 2025-12-31 | No
26INR0363 | Saint Charles Energy Storage | SS Completed, FIS Started, No IA | RSN STORAGE 001, LLC | TAP 138kV 3345 FLATBRA_8 - 3351 JIM_ENG_8 | Houston | NORTH | 2029-04-16 | OTH | BA | 202.7 |  | 2024-12-09 | 2024-02-27 | 2024-05-24 | 2024-11-20 |  | No |  | No
27INR0196 | Houston County BESS | SS Completed, FIS Started, No IA | Houston ESS, LLC | Tap ETEC 138kV #6733 Mustang Prairie to #6732 Latexo Sub | Houston | NORTH | 2029-12-31 | OTH | BA | 125.4 |  | 2024-02-02 | 2024-02-27 | 2024-05-20 | 2024-01-31 |  |  |  | No | Not Required | Not Required
19INR0174 | Elbow Creek repower | SS Completed, FIS Completed, IA | Elbow Creek Wind Project, LLC | 1058 Longshore 345kV | Howard | WEST | 2027-03-31 | WIN | WT | 0 |  | 2018-07-19 | 2018-05-04 | 2018-05-18 | 2018-07-19 | 2018-09-17 | No | 2007-11-30 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-06-27
22INR0347 | Crater BESS | SS Completed, FIS Started, No IA | BRP Crater BESS LLC | Tap 345 kV Rockhound Switch (10062) – Prong Moss Switch (10057) ckt 1 | Howard | WEST | 2029-05-01 | OTH | BA | 310.28 |  | 2020-05-18 | 2020-05-20 | 2020-07-30 | 2020-04-30 |  |  |  | No
25INR0106 | Luthor Solar | SS Completed, FIS Started, No IA | TREX US Luthor LLC | Tap 138kV 23831 Luther Station – 10032 Little Luther | Howard | WEST | 2027-09-25 | SOL | PV | 101 |  | 2023-05-10 | 2022-06-27 | 2022-09-21 | 2023-04-28 |  |  |  | No |  |  | Not Required
25INR0143 | Ariji BESS | SS Completed, FIS Completed, IA | Ariji BESS, LLC | Tap 138kV 1394 GTTYVTAP_8 - 1322 BIGSPRIG_8 | Howard | WEST | 2029-03-31 | OTH | BA | 100.32 |  | 2023-06-19 | 2022-09-15 | 2022-12-13 | 2023-06-09 | 2025-03-03 |  | 2025-08-01 | Yes |  |  |  | 2026-03-24
25INR0338 | Les Energy Storage | SS Completed, FIS Completed, No IA | Rocky Mountain Energy Development, LLC | Tap 138 kV 1326 Stanton East – 11324 Leatherwood Pod | Howard | WEST | 2028-04-30 | OTH | BA | 205.13 |  | 2023-02-23 | 2023-02-09 | 2023-05-05 | 2023-02-17 | 2025-06-09 |  |  | No
25INR0611 | Odessa Energy Storage | SS Completed, FIS Started, No IA | Odessa Energy Storage LLC, | 1058 LONGSHORE 345kV | Howard | WEST | 2029-05-01 | OTH | BA | 202.8 |  | 2024-01-03 | 2024-02-02 | 2024-04-29 | 2024-01-17 |  |  |  | No | Not Required | Not Required
25INR0629 | Midland Energy Storage | SS Completed, FIS Started, No IA | Midland Energy Storage LLC | Tap 345kV 10057 Prong Moss Switch - 10062 Rockhound Switch CKT 1 | Howard | WEST | 2029-06-09 | OTH | BA | 204.7 |  | 2024-06-17 | 2024-07-01 | 2024-09-26 | 2024-03-26 |  |  |  | No
26INR0301 | Bhalu Storage | SS Completed, FIS Started, No IA | Bhalu Storage, LLC | Tap 138kV Bulldog (#23833) – Elbow (#23834) | Howard | WEST | 2028-04-21 | OTH | BA | 205.5 |  | 2023-10-23 | 2023-10-30 | 2024-01-26 | 2023-10-23 |  | No |  | No | Not Required | Not Required
26INR0485 | Prospector Energy Storage | SS Completed, FIS Started, No IA | Prospector Storage LLC | Natural Dam 138kV Substation (23836) | Howard | WEST | 2026-09-30 | OTH | BA | 204.6 |  | 2024-06-28 | 2024-08-16 | 2024-11-01 | 2024-06-27 |  |  |  | No
27INR0323 | Prairie Blossom Storage | SS Completed, FIS Started, No IA | Prairie Blossom Storage, LLC | Tap 138kV #1322 Big Spring Switch – #1366 Big Spring CRMWD | Howard | WEST | 2029-05-08 | OTH | BA | 122.5 |  | 2024-12-05 | 2024-12-19 | 2025-02-03 | 2024-10-07 |  |  |  | No | Not Required | Not Required | 2025-09-15
27INR0325 | Calf Creek Storage | SS Completed, FIS Started, No IA | Coyote Ridge Storage, LLC | Buffalo 138 kV Substation #23837 | Howard | WEST | 2030-04-01 | OTH | BA | 103.3 |  | 2025-11-17 | 2025-11-24 | 2026-01-14 | 2025-11-18 |  |  |  | No
27INR0512 | Silver Hills Windpower | SS Completed, FIS Started, No IA | Silver Hills Windpower, LLC | 10066 Prong Moss Switch 138kV | Howard | WEST | 2029-06-01 | WIN | WT | 54.05 |  | 2025-07-07 | 2025-04-21 | 2025-07-19 |  |  |  |  | No |  |  | Not Required
28INR0419 | PRI Solar | SS Completed, FIS Started, No IA | BHER Power Resources, Inc. | The 345 kV Falcon Seaboard (#1025) substation; Oncor | Howard | WEST | 2027-01-31 | SOL | PV | 63.84 |  |  | 2025-07-29 | 2025-10-22 | 2025-07-29 |  |  |  | No |  |  | Not Required
29INR0019 | Infinium Solar | SS Completed, FIS Started, No IA | Jackalope Flats Solar, LLC | #1058 Longshore Switch - #18548 Prairieland Switch 345kV Ckt 1 | Howard | WEST | 2029-07-01 | SOL | PV | 401.6 |  | 2024-06-03 | 2024-08-16 | 2024-10-07 | 2024-07-18 |  |  |  | No |  |  | Not Required
29INR0177 | Rattlesnake Gap Wind SLF | SS Completed, FIS Started, No IA | ET Fuels US Inc. | 10119 Tributary Switch 138 kV | Howard | WEST | 2029-06-01 | WIN | WT | 200 |  | 2025-09-15 | 2025-09-22 | 2025-12-12 | 2025-09-12 |  | No |  | No |  |  | Not Required
29INR0178 | Rattlesnake Gap Solar SLF | SS Completed, FIS Started, No IA | ET Fuels US Inc. | 10119 Tributary Switch 138 kV | Howard | WEST | 2029-06-01 | SOL | PV | 0 |  | 2025-09-15 | 2025-09-22 | 2025-12-12 | 2025-09-15 |  | No |  | No |  |  | Not Required
29INR0179 | Rattlesnake Gap Storage SLF | SS Completed, FIS Started, No IA | ET Fuels US Inc. | 10119 Tributary Switch 138 kV | Howard | WEST | 2029-06-01 | OTH | BA | 0 |  | 2025-09-15 | 2025-09-22 | 2025-12-12 | 2025-09-15 |  | No |  | No
22INR0281 | Pink Solar SLF | SS Completed, FIS Started, IA | Pink Solar, LLC | 971 Pruitt 138kV | Hunt | NORTH | 2029-07-31 | SOL | PV | 152.41 |  | 2020-10-21 | 2020-01-30 | 2020-04-20 | 2020-10-16 |  |  | 2022-08-30 | No | Not Required | Not Required | Not Required
22INR0425 | MAKALU SOLAR | SS Completed, FIS Started, No IA | Abei Energy Green X LLC | Tap 138kV 977 Pruitt - 971 Greenville | Hunt | NORTH | 2028-07-24 | SOL | PV | 50.16 |  | 2021-08-17 | 2021-01-21 | 2021-01-28 | 2021-08-10 |  | No |  | No |  |  | Not Required
25INR0246 | VALDIVIAN SOLAR | SS Completed, FIS Started, IA | Abei Energy Green III LLC | 138kV 1816 Commerce Switch - 1809 Wolf City | Hunt | NORTH | 2028-09-22 | SOL | PV | 74.9 | SFS/NtP | 2022-11-17 | 2023-02-27 | 2023-05-26 | 2023-02-22 |  |  | 2026-09-03 | Yes |  |  | Not Required | 2026-09-21
25INR0371 | McMurtre Storage | SS Completed, FIS Completed, IA | BT McMurtre Storage, LLC | tap 138kV 1819 Commerce South - 1815 Cumby Tap | Hunt | NORTH | 2027-12-31 | OTH | BA | 176.13 |  | 2023-03-10 | 2023-03-13 | 2023-06-09 | 2023-03-06 | 2024-07-08 |  | 2025-09-17 | Yes
26INR0464 | Ceres BESS | SS Completed, FIS Started, No IA | Ceres BESS, LLC | Tap 138 kV 6883 QUINLAN NORTH SS - 6860 UNION VALLEY SS | Hunt | NORTH | 2028-08-10 | OTH | BA | 202.7 |  | 2024-10-24 | 2024-10-29 | 2025-01-14 | 2024-10-24 |  | No |  | No
27INR0461 | Fermata BESS | SS Completed, FIS Started, No IA | Fermata BESS, LLC | Tap 345kV 2464# CASHSW_T5 – 2461# ROYSE_N5 | Hunt | NORTH | 2028-07-01 | OTH | BA | 204 |  | 2025-02-20 | 2025-02-25 | 2025-05-20 | 2025-02-21 |  | Yes |  | No
27INR0489 | Power Lane II Gas - Alternate | SS Completed, FIS Started, No IA | GEUS | Tap 138kV Caddo Mills Explorer (11832) – Scatter Branch Sub (1818) Line via (future) GEUS_STM Substation | Hunt | NORTH | 2027-06-01 | GAS | IC | 104.39 |  | 2025-05-07 | 2025-06-03 | 2025-08-29 | 2025-05-28 |  |  |  | No
27INR0631 | Power Lane II - Gas | SS Started, FIS Started, No IA | GEUS | GREENV_IN_8 (977) via (future) GEUS_STM Substation | Hunt | NORTH | 2027-08-15 | GAS | IC | 104.5 |  | 2026-08-17 | 2026-08-17 |  | 2026-08-17 |  |  |  | No
28INR0327 | 18-BRAVO BESS | SS Completed, FIS Started, No IA | Scout Energy Management, LLC | 138 kV Commerce Switch Substation. Bus no. #1816 | Hunt | NORTH | 2028-02-01 | OTH | BA | 407 |  | 2025-03-28 | 2025-04-01 | 2025-06-25 | 2025-03-26 |  |  |  | No
29INR0293 | Pink Storage SLF | SS Completed, FIS Started, No IA | Pink Solar, LLC | 971 Pruitt 138kV | Hunt | NORTH | 2029-07-31 | OTH | BA | 0 |  | 2026-02-25 | 2026-02-26 | 2026-05-25 | 2026-02-24 |  |  |  | No
27INR0023 | Panhandle Flagship Solar 2 | SS Completed, FIS Started, IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005). Station 2 (27INR0023) connects to Station 1 (27INR0022 & 27INR0025) via a 4.9 mile internal tie line. Station 1 (27INR0022 & 27INR0025) connects to POIB via 22.5 mile tie-line | Hutchinson | PANHANDLE | 2031-06-30 | SOL | PV | 304.4 |  | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-02-23 |  | Yes | 2025-08-28 | No |  |  | Not Required
27INR0024 | Panhandle Flagship Solar 3 | SS Completed, FIS Started, IA | Panhandle Solar Group Operating Company LLC | 345 kV Railhead Substation (RAILHEAD #79005).Station 3 (27INR0024) connects to Station 2 (27INR0023) via a 4.4 mile internal tie line. Station 2 connects to Station 1 (27INR0022 & 27INR0025) via a 4.9 mile internal tie line. Station 1 connects to POI | Hutchinson | PANHANDLE | 2031-06-30 | SOL | PV | 260.3 |  | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-02-23 |  | Yes | 2025-08-28 | No |  |  | Not Required
29INR0356 | Enfinity Cedar | SS Started, FIS Started, No IA | EG Cedar LLC | 138kV Newton T.Busby Substation (60356) | Irion | WEST | 2030-07-17 | OTH | BA | 150 |  | 2026-06-29 | 2026-07-06 |  | 2026-06-12 |  |  |  | No
22INR0301 | Fortuna Wind | SS Completed, FIS Completed, IA | RWE Renewables Development, LLC | Tap 345kV 1429 Jacksboro - 1730 WKrum | Jack | NORTH | 2026-07-01 | WIN | WT | 295.3 |  | 2021-01-18 | 2020-03-06 | 2020-05-27 | 2020-11-24 | 2024-05-09 |  | 2024-08-08 | No |  |  | Not Required
23INR0174 | Campsey Wind | SS Completed, FIS Completed, No IA | RWE Clean Energy Development, LLC | tap 345kV 1458 Cobb - 1429 Jacksboro | Jack | NORTH | 2028-06-01 | WIN | WT | 238.3 |  | 2021-09-28 | 2021-02-09 | 2021-05-06 | 2021-09-01 | 2025-05-21 | No |  | No |  |  | Not Required
23INR0334 | Liberty Senate Energy Storage 1 | SS Completed, FIS Started, No IA | Senate Solar LLC | 1445 Burwick 345kV | Jack | NORTH | 2027-10-27 | OTH | BA | 207.4 |  | 2021-09-16 | 2021-10-05 | 2021-12-08 | 2021-10-03 |  | No |  | No | Not Required | Not Required
24INR0011 | Pinnington Storage | SS Completed, FIS Started, No IA | Hecate Energy Longhorn Storage LLC | tap both 345kV 1430 Graham - 1436 Parker 345kV lines | Jack | NORTH | 2029-04-20 | OTH | BA | 502.67 |  | 2020-11-10 | 2020-12-03 | 2021-02-17 | 2020-11-10 |  |  |  | No
24INR0094 | Dovetail Solar 1 | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Solar 1 LLC | Tap 345 KV 1421 Willow Creek - 60515 Clear Crossing Ckt 2 | Jack | NORTH | 2028-04-12 | SOL | PV | 666.1 |  | 2022-06-23 | 2021-09-21 | 2021-12-09 | 2022-06-06 |  |  |  | No | Not Required | Not Required | Not Required
24INR0095 | Dovetail Solar 2 | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Solar 2 LLC | Tap 345 KV 1421 Willow Creek - 60515 Clear Crossing | Jack | NORTH | 2029-04-20 | SOL | PV | 666.1 |  | 2022-07-29 | 2021-10-26 | 2022-01-21 | 2022-07-15 |  |  |  | No |  |  | Not Required
24INR0097 | Dovetail Solar 3 | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Solar Holdings LLC | Tap 345kV 1421 Willow Creek – 11523 THOMPRIC | Jack | NORTH | 2029-04-20 | SOL | PV | 666.1 |  | 2022-08-29 | 2021-12-13 | 2022-02-08 | 2022-08-06 |  |  |  | No |  |  | Not Required
24INR0098 | Dovetail Storage | SS Completed, FIS Started, No IA | Hecate Energy Dovetail Storage LLC | Tap 345 KV 1421 Willow Creek-60515 Clear Crossing CKT#2 | Jack | NORTH | 2028-04-12 | OTH | BA | 508.7 |  | 2022-06-20 | 2021-09-28 | 2021-12-03 | 2022-05-31 |  |  |  | No
24INR0118 | Possum Kingdom Solar | SS Completed, FIS Started, IA | PK Solar, LLC | Tap 345kV 1421 Willow Creek Switch – 11523 Thomas Price | Jack | NORTH | 2028-06-21 | SOL | PV | 262.22 | COD | 2022-06-02 | 2021-09-13 | 2021-11-29 | 2022-05-23 |  | No | 2025-07-25 | Yes | Not Required | Not Required | Not Required | 2026-06-09 |  |  | 2025-05-01 | 2026-05-08
24INR0375 | Possum Kingdom BESS | SS Completed, FIS Started, IA | PK Solar, LLC | Tap 345kV 1421 Willow Creek – 11523 Thomas Price | Jack | NORTH | 2028-10-29 | OTH | BA | 200.86 | COD | 2023-05-31 | 2022-09-02 | 2022-11-29 | 2023-05-25 |  | No | 2025-07-30 | Yes | Not Required | Not Required |  | 2026-06-09 |  |  | 2025-05-01 | 2026-05-08
25INR0657 | O'Bannion Energy Storage | SS Completed, FIS Completed, IA | O'Bannion Energy Storage, LLC | 1506 Long Hollow Switch 345 kV | Jack | NORTH | 2028-04-21 | OTH | BA | 306.4 |  | 2024-05-06 | 2024-05-09 | 2024-08-05 | 2024-05-01 | 2025-05-02 |  | 2025-12-05 | Yes | Not Required |  | 2026-01-12 | 2026-03-25
25INR0660 | Wooderson Energy Storage | SS Completed, FIS Started, No IA | Wooderson Energy Storage, LLC | Tap 345 kV 11418 TECUMSEH- 1421 Willow Creek | Jack | NORTH | 2028-09-30 | OTH | BA | 306.4 |  | 2024-04-15 | 2024-05-09 | 2024-08-05 | 2024-04-18 |  |  |  | No | [7 empty] | 2027-09-21
26INR0185 | Beitel Energy Storage | SS Completed, FIS Started, No IA | Brazos Energy Storage, LLC | 579 Jack County 138kV | Jack | NORTH | 2027-12-31 | OTH | BA | 200.6 |  | 2023-06-26 | 2023-08-14 | 2023-11-10 | 2023-08-02 |  |  |  | No | Not Required | Not Required
26INR0215 | JackGard BESS | SS Completed, FIS Completed, No IA | Jackgard BESS | 1429 Jacksboro 345kV | Jack | NORTH | 2028-04-17 | OTH | BA | 200.59 |  | 2023-08-12 | 2023-08-14 | 2023-11-02 | 2023-07-31 | 2024-11-15 | No |  | No
26INR0460 | Lightning Ridge Energy Storage | SS Completed, FIS Completed, No IA | Lightning Ridge Storage LLC | Tap #1429 Jacksboro Substation 345kV | Jack | NORTH | 2028-03-21 | OTH | BA | 204.7 |  | 2024-03-18 | 2024-03-29 | 2024-06-25 | 2024-03-27 | 2025-11-24 | No |  | No
28INR0509 | Thunder Bird 2 Gas | SS Completed, FIS Started, No IA | BKV Power Ventures Jack, LLC 3 | Tap Double circuit line between Jacksbro_5 (1429) to Willowck_5 (1421) and Jacksbro_5 (1429) to Hendrch_5 (1443) | Jack | NORTH | 2031-06-14 | GAS | CC | 1272.8 | MW Size | 2026-05-03 | 2026-05-26 | 2026-08-21 | 2026-07-07 |  |  |  | No
30INR0110 | Thunder Bird 1 Gas | SS Started, FIS Started, No IA | BKV Power Ventures Jack, LLC 3 | Tap Double circuit line between Jacksbro_5 (1429) to Willowck_5 (1421) and Jacksbro_5 (1429) to Hendrch_5 (1443) | Jack | NORTH | 2030-06-14 | GAS | CC | 1272.8 |  | 2026-04-27 | 2026-07-08 |  | 2026-07-07 |  |  |  | No
20INR0236 | New Hickory Solar | SS Completed, FIS Completed, IA | New Hickory Solar LLC | OLD_HCKRY_5 bus 5323 345 kV | Jackson | SOUTH | 2026-12-29 | SOL | PV | 209.15 |  | 2019-08-27 | 2019-01-25 | 2019-04-19 | 2019-08-12 | 2024-06-30 | No | 2020-06-30 | Yes | Not Required | Not Required | Not Required | 2021-04-12 | 2025-07-31 | 2025-07-31 |  |  | 2026-07-20 | 2026-09-15
23INR0361 | Third Coast BESS | SS Completed, FIS Completed, IA | Third Coast BESS LLC | 8125 Lolita substation 138kV | Jackson | SOUTH | 2028-12-15 | OTH | BA | 102.82 |  | 2021-09-16 | 2021-08-24 | 2021-11-16 | 2021-09-01 | 2024-12-02 | No | 2023-05-17 | Yes | Not Required | Not Required |  | 2025-01-29 | 2025-01-29 | 2025-01-29
25INR0441 | Dios BESS | SS Completed, FIS Completed, IA | Dios BESS, LLC | 8117 GANADO138kV | Jackson | SOUTH | 2027-12-31 | OTH | BA | 201.08 |  | 2023-04-26 | 2023-05-15 | 2023-08-11 | 2023-05-08 | 2025-12-02 |  | 2025-04-03 | Yes | Not Required | Not Required |  | 2025-09-08
27INR0251 | Sayle Solar SLF | SS Completed, FIS Started, No IA | Sayle Solar LLC | Tap 69kV #5522 Edna - #5518 El Toro SW | Jackson | SOUTH | 2028-05-31 | SOL | PV | 122.4 |  | 2024-05-09 | 2024-06-03 | 2024-08-30 | 2024-05-22 |  |  |  | No |  |  | Not Required
27INR0260 | Sayle Storage SLF | SS Completed, FIS Started, No IA | Sayle Storage LLC | Tap 69kV #5522 Edna - #5518 El Toro SW | Jackson | SOUTH | 2028-05-31 | OTH | BA | 122.3 |  | 2024-05-09 | 2024-06-03 | 2024-08-30 | 2024-05-22 |  |  |  | No
27INR0554 | Texas Sun Solar | SS Completed, FIS Started, No IA | Pigg Grounds LLC | Cordele Substation ; Bus no. 5524 | Jackson | SOUTH | 2027-12-18 | SOL | PV | 71.7 |  | 2025-08-26 | 2025-09-22 | 2025-11-19 | 2025-09-01 |  |  |  | No |  |  | Not Required
30INR0020 | Willow Oak Gas | SS Completed, FIS Started, No IA | Willow Oak Energy LLC | 40850 Jordan | Jefferson | HOUSTON | 2030-01-01 | GAS | CC | 1298 | MW Size | 2026-06-08 | 2025-09-09 | 2025-12-11 | 2026-06-03 |  |  |  | No
28INR0072 | Mirando Valley Wind | SS Completed, FIS Started, IA | ACE DevCo NC LLC | Tap 345kV 80220 Cenizo - 80079 Cruce Ckt-1 | Jim Hogg | SOUTH | 2028-07-06 | WIN | WT | 478.74 |  | 2024-06-12 | 2024-08-16 | 2024-11-12 | 2024-06-05 |  |  | 2025-12-31 | Yes |  |  | Not Required | 2026-03-25
28INR0242 | Ciervo Wind | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | Tap 345 kV 80355 DelSol7A - 80079 Cruce CKT 2 | Jim Hogg | SOUTH | 2028-12-31 | WIN | WT | 301.5 |  | 2024-12-17 | 2024-12-19 | 2025-02-25 | 2024-12-16 |  | No |  | No |  |  | Not Required
28INR0375 | Barranca Wind 1 | SS Completed, FIS Started, No IA | Barranca Wind Energy, LLC | Tap the 345 kV CENIZO (#80225) - DELSOL (#80307) line | Jim Hogg | SOUTH | 2028-06-01 | WIN | WT | 300.9 |  | 2025-07-07 | 2025-07-29 | 2025-10-06 | 2025-07-09 |  |  |  | No |  |  | Not Required
28INR0376 | Barranca Wind 2 | SS Completed, FIS Started, No IA | Barranca Wind Energy, LLC | Tap the 345 kV CENIZO7C (#80225) - DELSOL7C (#80307) line. | Jim Hogg | SOUTH | 2028-06-01 | WIN | WT | 298.6 |  | 2025-07-07 | 2025-07-29 | 2025-10-06 | 2025-07-09 |  |  |  | No |  |  | Not Required
28INR0434 | Viento Bravo Wind | SS Completed, FIS Started, IA | Webb Wind, LLC | Tap 345kV 80220 Cenizo - 80079 Cruce Ckt-1 | Jim Hogg | SOUTH | 2028-07-06 | WIN | WT | 366.51 |  | 2025-08-29 | 2025-10-03 | 2025-11-14 | 2025-09-23 |  |  | 2025-12-31 | Yes |  |  | Not Required | 2026-03-25
29INR0154 | Las Mujeres Solar | SS Completed, FIS Started, No IA | Las Mujeres Solar, LLC | Cruces 7A (Bus #80079) | Jim Hogg | SOUTH | 2029-12-01 | SOL | PV | 684.33 |  | 2026-05-13 | 2026-05-13 | 2026-08-06 | 2026-05-13 |  |  |  | No |  |  | Not Required
30INR0041 | Bell Song Solar | SS Completed, FIS Started, No IA | Bell Song Solar, LLC | Tap 345 kV #80079 CRUCE7A - #80355 DELSOL7A ckt 1 | Jim Hogg | SOUTH | 2029-09-15 | SOL | PV | 167.6 |  | 2025-05-15 | 2025-06-12 | 2025-09-04 | 2025-05-22 |  | Yes |  | No |  |  | Not Required
30INR0049 | Bell Song Solar 2 | SS Completed, FIS Started, No IA | Bell Song Solar, LLC 2 | Tap 345kV (#80079) CRUCE7A - (#80355) DELSOL7A ckt 1 | Jim Hogg | SOUTH | 2030-03-16 | SOL | PV | 167.6 |  | 2025-06-04 | 2025-06-12 | 2025-09-05 | 2025-06-06 |  | Yes |  | No |  |  | Not Required
31INR0009 | Bell Song Solar 3 | SS Completed, FIS Started, No IA | Bell Song Solar, LLC 3 | Tap 345 kV #80079 CRUCE7A - #80355 DELSOL7A ckt 1 | Jim Hogg | SOUTH | 2030-08-31 | SOL | PV | 167.6 |  | 2025-06-12 | 2025-06-19 | 2025-09-17 | 2025-06-13 |  | Yes |  | No |  |  | Not Required
23INR0331 | Orange Grove BESS | SS Completed, FIS Started, IA | Talitha Energy Project, LLC | 5660 Orange Grove Switching Station 138 kV | Jim Wells | SOUTH | 2027-04-30 | OTH | BA | 61.39 |  | 2021-07-20 | 2021-07-15 | 2021-09-28 | 2021-07-15 |  | No | 2022-11-30 | Yes | Not Required | Not Required |  | 2023-04-04
27INR0249 | Raghorn Solar SLF | SS Completed, FIS Started, No IA | Raghorn Solar LLC | Tap 69kV #5654 San Diego - #5658 Orange Grove | Jim Wells | SOUTH | 2028-05-31 | SOL | PV | 91.9 |  | 2024-05-14 | 2024-05-20 | 2024-08-16 | 2024-05-16 |  |  |  | No |  |  | Not Required
27INR0259 | Raghorn Storage SLF | SS Completed, FIS Started, No IA | Raghorn Storage LLC | Tap 69kV #5654 San Diego - #5658 Orange Grove | Jim Wells | SOUTH | 2028-05-31 | OTH | BA | 0 |  | 2024-05-16 | 2024-05-20 | 2024-08-16 | 2024-05-16 |  |  |  | No
27INR0307 | Beaverhead Solar SLF | SS Completed, FIS Started, No IA | Beaverhead Solar, LLC | Direct to Sub 69kv #5653 Ben Bolt. | Jim Wells | SOUTH | 2029-05-11 | SOL | PV | 61.5 |  | 2024-08-06 | 2024-08-16 | 2024-10-07 | 2024-08-05 |  |  |  | No |  |  | Not Required
27INR0308 | Beaverhead Storage SLF | SS Completed, FIS Started, No IA | Beaverhead Solar, LLC | Direct to Sub 69kv #5653 Ben Bolt. | Jim Wells | SOUTH | 2029-05-11 | OTH | BA | 61.5 |  | 2024-08-06 | 2024-08-16 | 2024-10-07 | 2024-08-05 |  |  |  | No
24INR0075 | Blue Bird Solar | SS Completed, FIS Started, IA | Gigawatt Solar LLC | tap 345kV 1880 Rocky Creek - 1898 Mitchell Bend Switch | Johnson | NORTH | 2028-12-15 | SOL | PV | 425.97 |  | 2021-11-10 | 2021-11-10 | 2022-02-07 | 2021-07-30 |  | Yes | 2024-01-18 | No |  |  | Not Required
27INR0173 | Trenno BESS | SS Completed, FIS Started, IA | JSB1, LLC | Tap 138kV 2281 Godley - 2888 Carmichael | Johnson | NORTH | 2027-09-13 | OTH | BA | 202.56 |  | 2024-03-25 | 2024-02-07 | 2024-04-30 | 2024-03-19 |  | No | 2025-08-18 | No | Not Required | Not Required | 2026-08-11
20INR0241 | Crowded Star Solar | SS Completed, FIS Completed, IA | Jones City Solar, LLC | tap 345kV 68001 Claytonville – 68004 Phantom Hill c2 (New Substation: Open Sky 68014) | Jones | WEST | 2026-08-17 | SOL | PV | 218.79 |  | 2019-05-23 | 2019-01-21 | 2019-04-19 | 2019-05-22 | 2024-11-05 | Yes | 2019-12-17 | Yes | Not Required | Not Required | Not Required | 2021-12-01 | 2025-07-24 | 2025-07-24 |  |  | 2026-04-22 | 2026-05-28
20INR0242 | Anson Solar 2 | SS Completed, FIS Completed, IA | Anson Solar Center 2, LLC | existing tap 345 kV 68004 Phantom Hill station | Jones | WEST | 2026-10-01 | SOL | PV | 200.9 |  | 2018-02-15 | 2017-06-23 | 2017-08-07 | 2018-02-15 | 2025-03-19 |  | 2024-08-15 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2025-05-22 | 2025-05-01 |  |  | 2025-11-04 | 2025-11-25
21INR0247 | Anson Solar Center, Phase III | SS Completed, FIS Started, No IA | Anson Solar Center 3, LLC | tap 345kV 68000 WShack - 68001 Clayton | Jones | WEST | 2028-06-01 | SOL | PV | 200 |  | 2018-02-15 | 2017-06-23 | 2017-08-07 | 2018-02-15 |  |  |  | No |  |  | Not Required
22INR0274 | Crowded Star Solar II | SS Completed, FIS Completed, IA | Jones City Solar II, LLC | tap 345kV 68001 Claytonville – 68004 Phantom Hill c2 (New Substation: Open Sky 68014) | Jones | WEST | 2026-09-18 | SOL | PV | 189.5 |  | 2019-05-23 | 2020-03-26 | 2020-06-05 | 2021-03-24 | 2024-11-05 | No | 2019-12-17 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2025-07-24 | 2025-07-24 |  |  | 2026-06-22 | 2026-07-08
22INR0457 | Anson BAT | SS Completed, FIS Completed, IA | Anson II Storage LLC | tap 345 kV 68004 Phantom Hill station | Jones | WEST | 2027-12-01 | OTH | BA | 153.55 |  | 2022-03-03 | 2020-12-03 | 2021-02-19 | 2022-02-23 | 2025-03-19 |  | 2024-08-15 | Yes |  |  |  | 2025-02-12
23INR0244 | Tiger Solar | SS Completed, FIS Completed, IA | Vaca Del Sol, LLC | 68004 PHANTOM HILL 345KV | Jones | WEST | 2027-02-26 | SOL | PV | 250.9 | COD | 2021-04-21 | 2021-04-29 | 2021-07-22 | 2021-04-29 | 2025-12-15 | Yes | 2024-10-30 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2026-01-30 | 2026-01-30
24INR0378 | Solara BESS 1 | SS Completed, FIS Started, No IA | CED Development Inc. | 60387 Hendrick 138kV | Jones | WEST | 2027-11-30 | OTH | BA | 150 |  | 2022-08-08 | 2022-07-05 | 2022-10-01 | 2022-07-26 |  |  |  | No
24INR0379 | Solara BESS 2 | SS Completed, FIS Started, No IA | CED Development Inc. | 60387 Hendrick 138kV | Jones | WEST | 2027-11-30 | OTH | BA | 150 |  | 2022-08-08 | 2022-07-05 | 2022-10-01 | 2022-07-26 |  |  |  | No
25INR0473 | Crowded Star I BESS | SS Completed, FIS Completed, IA | Jones City Solar II, LLC | 68014 Open Sky | Jones | WEST | 2027-07-09 | OTH | BA | 202.69 |  | 2023-07-25 | 2023-08-21 | 2023-11-02 | 2023-08-09 | 2025-11-10 |  | 2025-12-01 | Yes
26INR0440 | Hamby Solar | SS Completed, FIS Started, IA | Abilene GCE LLC | 6245 ABILENE ROBERTSON PRISON 138 KV | Jones | WEST | 2028-06-27 | SOL | PV | 205.8 |  | 2024-03-26 | 2024-03-22 | 2024-06-19 | 2024-03-20 |  |  | 2025-12-31 | Yes | Not Required | Not Required | Not Required | 2026-04-01
27INR0452 | Moccasin Storage | SS Completed, FIS Started, No IA | ENGIE IR Holdings LLC | Tap 345kV #60707 Kirchhoff - #60515 Clear Crossing CKT-1 | Jones | WEST | 2028-07-01 | OTH | BA | 603.08 |  | 2025-01-14 | 2025-01-28 | 2025-04-17 | 2025-01-15 |  |  |  | No
29INR0015 | Funston Solar | SS Completed, FIS Completed, IA | Funston Solar LLC | tap 345 kV 68000 West Shackelford – 68004 Phantom Hill Circuit 2 | Jones | WEST | 2027-02-26 | SOL | PV | 351.1 | COD | 2024-04-03 | 2024-02-27 | 2024-05-26 | 2024-03-19 | 2025-12-17 | Yes | 2024-10-23 | Yes | Not Required | Not Required | Not Required | 2025-09-15 | 2026-01-28 | 2026-01-28
29INR0393 | Lone Tiger Solar | SS Started, FIS Started, No IA | Origis Development, LLC | Tap 345 kV Claytonville (#68001) to phantom hill (#68004) | Jones | WEST | 2029-10-06 | SOL | PV | 242.8 | FIS Request | 2026-09-15 | 2026-09-18 |  | 2026-09-14 |  |  |  | No |  |  | Not Required
30INR0146 | Hackberry Draw Solar | SS Started, FIS Started, No IA | Orsted Onshore Development North America, LLC | Tap 345 kV (68000) West Shackleford - (60515) Clear Crossing Ckt 2 | Jones | WEST | 2030-04-30 | SOL | PV | 652.96 |  | 2026-07-22 | 2026-08-03 |  | 2026-07-15 |  |  |  | No |  |  | Not Required
25INR0491 | Tarim BESS | SS Completed, FIS Started, No IA | BRP Tarim BESS LLC | 5727 Pawnee Switching Substation 138kV | Karnes | SOUTH | 2027-12-01 | OTH | BA | 201 |  | 2024-10-07 | 2024-11-19 | 2025-02-14 | 2024-10-10 |  |  |  | No
26INR0068 | Charro Creek Solar 1 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2029-12-31 | SOL | PV | 203 |  | 2023-01-23 | 2023-01-30 | 2023-04-28 | 2023-02-10 |  |  |  | No |  |  | Not Required
26INR0069 | Charro Creek Storage 1 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2029-12-31 | OTH | BA | 0 |  | 2023-02-27 | 2023-03-08 | 2023-04-28 | 2023-02-15 |  |  |  | No
26INR0070 | Charro Creek Solar 2 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2029-12-31 | SOL | PV | 203 |  | 2023-02-27 | 2023-03-08 | 2023-06-01 | 2023-02-15 |  |  |  | No |  |  | Not Required
26INR0071 | Charro Creek Storage 2 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2029-12-31 | OTH | BA | 0 |  | 2023-02-27 | 2023-03-08 | 2023-06-01 | 2023-02-15 |  |  |  | No
26INR0072 | Charro Creek Solar 3 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap on PAWNEESW5 (#5725) - COLETO7A (#8164) Line | Karnes | SOUTH | 2029-12-31 | SOL | PV | 203 |  | 2023-02-27 | 2023-03-08 | 2023-06-01 | 2023-02-15 |  |  |  | No |  |  | Not Required
26INR0073 | Charro Creek Storage 3 SLF | SS Completed, FIS Started, No IA | Charro Creek Solar LLC | Tap 345kV 5725 PAWNEESW5 - 8164 COLETO7A | Karnes | SOUTH | 2029-12-31 | OTH | BA | 0 |  | 2023-01-23 | 2023-01-30 | 2023-04-28 | 2023-02-10 |  |  |  | No
27INR0151 | Coyote Den Storage | SS Completed, FIS Started, No IA | Coyote Den Energy Center, LLC | The Kenedy Switching Station #2 (#8186) to Rosata POD (#8153) Line ; AEP | Karnes | SOUTH | 2030-09-30 | OTH | BA | 156.93 |  | 2024-01-31 | 2024-02-07 | 2024-04-29 | 2024-01-09 |  |  |  | No
27INR0152 | New Shepherd Solar | SS Completed, FIS Started, No IA | New Shepherd Energy Center, LLC | the Kenedy Switching Station #2 (#8186) – Rosata POD (#8153) line, AEP. | Karnes | SOUTH | 2030-09-30 | SOL | PV | 150.84 |  | 2024-01-03 | 2024-01-11 | 2024-04-05 | 2023-12-19 |  |  |  | No |  |  | Not Required
28INR0073 | Daystar Solar | SS Completed, FIS Completed, No IA | Choate Solar, LLC | 5728 Choate 138kV | Karnes | SOUTH | 2028-09-15 | SOL | PV | 150 |  | 2024-04-09 | 2024-04-15 | 2024-07-05 | 2024-04-09 | 2026-01-13 |  |  | No |  |  | Not Required
28INR0442 | Zunkerville BESS | SS Completed, FIS Started, No IA | Zunkerville Energy, LLC | 345kV BUS #5725 PAWNEE SWITCHING STATION | Karnes | SOUTH | 2029-12-01 | OTH | BA | 206.74 |  | 2025-09-15 | 2025-09-22 | 2025-12-03 | 2025-09-05 |  | No |  | No
28INR0443 | Zunkerville Solar | SS Completed, FIS Started, No IA | Zunkerville Energy, LLC | #5725 PAWNEE SWITCHING STATION 345kV | Karnes | SOUTH | 2029-12-01 | SOL | PV | 200.67 |  | 2025-12-02 | 2025-12-02 | 2026-01-19 | 2025-11-25 |  | No |  | No |  |  | Not Required
29INR0332 | White Star Energy Storage | SS Completed, FIS Started, No IA | White Star Energy Storage, LLC | Milton Substation 78583 L_MILTON8_1Y | Karnes | SOUTH | 2029-12-31 | OTH | BA | 201.2 |  | 2026-04-21 | 2026-05-13 | 2026-08-07 | 2026-05-05 |  |  |  | No
22INR0426 | LUBIO SOLAR | SS Completed, FIS Started, IA | BDPU Solar Lubio LLC | tap 138kV 2727 Crandall - 2724 Kaufman Northwest | Kaufman | NORTH | 2028-04-20 | SOL | PV | 54.71 |  | 2021-07-01 | 2020-10-07 | 2020-12-28 | 2021-06-28 |  |  | 2024-11-08 | No |  |  | Not Required
22INR0552 | Sowers Storage | SS Completed, FIS Started, IA | Sowers Energy Storage LLC | 6894 Rose Hill_RC Sub 138 kV | Kaufman | NORTH | 2027-07-01 | OTH | BA | 208.89 |  | 2021-08-17 | 2021-08-18 | 2021-11-05 | 2021-08-18 |  | No | 2022-04-22 | Yes | Not Required | Not Required |  | 2022-12-05
23INR0222 | Sunbelt Solar | SS Completed, FIS Started, No IA | Rose Hill Solar LLC | tap 138kV 6902 Talty - 6801 Patton | Kaufman | NORTH | 2026-12-31 | SOL | PV | 81.5 |  | 2021-10-05 | 2021-03-16 | 2021-05-28 | 2021-09-30 |  |  |  | No |  |  | Not Required
23INR0409 | Sunbelt Storage | SS Completed, FIS Started, No IA | Rose Hill Solar LLC | Tap 138kV 6902 Talty - 6894 Rose Hill | Kaufman | NORTH | 2026-12-31 | OTH | BA | 52 |  | 2021-11-09 | 2021-11-12 | 2022-02-08 | 2021-11-09 |  |  |  | No
24INR0303 | Erika Solar | SS Completed, FIS Completed, IA | Erika Solar, LLC | Tap 345kV ELKTON 5 (#3105 ) to Tricrn1 5 (#2432) | Kaufman | NORTH | 2026-11-25 | SOL | PV | 200.5 |  | 2022-05-02 | 2022-07-25 | 2022-10-18 | 2022-07-06 | 2025-09-15 | No | 2023-10-12 | Yes | Not Required | Not Required | Not Required | 2025-09-15 | 2025-10-30 | 2025-10-30 |  |  | 2026-08-14 | 2026-08-27
24INR0339 | Mystic Springs Renewable Energy Solar SLF | SS Completed, FIS Completed, IA | Mystic Spring Renewable Energy LLC | Tap 345 kV Royse Switch (2478) – Poetry Switch (2485) | Kaufman | NORTH | 2028-03-31 | SOL | PV | 258.83 |  | 2022-12-14 | 2022-05-10 | 2022-08-06 | 2022-11-28 | 2025-04-17 | No | 2025-10-30 | No |  |  | Not Required
24INR0340 | Mystic Springs Renewable Energy Storage SLF | SS Completed, FIS Completed, No IA | Mystic Spring Renewable Energy LLC | Tap 345 kV Royse Switch (2478) – Poetry Switch (2485) | Kaufman | NORTH | 2028-03-31 | OTH | BA | 0 |  | 2022-12-14 | 2022-05-10 | 2022-08-06 | 2022-11-28 | 2025-04-17 | No |  | No
26INR0086 | Solarville Solar SLF | SS Completed, FIS Started, No IA | Ville Solar, LLC | Tap 345kV #3123 Trinidad Switch – #2432 Tri Corner. | Kaufman | NORTH | 2029-07-01 | SOL | PV | 402.86 |  | 2025-02-12 | 2024-05-20 | 2024-08-15 | 2025-02-05 |  |  |  | No |  |  | Not Required
26INR0502 | Fudge Ranch BESS | SS Completed, FIS Started, No IA | Crandall BESS LLC | <6902><TALTY_RC><138kV> | Kaufman | NORTH | 2027-06-30 | OTH | BA | 104 |  | 2024-12-02 | 2024-04-15 | 2024-07-11 | 2024-11-11 |  |  |  | No
27INR0455 | Yellow Leaf Solar | SS Completed, FIS Started, No IA | Lightsource Renewable Energy Development LLC | Tap 138kV Crandall (#2727) – Kaufman Northwest (#2724) | Kaufman | NORTH | 2028-09-25 | SOL | PV | 103.19 |  | 2025-04-24 | 2025-04-25 | 2025-07-22 | 2025-03-14 |  |  |  | No |  |  | Not Required
27INR0456 | Yellow Leaf BESS | SS Completed, FIS Started, No IA | Lightsource Renewable Energy Development LLC | Tap 138kV Crandall (#2727) – Kaufman Northwest (#2724) | Kaufman | NORTH | 2028-09-25 | OTH | BA | 103.1 |  | 2025-04-24 | 2025-04-25 | 2025-07-22 | 2025-03-14 |  |  |  | No
27INR0531 | Erika BESS | SS Completed, FIS Started, No IA | Erika Solar, LLC | Tap 345kV ELKTON 5 (#3105 ) to Tricrn1 5 (#2432) | Kaufman | NORTH | 2029-07-01 | OTH | BA | 100 |  | 2025-06-11 | 2025-06-19 | 2025-09-17 | 2025-06-06 |  |  |  | No
28INR0412 | Yellow Leaf II BESS | SS Completed, FIS Started, No IA | Yellow Leaf Energy Storage LLC | Tap 138kV 2727 CRANDALL1_8 - 2724 KAUFMN_8 | Kaufman | NORTH | 2028-09-25 | OTH | BA | 205.74 |  | 2025-07-22 | 2025-07-22 | 2025-10-09 | 2025-07-18 |  | No |  | No
28INR0431 | Solarville Wind SLF | SS Completed, FIS Started, No IA | Ville Solar, LLC | Tap 345 kV (#2432)Tri Corner - (#3105) Elkton | Kaufman | NORTH | 2028-09-19 | WIN | WT | 0 |  | 2025-11-13 | 2025-11-18 | 2026-01-19 | 2025-11-12 |  |  |  | No |  |  | Not Required
28INR0432 | Solarville BESS SLF | SS Completed, FIS Started, No IA | Ville Solar, LLC | Tap 345 kV (#2432)Tri Corner - (#3105) Elkton | Kaufman | NORTH | 2028-09-19 | OTH | BA | 0 |  | 2025-11-07 | 2025-11-18 | 2026-01-19 | 2025-11-07 |  |  |  | No
29INR0250 | Slash Pine Storage | SS Completed, FIS Started, No IA | EG Slash Pine LLC | 1698 Sulphur Springs Switch and 3174 Canton Switch 138 kV | Kaufman | NORTH | 2029-09-17 | OTH | BA | 200 |  | 2026-01-12 | 2026-01-13 | 2026-04-07 | 2025-12-22 |  | No |  | No
23INR0163 | Ringtail Ridge Storage | SS Completed, FIS Started, No IA | KCE TX 26, LLC | 7150 Kendall 138kV | Kendall | SOUTH | 2028-05-23 | OTH | BA | 100.57 |  | 2021-01-08 | 2021-01-25 | 2021-04-16 | 2020-12-29 |  |  |  | No
27INR0309 | Tall Saddle Solar | SS Completed, FIS Started, No IA | Tall Saddle Solar, LLC | 80076 AJO SUBSTATION 345kV | Kenedy | COASTAL | 2029-10-15 | SOL | PV | 252.3 |  | 2025-04-01 | 2024-07-01 | 2024-09-26 | 2025-03-25 |  | No |  | No |  |  | Not Required
27INR0310 | Tall Saddle Wind | SS Completed, FIS Started, No IA | Tall Saddle Wind, LLC | 80076 AJO SUBSTATION 345kV | Kenedy | COASTAL | 2029-10-15 | WIN | WT | 522.8 |  | 2025-04-02 | 2024-07-01 | 2024-09-26 | 2025-03-25 |  | No |  | No |  |  | Not Required
28INR0180 | Green Ocelot Solar | SS Completed, FIS Completed, No IA | Ocelot Solar LLC | Tap 345kV 80076 Ajo - 8601 Cebolla | Kenedy | COASTAL | 2028-11-17 | SOL | PV | 357 |  | 2025-01-14 | 2025-01-28 | 2025-04-18 | 2025-01-28 | 2026-09-29 | Yes |  | No |  |  | Not Required
28INR0189 | Green Ocelot Storage | SS Completed, FIS Completed, No IA | Ocelot Solar LLC | Tap 345kV 80076 Ajo 80076 - 8601 Cebolla | Kenedy | COASTAL | 2028-11-17 | OTH | BA | 178.5 |  | 2025-01-14 | 2025-01-28 | 2025-04-18 | 2025-01-28 | 2026-09-29 | Yes |  | No
22INR0215 | TEXAS SOLAR NOVA 3 | SS Completed, FIS Started, No IA | Texas Solar Nova 1, LLC | tap 345kV 11305 Dermott - 59904 Cottonwood | Kent | WEST | 2026-01-31 | SOL | PV | 200.2 |  | 2019-05-28 | 2019-06-24 | 2015-12-30 | 2019-06-19 |  |  |  | No |  |  | Not Required
27INR0435 | Clairemont Solar 1 | SS Completed, FIS Completed, IA | Clairemont Solar LLC | 59908 Novaprime 345kV | Kent | WEST | 2029-02-13 | SOL | PV | 251.75 |  | 2025-01-21 | 2025-01-28 | 2025-04-17 | 2025-01-21 | 2026-08-13 | No | 2025-11-24 | Yes | Not Required | Not Required | Not Required | 2026-01-15
27INR0447 | Jay Flat BESS | SS Completed, FIS Started, No IA | Jay Flat BESS LLC | 59908 Novaprime 345kV | Kent | WEST | 2029-02-13 | OTH | BA | 259.36 |  | 2025-01-21 | 2025-01-28 | 2025-04-17 | 2025-01-21 |  |  |  | No
28INR0301 | Carpet Tech Solar One | SS Completed, FIS Started, No IA | CT Solar One | #59911 MHOS 345 kV | Kent | WEST | 2029-06-01 | SOL | PV | 110.7 |  | 2025-06-19 | 2025-07-07 | 2025-10-01 | 2025-06-26 |  |  |  | No |  |  | Not Required
29INR0294 | Spurland Solar III | SS Started, FIS Started, No IA | Spurland Solar III, LLC | Nova Prime Substation | Kent | WEST | 2029-12-29 | SOL | PV | 321.85 | MW Size | 2026-08-20 | 2026-08-21 |  | 2026-08-13 |  |  |  | No |  |  | Not Required
29INR0394 | Buzzer Butte Solar | SS Started, FIS Started, No IA | Origis Development, LLC | Tap 345 kV Nova prime (BUS# 59908) to Mhos (BUS# 59911) | Kent | WEST | 2030-09-01 | SOL | PV | 242.8 | FIS Request | 2026-09-15 | 2026-09-18 |  | 2026-09-15 |  |  |  | No |  |  | Not Required
30INR0164 | Buzzer Butte 2 Solar | SS Started, FIS Started, No IA | Origis Development, LLC | Tap 345 kV Nova prime (BUS# 59908) to Mhos (BUS# 59911) | Kent | WEST | 2030-09-01 | SOL | PV | 242.8 | FIS Request | 2026-09-29 | 2026-09-30 |  | 2026-09-22 |  |  |  | No |  |  | Not Required
25INR0202 | East West BESS | SS Completed, FIS Started, IA | East West Energy Storage, LLC | 7750 LCRA MOUNTAIN HOME SUB | Kerr | SOUTH | 2028-03-17 | OTH | BA | 122.6 |  | 2022-09-28 | 2022-10-06 | 2022-12-29 | 2022-09-27 |  |  | 2024-07-12 | No | Not Required | Not Required
25INR0653 | Southfork Energy Storage | SS Completed, FIS Started, No IA | Southfork Energy Storage, LLC | tap 345kV 60709 Oersted - 60616 Edison CKT 1 | Kimble | SOUTH | 2028-11-30 | OTH | BA | 306.4 |  | 2024-06-19 | 2024-07-22 | 2024-10-08 | 2024-06-13 |  | Yes |  | No
24INR0508 | White Oak King Wind | SS Completed, FIS Started, No IA | KSK Wind Farm 1, LLC | 345 kV Gauss ( Bus # 60701) | King | WEST | 2030-08-31 | WIN | WT | 606.5 |  | 2023-01-06 | 2023-03-09 | 2023-06-05 | 2023-02-07 |  | No |  | No |  |  | Not Required
25INR0401 | WOE Gyp King Wind | SS Completed, FIS Started, No IA | KSK Wind Farm 1, LLC | Tap 138kV 33798 GYP_18 – 6088 BENJ4A | King | WEST | 2030-08-31 | WIN | WT | 304.29 |  | 2023-04-18 | 2023-04-19 | 2023-07-12 | 2023-04-17 |  |  |  | No |  |  | Not Required
27INR0127 | Bigway Solar I | SS Completed, FIS Started, IA | NextEra Energy Interconnection Holdings, LLC | Tap 345kV 59904 Cottonwood - 60500 Edith Clarke Ckt #2 | King | WEST | 2027-12-31 | SOL | PV | 195.2 |  | 2024-03-12 | 2024-01-11 | 2024-03-15 | 2024-02-28 |  |  | 2025-02-15 | Yes | Not Required | Not Required | Not Required | 2025-03-19
27INR0128 | Bigway Solar II | SS Completed, FIS Started, IA | NextEra Energy Interconnection Holdings, LLC | Tap 345KV #59904 Cottonwood - #60500 Edith Clarke Ckt #2 | King | WEST | 2027-12-31 | SOL | PV | 206 |  | 2024-03-04 | 2023-12-20 | 2024-03-15 | 2024-02-28 |  | No | 2025-02-15 | Yes | Not Required | Not Required | Not Required | 2025-03-19
23INR0284 | Las Moras Battery | SS Completed, FIS Started, No IA | Las Moras Storage, LLC | 8252 Brackett 138kV | Kinney | SOUTH | 2029-07-01 | OTH | BA | 101 |  | 2021-06-01 | 2021-06-07 | 2021-08-27 | 2021-06-02 |  | No |  | No
24INR0541 | Kinney County Energy | SS Completed, FIS Started, No IA | Kinney County Energy, LLC | Tap 138kV 8252 Brackett4A - 78255 L_PINTCR8_1Y | Kinney | SOUTH | 2027-05-15 | OTH | BA | 101.2 |  | 2023-11-10 | 2023-03-27 | 2023-06-19 | 2023-10-24 15:45 |  |  |  | No
25INR0501 | Longday Solar SLF | SS Completed, FIS Started, No IA | Longday Solar | Tap138 kV 8252 Brackettville - 8260 Escondido | Kinney | SOUTH | 2027-12-15 | SOL | PV | 200.8 |  | 2023-07-22 | 2023-07-31 | 2023-10-27 | 2023-07-20 |  | No |  | No | Not Required | Not Required | Not Required
25INR0502 | Longday BESS SLF | SS Completed, FIS Started, No IA | Longday Solar | Tap 138 kV 8252 Brackettville - 8260 Escondido | Kinney | SOUTH | 2027-12-15 | OTH | BA | 0 |  | 2023-07-22 | 2023-07-31 | 2023-10-27 | 2023-07-20 |  | No |  | No
25INR0622 | Turkey Creek Solar SLF | SS Completed, FIS Started, No IA | Greenray Solar Corporation | 7425 ODLASW 138kV | Kinney | SOUTH | 2028-09-01 | SOL | PV | 180.9 | COD | 2024-10-04 | 2024-02-26 | 2024-05-24 | 2024-08-23 |  |  |  | No |  |  | Not Required |  |  |  | 2026-04-01 | 2027-07-30
25INR0623 | Turkey Creek Battery Energy Storage System SLF | SS Completed, FIS Started, No IA | Greenray Solar Corporation | 7425 ODLASW 138 kV | Kinney | SOUTH | 2028-09-01 | OTH | BA | 0 | COD | 2024-09-26 | 2024-03-29 | 2024-05-24 | 2024-09-13 |  |  |  | No | [6 empty] | 2026-04-01 | 2027-07-30
29INR0251 | Sugarberry Solar SLF | SS Completed, FIS Started, No IA | EG Sugarberry LLC | 78255 Pinto Creek 138 kV | Kinney | SOUTH | 2029-12-18 | SOL | PV | 125 |  | 2026-02-11 | 2026-02-13 | 2026-05-13 | 2026-02-12 |  |  |  | No |  |  | Not Required
29INR0252 | Sugarberry Storage SLF | SS Completed, FIS Started, No IA | EG Sugarberry LLC | 78255 Pinto Creek 138 kV | Kinney | SOUTH | 2029-12-18 | OTH | BA | 0 |  | 2026-02-12 | 2026-04-02 | 2026-05-13 | 2026-03-26 |  |  |  | No
24INR0516 | French Riviera Storage | SS Completed, FIS Started, No IA | Arana Creek Battery Storage LLC | 5646 Riviera Substation 69kV | Kleberg | COASTAL | 2028-05-01 | OTH | BA | 75 |  | 2023-01-24 | 2023-02-09 | 2023-05-05 | 2023-01-21 |  |  |  | No
26INR0143 | Santa Garcias Solar | SS Completed, FIS Started, IA | Oxy Renewable Energy LLC | Tap 138kV 8515 Alazan - 8458 Barney Davis | Kleberg | COASTAL | 2029-05-30 | SOL | PV | 265 |  | 2023-06-06 | 2023-06-28 | 2023-09-22 | 2023-06-07 |  | No | 2025-12-31 | No |  |  | Not Required
24INR0258 | Zeissel Solar | SS Completed, FIS Started, IA | ZSS Power, LLC | #60094 Joule 345kV | Knox | WEST | 2028-06-30 | SOL | PV | 451.52 |  | 2022-05-19 | 2022-02-28 | 2022-05-27 | 2022-04-25 |  |  | 2024-02-24 | Yes | Not Required | Not Required | Not Required | 2025-02-12
26INR0112 | Lemma Solar | SS Completed, FIS Started, No IA | Greening USA Corp. | 6088 Benjamin AEP 138kV | Knox | WEST | 2028-07-01 | SOL | PV | 100.61 |  | 2023-05-23 | 2023-04-07 | 2023-07-05 | 2023-05-17 |  |  |  | No |  |  | Not Required
26INR0531 | West Munday Wind | SS Completed, FIS Started, IA | Lake Creek Wind, LLC | Tap 345kV 60703 Gauss7D – 60712 Quasar | Knox | WEST | 2029-08-31 | WIN | WT | 351.91 |  | 2024-11-05 | 2024-11-19 | 2025-02-20 | 2024-11-05 |  | No | 2025-07-21 | Yes |  |  | Not Required | 2026-06-15
26INR0617 | Knox County Moore Storage | SS Completed, FIS Started, No IA | DM-KCM, LLC | 6110 Munday East Substation 138kV | Knox | WEST | 2028-06-30 | OTH | BA | 77 |  | 2024-12-17 | 2024-12-19 | 2025-02-20 | 2024-12-13 |  | No |  | No
28INR0008 | Oriole Solar | SS Completed, FIS Started, IA | Rolling Plains Solar | Tap 345kV 6076 Foxtail - 60791 Perigee | Knox | WEST | 2028-12-29 | SOL | PV | 503.91 |  | 2023-05-03 | 2023-05-15 | 2023-08-11 | 2023-05-09 |  | No | 2025-12-08 | No |  |  | Not Required
28INR0009 | Oriole BES | SS Completed, FIS Started, IA | Rolling Plains Solar | Tap 345kV 6076 Foxtail - 60791 Perigee | Knox | WEST | 2028-12-29 | OTH | BA | 150.39 |  | 2023-04-28 | 2023-05-15 | 2023-08-11 | 2023-05-09 |  | No | 2025-12-08 | No
28INR0206 | Wagon Timber Solar | SS Completed, FIS Started, No IA | Wagon Timber Solar, LLC | 6110 Munday East 138kV | Knox | WEST | 2029-09-03 | SOL | PV | 172.1 |  | 2024-12-05 | 2024-12-19 | 2025-03-10 | 2024-11-15 |  | No |  | No |  |  | Not Required
28INR0207 | Wagon Timber Storage | SS Completed, FIS Started, No IA | Wagon Timber Storage, LLC | 6110 Munday East 138kV | Knox | WEST | 2029-09-03 | OTH | BA | 53.49 |  | 2024-12-05 | 2025-01-13 | 2025-04-08 | 2024-12-05 |  | No |  | No
16INR0112 | Loma Pinta Wind | SS Completed, FIS Started, IA | Enerverse | 5705 Fowlerton 138kV | La Salle | SOUTH | 2026-12-31 | WIN | WT | 197.01 |  |  | 2015-05-18 | 2015-07-02 | 2015-05-18 |  | No | 2017-12-13 | No | Not Required | Not Required | Not Required
22INR0357 | Loma Pinta Solar | SS Completed, FIS Started, No IA | Loma Pinta Wind Energy, LLC | 5705 Fowlerton 138kV | La Salle | SOUTH | 2028-05-31 | SOL | PV | 203.06 |  | 2020-09-08 | 2020-06-03 | 2020-08-18 | 2020-05-28 |  | No |  | No |  |  | Not Required
25INR0395 | Hinkell BESS | SS Completed, FIS Started, No IA | Reveille BESS | 8612 Reveille 138kV | La Salle | SOUTH | 2027-07-01 | OTH | BA | 78.05 |  | 2023-08-15 | 2023-08-21 | 2023-11-17 | 2023-08-14 |  | No |  | No
26INR0088 | La Salle Solar | SS Completed, FIS Started, IA | La Salle Solar LLC | Tap 345kV LOBO7A (#80219) - FOWLERTONSW5 (#5709) (Cuernos 345 kV New Station) | La Salle | SOUTH | 2028-09-13 | SOL | PV | 512.6 |  | 2023-03-31 | 2023-04-19 | 2023-07-14 | 2023-04-03 |  | No | 2025-11-03 | Yes |  |  | Not Required
26INR0089 | Crescent C BESS | SS Completed, FIS Started, No IA | OCI La Salle ESS LLC | Tap 345kV LOBO7A (#80219) - FOWLERTONSW5 (#5709) CKT#2 | La Salle | SOUTH | 2028-02-12 | OTH | BA | 508.34 |  | 2023-03-15 | 2023-04-07 | 2023-07-03 | 2023-03-15 |  | Yes |  | No
21INR0221 | Samson Solar 1 | SS Completed, FIS Completed, IA | Samson Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2026-12-31 | SOL | PV | 250 |  | 2019-05-13 | 2018-11-20 | 2019-01-04 | 2019-05-03 | 2020-06-09 | No | 2020-08-26 | Yes | Not Required | Not Required | Not Required | 2020-08-26 | 2020-10-15 | 2020-10-26 |  |  | 2021-06-30 | 2021-08-31
21INR0490 | Samson Solar 2 | SS Completed, FIS Completed, IA | Samson Solar Energy II LLC | 345 kV TTRSW 11688 | Lamar | NORTH | 2026-12-31 | SOL | PV | 203 |  | 2020-01-14 | 2020-01-13 | 2019-01-04 | 2020-01-13 | 2020-06-09 |  | 2020-08-27 | Yes | Not Required | Not Required | Not Required | 2021-04-12 | 2022-08-12 | 2022-08-12 |  |  | 2024-08-19 | 2024-10-14
21INR0491 | Samson Solar 3 | SS Completed, FIS Completed, IA | Samson Solar Energy III LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2026-12-31 | SOL | PV | 250 |  | 2020-01-14 | 2020-01-13 | 2019-01-04 | 2020-01-13 | 2020-06-09 |  | 2020-08-27 | Yes | Not Required | Not Required | Not Required | 2020-08-27 | 2020-10-15 | 2020-10-26 |  |  | 2021-06-30 | 2021-10-26
22INR0202 | Delilah Solar 1 | SS Completed, FIS Completed, IA | Delilah Solar Energy LLC | tap both 345kV 1685 FarmersVl - 1695 Moses ckts | Lamar | NORTH | 2026-12-31 | SOL | PV | 300 |  | 2019-05-13 | 2018-11-20 | 2019-01-03 | 2019-05-03 | 2020-06-09 | No | 2020-12-22 | Yes | Not Required | Not Required | Not Required | 2021-03-23 | 2021-03-23 | 2021-04-27 |  |  | 2023-07-11 | 2024-03-21
22INR0203 | Delilah Solar 2 | SS Completed, FIS Completed, IA | Delilah Solar Energy II LLC | 345 kV TTRSW 11688 | Lamar | NORTH | 2026-12-31 | SOL | PV | 317.58 |  | 2019-05-13 | 2018-11-20 | 2019-01-03 | 2019-05-03 | 2020-06-09 | No | 2020-12-22 | Yes | Not Required | Not Required | Not Required | 2021-03-23 | 2022-08-12 | 2022-08-12 |  |  | 2024-10-29 | 2025-01-13
22INR0314 | Lan Solar SLF | SS Completed, FIS Started, No IA | BR Solar, LLC | Tap 345kV 1729 Valley South – 1692 Paris Switch | Lamar | NORTH | 2028-08-26 | SOL | PV | 182.2 |  | 2021-10-12 | 2020-05-01 | 2020-07-07 | 2021-01-04 |  | No |  | No | Not Required | Not Required | Not Required
23INR0026 | Baker Branch Solar | SS Completed, FIS Completed, IA | Mockingbird Solar Center, LLC | tap 345kV 1692 Paris - 1690 Valley | Lamar | NORTH | 2026-09-30 | SOL | PV | 469.42 |  | 2020-04-09 | 2020-03-26 | 2020-06-04 | 2020-03-05 | 2023-10-30 |  | 2022-02-14 | Yes | Not Required | Not Required | Not Required | 2023-10-03 | 2023-10-30 | 2023-10-30 |  |  | 2024-04-01 | 2024-04-10
23INR0225 | MRG GOODY SOLAR | SS Completed, FIS Completed, IA | MRG GOODY SOLAR PROJECT, LLC | Tap 138 kV Toco Switch (#1700) – Paris Switch (#1693) | Lamar | NORTH | 2026-08-28 | SOL | PV | 170.82 |  | 2022-04-04 | 2021-03-16 | 2021-06-11 | 2022-03-22 | 2025-06-17 | No | 2023-11-07 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2025-07-31 | 2025-07-31 |  |  | 2026-02-06 | 2026-03-27
23INR0441 | Bug Tussle Wind Project | SS Completed, FIS Started, IA | Bug Tussle Wind, LLC | Tap 1729 Valley South and 1692 Paris | Lamar | NORTH | 2028-09-18 | WIN | WT | 396.8 |  | 2022-08-30 | 2022-01-13 | 2022-04-11 | 2022-08-16 |  | No | 2024-07-10 | No |  |  | Not Required
23INR0486 | Lamar Unit 1 Repower | SS Completed, FIS Started, No IA | La Frontera Holdings, LLC | 1692 Paris Switch Station 345kV | Lamar | NORTH | 2027-12-18 | GAS | CC | 66 |  | 2023-06-26 | 2022-06-02 | 2022-08-30 | 2023-05-15 20:25 |  |  |  | No
24INR0186 | Rowdy Creek Solar | SS Completed, FIS Completed, IA | Rowdy Creek Solar LLC | Woodfin Switch (#1465) 345kV | Lamar | NORTH | 2027-12-29 | SOL | PV | 351.78 |  | 2021-12-13 | 2022-01-28 | 2022-04-27 | 2022-01-25 | 2026-09-17 | No | 2025-05-02 | Yes |  |  | Not Required | 2025-07-29
24INR0262 | Lan Battery SLF | SS Completed, FIS Started, No IA | BR Solar, LLC | Tap 345kV 1729 Valley South – 1692 Paris Switch | Lamar | NORTH | 2028-08-26 | OTH | BA | 0 |  | 2022-04-04 | 2022-06-10 | 2022-09-06 | 2022-04-27 |  | No |  | No
24INR0305 | MRG Goody Storage | SS Completed, FIS Completed, IA | MRG Goody Solar Project LLC | Tap 138 kV Toco Switch (#1700) – Paris Switch (#1693) | Lamar | NORTH | 2026-08-28 | OTH | BA | 52.29 |  | 2022-04-07 | 2022-05-10 | 2022-08-05 | 2022-04-11 | 2025-06-17 | No | 2023-11-07 | Yes | Not Required | Not Required |  | 2025-02-12 | 2025-07-31 | 2025-07-31 |  |  | 2026-02-06 | 2026-03-27
25INR0164 | Star Dairy Solar | SS Completed, FIS Completed, IA | Star Dairy Solar LLC | Tap 345kV 1692 PARIS_SW1_5 -- 11699 WOODARD_5 | Lamar | NORTH | 2027-07-12 | SOL | PV | 115.61 |  | 2022-11-18 | 2022-11-23 | 2023-02-17 | 2022-11-09 | 2026-09-16 | No | 2024-12-09 | No | Not Required | Not Required | Not Required
25INR0334 | Star Dairy Storage | SS Completed, FIS Completed, IA | Star Dairy Storage | Tap 345kV 1692 PARIS_SW1_5 -- 11699 WOODARD_5 | Lamar | NORTH | 2027-07-12 | OTH | BA | 205.24 |  | 2023-04-17 | 2023-04-19 | 2023-07-14 | 2023-04-11 | 2026-09-16 | No | 2024-12-09 | No | Not Required | Not Required
25INR0368 | Echols Grove Solar | SS Completed, FIS Completed, IA | Echols Grove, LLC | Tap 138kV Hawk Hollow Switch (#11768) and Lamar Blossom Switch (#11770) | Lamar | NORTH | 2027-06-30 | SOL | PV | 201.56 | COD | 2023-03-17 | 2023-04-07 | 2023-07-05 | 2023-03-22 | 2026-06-18 | No | 2024-07-06 | Yes | Not Required | Not Required | Not Required | 2026-07-08
25INR0505 | Mud Cat Solar SLF | SS Completed, FIS Started, No IA | Mud Cat Solar, LLC | Tap 138KV 11768 Hawk Hollow – 1768 Deport | Lamar | NORTH | 2028-09-18 | SOL | PV | 100.5 |  | 2024-05-13 | 2023-10-20 | 2024-01-16 | 2024-05-14 |  | No |  | No |  |  | Not Required
25INR0507 | Mud Cat Storage SLF | SS Completed, FIS Started, No IA | Mud Cat Solar, LLC | 11768 Hawk Hollow – 1768 Deport 138kV | Lamar | NORTH | 2028-09-18 | OTH | BA | 0 |  | 2024-05-13 | 2023-10-20 | 2024-01-16 | 2024-05-14 |  | No |  | No
26INR0184 | Arc Energy Storage | SS Completed, FIS Completed, No IA | Paris Energy Storage, LLC | Tap 138kV 1693 Paris Switch - 11806 ENLOE T8 | Lamar | NORTH | 2028-06-30 | OTH | BA | 204.5 |  | 2023-06-19 | 2023-07-31 | 2023-10-27 | 2023-07-25 | 2025-05-02 |  |  | No
26INR0469 | Roxton Storage | SS Completed, FIS Completed, IA | Roxton Solar, LLC | Tap 138 KV Bois Pump (1835) - Brookston (1833) | Lamar | NORTH | 2028-07-21 | OTH | BA | 102 | SFS/NtP | 2024-05-22 | 2024-11-26 | 2025-02-03 | 2024-11-05 | 2026-03-10 |  | 2026-09-03 | Yes |  |  |  | 2026-09-08
26INR0470 | Roxton Solar | SS Completed, FIS Completed, IA | Roxton Solar, LLC | Tap 138 KV Bois Pump (1835) - Brookston (1833) | Lamar | NORTH | 2028-07-21 | SOL | PV | 116.8 | SFS/NtP | 2024-11-20 | 2024-11-26 | 2025-02-03 | 2024-11-05 | 2026-03-10 | No | 2026-09-03 | Yes |  |  | Not Required | 2026-09-08
27INR0409 | Baker Branch BESS | SS Completed, FIS Started, No IA | Mockingbird Storage Center, LLC | Pacific Switch (PACSW) 345 kV Bus 11683 | Lamar | NORTH | 2029-12-31 | OTH | BA | 287.22 |  | 2025-06-13 | 2025-06-19 | 2025-09-11 | 2025-06-10 |  | No |  | No
28INR0087 | North Royal Thermal (TEF- Due Diligence) | SS Completed, FIS Started, No IA | Invenergy Energy Transition Development LLC | Tap 345kV 1695 MOSES_5 - 11699 WOODARD_5 | Lamar | NORTH | 2030-08-01 | GAS | GT | 479 |  | 2025-02-05 | 2024-06-13 | 2024-09-10 | 2024-12-17 |  |  |  | No
30INR0002 | Southeast Oklahoma Pumped Storage | SS Completed, FIS Started, No IA | Apex Energy Solutions, LLC | 1692 Paris Switch 345kV | Lamar | NORTH | 2030-01-01 | WAT | OT | 1232 |  | 2023-03-28 | 2022-08-05 | 2022-11-01 | 2023-03-10 |  |  |  | No
24INR0069 | Triple B Solar Alt#2 | SS Completed, FIS Started, No IA | Triple B Solar LLC | Tap 138kV 7066 Adamsville - 7064 Lampasas | Lampasas | NORTH | 2028-07-01 | SOL | PV | 150 |  | 2021-12-15 | 2021-06-10 | 2021-09-01 | 2021-11-15 |  |  |  | No |  |  | Not Required
24INR0494 | Hana Springs BESS | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II LLC | 7064 LAMPASAS 138KV | Lampasas | NORTH | 2028-05-15 | OTH | BA | 100.8 |  | 2022-11-22 | 2022-11-23 | 2023-02-17 | 2022-11-18 |  |  |  | No | Not Required | Not Required | 2025-10-02
24INR0543 | Thomas Cameron BESS | SS Completed, FIS Completed, IA | Thomas Cameron BESS LLC | Tap 345kV 3424 BUCKHORN SWITCH - 3422 KILLEEN SWITCH | Lampasas | NORTH | 2029-04-28 | OTH | BA | 205.5 |  | 2023-06-01 | 2023-06-07 | 2023-09-01 | 2023-06-02 | 2024-07-23 | Yes | 2024-10-30 | Yes | Not Required | Not Required |  | 2025-09-12
25INR0666 | GIBSON BRANCH BESS | SS Completed, FIS Started, No IA | Gibson Branch BESS LLC | 7064 Lampasas Substation 138kV | Lampasas | NORTH | 2028-01-15 | OTH | BA | 142.9 |  | 2024-05-09 | 2024-05-20 | 2024-08-14 | 2024-04-24 |  |  |  | No
26INR0147 | Seven Springs Solar | SS Completed, FIS Started, IA | Hancock Springs, LLC | Tap 7061 COPPERAS COVE 7260 Kempner 138kV | Lampasas | NORTH | 2028-05-26 | SOL | PV | 145 |  | 2023-08-18 | 2023-09-22 | 2023-12-14 | 2023-09-05 |  |  | 2025-08-28 | Yes | Not Required | Not Required | Not Required
28INR0277 | Aurora Energy Storage | SS Completed, FIS Completed, No IA | Aurora Energy Storage, LLC | Tap 345kV --- KILL_SS_5 (3422) --- BUCK_H_5 (3424) | Lampasas | NORTH | 2028-09-26 | OTH | BA | 306.2 |  | 2025-02-03 | 2025-02-14 | 2025-05-13 | 2025-02-05 | 2026-05-04 |  |  | No
28INR0324 | Barkley Creek Solar | SS Completed, FIS Started, No IA | 174 Power Global Properties, LLC | Tap 345 kV Line from Russel Gap Switch (Bus# 3348) - Killeen Switch (Bus# 3422) | Lampasas | NORTH | 2029-10-15 | SOL | PV | 312.37 |  | 2025-08-12 | 2025-08-26 | 2025-09-30 | 2025-08-19 |  |  |  | No |  |  | Not Required
28INR0462 | Senterfitt Solar | SS Completed, FIS Started, No IA | AETS Development Holdings LLC | Tap 138 kV 7080 Lometa - 7064 Lampasas | Lampasas | NORTH | 2029-07-03 | SOL | PV | 68.39 |  | 2025-11-17 | 2026-03-11 | 2026-06-05 | 2026-03-11 |  |  |  | No | Not Required | Not Required | Not Required
30INR0037 | Solgen Solar | SS Completed, FIS Started, No IA | Lampasas Hybrid Energy LLC | 7066 Adamsville 138kV | Lampasas | NORTH | 2029-08-30 | SOL | PV | 160.2 |  | 2025-12-16 | 2025-04-25 | 2025-07-23 | 2025-11-25 |  |  |  | No |  |  | Not Required
30INR0038 | Solgen Storage | SS Completed, FIS Started, No IA | Lampasas Hybrid Energy LLC | 7066 Adamsville 138kV | Lampasas | NORTH | 2029-08-30 | OTH | BA | 150.3 |  | 2025-12-16 | 2025-04-25 | 2025-07-23 | 2025-11-25 |  |  |  | No
27INR0091 | Oak Tree Energy Storage | SS Completed, FIS Started, IA | Live Oak Energy Storage, LLC | Tap Shaula (#5380) – South Texas (#5915) | Lavaca | SOUTH | 2030-09-20 | OTH | BA | 310.2 |  | 2023-11-14 | 2023-12-04 | 2024-02-21 | 2023-11-21 |  |  | 2026-05-26 | No
21INR0371 | Pecan Prairie South | SS Completed, FIS Completed, IA | ConnectGen Operating LLC | CTT Yellow Wolf, bus # 79007 | Leon | NORTH | 2027-05-01 | SOL | PV | 132.98 |  | 2019-08-27 | 2019-08-16 | 2019-11-05 | 2019-08-22 | 2026-03-13 | No | 2021-02-21 | Yes | Not Required | Not Required | Not Required | 2026-04-24 | 2026-05-19 | 2026-04-24
21INR0428 | Pecan Prairie North | SS Completed, FIS Completed, IA | CG Leon County II LLC | CTT Yellow Wolf, bus # 79007 | Leon | NORTH | 2027-05-01 | SOL | PV | 324.11 |  | 2019-08-16 | 2019-09-23 | 2019-12-10 | 2019-09-11 | 2026-03-13 | No | 2021-02-26 | Yes | Not Required | Not Required | Not Required | 2025-08-20 | 2026-05-19 | 2026-04-24
24INR0422 | Hollow Branch Creek Solar | SS Completed, FIS Started, IA | Hollow Branch Creek Solar LLC | Tap 345kV 3390 Jewett - 44645 Singleton | Leon | NORTH | 2028-06-30 | SOL | PV | 460 |  | 2022-09-06 | 2022-09-02 | 2022-11-29 | 2022-08-15 |  | Yes | 2024-10-22 | Yes | Not Required | Not Required | Not Required | 2025-09-22
25INR0230 | Great Rock BESS | SS Completed, FIS Started, IA | Great Rock Storage LLC | Tap 345kV 46020 Limestone - 967 Gibbon Creek Ckt 18 | Leon | NORTH | 2027-12-20 | OTH | BA | 300.9 |  | 2022-10-19 | 2022-11-07 | 2023-02-04 | 2022-10-19 |  | No | 2024-08-23 | No | [6 empty] | 2026-10-20 | 2027-12-20
25INR0342 | Nickel Spruce Solar | SS Completed, FIS Started, No IA | Nickel Spruce Solar LLC | Tap 138kV 6735 Pleasant Springs Switching Station - 6736 Middl | Leon | NORTH | 2027-12-15 | SOL | PV | 150 |  | 2023-11-10 | 2023-01-30 | 2023-04-28 | 2023-10-31 17:43 |  |  |  | No |  |  | Not Required
25INR0513 | Kahla Storage | SS Completed, FIS Started, No IA | BT Kahla Storage, LLC | Tap 345kV 46020 Limestone 967 Gibbons Creek Circuit 50 | Leon | NORTH | 2028-12-29 | OTH | BA | 200.9 |  | 2023-08-16 | 2023-08-21 | 2023-11-17 | 2023-08-15 |  | No |  | No
25INR0693 | Leon BESS | SS Completed, FIS Started, No IA | Leon BESS | Tab 138kv 3355 Grapeland_Magnolia - 3357 Pleasant_Springs. | Leon | NORTH | 2028-02-16 | OTH | BA | 153.7 |  | 2024-11-13 | 2024-11-26 | 2025-02-18 | 2024-11-18 |  | No |  | No
26INR0632 | Dempsey Solar SLF | SS Completed, FIS Started, No IA | Dempsey Solar LLC | Tap 138 KV Ridge (#37)-Robertson (#32) line; BEPC | Leon | NORTH | 2028-09-08 | SOL | PV | 245.34 |  | 2025-02-06 | 2025-02-25 | 2025-05-20 | 2025-03-20 |  |  |  | No |  |  | Not Required
27INR0092 | Pecan BESS | SS Completed, FIS Completed, No IA | Gransolar Texas Three LLC | (PSSE BUS# 47) HILTOPLKS8 138kV | Leon | NORTH | 2028-12-31 | OTH | BA | 157.12 |  | 2023-10-11 | 2023-10-25 | 2024-01-22 | 2023-10-12 | 2025-07-29 |  |  | No
28INR0238 | Dempsey Storage SLF | SS Completed, FIS Started, No IA | Dempsey Storage LLC | Tap the 138 KV Ridge (#37)-Robertson (#32) line; BEPC | Leon | NORTH | 2028-09-08 | OTH | BA | 0 |  | 2025-02-06 | 2025-02-25 | 2025-05-20 | 2025-03-20 |  |  |  | No
30INR0091 | BM Great Rock Energy Center | SS Completed, FIS Started, No IA | Black Mountain Energy Storage II | Tap <345kV> <967> <GIBN_CREK_5> - <46020> <LIMEST_POI_5> Ckt<18> and <345kV> <79007> < YELLOW WOLF> - <46020> <LIMEST_POI_5> Ckt<50> | Leon | NORTH | 2029-05-15 | GAS | CC | 1981.2 |  | 2026-02-27 | 2026-03-03 | 2026-05-25 | 2026-02-19 |  |  |  | No
21INR0260 | Chariot Storage | SS Completed, FIS Started, No IA | Chariot Storage LLC | tap 69kV 99 Ben Hur - 107 Prairie Hill | Limestone | NORTH | 2028-02-29 | OTH | BA | 50 |  | 2019-02-19 | 2019-03-06 | 2019-05-24 | 2019-02-11 |  | No |  | No | Not Required | Not Required
23INR0367 | Fewell Solar | SS Completed, FIS Completed, IA | Fewell Solar LLC | Tap 138kV 3597 Groesbeck - 3634 Groesbeck Main | Limestone | NORTH | 2028-05-15 | SOL | PV | 203.5 |  | 2022-02-28 | 2021-08-19 | 2021-11-05 | 2022-02-17 | 2023-04-17 | No | 2023-08-18 | Yes | Not Required | Not Required | Not Required | 2023-08-28
24INR0127 | Naduah Solar | SS Completed, FIS Started, No IA | Gransolar Texas Fifteen, LLC | Tap 69kV Ben Hur (99) - Prairie Hill (107) | Limestone | NORTH | 2028-04-15 | SOL | PV | 77.6 | COD | 2022-06-17 | 2021-09-27 | 2021-12-09 | 2022-06-06 |  | No |  | No |  |  | Not Required
24INR0298 | Leighton Solar | SS Completed, FIS Started, IA | Lavender Solar LLC | 98 Fernleaf 138 kV | Limestone | NORTH | 2027-12-06 | SOL | PV | 181 |  | 2022-04-27 | 2022-05-11 | 2022-08-05 | 2022-03-16 |  | No | 2024-05-28 | Yes | Not Required | Not Required | Not Required | 2025-02-13
25INR0021 | Findley Solar | SS Completed, FIS Started, No IA | Adon Texas Sixteen LLC | Tap 69kV #107 Prairie Hill - #99 Ben Hur | Limestone | NORTH | 2028-01-01 | SOL | PV | 50.34 |  | 2022-07-05 | 2021-10-05 | 2021-12-10 | 2022-05-24 |  | No |  | No |  |  | Not Required
25INR0199 | Bonham Solar SLF | SS Completed, FIS Completed, IA | J&J Solar Ranch LLC | TAP 138 kV MEXIA_2_1_8 3632 - GROES_SE1_8 3634 | Limestone | NORTH | 2027-04-06 | SOL | PV | 138.4 |  | 2022-11-09 | 2022-11-15 | 2023-02-09 | 2022-10-31 | 2026-06-26 | No | 2024-08-07 | Yes | Not Required | Not Required | Not Required | 2025-05-09 | 2026-07-20 | 2026-07-20
26INR0619 | Bonham Storage SLF | SS Completed, FIS Completed, No IA | J&J Solar Ranch LLC | Tap 138kV 3632 Mexia_Main - 3634 Groesbeck_Main | Limestone | NORTH | 2027-07-01 | OTH | BA | 104.92 |  | 2025-01-16 | 2025-01-28 | 2025-04-15 | 2025-01-16 | 2026-09-17 | No |  | Yes
28INR0013 | Varadero Solar | SS Completed, FIS Started, IA | NextEra Energy Interconnection Holdings, LLC | #68092 Liberty Station 345kV | Limestone | NORTH | 2029-04-01 | SOL | PV | 206 |  | 2023-06-26 | 2023-07-10 | 2023-10-03 | 2023-07-05 |  | Yes | 2025-12-12 | Yes |  |  | Not Required | 2026-04-20
28INR0048 | Findley BESS | SS Completed, FIS Completed, No IA | Adon Texas Sixteen LLC | Tap 69kV #107 Prairie Hill - #99 Ben Hur | Limestone | NORTH | 2028-01-01 | OTH | BA | 51.74 |  | 2023-12-23 | 2024-02-07 | 2024-04-30 | 2024-01-16 | 2026-01-21 | No |  | No | Not Required | Not Required
22INR0467 | Bird Dog Energy Storage | SS Completed, FIS Completed, IA | VESI 37 LLC | 5669 Argenta 69kV | Live Oak | SOUTH | 2026-10-23 | OTH | BA | 60.4 |  | 2022-06-02 | 2021-02-04 | 2021-04-19 | 2022-05-19 | 2025-06-18 |  | 2024-02-16 | Yes | Not Required | Not Required |  | 2024-02-16 | 2025-08-07 | 2025-09-22 |  |  | 2026-08-05 | 2026-08-28
23INR0487 | Brightside Solar Alt POI | SS Completed, FIS Not Started, IA | Brightside Solar, LLC | 8156 Charter Substation 138kV | Live Oak | SOUTH | 2026-08-14 | SOL | PV | 50 |  |  | 2022-05-16 | 2022-08-05 |  |  |  | 2020-06-11 | Yes |  |  | Not Required
25INR0621 | Anagram Solar | SS Completed, FIS Started, No IA | Anagram Solar | 8156 Charter 138 kV | Live Oak | SOUTH | 2027-12-31 | SOL | PV | 130.56 |  | 2025-01-07 | 2024-04-09 | 2024-07-05 | 2025-01-02 |  |  |  | No |  |  | Not Required
27INR0375 | Buck Ranch Solar SLF | SS Completed, FIS Started, No IA | Buck Ranch Solar, LLC | 5690 WEST GEORGE WEST SUB 69kV | Live Oak | SOUTH | 2028-08-02 | SOL | PV | 40.8 |  | 2024-11-13 | 2024-12-19 | 2025-02-03 | 2024-12-16 |  |  |  | No |  |  | Not Required
27INR0376 | Buck Ranch Storage SLF | SS Completed, FIS Started, No IA | Buck Ranch Solar, LLC | 5690 WEST GEORGE WEST SUB 69kV | Live Oak | SOUTH | 2028-08-09 | OTH | BA | 40.8 |  | 2024-11-13 | 2025-01-28 | 2025-04-15 | 2024-12-16 |  |  |  | No
26INR0529 | Electric E - West Texas Generation | SS Completed, FIS Started, No IA | Electric E Power Marketing | #11166 ENPOD 138kV | Loving | WEST | 2028-04-09 | GAS | GT | 43.64 |  | 2024-08-19 | 2024-10-18 | 2025-01-10 | 2024-10-10 |  |  |  | No
30INR0099 | Quadspring BESS | SS Completed, FIS Started, No IA | Quadspring BESS, LLC | 138 kV ANDRANCHT_8(#1081) - Loving_8(#1092) | Loving | WEST | 2030-06-30 | OTH | BA | 200.7 |  | 2026-06-08 | 2026-06-12 | 2026-09-04 | 2026-06-08 |  |  |  | No
23INR0310 | Dunkel BESS | SS Completed, FIS Started, No IA | Momentum Energy Storage Partners | 59156 Yellow House Canyon 115kV | Lubbock | PANHANDLE | 2027-11-02 | OTH | BA | 226.4 |  | 2022-06-10 | 2022-06-27 | 2022-09-22 | 2022-06-20 |  |  |  | No
25INR0131 | SOSA Storage | SS Completed, FIS Completed, IA | Sosa Energy Center, LLC | Tap 138kV 25 North Zulch - 47 Hilltop Lakes | Madison | NORTH | 2027-07-20 | OTH | BA | 154.63 |  | 2022-07-21 | 2022-07-25 | 2022-10-20 | 2022-07-21 | 2026-07-13 | No | 2023-12-05 | Yes | Not Required | Not Required |  | 2025-02-13
25INR0176 | Masava Storage | SS Completed, FIS Started, No IA | Savannah Oaks Solar Project, LLC | tap 345 kV 46020 Limestone Plant - 967 Gibbons Creek ckt 18 | Madison | NORTH | 2028-09-30 | OTH | BA | 257.04 |  | 2022-08-23 | 2022-09-02 | 2022-11-30 | 2022-08-17 |  |  |  | No
25INR0286 | Savannah Oaks Solar | SS Completed, FIS Started, No IA | Savannah Oaks Solar Project LLC | Tap 345kV 46020 Limestone Plant - 967 Gibbons Creek | Madison | NORTH | 2028-09-30 | SOL | PV | 201.19 |  | 2022-12-19 | 2023-01-03 | 2023-03-30 | 2022-12-02 |  |  |  | No |  |  | Not Required
26INR0411 | Tex-Bar ESS | SS Completed, FIS Completed, IA | Tex-Bar ESS LLC | Tap 345kV JEWETT_S5 (#3390) -- SINGLETON (#44645) | Madison | NORTH | 2029-09-08 | OTH | BA | 201.5 |  | 2024-02-14 | 2024-03-22 | 2024-06-19 | 2024-02-26 | 2024-09-26 | Yes | 2025-12-26 | No
24INR0275 | Picadillo BESS | SS Completed, FIS Completed, IA | Black Mountain Energy Storage II | 23837 Buffalo 138kV | Martin | WEST | 2028-05-15 | OTH | BA | 100.83 |  | 2022-02-25 | 2022-03-07 | 2022-06-02 | 2022-02-28 | 2023-06-13 |  | 2024-01-23 | No | Not Required | Not Required | 2025-10-02
25INR0396 | Stewart Grady BESS | SS Completed, FIS Started, No IA | Grady BESS | Tap 138kV 11368 Expanse Switch – 23841 Sale Ranch | Martin | WEST | 2029-04-17 | OTH | BA | 150.5 |  | 2023-05-22 | 2023-05-26 | 2023-08-22 | 2023-05-01 |  | No |  | No
26INR0247 | Jane Storage Energy Center | SS Completed, FIS Started, No IA | NMRE Holdings, LLC | 59901 Grelton 345 kV | Martin | WEST | 2030-11-01 | OTH | BA | 240.6 |  | 2023-08-13 | 2023-09-08 | 2023-12-01 | 2023-08-28 |  |  |  | Yes | Not Required | Not Required
20INR0155 | Peyton Creek Wind II | SS Completed, FIS Completed, IA | RWE Renewables Development, LLC | 42400 Refuge 345kV | Matagorda | COASTAL | 2026-12-31 | WIN | WT | 241.2 |  | 2019-01-30 | 2018-08-21 | 2018-11-02 | 2019-03-14 | 2024-06-25 | No | 2026-04-29 | Yes | Not Required | Not Required | Not Required | 2024-06-25 | 2024-07-24 | 2024-07-24 |  |  | 2024-12-30 | 2025-02-05
22INR0342 | Matagorda Solar | SS Completed, FIS Completed, IA | Matagorda Solar Farm, LLC | 5555 Shropshire 69kV | Matagorda | COASTAL | 2027-08-25 | SOL | PV | 101 |  | 2020-12-08 | 2020-05-01 | 2020-07-15 | 2020-11-05 | 2021-09-14 |  | 2022-06-08 | Yes |  |  | Not Required | 2025-02-12
23INR0057 | Duffy Solar | SS Completed, FIS Started, IA | Duffy Project Co LLC | Tap 345kV WAP to STP CKT39 (PTI# 5915-44000 CKT 39) | Matagorda | COASTAL | 2027-12-31 | SOL | PV | 502.46 |  | 2021-02-05 | 2020-09-11 | 2020-11-19 | 2021-02-04 |  | Yes | 2023-04-12 | Yes |  |  | Not Required | 2023-05-24
23INR0466 | Shoshana Storage | SS Completed, FIS Started, No IA | Shoshana Storage Project LLC | Tap STP – Refuge ckt 27 | Matagorda | COASTAL | 2028-05-30 | OTH | BA | 221 |  | 2022-05-31 | 2022-03-30 | 2022-06-26 | 2022-05-16 |  | Yes |  | No
24INR0020 | Percy Farm Solar | SS Completed, FIS Started, No IA | Percy Farm Solar 1, LLC | Tap 345kV 8123 Blessing - 5915 STP | Matagorda | COASTAL | 2029-05-31 | SOL | PV | 198.63 |  | 2021-08-05 | 2021-03-16 | 2021-06-11 | 2021-07-21 |  | No |  | No | Not Required | Not Required | Not Required
24INR0337 | Eldora Solar | SS Completed, FIS Started, IA | Eldora Energy LLC | Tap 345 kV 5915 South Texas Project – 44200 Hillje Ckt 1 | Matagorda | COASTAL | 2028-07-02 | SOL | PV | 200.94 |  | 2022-05-31 | 2022-06-10 | 2022-09-06 | 2022-06-01 |  |  | 2023-11-15 | Yes | Not Required | Not Required | Not Required | 2023-12-18
24INR0338 | Eldora BESS | SS Completed, FIS Completed, IA | Eldora Energy LLC | 345 kV South Texas Project (Bus# 5915) – Hillje (Bus# 44200) Transmission Line Ckt 1 | Matagorda | COASTAL | 2028-07-02 | OTH | BA | 201.31 |  | 2022-06-03 | 2022-06-10 | 2022-09-06 | 2022-06-01 | 2023-12-18 |  | 2023-11-15 | Yes | Not Required | Not Required |  | 2023-12-18
25INR0232 | Isaac Solar | SS Completed, FIS Completed, IA | Industrial Bravo Project LLC | 8114 Conoco 138kV | Matagorda | COASTAL | 2027-04-15 | SOL | PV | 50.73 |  | 2022-10-24 | 2022-11-07 | 2023-02-03 | 2022-10-27 | 2025-12-18 | No | 2023-10-18 | Yes | Not Required | Not Required | Not Required | 2023-10-31 | 2026-01-29 | 2026-01-29
25INR0271 | City Breeze BESS | SS Completed, FIS Completed, IA | City Breeze BESS LLC | 8111 MAGILL4A 138KV | Matagorda | COASTAL | 2027-03-18 | OTH | BA | 143.1 |  | 2022-12-14 | 2022-12-15 | 2023-03-11 | 2022-12-06 | 2026-06-02 | No | 2024-05-15 | Yes | Not Required | Not Required |  | 2024-05-25 | 2026-07-30 | 2026-07-30
25INR0405 | Pledgor BESS | SS Completed, FIS Completed, No IA | Pledgor BESS | Tap Gulftie (43340) – Pledger (43120) circuit 60 | Matagorda | COASTAL | 2028-04-06 | OTH | BA | 100.33 |  | 2023-04-26 | 2023-05-03 | 2023-07-31 | 2023-04-25 | 2024-08-27 | No |  | No
26INR0250 | Duffy BESS | SS Completed, FIS Completed, IA | Duffy Energy Storage LLC | Tap 345kV WAP to STP CKT39 (PTI# 5915-44000 CKT 39) | Matagorda | COASTAL | 2026-12-31 | OTH | BA | 241.05 |  | 2023-08-14 | 2023-08-21 | 2023-11-17 | 2023-08-08 | 2026-03-03 | No | 2025-07-28 | Yes |  |  |  | 2025-08-04 | 2026-04-27 | 2026-04-27
26INR0258 | Running Iron Solar | SS Completed, FIS Started, No IA | Running Iron Solar, LLC | Tap 138kV Conoco 8138 - Black Cat 80124 | Matagorda | COASTAL | 2028-10-16 | SOL | PV | 204.74 |  | 2023-10-04 | 2023-10-25 | 2024-01-22 | 2023-10-19 |  | No |  | No |  |  | Not Required
26INR0347 | Midfield PV Project SLF | SS Completed, FIS Started, No IA | HQC Solar Holdings 1, LLC | Tap 138kV 8121 Blessing - 8125 Lolita | Matagorda | COASTAL | 2028-07-01 | SOL | PV | 150 |  | 2023-11-13 | 2023-12-04 | 2024-02-27 | 2023-11-28 |  |  |  | No |  |  | Not Required
26INR0362 | Midfield BESS Project SLF | SS Completed, FIS Started, No IA | HQC Solar Holdings 1, LLC | Tap 138kV 8121 Blessing - 8125 Lolita | Matagorda | COASTAL | 2028-07-01 | OTH | BA | 0 |  | 2024-04-09 | 2024-05-20 | 2024-07-22 | 2024-05-07 |  |  |  | No
26INR0376 | Blackcat Storage | SS Completed, FIS Started, No IA | Matagorda ESS, LLC | 138kV Blackcat Substation (#80124) | Matagorda | COASTAL | 2027-12-31 | OTH | BA | 200.59 |  | 2024-01-02 | 2024-01-11 | 2024-04-08 | 2023-11-30 |  | No |  | No | Not Required | Not Required
26INR0429 | Post Trail Energy | SS Completed, FIS Started, No IA | Post Trail Energy, LLC | Tap 138kV Conoco 8138 - Black Cat 80124 | Matagorda | COASTAL | 2028-10-16 | OTH | BA | 103.5 |  | 2024-08-26 | 2024-09-10 | 2024-12-08 | 2024-08-26 |  | No |  | No
27INR0120 | Solar Star Bay City Storage | SS Completed, FIS Started, No IA | Solar Star Bay City Storage | Tap 138kV Conoco (#8138) – Black Cat (#80124) | Matagorda | COASTAL | 2029-02-27 | OTH | BA | 206.27 |  | 2024-12-06 | 2023-12-20 | 2024-03-11 | 2024-11-25 |  |  |  | No
27INR0141 | Bluefox Solar 1 | SS Completed, FIS Started, No IA | Industrial November Project LLC | #8754 Zoisite 345kV | Matagorda | COASTAL | 2029-05-31 | SOL | PV | 402.6 |  | 2024-03-12 | 2024-03-22 | 2024-06-19 | 2024-02-21 |  | Yes |  | No |  |  | Not Required
27INR0557 | STP Unit2 High Pressure Turbine Upgrade | SS Completed, FIS Started, No IA | Constellation South Texas, LLC | 5915 SO_TEX__345A 345 kV | Matagorda | COASTAL | 2027-04-23 | NUC | ST | 1336.52 |  | 2026-04-28 | 2026-04-30 | 2026-07-24 | 2026-04-29 |  |  |  | No |  |  | 2026-09-10
28INR0063 | Bluefox Solar 2 | SS Completed, FIS Started, No IA | Industrial November Project LLC | #8754 Zoisite 345kV | Matagorda | COASTAL | 2030-01-17 | SOL | PV | 401.8 |  | 2024-03-12 | 2024-03-22 | 2024-06-19 | 2024-02-21 |  | Yes |  | No |  |  | Not Required
28INR0064 | Bluefox Solar 3 | SS Completed, FIS Started, No IA | Industrial November Project LLC | #8754 Zoisite 345kV | Matagorda | COASTAL | 2030-04-18 | SOL | PV | 201.8 |  | 2024-03-12 | 2024-03-22 | 2024-06-19 | 2024-02-21 |  | Yes |  | No |  |  | Not Required
28INR0341 | Bastion BESS | SS Completed, FIS Started, No IA | BESS BASTION LLC | Blessing Substation 138 kV (ID 8121) | Matagorda | COASTAL | 2028-11-01 | OTH | BA | 154.3 |  | 2025-06-26 | 2025-07-07 | 2025-10-01 | 2025-06-19 |  | No |  | No
24INR0142 | De Los Santos | SS Completed, FIS Started, No IA | BRP De Los Santos BESS LLC | 78016 Sunglow Substation 138kV | Maverick | SOUTH | 2027-12-01 | OTH | BA | 200.97 |  | 2022-02-09 | 2022-05-10 | 2022-08-05 | 2022-04-18 |  |  |  | No | Not Required | Not Required
24INR0617 | Serrano Storage | SS Completed, FIS Started, No IA | Maverick ESS, LLC | 8267 GANSO Substation 138kV | Maverick | SOUTH | 2027-12-01 | OTH | BA | 185.59 |  | 2023-09-11 | 2023-09-23 | 2023-12-20 | 2023-08-31 |  | No |  | No | Not Required | Not Required
26INR0311 | Senator Aggreko Solar | SS Completed, FIS Started, IA | Senator Aggreko Solar LLC | 138 kV Sunglow Substation (#78016) | Maverick | SOUTH | 2029-03-31 | SOL | PV | 258.91 | MW Size | 2024-01-30 | 2024-02-02 | 2024-04-29 | 2023-10-18 |  |  | 2025-12-31 | No |  |  | Not Required
26INR0312 | Senator Aggreko Storage | SS Completed, FIS Started, IA | Senator Aggreko Storage LLC | 138 kV Sunglow Substation (#78016) | Maverick | SOUTH | 2029-03-31 | OTH | BA | 147.63 | MW Size | 2023-11-09 | 2023-11-14 | 2024-01-08 | 2023-10-25 |  |  | 2025-12-31 | No
27INR0253 | Old Victory Energy Center | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | 8692 MAVERICK4A 138kV | Maverick | SOUTH | 2030-06-01 | OTH | BA | 202.5 |  | 2024-04-17 | 2024-05-09 | 2024-08-05 | 2024-04-25 |  |  |  | No
27INR0389 | Sugaree Solar | SS Completed, FIS Started, IA | Sugaree Solar LLC | 138kV Escondido (8260) to Brackettville (8252) | Maverick | SOUTH | 2028-09-21 | SOL | PV | 251.4 |  | 2024-10-08 | 2024-10-10 | 2024-12-09 | 2024-10-08 |  | No | 2025-09-29 | Yes | Not Required | Not Required | Not Required | 2026-01-08
27INR0465 | Althea Storage | SS Completed, FIS Started, IA | Sugaree Solar LLC | Tap Escondido (8260) - Brackettville (8252) | Maverick | SOUTH | 2028-09-21 | OTH | BA | 251.3 |  | 2025-01-13 | 2025-02-12 | 2025-04-22 | 2024-12-30 |  |  | 2025-09-29 | Yes | Not Required | Not Required |  | 2026-01-08
27INR0593 | Pecan Ridge | SS Completed, FIS Started, No IA | Luminous Energy Renewables LLC | 60386 HEARTLAN2A 69kV | McCulloch | SOUTH | 2027-06-30 | OTH | BA | 150.79 |  | 2025-12-09 | 2025-12-17 | 2026-01-13 | 2025-11-26 |  |  |  | No
28INR0110 | Biggs BESS | SS Completed, FIS Started, No IA | Biggs Battery Facility, LLC | 76006 Bow Wood 345 kV | McCulloch | SOUTH | 2029-06-16 | OTH | BA | 200 | COD | 2025-04-28 | 2024-07-22 | 2024-10-18 | 2025-04-21 |  |  |  | No
28INR0111 | Biggs Solar | SS Completed, FIS Started, No IA | Biggs Solar Farm, LLC | #76006 Bow Wood 345 kV | McCulloch | SOUTH | 2029-06-16 | SOL | PV | 400 | COD | 2025-04-28 | 2024-07-22 | 2024-10-18 | 2025-04-21 |  |  |  | No |  |  | Not Required
19INR0100 | Prairie Hill Wind | SS Completed, FIS Completed, IA | Prairie Hill LLC | tap 345kV 3405 Tradinghouse - 3402 Lake Creek | McLennan | NORTH | 2027-09-30 | WIN | WT | 297.2 |  | 2017-06-19 | 2017-06-19 | 2017-08-11 | 2017-06-19 | 2020-04-03 | No | 2018-09-17 | Yes | Not Required | Not Required | Not Required | 2018-11-27 | 2020-04-21 | 2020-04-21 |  |  | 2020-10-19 | 2020-11-12
23INR0349 | Tokio Solar | SS Completed, FIS Started, IA | Gransolar Texas Eight, LLC | Tap 138kV 3592 Waco Atco - 170 Cotton Belt | McLennan | NORTH | 2027-08-25 | SOL | PV | 170.45 |  | 2022-05-04 | 2021-08-12 | 2021-11-01 | 2022-04-14 |  |  | 2023-11-06 | Yes | Not Required | Not Required | Not Required | 2023-11-17
24INR0038 | Jaguar Solar | SS Completed, FIS Started, IA | PP Jaguar Solar LLC | Tap 345kV 13405 Tradinghouse SES - 68090 Sam Switch | McLennan | NORTH | 2027-12-11 | SOL | PV | 300.87 |  | 2021-07-23 | 2021-03-18 | 2021-06-11 | 2021-07-15 |  |  | 2022-09-12 | Yes |  |  | Not Required | 2023-08-25 | 2024-01-23
24INR0104 | Braswell Solar | SS Completed, FIS Started, No IA | Gransolar Texas Nine, LLC | Tap 69kV 147 Lorena - 3580 Eddy Substation (Will be converted to 138kV line before 3/14/25 per TSP) | McLennan | NORTH | 2028-03-15 | SOL | PV | 42.6 |  | 2022-04-20 | 2021-08-30 | 2021-11-18 | 2022-04-08 |  | No |  | No | Not Required | Not Required | Not Required
24INR0356 | Cibeles Solar | SS Completed, FIS Started, IA | Elawan Cibeles Solar, LLC | 3379 Tiger Creek Switch (TIGERCREEK_5) 345 kV Substation | McLennan | NORTH | 2028-08-15 | SOL | PV | 252.3 |  | 2023-01-31 | 2022-05-16 | 2022-08-13 | 2023-01-13 |  | No | 2025-02-25 | Yes | Not Required | Not Required | Not Required | 2026-03-24
25INR0071 | Albatross BESS | SS Completed, FIS Completed, IA | Albatross Solar, LLC | From Bus #165 Windsor Switch To Bus #161 McGregor | McLennan | NORTH | 2028-12-30 | OTH | BA | 50.4 | SFS/NtP | 2023-01-27 | 2022-05-16 | 2022-08-13 | 2022-10-25 | 2025-10-30 | No | 2026-09-02 | Yes |  |  |  | 2026-09-21
25INR0579 | Albatross BESS 2 | SS Completed, FIS Completed, IA | Albatross Solar, LLC | Tap 138kV 165 Windsor Switch - 161 McGregor | McLennan | NORTH | 2028-12-30 | OTH | BA | 159.6 | SFS/NtP | 2024-02-01 | 2024-02-27 | 2024-05-22 | 2024-01-03 | 2025-10-30 | No | 2026-09-02 | Yes |  |  |  | 2026-09-21
26INR0111 | Graphic Packaging Gas | SS Completed, FIS Completed, IA | Graphic Packaging International | Tap 138kV 3446 Peppervine Switch - 3544 Castleman Substation | McLennan | NORTH | 2027-02-15 | GAS | GT | 43.36 |  | 2024-01-05 | 2024-01-11 | 2024-03-19 | 2024-01-05 | 2024-12-03 |  | 2026-07-30 | Yes | 2023-07-27 | Not Required | 2026-06-23 | 2026-08-17 | 2026-08-17 | 2026-08-17
26INR0252 | Neutron Storage | SS Completed, FIS Completed, IA | Elawan Neutron Storage, LLC | Tap 345kV 13405 Trading House - 68090 Sam Switch | McLennan | NORTH | 2028-04-29 | OTH | BA | 104.5 |  | 2023-08-21 | 2023-09-08 | 2023-12-01 | 2023-08-21 | 2025-05-16 | No | 2025-12-05 | Yes | Not Required | Not Required
26INR0380 | Pepper Solar Farm | SS Completed, FIS Completed, IA | Pepper Solar Farm LLC | Tap 345kV 3405 THOUSE__5 - 3406 ELM_MOTT_5 | McLennan | NORTH | 2027-09-20 | SOL | PV | 120.72 |  | 2024-02-21 | 2024-02-27 | 2024-05-20 | 2024-02-22 | 2026-08-17 | No | 2025-06-23 | Yes |  |  | Not Required | 2025-08-11
26INR0422 | PowerVault BESS | SS Completed, FIS Started, No IA | SMT Elm Mott BESS | Tap 345kV 3406 Elm Mott - 3405 Tradinghouse Ses | McLennan | NORTH | 2028-07-01 | OTH | BA | 254.8 |  | 2024-04-07 | 2024-03-22 | 2024-06-19 | 2024-04-02 |  |  |  | No
27INR0498 | Infrakey Waco Data Park Gas 2 | SS Completed, FIS Started, No IA | Infrakey Capital LLC | 252 BOSQUESW8 138kV (Brazos Connection) | McLennan | NORTH | 2030-06-01 | GAS | GT | 0 |  | 2026-01-30 | 2025-04-21 | 2025-07-19 | 2026-01-14 |  |  |  | No
27INR0607 | Prairie Phoenix Wind | SS Completed, FIS Started, No IA | Prairie Hill Wind Project LLC | 3403 Lake Hall 345kV | McLennan | NORTH | 2028-08-24 | WIN | WT | 297.25 |  | 2026-02-11 | 2026-02-25 | 2026-05-01 | 2026-02-13 |  | No |  | No |  |  | Not Required
28INR0157 | Axtell BESS | SS Completed, FIS Started, No IA | PP Axtell BESS LLC | 345 kV Tiger Creek Switch (#3379) | McLennan | NORTH | 2029-04-16 | OTH | BA | 306.94 |  | 2025-04-30 | 2024-10-01 | 2024-12-09 | 2026-05-01 |  |  |  | No
28INR0294 | Infrakey Waco Data Park Gas 1 | SS Completed, FIS Started, No IA | Infrakey Capital LLC | Tap 345kV 246 BOSQUESW5 – 3406 ELM_MOTT__5 | McLennan | NORTH | 2030-06-01 | GAS | GT | 180 |  | 2026-01-30 | 2025-04-21 | 2025-07-19 | 2026-01-14 |  |  |  | No
28INR0363 | Finch Storage | SS Completed, FIS Started, No IA | Finch Storage, LLC | 165 WINDSORSW 138kV | McLennan | NORTH | 2028-09-30 | OTH | BA | 201.3 |  | 2025-05-08 | 2025-06-05 | 2025-09-02 | 2025-04-28 |  |  |  | No
29INR0229 | Brazos Energy Center 1 | SS Completed, FIS Started, No IA | Ferrovial Energy US 1 | Tap <345><3791><POSSUMTROT_5 >-<3403> <LAKE_HALL_5> | McLennan | NORTH | 2029-09-18 | OTH | BA | 300.6 |  | 2026-01-05 | 2026-01-13 | 2026-04-07 | 2025-12-17 |  | No |  | No
29INR0230 | Brazos Energy Center 2 | SS Completed, FIS Started, No IA | Ferrovial Energy US 1 | Tap <345><3791><POSSUMTROT_5 >-<3403> <LAKE_HALL_5> | McLennan | NORTH | 2029-09-18 | OTH | BA | 300.6 |  | 2026-01-09 | 2026-01-13 | 2026-04-07 | 2025-12-17 |  | No |  | No
24INR0161 | Miranda Solar Project | SS Completed, FIS Completed, IA | Miranda Solar Project, LLC | Tap 345kV 5709 Fowlerton - 5901 San Miguel Ckt 1 | McMullen | SOUTH | 2027-12-06 | SOL | PV | 261.67 | MW Size | 2022-06-27 | 2021-11-03 | 2022-01-07 | 2022-06-22 | 2024-09-03 |  | 2024-07-16 | Yes | Not Required |  | Not Required
25INR0610 | Adam Bryant BESS | SS Completed, FIS Started, No IA | Adam Bryant BESS LLC | Tap 138kV 5225 HONDO – 5819 HONDO CREEK | Medina | SOUTH | 2027-12-01 | OTH | BA | 99.52 |  | 2024-04-15 | 2024-02-26 | 2024-05-24 | 2024-04-12 |  |  |  | No
27INR0203 | Dunlay Solar | SS Completed, FIS Started, No IA | Medina PV, LLC | Tap 138kV 5813 PearsonSW - 5225 Hondo | Medina | SOUTH | 2030-12-31 | SOL | PV | 150.5 |  | 2024-03-12 | 2024-03-22 | 2024-06-19 | 2024-03-12 |  |  |  | No |  |  | Not Required
27INR0206 | Chacon Creek | SS Completed, FIS Started, No IA | Cattlemen BESS LLC | (#8962) LYTLE4A 138KV | Medina | SOUTH | 2027-10-31 | OTH | BA | 188.95 |  | 2024-03-07 | 2024-03-22 | 2024-06-19 | 2024-03-14 |  | No |  | No
27INR0301 | Hondo Arroyo Solar | SS Completed, FIS Started, No IA | Hondo Creek Solar, LLC | Tap 138 kV 5225 Hondo - 5813 Pearson | Medina | SOUTH | 2028-07-01 | SOL | PV | 60.4 |  | 2024-06-11 | 2024-06-13 | 2024-09-10 | 2024-06-06 |  |  |  | No | Not Required | Not Required | Not Required
27INR0437 | Hondo Arroyo Storage | SS Completed, FIS Started, No IA | Hondo Creek Solar, LLC | Tap 138 kV 5225 Hondo - 5813 Pearson | Medina | SOUTH | 2028-07-01 | OTH | BA | 100.7 |  | 2024-11-27 | 2024-12-19 | 2025-03-17 | 2024-12-06 |  |  |  | No | Not Required | Not Required | 2025-09-15
28INR0392 | Devine Mary BESS | SS Completed, FIS Started, No IA | Devine Mary BESS | 5813 PEARSONSW8 138 kV | Medina | SOUTH | 2028-11-21 | OTH | BA | 200.58 |  | 2025-06-12 | 2025-07-07 | 2025-10-01 | 2025-06-19 |  |  |  | No
29INR0152 | Ranger BESS | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | SSWG Bus name: CSTROVILESB8 , Bus# : 5804 Planning Bus long name: CSTROVILESB8, 138 kV | Medina | SOUTH | 2029-04-29 | OTH | BA | 155.2 |  | 2025-05-20 | 2025-06-12 | 2025-09-04 | 2025-05-15 |  |  |  | No
24INR0386 | Black & Gold Energy Storage | SS Completed, FIS Started, IA | Black & Gold Energy Storage, LLC | 6364 Yellow Jacket Sub 138kV | Menard | WEST | 2027-07-30 | OTH | BA | 203.8 |  | 2022-09-13 | 2022-07-18 | 2022-10-14 | 2022-08-30 |  | No | 2024-08-14 | Yes | Not Required | Not Required |  | 2025-02-13
27INR0241 | Callan Solar | SS Completed, FIS Started, No IA | Menard PV, LLC | Tap 69kV 60386 Heartland to 6363 Yellow Jacket | Menard | WEST | 2029-12-30 | SOL | PV | 90.97 | COD | 2024-05-22 | 2024-06-13 | 2024-08-07 | 2024-06-04 |  | No |  | No |  |  | Not Required
23INR0300 | Holzer Solar | SS Completed, FIS Completed, IA | Greater Bryant G Solar, LLC | 11165 Sloan Switch 138kV | Midland | WEST | 2026-11-16 | SOL | PV | 17.7 |  | 2021-06-09 | 2021-06-17 | 2021-09-01 | 2021-06-16 | 2025-04-09 | No | 2022-07-18 | Yes | Not Required | Not Required | Not Required | 2025-06-18 | 2025-10-10 | 2025-10-10 |  |  | 2026-06-11 | 2026-07-02
25INR0144 | Jasper BESS | SS Completed, FIS Completed, IA | Jasper BESS, LLC | Tap 138kV 71230 Pleasant Farms - 1236 Pegasus South | Midland | WEST | 2028-10-11 | OTH | BA | 201.13 | SFS/NtP | 2023-04-03 | 2022-09-21 | 2022-12-19 | 2023-03-28 | 2026-04-21 |  | 2026-07-27 | Yes |  |  |  | 2026-09-21
26INR0121 | Pioneer Hutt Solar (Alternative POI) | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings LLC | TAP 345kV 11028 Odessa Ehv - 59901 Grelton (West C) | Midland | WEST | 2028-07-01 | SOL | PV | 116 |  | 2023-06-26 | 2023-06-28 | 2023-09-22 | 2023-06-12 |  |  |  | No |  |  | Not Required
26INR0231 | Energy City BESS | SS Completed, FIS Started, No IA | Energy City BESS LLC | Tap 138kV AQUEDUCT SUB(#1172) - Mockingbird North Tap(#11299) | Midland | WEST | 2029-05-07 | OTH | BA | 204.9 |  | 2023-09-13 | 2023-10-04 | 2023-12-30 | 2023-09-25 |  |  |  | No
26INR0597 | Electric E - West Texas Generation 2 | SS Completed, FIS Started, No IA | Electric E Power Marketing | #18664 SHAWPD 138kV | Midland | WEST | 2028-09-19 | GAS | GT | 0 |  | 2024-12-17 | 2024-12-19 | 2025-02-20 | 2024-11-06 |  |  |  | No
27INR0290 | Drill Baby Drill BESS | SS Completed, FIS Started, No IA | SBESS TX8 LLC | 23859 SALTFLAT 138KV | Midland | WEST | 2028-10-11 | OTH | BA | 204.31 |  | 2025-05-12 | 2024-09-04 | 2024-11-20 | 2025-05-07 |  |  |  | No
29INR0305 | Flurry Gas 1 | SS Completed, FIS Started, No IA | NET Power Canaveral LLC | Tap 345 kV 1185 Midland County Northwest Switch (bus #1185) – Midland East (bus #1021) 345 kV Line Ckt 01 | Midland | WEST | 2029-04-16 | GAS | CC | 109.8 |  | 2026-02-12 | 2026-02-25 | 2026-05-22 | 2026-02-17 |  |  |  | No
21INR0203 | Eastbell Milam Solar | SS Completed, FIS Completed, IA | EDP RENEWABLES NORTH AMERICA LLC | 345 kV Bell County East Switch (bus# 3687) - TNP One (bus# 39950) circuit 2 | Milam | SOUTH | 2026-11-01 | SOL | PV | 244.86 | COD | 2019-04-23 | 2018-10-10 | 2018-12-09 | 2019-04-23 | 2022-10-28 | No | 2022-09-02 | Yes | Not Required | Not Required | Not Required | 2022-11-03 | 2022-11-03 | 2022-11-12 |  |  | 2023-10-13 | 2023-11-01
22INR0350 | Sandow Solar | SS Completed, FIS Completed, No IA | Sandow Lakes Ranch Solar I, LLC | tap one 345kV 7040 Austrop - 13429 Sandow line | Milam | SOUTH | 2028-06-01 | SOL | PV | 287.18 |  | 2020-08-24 | 2020-09-11 | 2021-02-08 | 2020-05-28 | 2024-07-18 |  |  | Yes | Not Required | Not Required | Not Required | 2025-11-10
22INR0605 | Camino Santiago Solar | SS Completed, FIS Completed, IA | Camino Solar Project, LLC | 345 kV Herndon Switch Substation (#3804) | Milam | SOUTH | 2027-09-01 | SOL | PV | 196.3 |  | 2023-02-08 | 2022-09-02 | 2022-11-30 | 2023-01-05 | 2026-09-17 | No | 2024-12-06 | Yes | Not Required |  | Not Required | 2025-06-11
23INR0235 | Hoyte Solar | SS Completed, FIS Completed, IA | Milano Solar LLC | (3707) Cannon Switch 138kV | Milam | SOUTH | 2027-04-15 | SOL | PV | 206.75 |  | 2021-04-02 | 2021-04-01 | 2021-07-02 | 2021-03-25 | 2026-03-16 | No | 2022-10-14 | Yes | Not Required | Not Required | Not Required | 2025-02-13 | 2026-05-01 | 2026-05-01 | 2025-08-11
23INR0468 | Petunia Storage Project | SS Completed, FIS Started, No IA | Petunia Storage Project LLC | 138kV Tap 3675 Rogers - 3485 Tin Roof Pod | Milam | SOUTH | 2028-06-30 | OTH | BA | 231.86 |  | 2022-04-14 | 2022-03-12 | 2022-06-02 | 2022-04-01 |  | No |  | No | Not Required | Not Required
23INR0478 | Rhoda Storage | SS Completed, FIS Started, IA | Milam Energy, LLC | Tap 138kV 32 Robertson - 64 Milano | Milam | SOUTH | 2028-08-01 | OTH | BA | 141.23 |  | 2022-03-31 | 2022-04-18 | 2022-07-15 | 2022-03-18 |  |  | 2025-12-31 | No | Not Required | Not Required
23INR0502 | Adelite Storage | SS Completed, FIS Completed, IA | Adelite Storage Project LLC | Tap 138kV Thorndale North (bus #3659) – Rookie Switch (bus #3701) | Milam | SOUTH | 2028-04-20 | OTH | BA | 231.88 | COD | 2022-09-13 | 2022-06-27 | 2022-09-22 | 2022-09-09 | 2024-05-01 | No | 2024-08-27 | Yes
24INR0031 | Stoneridge Solar | SS Completed, FIS Completed, IA | Stoneridge Solar, LLC | Tap 345 kV 13429 SANDOW SWITCH - 7040 AUSTROP Beulah Switch to tap above line | Milam | SOUTH | 2026-12-31 | SOL | PV | 201.6 |  | 2022-02-14 | 2021-10-08 | 2022-01-03 | 2022-01-31 | 2024-05-21 | No | 2023-05-15 | Yes | Not Required | Not Required | Not Required | 2024-07-18 | 2024-07-18 | 2024-07-18 |  |  | 2025-01-10 | 2025-04-01
24INR0042 | Yaupon Solar SLF | SS Completed, FIS Completed, IA | Yaupon Solar, LLC | Tap 345 kV Gibson Switch (3706) – TNP One (39950) | Milam | SOUTH | 2026-11-18 | SOL | PV | 200.78 |  | 2021-12-07 | 2021-03-30 | 2021-06-17 | 2021-11-23 | 2025-09-16 | No | 2023-09-28 | Yes |  |  | Not Required | 2025-09-08 | 2025-10-24 | 2025-10-24 |  |  | 2026-05-27 | 2026-08-13
24INR0070 | Sypert Branch Solar Project | SS Completed, FIS Completed, IA | Sypert Branch Solar LLC | Tap 345kV #3751 Scooter Switch - #3687 Bell County East Switch Ckt 2 | Milam | SOUTH | 2026-04-30 | SOL | PV | 261.15 |  | 2022-05-10 | 2021-09-21 | 2021-12-06 | 2022-04-28 | 2024-10-31 | No | 2023-10-12 | Yes | Not Required | Not Required | Not Required | 2023-10-18 | 2025-04-17 | 2025-04-17 |  |  | 2025-12-10 | 2025-12-12
24INR0169 | Yaupon Storage SLF | SS Completed, FIS Started, IA | Yaupon Solar, LLC | to Tap 345 kV Gibson Switch (3706) – TNP One (39950) | Milam | SOUTH | 2028-07-01 | OTH | BA | 0 |  | 2022-01-12 | 2021-11-10 | 2022-02-08 | 2022-01-10 |  |  | 2023-09-28 | Yes |  |  |  | 2025-02-12
24INR0208 | Eastbell Milam Solar II | SS Completed, FIS Completed, IA | Cattlemen Solar Park II LLC | 345 kV Bell County East Switch (bus# 3687) - TNP One (bus# 39950) circuit 2 | Milam | SOUTH | 2026-11-01 | SOL | PV | 150.6 | COD | 2022-02-07 | 2022-03-07 | 2022-06-02 | 2022-02-03 | 2024-02-01 |  | 2023-10-25 | Yes |  |  | Not Required | 2024-02-01 | 2024-02-01 | 2024-02-01 |  |  | 2024-09-13 | 2024-11-20
25INR0214 | Burgos Solar | SS Completed, FIS Completed, No IA | Twin Oaks Solar, LLC | 3701 Rookie Switch 138 kV | Milam | SOUTH | 2027-11-22 | SOL | PV | 105.52 |  | 2023-03-17 | 2022-10-18 | 2023-01-13 | 2023-03-03 | 2026-05-14 |  |  | No |  |  | Not Required
25INR0382 | HappyDogSolar | SS Completed, FIS Completed, IA | Rosula Solar LLC | Tap 345kV 3704 Hog Creek Switch – 3687 Bell County East Switch | Milam | SOUTH | 2027-08-04 | SOL | PV | 85.54 |  | 2023-05-30 | 2023-06-07 | 2023-09-01 | 2023-05-25 | 2025-01-07 | No | 2024-12-16 | No |  |  | Not Required
25INR0389 | Stoneridge BESS | SS Completed, FIS Completed, IA | Stoneridge Solar, LLC | Tap 345 kV 13429 SANDOW SWITCH - 7040 AUSTROP CKT 2 | Milam | SOUTH | 2026-12-31 | OTH | BA | 101.9 |  | 2023-03-09 | 2023-03-13 | 2023-06-09 | 2023-03-09 | 2024-09-06 | No | 2024-04-19 | Yes | Not Required | Not Required |  | 2025-01-28 | 2025-01-28 | 2025-01-28 |  |  | 2025-06-26 | 2025-07-10
25INR0442 | Happy Dog Storage | SS Completed, FIS Completed, IA | Rosula Storage LLC | Tap 345kV 3704 Hog Creek Switch – 3687 Bell County East Switch | Milam | SOUTH | 2027-08-04 | OTH | BA | 104.52 |  | 2023-05-23 | 2023-06-07 | 2023-09-01 | 2023-06-02 | 2026-09-16 | No | 2024-12-16 | No
26INR0609 | Scorpius Solar | SS Completed, FIS Started, No IA | Ben Milam Solar 4 | 3377 LTPSW 345KV | Milam | SOUTH | 2029-06-14 | SOL | PV | 600 |  | 2024-11-19 | 2024-12-16 | 2025-03-03 | 2024-11-20 |  |  |  | No |  |  | Not Required
26INR0630 | Betel Storage I | SS Completed, FIS Started, No IA | BETEL STORAGE I | 3377 Little Pond Switch ( LTPSW) 345 | Milam | SOUTH | 2026-08-12 | OTH | BA | 500 |  | 2024-12-06 | 2025-01-28 | 2025-04-15 | 2025-01-22 |  |  |  | No
26INR0633 | Betel Storage II | SS Completed, FIS Started, No IA | BETEL STORAGE II | 3377 Little Pond 345 | Milam | SOUTH | 2026-12-17 | OTH | BA | 500 |  | 2024-12-06 | 2025-01-28 | 2025-04-15 | 2025-01-22 |  |  |  | No
26INR0635 | Aquila Solar | SS Completed, FIS Started, No IA | Ben Milam Solar 5 | 3706 Gibson Switch 345kV | Milam | SOUTH | 2026-11-12 | SOL | PV | 500 |  | 2025-11-05 | 2025-11-18 | 2026-01-19 | 2025-11-17 |  | No |  | No |  |  | Not Required
27INR0071 | Sandow Lakes Energy Station | SS Completed, FIS Started, No IA | SL Energy Power Plant I, LLC | #13430 Sandow Switch 138kV | Milam | SOUTH | 2028-04-01 | GAS | GT | 1291.6 |  | 2024-12-20 | 2024-03-22 | 2024-06-19 | 2024-11-22 |  |  |  | No
27INR0216 | Champs Elysees BESS | SS Completed, FIS Started, No IA | Champs Elysees Renewables, LLC | Tap 345 kV 3377 Little Pond Switch - 3704 Hog Creek Switch | Milam | SOUTH | 2027-12-15 | OTH | BA | 256.1 |  | 2024-07-25 | 2024-08-16 | 2024-10-08 | 2024-07-26 |  |  |  | No
27INR0441 | Pavo Creek Storage | SS Completed, FIS Started, No IA | Pavo Creek Storage, LLC | Tap #3659 Thorndale North - #3701 Rookie Switch 138 kV | Milam | SOUTH | 2028-09-21 | OTH | BA | 154.2 |  | 2025-02-20 | 2025-02-25 | 2025-05-13 | 2025-02-20 |  |  |  | No | Not Required | Not Required | 2025-09-15
27INR0494 | Obbligato BESS | SS Completed, FIS Started, No IA | Obbligato BESS, LLC | Tap 138kV 120# TALBRTRIDG – 3683# MINERVA1_8 | Milam | SOUTH | 2030-02-28 | OTH | BA | 200.71 | COD | 2025-06-06 | 2025-06-19 | 2025-09-10 | 2025-06-09 |  |  |  | No
28INR0185 | San Gabriel Solar | SS Completed, FIS Completed, IA | San Gabriel Solar LLC | Tap 138 kV 3750 Vosslake - 3749 Buckholts | Milam | SOUTH | 2028-07-01 | SOL | PV | 255 |  | 2025-01-07 | 2025-01-28 | 2025-04-17 | 2025-01-08 | 2026-07-20 | No | 2026-08-06 | No | Not Required | Not Required | Not Required
28INR0191 | San Gabriel Storage | SS Completed, FIS Completed, IA | San Gabriel Solar LLC | Tap 138 kV 3750 Vosslake - 3749 Buckholts | Milam | SOUTH | 2028-07-01 | OTH | BA | 127.5 |  | 2025-01-07 | 2025-01-28 | 2025-04-17 | 2025-01-08 | 2026-07-20 | No | 2026-08-06 | No | Not Required | Not Required
29INR0058 | Brahman Renewables Solar | SS Completed, FIS Started, No IA | Brahman Renewables | Tap Voss Lake switch #3751 – Badger Switch #3761 345 kV | Milam | SOUTH | 2029-05-01 | SOL | PV | 100.6 |  | 2025-04-28 | 2024-10-29 | 2025-01-25 | 2025-04-09 |  |  |  | No |  |  | Not Required
29INR0059 | Brahman Renewables Storage | SS Completed, FIS Started, No IA | Brahman Renewables | Tap Voss Lake switch #3751 – Badger Switch #3761 345 kV | Milam | SOUTH | 2029-05-01 | OTH | BA | 206.88 | MW Size | 2025-04-21 | 2024-10-29 | 2025-01-25 | 2025-04-09 |  |  |  | No
29INR0120 | MilamStation Power Secured Gas Generation | SS Completed, FIS Started, No IA | LCC-TX8, LLC | Little Pond Switch (Bus #3377) – Hog Creek Switch (Bus #3704) 345 kV Line | Milam | SOUTH | 2029-09-25 | GAS | CC | 846 |  | 2025-12-17 | 2025-03-24 | 2025-06-19 | 2025-12-12 |  | No |  | No
16INR0085 | Priddy Wind | SS Completed, FIS Completed, IA | ENGIE North America | tap 345kV 1444 Brown – 3422 Killeen | Mills | NORTH | 2026-12-31 | WIN | WT | 302.4 |  | 2015-03-06 | 2015-01-14 | 2015-02-10 | 2015-03-06 | 2021-04-30 | No | 2020-08-13 | Yes | Not Required | Not Required | Not Required | 2021-03-29 | 2021-04-30 | 2021-04-30 |  |  | 2021-10-13 | 2021-11-19
26INR0238 | Clapton Solar | SS Completed, FIS Started, No IA | Clapton Solar | Tap 345 kV 3424 Buckhorn Switch - 1444 Brown Switch | Mills | NORTH | 2028-08-09 | SOL | PV | 200.99 |  | 2024-02-05 | 2024-03-22 | 2024-06-19 | 2024-02-13 |  |  |  | No |  |  | Not Required
26INR0430 | Clapton Storage | SS Completed, FIS Started, No IA | Clapton BESS | Tap 345 kV 3424 Buckhorn Switch - 1444 Brown Switch | Mills | NORTH | 2028-08-09 | OTH | BA | 208.91 |  | 2024-02-05 | 2024-03-22 | 2024-06-19 | 2024-02-13 |  |  |  | No
27INR0105 | Starlight Solar | SS Completed, FIS Started, IA | Mills Tx Solar LLC | tap the 138 kV Goldthwaite (#7070) – San Saba Switch (#77074) | Mills | NORTH | 2030-05-09 | SOL | PV | 130.72 |  | 2023-10-06 | 2024-02-27 | 2024-05-22 | 2024-02-08 |  |  | 2025-12-31 | No | Not Required | Not Required | Not Required
27INR0107 | Starlight Storage | SS Completed, FIS Started, IA | Mills Tx Solar LLC | Tap 138kV 7070 Goldthwaite – 77074 San Saba Switch | Mills | NORTH | 2030-05-09 | OTH | BA | 208.96 | MW Size | 2024-02-16 | 2024-02-27 | 2024-05-22 | 2024-02-08 |  |  | 2025-12-31 | No | Not Required | Not Required
28INR0438 | Moss Rock Storage | SS Completed, FIS Started, No IA | Invenergy Storage Development LLC | #7070 Goldthwaite 138kV | Mills | NORTH | 2029-12-31 | OTH | BA | 157.12 |  | 2026-04-14 | 2025-09-22 | 2025-12-02 |  |  |  |  | No
29INR0065 | Cash Mills Storage Center | SS Completed, FIS Started, No IA | Mills Storage Center | Tap Line between Evant (bus#7068) and Goldthwaite (Bus# 7070) | Mills | NORTH | 2029-06-01 | OTH | BA | 200.66 |  | 2025-03-28 | 2024-11-26 | 2025-02-18 | 2025-03-19 |  |  |  | No
23INR0143 | Sepik BESS | SS Completed, FIS Started, No IA | BRP Sepik BESS LLC | tap 138kV 11342 Loraine South – 10050 Ranger Camp | Mitchell | WEST | 2028-03-01 | OTH | BA | 204.96 |  | 2020-12-08 | 2020-12-22 | 2021-03-15 | 2020-12-01 |  |  |  | No
25INR0139 | Dolce BESS | SS Completed, FIS Completed, No IA | Dolce BESS, LLC | Tap 138kV 1189 BARBER_LK1_8 - 19520 CHINAGRVX2_8 | Mitchell | WEST | 2029-01-31 | OTH | BA | 100.65 |  | 2023-03-30 | 2022-09-27 | 2022-12-21 | 2023-03-28 | 2026-02-26 | No |  | No
25INR0430 | Hackberry Creek Solar | SS Completed, FIS Completed, IA | Hackberry Creek Solar LLC | tap 345kV 10053 Cattleman Switch - 1058 Longshore Switch | Mitchell | WEST | 2028-01-01 | SOL | PV | 175.51 |  | 2023-07-19 | 2023-07-31 | 2023-10-27 | 2023-07-19 | 2025-10-22 |  | 2025-12-02 | Yes |  |  | Not Required | 2026-03-17
25INR0588 | Zeus Mitchell Solar | SS Completed, FIS Started, No IA | Mitchell Solar, LLC | Tap 345 kV 10049 Ranger Camp - 10057 Prong Moss CKT #01 and #02 | Mitchell | WEST | 2029-04-17 | SOL | PV | 804.71 |  | 2024-05-14 | 2024-03-22 | 2024-06-19 | 2025-03-28 |  |  |  | No |  |  | Not Required |  |  |  | 2025-02-18 | 2026-03-15
25INR0589 | Zeus Mitchell BESS | SS Completed, FIS Started, No IA | Mitchell BESS | Tap 345 kV 10049 Ranger Camp - 10057 Prong Moss CKT #01 and #02 | Mitchell | WEST | 2029-04-17 | OTH | BA | 1042.94 |  | 2025-06-02 | 2024-05-20 | 2024-06-19 | 2025-03-28 |  |  |  | No | [6 empty] | 2025-02-18 | 2026-03-15
26INR0386 | Zeus Spade Wind | SS Completed, FIS Started, No IA | Spade Wind, LLC | Tap 345 kV 1030 Morgan Creek to 76030 Gasconades Creek | Mitchell | WEST | 2028-03-20 | WIN | WT | 987.3 |  |  | 2024-03-29 | 2024-06-25 | 2025-01-07 |  |  |  | No |  |  | Not Required |  |  |  | 2026-10-01 | 2027-10-10
26INR0387 | Zeus Spade BESS | SS Completed, FIS Started, No IA | Spade BESS | Tap 345 kV 1030 Morgan Creek to 76030 Gasconades Creek | Mitchell | WEST | 2028-03-20 | OTH | BA | 446.3 |  | 2025-02-04 | 2024-03-29 | 2024-06-25 | 2025-01-24 |  |  |  | No | [6 empty] | 2026-10-01 | 2026-10-15
26INR0420 | Whitetail BESS | SS Completed, FIS Started, No IA | Hunt Energy Network, LLC | tap Salt Mine (#23846) to Bulldog (#23833) 138kV | Mitchell | WEST | 2029-06-08 | OTH | BA | 180 |  | 2025-08-26 | 2024-02-27 | 2024-05-24 | 2025-03-06 |  |  |  | No
26INR0686 | Zeus Mitchell BESS II | SS Completed, FIS Started, No IA | Zeus Mitchell BESS II, LLC | Tap 345 kV 10049 Ranger Camp - 10057 Prong Moss CKT #01 and #02 | Mitchell | WEST | 2027-05-01 | OTH | BA | 1042.94 |  | 2025-05-20 | 2025-06-19 | 2025-09-16 | 2025-05-20 |  |  |  | No
27INR0327 | Sunflower Valley Storage | SS Completed, FIS Started, No IA | Sunflower Valley Storage, LLC | 1414 Champion Creek Substation 345 kV | Mitchell | WEST | 2029-04-17 | OTH | BA | 205.7 |  | 2025-04-07 | 2025-04-25 | 2025-07-22 | 2025-04-08 |  |  |  | No | Not Required | Not Required | 2025-09-15
27INR0348 | Johnson Grass Solar | SS Completed, FIS Started, No IA | Johnson Grass Solar ,LLC | Tap 138kV (#11395) Navigation - (#10054) Cattlemen | Mitchell | WEST | 2028-04-19 | SOL | PV | 195.8 |  | 2024-09-30 | 2024-10-01 | 2024-12-09 | 2024-09-30 |  |  |  | No | Not Required | Not Required | Not Required
28INR0119 | Rabbit Hollow Energy Storage | SS Completed, FIS Started, No IA | Rabbit Hollow Energy Storage, LLC | 1190 Barber Lake Switch 138kV | Mitchell | WEST | 2029-12-31 | OTH | BA | 341.8 |  | 2024-11-26 | 2024-12-19 | 2025-03-18 | 2024-12-01 |  | No |  | No
28INR0307 | Prairie Power Wind | SS Completed, FIS Started, No IA | Prairie Power Wind, LLC | Tap 345 kV Longshore Switch (Bus# 1058) to Cattleman Switch (Bus# 10053) CKT 4 | Mitchell | WEST | 2029-04-17 | WIN | WT | 302.9 |  | 2025-05-27 | 2025-06-05 | 2025-09-02 | 2025-05-27 |  |  |  | No |  |  | Not Required
29INR0212 | Rosenix Solar | SS Started, FIS Started, No IA | Rosenix Solar, LLC | Cattleman (#10053) – Gasconades (#76030) | Mitchell | WEST | 2030-04-20 | SOL | PV | 501.64 | MW Size COD | 2026-06-29 | 2026-07-08 |  | 2026-07-01 |  |  |  | No |  |  | Not Required
29INR0213 | Rosenix Storage | SS Started, FIS Started, No IA | Rosenix Solar, LLC | Cattleman (#10053) – Gasconades (#76030) | Mitchell | WEST | 2030-04-20 | OTH | BA | 258.26 | MW Size COD | 2026-07-10 | 2026-07-22 |  | 2026-07-10 |  |  |  | No
25INR0190 | Fortissimo BESS | SS Completed, FIS Completed, No IA | Fortissimo BESS, LCC | 741 Dyemound 138kV | Montague | NORTH | 2028-04-24 | OTH | BA | 202.65 |  | 2023-02-28 | 2022-10-18 | 2023-01-13 | 2023-02-09 01:31 | 2024-09-12 | No |  | No
28INR0422 | Prairie Branch Solar | SS Completed, FIS Started, No IA | Prairie Branch Energy, LLC | Tap 345kV #1730 Krum West - #6111 Riley Ckt 1 | Montague | NORTH | 2029-12-01 | SOL | PV | 301.23 |  | 2025-09-05 | 2025-09-09 | 2025-11-14 | 2025-08-28 |  |  |  | No | Not Required | Not Required | Not Required
28INR0423 | Prairie Branch BESS | SS Completed, FIS Started, No IA | Prairie Branch Energy, LLC | Tap 345kV #1730 Krum West - #6111 Riley Ckt 1 | Montague | NORTH | 2029-12-01 | OTH | BA | 310.17 |  | 2025-08-27 | 2025-09-09 | 2025-11-14 | 2025-08-18 |  |  |  | No | Not Required | Not Required
30INR0140 | Enfinity Primrose | SS Started, FIS Started, No IA | EG Primrose LLC | (741) DYEMOUND Substation 138kV | Montague | NORTH | 2030-07-17 | OTH | BA | 200 |  | 2026-07-20 | 2026-07-22 |  | 2026-07-14 |  |  |  | No
27INR0109 | Two Barbaras BESS | SS Completed, FIS Started, IA | Two Barbaras BESS | Tap 138 kV Pinehurst (#46240) – Mill Creek (#44850) Line | Montgomery | HOUSTON | 2029-01-04 | OTH | BA | 217.16 |  | 2024-03-15 | 2024-03-22 | 2024-06-19 | 2024-03-14 |  | No | 2025-10-01 | Yes
27INR0324 | LONE STAR INDUSTRIAL PARK GAS POWER PROJECT | SS Completed, FIS Started, No IA | LONE STAR INDUSTRIAL PARK, LLC | 1795 Monticello SES 138kV | Morris | NORTH | 2028-05-11 | GAS | IC | 166 |  | 2024-08-29 | 2024-09-04 | 2024-12-02 | 2024-08-28 |  |  |  | No
24INR0399 | Buzios Solar | SS Completed, FIS Completed, IA | Roaring Springs Solar, LLC | Tap between Cottonwood (#59904) and White River (#23922) | Motley | PANHANDLE | 2026-07-31 | SOL | PV | 252 |  | 2022-08-03 | 2022-09-15 | 2022-12-13 | 2022-08-04 | 2025-03-10 | No | 2023-11-06 | Yes | Not Required | Not Required | Not Required | 2025-02-11 | 2025-04-30 | 2025-04-30 |  |  | 2025-08-27 | 2025-10-01
28INR0017 | Sitges Wind | SS Completed, FIS Started, No IA | Whistling Flats Wind, LLC | Tap 345kV 59904 Cottonwood–60500 Edith Clarke | Motley | PANHANDLE | 2030-03-31 | WIN | WT | 600 |  | 2024-02-29 | 2024-03-22 | 2024-06-19 | 2024-02-29 |  | Yes |  | No |  |  | Not Required
29INR0021 | Buzios BESS SLF | SS Completed, FIS Started, No IA | Buzios Energy Storage, LLC | Tap 345kV 59904 Cottonwood - 23922 White River Ckt 2 | Motley | PANHANDLE | 2029-07-01 | OTH | BA | 0 |  | 2025-04-03 | 2025-04-08 | 2025-07-01 | 2025-01-23 |  |  |  | No
26INR0161 | Timberline Solar | SS Completed, FIS Started, No IA | Timberline Renewables, LLC | Tap 345 kV 3119 Nacogdoches SE - 3116 Mt Enterprise | Nacogdoches | NORTH | 2029-10-05 | SOL | PV | 201 |  | 2023-07-24 | 2023-08-14 | 2023-11-10 | 2023-08-02 |  | Yes |  | No | Not Required | Not Required | Not Required
26INR0162 | Timberline Storage | SS Completed, FIS Started, No IA | Timberline Renewables, LLC | Tap 345 kV 3119 Nacogdoches SE - 3116 Mt Enterprise | Nacogdoches | NORTH | 2029-10-05 | OTH | BA | 100.5 |  | 2023-08-15 | 2023-08-14 | 2023-11-10 | 2023-08-04 |  | Yes |  | No
27INR0313 | Spindletop Solar | SS Completed, FIS Completed, IA | Banita Creek Solar LLC | Tap Stryker [3109] - Lufkin [3117] 345 kV line | Nacogdoches | NORTH | 2027-12-29 | SOL | PV | 286.4 |  | 2024-07-16 | 2024-07-30 | 2024-10-25 | 2024-07-26 | 2026-09-16 | No | 2025-12-29 | Yes |  |  | Not Required | 2026-03-25
21INR0324 | Board Creek Wind | SS Completed, FIS Completed, IA | Limestone Wind Project, LLC | 345kV 3386 Outlaw Switch | Navarro | NORTH | 2026-10-31 | WIN | WT | 299.2 |  | 2019-11-08 | 2019-04-24 | 2019-07-22 | 2019-11-05 | 2022-04-26 | No | 2021-08-19 | Yes | Not Required | Not Required | Not Required | 2022-04-05 | 2022-04-21 | 2022-04-26 |  |  | 2022-09-19 | 2022-10-06
21INR0421 | Armadillo Solar | SS Completed, FIS Completed, IA | Armadillo Solar Center, LLC | 3387 Revolution 138kV | Navarro | NORTH | 2026-12-31 | SOL | PV | 150.48 | COD | 2019-09-05 | 2019-08-28 | 2019-11-22 | 2019-08-28 | 2025-10-08 | No | 2021-02-02 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2025-10-31 | 2025-10-16 |  |  | 2026-07-27
22INR0437 | TORMES SOLAR | SS Completed, FIS Completed, IA | BDPU SOLAR TORMES LLC | tap 345kV 1906 Venus - 68091 Navarro | Navarro | NORTH | 2027-03-31 | SOL | PV | 356.6 |  | 2021-07-26 | 2020-10-23 | 2021-01-12 | 2021-07-19 | 2026-06-23 |  | 2024-04-10 | Yes |  |  | Not Required | 2025-02-13 | 2026-07-31 | 2026-07-31
23INR0171 | Goodalta Solar | SS Completed, FIS Completed, No IA | GoodAlta Power Center LLC | tap 138kV 3127 Trinidad - 212 Winkler | Navarro | NORTH | 2027-09-20 | SOL | PV | 221.36 |  | 2021-08-03 | 2021-01-25 | 2021-04-12 | 2021-01-07 | 2026-02-17 | No |  | No |  |  | Not Required
24INR0086 | Pisgah Ridge Solar 2 | SS Completed, FIS Started, No IA | Pisgah Ridge Solar 2, LLC | Tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2029-03-31 | SOL | PV | 101.89 |  | 2021-09-07 | 2021-07-14 | 2021-10-07 | 2021-08-25 |  | No |  | No | Not Required | Not Required | Not Required
24INR0087 | Pisgah Ridge Storage 3 | SS Completed, FIS Started, No IA | Pisgah Ridge 3, LLC | Tap 345kV 68091 Navarro - 46020 Limestone | Navarro | NORTH | 2029-03-31 | OTH | BA | 101.36 |  | 2021-09-07 | 2021-07-14 | 2021-10-07 | 2021-08-25 |  | No |  | No | Not Required | Not Required
24INR0120 | Eytcheson Ranches Solar | SS Completed, FIS Started, No IA | Gransolar Texas Fourteen, LLC | Tap 69kV 186 Navarro Mills – 107 Prairie Hill | Navarro | NORTH | 2028-01-01 | SOL | PV | 76.42 |  | 2022-05-31 | 2021-09-14 | 2021-11-29 | 2022-05-26 |  | No |  | No |  |  | Not Required
24INR0188 | Tehuacana Creek Solar | SS Completed, FIS Completed, IA | Tehuacana Creek Solar LLC | Tap 345kV 3381 Big Brown – 68091 Navarro circuit | Navarro | NORTH | 2027-05-18 | SOL | PV | 505.43 |  | 2021-12-15 | 2021-12-20 | 2022-03-10 | 2021-12-09 | 2026-06-16 | No | 2024-11-25 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2026-04-23 | 2026-08-03
24INR0205 | Wensowitch Solar | SS Completed, FIS Completed, No IA | Greenalia Solar Power Wensowitch LLC | Tapping 138 kV line Telico (192) to Montfort Switch (3454) | Navarro | NORTH | 2029-04-17 | SOL | PV | 146.08 | COD | 2022-08-15 | 2022-01-07 | 2022-04-01 | 2022-07-25 | 2026-01-09 |  |  | No | Not Required | Not Required | Not Required
24INR0206 | Glasgow Solar | SS Completed, FIS Started, IA | Glasgow Solar LLC | Tap 345kV #2466 Big Onion - #68091 Navarro | Navarro | NORTH | 2028-03-16 | SOL | PV | 203.5 |  | 2022-02-03 | 2022-02-07 | 2022-05-07 | 2022-01-12 |  | No | 2023-11-08 | Yes | Not Required | Not Required | Not Required | 2025-02-12
24INR0207 | Glasgow Storage | SS Completed, FIS Started, IA | Glasgow Solar LLC | Tap 345kV #2466 Big Onion - #68091 Navarro | Navarro | NORTH | 2028-03-16 | OTH | BA | 101 |  |  | 2022-02-21 | 2022-05-07 | 2022-02-02 |  |  | 2023-11-08 | Yes | Not Required | Not Required |  | 2025-02-12
24INR0256 | Kennedy Solar | SS Completed, FIS Started, No IA | Kennedy Bypass Solar LLC | Tap 345kV 68040 Kopprl Capacitor Yard - 68091 Navarro | Navarro | NORTH | 2028-12-31 | SOL | PV | 101.5 |  | 2022-07-11 | 2022-03-07 | 2022-06-02 | 2022-06-29 |  |  |  | No |  |  | Not Required
24INR0391 | Kennedy Storage | SS Completed, FIS Started, No IA | Kennedy Bypass Solar LLC | Tap 345kV 68040 Kopprl Capacitor Yard - 68091 Navarro | Navarro | NORTH | 2028-12-31 | OTH | BA | 25.3 |  | 2022-07-06 | 2022-07-18 | 2022-10-12 | 2022-07-06 |  |  |  | No
25INR0018 | Yellow Cat Wind | SS Completed, FIS Completed, IA | Yellow Cat Wind LLC | Tap 345kV 1906 Venus - 68091 Navarro | Navarro | NORTH | 2027-03-05 | WIN | WT | 262 |  | 2022-03-18 | 2021-08-17 | 2021-11-05 | 2022-03-07 | 2025-12-09 | No | 2024-07-09 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2026-01-27 | 2026-01-28
25INR0029 | Whistle Solar | SS Completed, FIS Started, No IA | Gransolar Texas Nineteen, LLC | Tap 138kV 213 Haney – 3478 Navarro | Navarro | NORTH | 2028-05-15 | SOL | PV | 56.3 |  | 2022-08-10 | 2021-11-23 | 2022-02-18 | 2022-08-05 |  |  |  | No |  |  | Not Required
25INR0220 | Hector Solar | SS Completed, FIS Started, No IA | Hector Solar, LLC | Haney (213) - Hubbard_8 (3515) 138kV Line | Navarro | NORTH | 2028-10-08 | SOL | PV | 81.59 |  | 2023-01-06 | 2022-10-24 | 2023-01-20 |  |  | No |  | No |  |  | Not Required
25INR0221 | Hector Storage | SS Completed, FIS Started, No IA | Hector Solar, LLC | Haney (213) - Hubbard_8 (3515) 138kV Line | Navarro | NORTH | 2028-10-08 | OTH | BA | 42.69 |  | 2023-01-06 | 2022-10-24 | 2023-01-20 | 2023-01-02 |  | No |  | No
25INR0247 | Bluebonnet Prairie Wind | SS Completed, FIS Started, IA | Bluebonnet Prairie Wind, LLC | Tap 138kV 200 CHATFIELD - 3454 MONTFTSS__8 | Navarro | NORTH | 2028-07-15 | WIN | WT | 180 |  | 2022-12-06 | 2022-12-07 | 2023-03-06 | 2022-11-23 |  | No | 2025-07-03 | Yes |  |  | Not Required |  |  |  | 2027-08-01 | 2028-05-01
26INR0130 | Elm Flats Solar SLF | SS Completed, FIS Started, IA | Orca Falls Solar, LLC | Tap 138kV 3472 BRIAR_CRK_8 – 3467 POWELL1_8 | Navarro | NORTH | 2027-11-01 | SOL | PV | 125.84 | COD | 2023-05-12 | 2024-07-30 | 2023-09-01 | 2023-06-13 |  |  | 2025-11-21 | Yes |  |  | Not Required
26INR0131 | Elm Flats Storage SLF | SS Completed, FIS Started, IA | Orca Falls Solar, LLC | Tap 138kV 3472 BRIAR_CRK_8 – 3467 POWELL1_8 | Navarro | NORTH | 2027-11-01 | OTH | BA | 0 | COD | 2023-05-17 | 2023-06-07 | 2023-09-01 | 2023-05-22 |  |  | 2025-11-21 | Yes | Not Required | Not Required
26INR0180 | Cape Rich BESS | SS Completed, FIS Completed, IA | Cape Rich BESS | 3387 Revolution Switch 138kV | Navarro | NORTH | 2030-04-18 | OTH | BA | 150.52 |  | 2023-07-03 | 2023-07-10 | 2023-10-06 | 2023-07-03 | 2024-06-26 | No | 2025-02-03 | No | Not Required | Not Required
26INR0228 | Santa Monica Solar | SS Completed, FIS Completed, No IA | Karol Solar IV | Tap 345 KV 68091 NAVARRO - 3381 BIGBRNW_5 Ckt 2 | Navarro | NORTH | 2028-09-20 | SOL | PV | 105.85 |  | 2024-10-03 | 2023-09-07 | 2023-12-04 | 2024-09-24 | 2026-08-12 | No |  | No |  |  | Not Required
28INR0182 | Ponferrada Solar | SS Completed, FIS Started, No IA | Karol Solar VI | Tap 138 KV 3456 CORSWEST1_8 - 3457 CORS_MOBT_8 | Navarro | NORTH | 2029-04-06 | SOL | PV | 148.87 |  | 2025-04-02 | 2024-10-01 | 2024-12-18 | 2025-04-15 |  |  |  | No |  |  | Not Required
28INR0292 | Wildflower Storage | SS Completed, FIS Started, No IA | Wildflower Storage LLC | Drane switch #3295 | Navarro | NORTH | 2028-09-30 | OTH | BA | 359.1 |  | 2025-05-08 | 2025-06-05 | 2025-09-02 | 2025-05-15 |  |  |  | No
28INR0335 | Oak Valley Solar | SS Completed, FIS Started, No IA | Oak Valley Solar LLC | 68091 (Navarro) (345) | Navarro | NORTH | 2029-09-28 | SOL | PV | 251.3 |  | 2025-03-25 | 2025-04-01 | 2025-06-25 | 2025-03-19 |  | Yes |  | No |  |  | Not Required
28INR0467 | Main Horn Solar | SS Completed, FIS Started, No IA | Main Horn Solar LLC | 3387 Revolution 138 KV | Navarro | NORTH | 2029-09-17 | SOL | PV | 100.43 |  | 2025-12-29 | 2026-01-13 | 2026-02-09 | 2025-12-29 |  | No |  | No |  |  | Not Required
17INR0068 | Sweetwater 2 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2024-11-30 | WIN | WT | 7.3 |  | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-10-05 | 2017-11-10 | No | 2003-06-27 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2017-12-20
17INR0069 | Trent repower | SS Completed, FIS Completed, IA | TRENT WIND FARM LLC | 1338 Eskota 138kV | Nolan | WEST | 2026-01-01 | WIN | WT | 6.4 |  | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-03-01 | No | 2018-10-19 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-05-09
18INR0031 | Maryneal Wind | SS Completed, FIS Completed, IA | Maryneal Windpower, LLC | 71050 Bitter Creek 345kV | Nolan | WEST | 2026-08-31 | WIN | WT | 182.4 |  | 2016-07-22 | 2016-05-26 | 2016-07-21 | 2016-07-22 | 2020-01-31 | No | 2020-01-31 | Yes | Not Required | Not Required | Not Required | 2020-01-31 | 2020-01-31 | 2020-01-31 |  |  | 2021-01-08 | 2021-04-23
18INR0073 | Sweetwater 1 repower | SS Completed, FIS Completed, IA | Leeward Energy | 71050 Bitter Creek 345kV | Nolan | WEST | 2024-11-30 | WIN | WT | 3 |  | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-02-09 | 2018-12-27 | No | 2002-10-23 | No | Not Required | Not Required | Not Required
23INR0008 | Harley Hand Solar | SS Completed, FIS Started, No IA | HECTATE ENERGY HARLEY HAND SOLAR LLC | 11420 Sweetwater East 345kV | Nolan | WEST | 2029-04-07 | SOL | PV | 505.5 |  | 2019-12-12 | 2019-12-16 | 2020-03-11 | 2019-12-06 |  | No |  | No | Not Required | Not Required | Not Required
23INR0214 | Harley Hand Storage | SS Completed, FIS Started, No IA | Hecate Energy Harley Hand Storage LLC | 11420 Sweetwater East 345kV | Nolan | WEST | 2029-04-07 | OTH | BA | 503.4 |  | 2022-04-04 | 2021-03-01 | 2021-05-13 | 2022-03-22 |  |  |  | No | Not Required | Not Required
23INR0473 | Sepanta Solar | SS Completed, FIS Started, No IA | BREG - Belgian Renewable Energy Group | 10198 ESKOTA_9 138kV (PSS/E BUS #10198, Station Name: ESKOTA_8, kV: 138 kV) Property is adjacent (West) to the Oncor Sweetwater Eskota Switch #10198. POI would simply be on the other side of the fence of the switch. | Nolan | WEST | 2029-09-18 | SOL | PV | 218 |  | 2022-11-17 | 2022-10-18 | 2023-01-13 | 2022-11-15 |  | No |  | No |  |  | Not Required
24INR0627 | Champion Wind Repower | SS Completed, FIS Completed, IA | Champion Wind Farm, LLC | Bus# 1048 - Tonkawa | Nolan | WEST | 2026-12-31 | WIN | WT | 0.31 |  | 2023-09-13 | 2023-09-25 | 2023-12-21 | 2023-09-13 | 2024-04-26 |  | 2007-01-19 | Yes | Not Required | Not Required | Not Required | 2024-07-29 | 2024-07-30 | 2024-07-30 |  |  |  | 2025-01-13
26INR0297 | Buzzi Maryneal Wind Project | SS Completed, FIS Started, No IA | Buzzi Unicem USA | 1413 SWEETCRK-9 | Nolan | WEST | 2026-01-02 | WIN | WT | 18 |  | 2023-10-02 | 2023-10-25 | 2024-01-22 | 2023-10-16 |  | No |  | No | Not Required | Not Required | Not Required
26INR0625 | Buffalo Gap 2 Wind Repower | SS Completed, FIS Completed, IA | Buffalo Gap Wind Farm 2, LLC | 6216 Bluff Creek 138 kV | Nolan | WEST | 2027-02-01 | WIN | WT | 231.49 |  | 2024-12-03 | 2024-12-19 | 2025-02-20 | 2024-11-26 | 2026-03-17 | No | 2005-02-28 | Yes | Not Required | Not Required | Not Required | 2026-03-25 | 2026-05-05 | 2026-05-05
27INR0218 | Themisto Solar | SS Completed, FIS Started, No IA | Themisto Solar, LLC | Tap 345kV Champion Creek #1414 – Sweetwater East #11420 | Nolan | WEST | 2029-06-30 | SOL | PV | 301.4 |  | 2023-08-23 | 2024-02-26 | 2024-05-24 | 2024-02-13 |  | No |  | No |  |  | Not Required
27INR0575 | Trailblazer Natural Gas Generation Plant | SS Completed, FIS Started, No IA | Trailblazer Infrastructure LLC | 11420 Sweetwater East Switch 345 kV | Nolan | WEST | 2027-12-12 | GAS | GT | 1026 |  | 2026-04-29 | 2026-05-11 | 2026-08-06 | 2026-04-30 |  |  |  | No
27INR0576 | Trailblazer BESS | SS Completed, FIS Started, No IA | Trailblazer Infrastructure LLC | 11420 Sweetwater East Switch 345 kV | Nolan | WEST | 2027-12-12 | OTH | BA | 261.97 |  | 2026-02-24 | 2026-03-18 | 2026-06-15 | 2026-03-11 |  | No |  | No
27INR0578 | Trailblazer Solar | SS Completed, FIS Started, No IA | Trailblazer Infrastructure LLC | #11420 Sweetwater East Switch 345 kV | Nolan | WEST | 2027-12-12 | SOL | PV | 323.02 |  | 2026-03-18 | 2026-03-18 | 2026-06-15 | 2026-03-11 |  | No |  | No |  |  | Not Required
28INR0349 | Jaguarundi Energy Storage | SS Completed, FIS Started, No IA | PowerPulse LLC | Bus # 1339, Eskota 138kV | Nolan | WEST | 2029-11-10 | OTH | BA | 152.02 |  | 2025-05-29 | 2025-06-05 | 2025-09-02 | 2025-06-02 |  |  |  | No
28INR0386 | Sagebrush Wind | SS Completed, FIS Started, No IA | ACE DevCo NC, LLC | TAP 345KV 11420 SWEETWATER EAST - 11406 CENTRAL BLUFF CKT2 | Nolan | WEST | 2029-12-01 | WIN | WT | 200.5 |  | 2025-05-28 | 2025-07-29 | 2025-10-06 | 2025-07-28 |  |  |  | No |  |  | Not Required
28INR0504 | Sweetwater 5 Repower | SS Completed, FIS Started, No IA | Sweetwater Wind 5 LLC | Bitter Creek Substation | Nolan | WEST | 2029-02-01 | WIN | WT | 79.1 |  | 2026-04-13 | 2026-04-22 | 2026-07-08 | 2026-04-13 |  |  |  | No |  |  | Not Required
29INR0325 | Sweetwater 4 Repower | SS Completed, FIS Started, No IA | Sweetwater Wind 4 LLC | <71050> <L_BITTCR5_1Y> <345kV> | Nolan | WEST | 2029-02-01 | WIN | WT | 421.2 |  | 2026-04-13 | 2026-04-22 | 2026-07-08 | 2026-04-13 |  |  |  | No |  |  | Not Required
23INR0061 | Noria Solar DCC | SS Completed, FIS Started, IA | Noria Hondo Solar LLC | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2028-04-21 | SOL | PV | 145 |  | 2021-03-15 | 2020-08-04 | 2020-10-28 | 2021-03-10 |  |  | 2022-10-12 | Yes |  |  | Not Required | 2025-02-12
23INR0062 | Noria Storage | SS Completed, FIS Started, IA | Noria Hondo Solar LLC | 85000 Nelson Sharpe 345kV | Nueces | COASTAL | 2028-04-21 | OTH | BA | 75 |  | 2021-04-01 | 2020-08-04 | 2020-10-28 | 2021-03-30 |  |  | 2022-10-12 | Yes | Not Required | Not Required |  | 2023-04-12
24INR0528 | Blanquilla BESS | SS Completed, FIS Started, IA | Blanquilla BESS LLC | Tap 138kV 8452 LON_HILL4A - 8441 NUECES_B4A | Nueces | COASTAL | 2028-05-19 | OTH | BA | 200.78 |  | 2023-03-14 | 2023-02-09 | 2023-05-08 | 2023-03-07 |  |  | 2024-09-05 | Yes |  |  |  | 2025-02-13 | 2025-07-31 | 2025-07-16
25INR0076 | Violet Storage | SS Completed, FIS Started, No IA | VIOLET STORAGE | McKenzie Road (8858) 138 kV Substation | Nueces | COASTAL | 2029-07-01 | OTH | BA | 151 |  | 2022-04-13 | 2022-05-10 | 2022-08-06 | 2022-04-14 |  | No |  | No
25INR0329 | Lynx Energy Storage | SS Completed, FIS Completed, IA | Corpus Battery Storage, LLC | 138KV Tap 8921 Terra Verde - 8518 Kingsville | Nueces | COASTAL | 2026-05-01 | OTH | BA | 125.3 |  | 2023-03-02 | 2023-03-08 | 2023-06-01 | 2023-03-01 | 2025-08-22 | No | 2024-04-09 | Yes | Not Required | Not Required |  | 2025-02-12 | 2025-10-23 | 2025-10-24 |  |  | 2026-03-19 | 2026-04-07
25INR0375 | NavBoot BESS | SS Completed, FIS Started, IA | Navboot BESS LLC | 8858 MCKENZIE4A 138kV | Nueces | COASTAL | 2027-11-11 | OTH | BA | 303.7 |  | 2023-03-10 | 2023-03-13 | 2023-06-09 | 2023-03-10 |  | No | 2025-10-20 | No
26INR0222 | GOTHAM BESS | SS Completed, FIS Started, No IA | AEU BATTERY PROJECT IV LLC | 5640 DRISCOLLSUB9 69kV | Nueces | COASTAL | 2027-03-17 | OTH | BA | 151.2 |  | 2024-07-01 | 2023-07-31 | 2023-10-27 | 2024-06-17 |  |  |  | No
27INR0047 | Sunscape Renewable Energy Solar SLF | SS Completed, FIS Started, IA | Sunscape Renewable Energy LLC | Bus# 8455 Lon C Hill to Bus# 80078 Reforzar 345 kV Line | Nueces | COASTAL | 2028-10-31 | SOL | PV | 522.75 |  | 2023-06-14 | 2023-06-28 | 2023-09-20 | 2023-05-30 |  | Yes | 2024-07-18 | Yes |  |  | Not Required | 2025-08-10
27INR0048 | Sunscape Renewable Energy Storage SLF | SS Completed, FIS Started, IA | Sunscape Renewable Energy LLC | Tap 345kV 8455 Lon C Hill -- 80078 Reforzar | Nueces | COASTAL | 2028-10-31 | OTH | BA | 0 |  | 2023-06-06 | 2023-06-28 | 2023-09-20 | 2023-06-06 |  | Yes | 2024-07-18 | Yes |  |  |  | 2025-08-10
27INR0337 | Jalisco Cogen | SS Completed, FIS Started, No IA | HEP Power Generation, LLC | 8475 JAVELINA4A 138 KV | Nueces | COASTAL | 2029-05-31 | GAS | CC | 167.8 |  | 2025-05-06 | 2024-08-16 | 2024-11-05 | 2025-05-01 |  | No |  | No
27INR0655 | Lynx Energy Storage_Full | SS Started, FIS Started, No IA | Corpus Battery Storage, LLC | PRIMAVERA 138kV Substation | Nueces | COASTAL | 2027-12-01 | MWH | SO | 50 | FIS Request | 2026-08-20 | 2026-08-06 |  | 2026-09-01 |  |  |  | No
28INR0121 | Jalisco Peaker | SS Completed, FIS Started, No IA | HEP Power Generation, LLC | 8475 JAVELINA4A 138kV | Nueces | COASTAL | 2029-05-31 | GAS | GT | 183.6 |  | 2025-05-06 | 2024-08-16 | 2024-11-04 | 2025-05-01 |  | No |  | No
28INR0437 | Barbara BESS | SS Completed, FIS Started, No IA | Barbara BESS LLC | LINE TAP OF WESTSIDE (8485) AND WEIL TRACT (8482) 138 KV TRANSMISSION LINE | Nueces | COASTAL | 2028-05-02 | OTH | BA | 200.51 |  | 2025-09-16 | 2025-09-22 | 2025-12-02 | 2025-10-01 |  |  |  | No
21INR0509 | McClure Solar | SS Completed, FIS Started, No IA | McClure Solar LLC | tap 69kV 785 Oran - 343 Morris Sheppard | Palo Pinto | NORTH | 2025-12-31 | SOL | PV | 105.73 |  | 2021-03-18 | 2020-06-03 | 2020-08-18 | 2021-02-24 |  | No |  | No |  |  | Not Required
25INR0482 | Vault Solar | SS Completed, FIS Completed, IA | PPM THR Solar | Tap #331 Rwmiller - #320 Jaybird 138kV | Palo Pinto | NORTH | 2027-12-31 | SOL | PV | 108.5 |  | 2023-06-20 | 2023-06-28 | 2023-09-20 | 2023-06-16 | 2024-12-02 | No | 2026-06-30 | Yes |  |  | Not Required
26INR0364 | Pollo Pinto Solar | SS Completed, FIS Completed, No IA | TX Palo Pinto SB 6, LLC | Tap 138kV 331 RWMILLER - 320 JAYBIRD | Palo Pinto | NORTH | 2029-02-24 | SOL | PV | 100.57 |  | 2023-12-11 | 2024-02-27 | 2024-05-20 | 2024-02-26 | 2026-04-01 |  |  | No |  |  | Not Required
23INR0368 | Rocking X Solar | SS Completed, FIS Started, No IA | 7100 Tin Top LLC | Tap the 345 kV Parker Switch (bus#1436) – Comanche Peak SES (bus#1900) Double-Circuit line, Circuit 1. | Parker | NORTH | 2027-09-20 | SOL | PV | 602.2 |  | 2023-09-25 | 2023-10-04 | 2023-12-19 | 2023-09-06 |  | No |  | No | Not Required | Not Required | Not Required
26INR0498 | Buckaroo BESS | SS Completed, FIS Started, No IA | Weatherford BESS LLC | Tap 138kV BROCK(487) – STHBROCKSW(489) | Parker | NORTH | 2027-12-08 | OTH | BA | 120 |  | 2024-11-25 | 2024-05-09 | 2024-08-05 | 2024-11-11 |  |  |  | No
27INR0571 | Nabla Energy Storage I | SS Completed, FIS Started, No IA | Nabla Park LLC | Double Tap 345kV Parker (1436) - Benbrook (1873 & 1869) DCKT | Parker | NORTH | 2029-09-17 | OTH | BA | 750 |  | 2025-10-29 | 2025-11-05 | 2026-01-12 | 2025-10-30 |  |  |  | No | Not Required | Not Required
28INR0466 | Nabla Energy Storage II | SS Completed, FIS Started, No IA | Nabla Park LLC | Double Tap 345kV Parker (1436) - Benbrook (1873 & 1869) DCKT | Parker | NORTH | 2029-09-17 | OTH | BA | 750 |  | 2025-10-29 | 2025-11-05 | 2026-01-12 | 2025-10-30 |  |  |  | No | Not Required | Not Required
17INR0070 | Desert Sky repower | SS Completed, FIS Completed, IA | DESERT SKY WIND FARM LLC | two LCRA 138kV | Pecos | WEST | 2023-05-16 | WIN | WT | 7.2 |  | 2017-11-08 | 2017-11-08 | 2017-11-28 | 2017-11-08 | 2018-02-06 | No | 2018-10-18 | Yes | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2019-09-06
18INR0069 | Indian Mesa repower | SS Completed, FIS Completed, IA | Nextera | 76019 Indian NWP 138kV | Pecos | WEST | 2026-12-31 | WIN | WT | 9.3 |  | 2018-05-22 | 2018-05-22 | 2018-08-29 | 2018-05-22 | 2018-10-03 | No | 2018-12-04 | No | Not Required | Not Required | Not Required | 2018-10-31 | 2018-10-31 | 2018-10-31 |  |  |  | 2018-11-02
18INR0079 | Woodward I repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2026-12-31 | WIN | WT | 0 |  | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2019-01-09 | No | 2018-12-12 | Yes | Not Required | Not Required | Not Required | 2020-10-30 | 2020-10-30 | 2020-10-30 |  |  | 2019-11-07 | 2019-11-13
18INR0080 | Woodward 2 repower | SS Completed, FIS Completed, IA | Nextera | 60400 Lynx 138kV | Pecos | WEST | 2026-12-31 | WIN | WT | 0 |  | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-06-19 | 2018-11-27 | No | 2018-12-18 | Yes | Not Required | Not Required | Not Required | 2018-11-29 | 2018-11-29 | 2020-10-30 |  |  |  | 2018-12-19
19INR0120 | Sherbino II Wind repower | SS Completed, FIS Completed, IA | Sherbino II Wind Farm LLC | 38430 TN White Baker 138kV | Pecos | WEST | 2026-08-22 | WIN | WT | -18 |  | 2017-09-21 | 2017-08-18 | 2017-09-28 | 2017-09-21 | 2018-12-04 | No | 2008-02-28 | Yes | Not Required | Not Required | Not Required | 2019-10-28 | 2019-10-28 | 2019-10-28 |  |  |  | 2020-06-09
22INR0365 | Mensa BESS | SS Completed, FIS Started, No IA | BRP Mensa BESS LLC | 60718 Pecos Valley 138kV | Pecos | WEST | 2028-06-01 | OTH | BA | 308.98 |  | 2020-07-03 | 2020-06-26 | 2020-09-14 | 2020-06-22 |  |  |  | No | Not Required | Not Required
22INR0386 | BRP Octans BESS | SS Completed, FIS Started, No IA | BRP OCTANS BESS LLC | 6671 Tombstone 138kV | Pecos | WEST | 2029-12-01 | OTH | BA | 129.57 |  | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  | No |  | No
24INR0452 | Longfellow Solar I | SS Completed, FIS Started, IA | CENTURY GAS PROCESSING, LLC | 38431 TNCENTRY1_1 138 KV | Pecos | WEST | 2028-12-31 | SOL | PV | 178.2 |  | 2023-04-26 | 2022-11-07 | 2023-02-03 | 2023-04-17 |  | No | 2025-04-15 | No |  |  | Not Required
24INR0453 | Longfellow BESS I | SS Completed, FIS Completed, IA | CENTURY GAS PROCESSING, LLC | 38432 TNCENTRY1_1 138 KV | Pecos | WEST | 2028-03-30 | OTH | BA | 54.99 | COD | 2023-04-25 | 2022-11-07 | 2023-02-03 | 2023-04-12 | 2025-12-17 |  | 2025-04-15 | Yes | Not Required | Not Required |  | 2025-04-29 | 2026-01-29 | 2026-01-29
24INR0454 | Longfellow Solar II | SS Completed, FIS Started, IA | CENTURY GAS PROCESSING, LLC | 38432 TNCENTRY2_1 138 KV | Pecos | WEST | 2028-12-31 | SOL | PV | 207.36 |  | 2023-04-25 | 2022-11-07 | 2023-02-03 | 2023-04-13 |  | No | 2025-04-15 | No |  |  | Not Required
24INR0455 | Longfellow BESS II | SS Completed, FIS Completed, IA | CENTURY GAS PROCESSING, LLC | 38432 TNCENTRY2_1 138 KV | Pecos | WEST | 2028-03-30 | OTH | BA | 105.75 | COD | 2023-04-26 | 2022-11-07 | 2023-02-03 | 2023-04-12 | 2025-12-17 |  | 2025-04-15 | Yes | Not Required | Not Required |  | 2025-04-29 | 2026-01-29 | 2026-01-29
26INR0230 | Titus Sienta Solar | SS Completed, FIS Completed, No IA | Sol Sienta Solar, LLC | Tap 138kV 1239 Coyanosa - 11238 Blair Lake Sub | Pecos | WEST | 2029-04-19 | SOL | PV | 501.93 | Status Change INA-to-PLN | 2023-08-21 | 2023-10-13 | 2024-01-09 | 2023-10-09 | 2026-02-27 |  |  | No |  |  | Not Required |  |  |  | 2025-10-01 | 2026-04-01
26INR0296 | Sherbino II BESS SLF | SS Completed, FIS Completed, IA | Phoenix Battery Storage, LLC | 38430 TNMP White baker Switching Station 138kV | Pecos | WEST | 2027-04-19 | OTH | BA | 77.37 |  | 2023-11-19 | 2023-11-30 | 2024-02-27 | 2023-11-16 | 2025-04-23 |  | 2024-08-01 | Yes |  |  |  | 2025-02-12 | 2025-05-14 | 2025-05-01
26INR0537 | Comanche Creek generating station | SS Completed, FIS Started, No IA | Longfellow Power LLC | TNCENTRY1_1 [138 kV] ( 38431) | Pecos | WEST | 2027-12-31 | GAS | IC | 107 |  | 2024-06-10 | 2024-07-01 | 2024-09-23 | 2024-06-18 |  |  |  | No
26INR0550 | Grand Mesa BESS | SS Completed, FIS Started, No IA | PERRY GREEN POWER LLC | 76582 MESA VIEW SWITCH 138kV | Pecos | WEST | 2027-09-28 | OTH | BA | 253.28 |  | 2024-08-02 | 2024-08-16 | 2024-11-13 | 2024-08-01 |  |  |  | No
26INR0715 | Tierra Bonita BESS SLF | SS Completed, FIS Started, No IA | Greasewood II BESS LLC | 860 GIRVINSW 345kV | Pecos | WEST | 2029-06-01 | OTH | BA | 0 |  | 2025-12-30 | 2026-01-26 | 2026-04-17 | 2026-01-16 |  | No |  | No
27INR0056 | Laurel Wind Energy Center | SS Completed, FIS Started, IA | LAUREL ENERGY CENTER, LLC | Tap Solstice to Bakersfield (Bus# 60404 -76002) 345kV Ckt 2 and Tap Solstice to Bakersfield (Bus# 60404 -76002) 345kV Ckt 1 | Pecos | WEST | 2027-12-31 | WIN | WT | 306.6 |  | 2023-06-15 | 2023-06-28 | 2023-09-22 | 2023-06-08 |  | Yes | 2024-10-25 | Yes | Not Required | Not Required | Not Required | 2025-09-15
27INR0139 | Gatsby Energy Storage | SS Completed, FIS Started, No IA | Gatsby Energy Storage LLC | Fort Lancaster 138 kV Substation (PSSE Bus #76579) | Pecos | WEST | 2030-12-31 | OTH | BA | 103.36 |  | 2023-12-07 | 2024-02-07 | 2024-04-29 | 2023-12-07 |  |  |  | No
27INR0146 | Larrea Solar | SS Completed, FIS Started, No IA | Greasewood IV LLC | Tap 345kV 76002 Bakerfield - 60404 Solstice CKT#1 | Pecos | WEST | 2029-09-18 | SOL | PV | 231.6 | COD | 2024-06-10 | 2024-01-03 | 2024-03-29 | 2024-06-05 |  |  |  | No |  |  | Not Required
27INR0438 | Wisdom Solar SLF | SS Completed, FIS Completed, IA | Wisdom Green Energy LLC | Tap 138 kV #38455 HOLIDAY SUB TNP - #38450 SOAPTREE TNP | Pecos | WEST | 2027-10-06 | SOL | PV | 299.37 |  | 2025-01-17 | 2025-02-12 | 2025-04-18 | 2025-02-05 | 2025-10-09 | No | 2026-03-18 | No |  |  | Not Required
27INR0440 | Wisdom BESS SLF | SS Completed, FIS Completed, IA | Wisdom Green Energy LLC | Tap 138 kV #38455 HOLIDAY SUB TNP - 138 kV #38450 SOAPTREE TNP | Pecos | WEST | 2027-10-06 | OTH | BA | 102.88 |  | 2025-01-27 | 2025-02-12 | 2025-04-18 | 2025-02-21 | 2025-10-09 | No | 2026-03-18 | No
27INR0510 | Pecos Wind | SS Completed, FIS Not Started, IA | Midnight Energy Center, LLC | Tap 345 kV 60404 Solstice (SOLSTICE7A) – 76002 Bakersfield (L_BAKERS5_1Y) | Pecos | WEST | 2028-05-30 | WIN | WT | 193.8 |  | 2025-07-23 | 2025-07-07 | 2025-09-30 |  |  |  | 2026-03-18 | No |  |  | Not Required
27INR0620 | st gall IIIA Storage | SS Completed, FIS Started, No IA | Tempus Power Management LLC | 38355 LEON_CRK 138kV | Pecos | WEST | 2028-06-01 | OTH | BA | 200.69 |  | 2026-04-22 | 2026-04-22 | 2026-07-07 | 2026-03-17 |  |  |  | No | Not Required | Not Required
27INR0621 | st gall IIIB Storage | SS Completed, FIS Started, No IA | Tempus Power Management LLC | 38355 LEON_CRK 138kV | Pecos | WEST | 2028-06-01 | OTH | BA | 200.69 |  | 2026-04-22 | 2026-04-22 | 2026-07-07 | 2026-03-17 |  |  |  | No | Not Required | Not Required
27INR0653 | Rock House Draw Gas | SS Completed, FIS Started, No IA | Longfellow Power LLC | 38431 TNCENTRY1_1 138 KV | Pecos | WEST | 2027-11-29 | GAS | IC | 523 |  | 2026-06-25 | 2026-06-25 | 2026-09-20 | 2026-06-25 |  |  |  | No
28INR0114 | Elk Ridge Solar | SS Completed, FIS Started, IA | Elk Ridge Solar, LLC | AEP Solstice Substation #60404 | Pecos | WEST | 2030-07-01 | SOL | PV | 503 | SFS/NtP | 2025-09-26 | 2025-11-05 | 2026-01-12 | 2025-09-26 |  | No | 2026-09-22 | Yes |  |  | Not Required
28INR0260 | Rio Vista Solar | SS Completed, FIS Started, No IA | Rio Vista Solar, LLC | Tap 138kV #60393 PigCreek4A – #60385 Solstice4A | Pecos | WEST | 2030-09-02 | SOL | PV | 553.66 |  | 2025-01-13 | 2025-06-19 | 2025-09-17 | 2025-01-21 |  |  |  | No |  |  | Not Required
28INR0261 | Rio Vista Storage | SS Completed, FIS Started, No IA | Rio Vista Storage, LLC | Tap 138kV #60393 Pigcreek4A – #60385 Solstice4A | Pecos | WEST | 2030-09-02 | OTH | BA | 103.37 |  | 2025-01-14 | 2025-06-19 | 2025-09-17 | 2025-01-21 |  |  |  | No
29INR0025 | Skyrider Wind | SS Completed, FIS Started, IA | NextEra Energy Interconnection Holdings, LLC | 138kV #38365 TNPINION | Pecos | WEST | 2028-07-01 | WIN | WT | 370 |  | 2024-11-04 | 2024-11-19 | 2025-02-18 | 2024-10-29 |  | No | 2025-12-23 | Yes | Not Required |  | Not Required | 2026-03-30
29INR0147 | Selenite Springs Solar | SS Completed, FIS Started, IA | Selenite Springs Solar, LLC | Tap 138kV 38355 Leon Creek Switching Station - 38308 Woodhouse Switching Station | Pecos | WEST | 2028-08-30 | SOL | PV | 253 |  | 2025-04-16 | 2025-04-21 | 2025-07-19 | 2025-04-18 |  | No | 2025-12-24 | Yes | Not Required | Not Required | Not Required | 2026-03-24
29INR0181 | Pecos Flats Solar | SS Completed, FIS Started, No IA | Glass Mountain Solar, LLC | 60404 SOLSTICE 345 kV | Pecos | WEST | 2029-10-20 | SOL | PV | 302.38 |  | 2025-08-22 | 2025-09-22 | 2025-12-15 | 2025-09-05 |  |  |  | No |  |  | Not Required
29INR0182 | Pecos Flats Solar II | SS Completed, FIS Started, No IA | Glass Mountain Solar, LLC | Tap 345 kV 60404 SOLSTICE - 11098 SANDLAKE_5 | Pecos | WEST | 2029-02-05 | SOL | PV | 301.5 |  | 2025-08-25 | 2025-09-22 | 2025-12-15 | 2025-09-05 |  |  |  | No |  |  | Not Required
29INR0183 | Pecos Flats Solar III | SS Completed, FIS Started, No IA | Glass Mountain Solar, LLC | Tap 345 kV 60404 SOLSTICE - 11098 SANDLAKE_5 | Pecos | WEST | 2029-02-05 | SOL | PV | 301.5 |  | 2025-08-25 | 2025-09-22 | 2025-12-15 | 2025-09-05 |  |  |  | No |  |  | Not Required
29INR0188 | Star Of Texas Solar | SS Completed, FIS Started, No IA | BOULEVARD ASSOCIATES, LLC | 60152 Fort Stockton Switch 345kV | Pecos | WEST | 2029-07-01 | SOL | PV | 415 |  | 2025-08-05 | 2025-08-18 | 2025-11-10 | 2025-08-12 |  | No |  | No |  |  | Not Required
29INR0263 | Whitethorn Solar Project | SS Completed, FIS Started, No IA | Greasewood III LLC | 345KV 860 GIRVINSW | Pecos | WEST | 2029-04-26 | SOL | PV | 163.1 | FIS Request | 2026-09-08 | 2026-01-13 | 2026-04-10 |  |  | No |  | No |  |  | Not Required
29INR0287 | Valentine Energy Center | SS Completed, FIS Started, No IA | Valentine Energy Center, LLC | 60400 Lynx 138kV | Pecos | WEST | 2031-02-28 | GAS | IC | 162.3 |  | 2026-02-09 | 2026-02-10 | 2026-03-26 | 2026-02-09 |  |  |  | No
29INR0324 | Ashtrom Marigold BESS SLF | SS Started, FIS Started, No IA | Marigold BESS LLC | 860 GIRVINSW 345kV | Pecos | WEST | 2029-04-26 | OTH | BA | 153.9 |  | 2026-06-30 | 2026-07-08 |  | 2026-07-07 |  |  |  | No
29INR0347 | Glass Mountain BB Solar 1 | SS Completed, FIS Started, No IA | Glass Mountain Solar, LLC | Tap 345kV 60404 Solstice to 38441 Bottlebrush | Pecos | WEST | 2029-03-01 | SOL | PV | 302.66 |  | 2026-06-10 | 2026-06-11 | 2026-08-28 | 2026-05-29 |  |  |  | No |  |  | Not Required
29INR0348 | Glass Mountain BB Solar 2 | SS Completed, FIS Started, No IA | Glass Mountain Solar II, LLC | Tap 345kV 60404 Solstice to 38441 Bottlebrush | Pecos | WEST | 2029-03-01 | SOL | PV | 302.66 |  | 2026-06-10 | 2026-06-11 | 2026-08-28 | 2026-05-29 |  |  |  | No |  |  | Not Required
29INR0349 | Glass Mountain BB Solar 5 | SS Completed, FIS Started, No IA | Glass Mountain Solar V, LLC | Tap 345kV 60404 Solstice to 38441 Bottlebrush | Pecos | WEST | 2029-10-01 | SOL | PV | 302.61 |  | 2026-06-11 | 2026-06-11 | 2026-08-28 | 2026-05-29 |  |  |  | No |  |  | Not Required
29INR0357 | Glass Mountain BB Solar 3 | SS Completed, FIS Started, No IA | Glass Mountain Solar III, LLC | Tap 345kV 60404 Solstice to 38441 Bottlebrush | Pecos | WEST | 2029-10-01 | SOL | PV | 302.61 |  | 2026-06-11 | 2026-06-11 | 2026-08-28 | 2026-05-29 |  |  |  | No |  |  | Not Required
29INR0358 | Glass Mountain BB Solar 4 | SS Completed, FIS Started, No IA | Glass Mountain Solar IV, LLC | Tap 345kV 60404 Solstice to 38441 Bottlebrush | Pecos | WEST | 2029-10-01 | SOL | PV | 302.61 |  | 2026-06-11 | 2026-06-11 | 2026-08-28 | 2026-05-29 |  |  |  | No |  |  | Not Required
30INR0018 | Big Canyon Wind | SS Completed, FIS Started, IA | Longfellow Wind, LLC | 38441 Bottlebrush 345kV | Pecos | WEST | 2030-07-01 | WIN | WT | 1500 |  | 2025-01-07 | 2025-01-13 | 2025-04-08 | 2025-01-08 |  | Yes | 2025-12-24 | Yes |  |  | Not Required | 2026-03-25
30INR0053 | MRR Solar | SS Completed, FIS Started, IA | Antler Peak Solar, LLC | Solstice Substation #60384 -AEP | Pecos | WEST | 2030-07-01 | SOL | PV | 500 | SFS/NtP | 2025-07-15 | 2025-07-29 | 2025-10-26 | 2025-07-18 |  | Yes | 2026-09-15 | Yes |  |  | Not Required
30INR0058 | Springfield Solar | SS Completed, FIS Started, IA | BOULEVARD ASSOCIATES, LLC | Tap Leon Creek (#38355) to Woodhouse Station (#38308) 138kV line | Pecos | WEST | 2028-08-30 | SOL | PV | 400 |  | 2025-08-12 | 2025-09-09 | 2025-10-15 | 2025-09-08 |  | No | 2025-12-24 | Yes | Not Required | Not Required | Not Required | 2026-03-24
30INR0083 | Gravitas I Solar | SS Completed, FIS Started, No IA | S&S Renewables, LLC | Tap 345kV Solstice (60404) - Bakersfield (76002) Double circuit line | Pecos | WEST | 2030-06-30 | SOL | PV | 1124.75 |  | 2026-03-19 | 2026-03-24 | 2026-06-19 | 2026-03-18 |  |  |  | No |  |  | Not Required
30INR0084 | Gravitas I Natural Gas | SS Completed, FIS Started, No IA | S&S Renewables, LLC | Tap 345kV Solstice (60404) - Bakersfield (76002) Double circuit line | Pecos | WEST | 2030-06-30 | GAS | IC | 1247.04 |  | 2026-03-19 | 2026-03-24 | 2026-06-19 | 2026-03-18 |  |  |  | No
30INR0085 | Gravitas I Wind | SS Completed, FIS Started, No IA | S&S Renewables, LLC | Tap 345kV Solstice (60404) - Bakersfield (76002) Double circuit line | Pecos | WEST | 2030-06-30 | WIN | WT | 636.54 |  | 2026-03-19 | 2026-03-24 | 2026-06-19 | 2026-03-18 |  |  |  | No |  |  | Not Required
30INR0086 | Permian I Wind | SS Completed, FIS Started, No IA | S&S Renewables, LLC | Tap TNMP White Baker (38435)–Bottlebrush(38441) 345-kV double-circuit | Pecos | WEST | 2030-06-30 | WIN | WT | 636.54 |  | 2026-01-20 | 2026-01-26 | 2026-02-17 | 2026-01-20 |  | No |  | No |  |  | Not Required
30INR0100 | Pentarise BESS | SS Completed, FIS Started, No IA | Pentarise BESS, LLC | 138 kV Pig Creek (#60393) | Pecos | WEST | 2030-06-30 | OTH | BA | 150.6 |  | 2026-06-08 | 2026-06-12 | 2026-09-04 | 2026-06-08 |  |  |  | No
30INR0105 | The Giant Arc-II | SS Completed, FIS Started, No IA | Powering Knowledge, LLC | Bus #60404 SOLSTICE CKT 02 | Pecos | WEST | 2030-04-11 | GAS | IC | 1300 |  | 2026-04-21 | 2026-04-22 | 2026-07-09 | 2026-04-10 |  |  |  | No
30INR0113 | The Giant Arc I | SS Completed, FIS Started, No IA | Powering Knowledge, LLC | Bus #60404 SOLSTICE CKT 01 | Pecos | WEST | 2030-04-08 | GAS | IC | 1300 |  | 2026-05-04 | 2026-05-08 | 2026-07-09 | 2026-04-29 |  |  |  | No
30INR0131 | Pecos Flats Wind I | SS Started, FIS Started, No IA | Pecos Flats Wind, LLC | Tap Bottlebrush (38441) to White Baker (38435) 345kV Line (TNMP) | Pecos | WEST | 2030-06-29 | WIN | WT | 506.9 |  | 2026-07-10 | 2026-07-22 |  | 2026-07-07 |  |  |  | No |  |  | Not Required
30INR0132 | Pecos Flats Wind II | SS Started, FIS Started, No IA | Pecos Flats Wind II, LLC | Tap 345kV 38441 Bottlebrush to 38435 White Baker 345kV line (TNMP) | Pecos | WEST | 2030-06-29 | WIN | WT | 507.9 |  | 2026-07-10 | 2026-07-22 |  | 2026-07-07 |  |  |  | No | Not Required | Not Required | Not Required
31INR0018 | Permian I Solar | SS Completed, FIS Started, No IA | S&S Renewables, LLC | Tap TNMP White Baker (38435)–Bottlebrush(38441) 345-kV double-circuit | Pecos | WEST | 2030-06-30 | SOL | PV | 1125.73 |  | 2026-01-06 | 2026-01-13 | 2026-02-17 | 2025-12-29 |  | No |  | No |  |  | Not Required
31INR0019 | Permian I Natural Gas | SS Completed, FIS Started, No IA | S&S Renewables, LLC | Tap TNMP White Baker (38435)–Bottlebrush(38441) 345-kV double-circuit | Pecos | WEST | 2030-06-30 | GAS | IC | 1246.95 |  | 2026-01-06 | 2026-01-13 | 2026-02-17 | 2025-12-29 |  |  |  | No
25INR0370 | Willis Storage | SS Completed, FIS Completed, IA | Majewski Storage LLC | tap 138kV Emory North 3171 to Liberty POD 1723 | Rains | NORTH | 2028-05-31 | OTH | BA | 176.13 |  | 2023-03-03 | 2023-03-27 | 2023-06-24 | 2023-03-13 | 2024-11-08 |  | 2025-04-07 | Yes |  |  |  | 2025-07-07
22INR0383 | BRP Musca BESS | SS Completed, FIS Started, No IA | BRP Musca BESS LLC | 60361 Santa Rita 138kV | Reagan | WEST | 2027-12-01 | OTH | BA | 100.51 |  | 2020-08-13 | 2020-07-24 | 2020-10-08 | 2020-08-13 |  | No |  | No
27INR0315 | Old Roman Energy Center | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | 23868 STILES 138 KV | Reagan | WEST | 2029-07-26 | OTH | BA | 207.34 |  | 2024-09-11 | 2024-10-01 | 2024-11-13 | 2024-08-30 |  |  |  | No
29INR0042 | Slager Lake Wind | SS Completed, FIS Started, IA | NextEra Energy Resources Interconnection Holdings, LLC | Tap 345kV 59903 Bearkat – 76000 NORTMC5_1Y; Badger 345 kV Station | Reagan | WEST | 2029-07-01 | WIN | WT | 310.2 |  | 2025-09-05 | 2025-09-09 | 2025-11-16 | 2025-09-03 |  |  | 2025-12-23 | No | Not Required | Not Required | Not Required
27INR0292 | Donelson Solar SLF | SS Completed, FIS Started, No IA | Donelson Solar | Tap the 69 kV Bagwell (#1785) - Clarksville (#11784) line, ONCOR | Red River | NORTH | 2028-10-17 | SOL | PV | 75.44 |  | 2025-03-13 | 2025-03-24 | 2025-06-09 | 2025-03-04 |  |  |  | No |  |  | Not Required
27INR0293 | Donelson Storage SLF | SS Completed, FIS Started, No IA | Donelson Storage | Tap the 69 kV Bagwell (#1785) - Clarksville (#11784) line, ONCOR | Red River | NORTH | 2028-10-17 | OTH | BA | 0 |  | 2025-03-13 | 2025-03-24 | 2025-06-09 | 2025-03-04 |  |  |  | No
28INR0124 | Silverbell Storage | SS Completed, FIS Started, No IA | Silverbell Energy Center, LLC | Tap 138kV Rivercrest SES 1780 - Deport REA 1768 | Red River | NORTH | 2028-09-30 | OTH | BA | 129.18 |  | 2024-08-07 | 2024-08-16 | 2024-10-07 | 2024-07-31 |  |  |  | No
28INR0125 | Silverbell Solar | SS Completed, FIS Started, No IA | Silverbell Energy Center, LLC | Tap 138kV Rivercrest SES 1780 - Deport REA 1768 | Red River | NORTH | 2028-09-30 | SOL | PV | 125.59 |  | 2024-08-07 | 2024-08-16 | 2024-10-07 | 2024-07-31 |  |  |  | No |  |  | Not Required
23INR0116 | Cantaloupe Solar | SS Completed, FIS Started, IA | Saragosa Del Sol Energy, LLC | 60716 Saragosa 138kV | Reeves | WEST | 2028-07-01 | SOL | PV | 307 |  | 2020-10-28 | 2020-12-22 | 2021-03-09 | 2020-12-01 |  |  | 2024-04-23 | Yes | Not Required | Not Required | Not Required | 2025-05-28
25INR0112 | August Draw Solar | SS Completed, FIS Started, IA | August Draw Solar Holdings, LLC | Tap 138kV 60207 Verhalen – 60808 Hoefs Road | Reeves | WEST | 2028-06-27 | SOL | PV | 250 |  | 2023-06-22 | 2022-09-15 | 2022-12-13 | 2023-06-09 |  | No | 2025-09-12 | Yes | Not Required | Not Required | Not Required | 2025-09-25
25INR0146 | Blue Heron BESS | SS Completed, FIS Started, IA | Blue Heron BESS, LLC | Tap 138kV MANSON (1094) - Riverton (11083) | Reeves | WEST | 2028-10-11 | OTH | BA | 201.13 | SFS/NtP | 2023-04-26 | 2022-10-24 | 2023-01-20 | 2023-04-10 |  | No | 2026-07-27 | Yes |  |  |  | 2026-09-21
26INR0034 | Bracero Pecan Storage | SS Completed, FIS Started, IA | Bracero Pecan Storage LLC | 60716 SARAGOSA 138kV | Reeves | WEST | 2027-07-01 | OTH | BA | 238.21 |  | 2023-07-13 | 2022-11-07 | 2023-02-04 | 2023-07-10 |  |  | 2024-06-27 | Yes |  |  |  | 2025-02-12
26INR0385 | Nanulak BESS | SS Completed, FIS Completed, IA | Nanulak BESS, L.L.C. | 38113 TNCOYOTSPG1 138kV | Reeves | WEST | 2027-06-30 | OTH | BA | 181.54 | COD | 2025-03-26 | 2024-03-22 | 2024-06-19 | 2025-03-06 | 2026-06-06 |  | 2025-11-19 | No
26INR0388 | Aggie Solar Project SLF | SS Completed, FIS Completed, No IA | reNRG TX 8 LLC | POI: COYOTE SPRINGS SUBSTATION - 138KV BUS NUMBER : 38113 COUNTY : REEVES POI LOCATION: 31.396675, -103.6252777 | Reeves | WEST | 2027-11-30 | SOL | PV | 103.7 |  | 2024-01-17 | 2024-02-02 | 2024-04-29 | 2023-12-08 | 2025-07-03 |  |  | No | Not Required | Not Required | Not Required
26INR0389 | AGGIE STORAGE PROJECT SLF | SS Completed, FIS Completed, No IA | reNRG TX 8 LLC | POI: COYOTE SPRINGS SUBSTATION - 138KV BUS NUMBER: 38113 POI LOCATION: 31.396675, -103.6252777 COUNTY: REEVES | Reeves | WEST | 2027-11-30 | OTH | BA | 0 |  | 2024-01-17 | 2024-02-02 | 2024-04-29 | 2023-12-08 | 2025-07-03 |  |  | No | Not Required | Not Required
26INR0396 | Kodiak AGR1 | SS Completed, FIS Started, No IA | Hunt Energy Network, LLC | 38113 TNCOYOTSPG1 | Reeves | WEST | 2029-06-08 | OIL | OT | 132 | COD | 2024-10-03 | 2024-02-27 | 2024-05-28 | 2024-09-10 |  |  |  | No
26INR0685 | Exergy Energy West Texas Natural Gas Reciprocating Power I | SS Completed, FIS Started, No IA | August Partners LLC | 38095 TNJACKRBT1 138kV | Reeves | WEST | 2027-05-01 | GAS | IC | 400 |  | 2025-12-10 | 2025-07-22 | 2025-10-09 |  |  |  |  | No
27INR0297 | Tolivar Power Plant (TEF- Due Diligence) | SS Completed, FIS Completed, IA | Pecos Power Plant, LLC | Tap 138 KV 38045 IH20-38043 COWPEN | Reeves | WEST | 2027-06-11 | GAS | IC | 224.5 |  | 2024-06-10 | 2024-07-01 | 2025-11-19 | 2024-06-14 | 2025-06-23 | No | 2025-07-01 | Yes | 2024-12-12 | Not Required | 2025-03-25 | 2025-08-04 | 2026-06-16 | 2026-08-06
27INR0572 | Kilby1 Part 1 Small Block Simple Cycle | SS Completed, FIS Started, No IA | Energy Forge One LLC | #60404 Solstice Substation 345 kV | Reeves | WEST | 2027-11-04 | GAS | GT | 371 |  | 2025-10-16 | 2025-10-21 | 2026-01-06 | 2025-10-16 |  |  |  | No
28INR0219 | Neptune Gas Generation Plant | SS Completed, FIS Started, No IA | BPX Production Company | 11200 Longpast_T8 138kv | Reeves | WEST | 2028-03-15 | GAS | IC | 113.77 |  | 2025-10-24 | 2024-12-19 | 2025-04-18 | 2025-10-15 |  |  |  | No
28INR0413 | Tolivar Power Plant Phase 2 | SS Completed, FIS Completed, IA | Pecos Power Plant, LLC | Tap 138 KV 38055 Saltdraw-38043 COWPEN | Reeves | WEST | 2027-09-29 | GAS | IC | 224.5 |  | 2025-07-03 | 2025-07-29 | 2025-10-13 | 2025-07-07 | 2026-02-25 | No | 2026-04-14 | Yes | 2026-03-27 | 2026-03-27 | 2026-06-17 | 2026-05-04
28INR0457 | Kilby1 Part 2 Tier1 BESS | SS Completed, FIS Started, No IA | Energy Forge One LLC | #60404 Solstice Substation 345 kV | Reeves | WEST | 2028-01-21 | OTH | BA | 330 |  | 2025-12-17 | 2026-01-26 | 2026-03-12 | 2026-01-23 |  | No |  | No
28INR0459 | Kilby1 Part 4 Large Block Simple Cycle | SS Completed, FIS Started, No IA | Energy Forge One LLC | #60404 Solstice Substation 345 kV | Reeves | WEST | 2028-04-20 | GAS | GT | 950 |  | 2025-11-17 | 2025-11-18 | 2026-02-04 | 2025-11-06 |  | No |  | No
28INR0468 | Glass Mountain Wind 2 | SS Completed, FIS Started, No IA | Glass Mountain Wind, LLC | Tap 345 kV 60404 SOLSTICE - 11098 SANDLAKE_5 | Reeves | WEST | 2028-12-31 | WIN | WT | 519.2 |  | 2026-01-09 | 2026-01-13 | 2026-04-07 | 2025-12-31 |  | No |  | No |  |  | Not Required
28INR0499 | Alpha Digital Campus Combined-cycle and Co-located Load | SS Completed, FIS Started, No IA | PowerBridge LLC | 38044 TNCOWPEN__3 345kV | Reeves | WEST | 2027-12-31 | GAS | CC | 58.26 |  | 2026-04-06 | 2026-04-28 | 2026-07-09 | 2026-04-15 |  |  |  | No
29INR0194 | Glass Mountain Wind 1 | SS Completed, FIS Started, No IA | Glass Mountain Wind, LLC | Tap 345 kV 60404 SOLSTICE - 11098 SANDLAKE_5 | Reeves | WEST | 2028-12-31 | WIN | WT | 511.5 |  | 2026-01-09 | 2026-01-13 | 2026-04-07 | 2026-01-09 |  |  |  | No |  |  | Not Required
29INR0199 | Kilby1 Part 6 Large Block Combined Cycle | SS Completed, FIS Started, No IA | Energy Forge One LLC | #60404 Solstice Substation 345 kV | Reeves | WEST | 2029-07-19 | GAS | GT | 1056 |  | 2026-02-16 | 2026-02-25 | 2026-05-22 | 2026-02-16 |  |  |  | No
29INR0354 | Wolf Bone North Energy Center | SS Started, FIS Started, No IA | NRG Wolf Bone Energy Center LLC | TNMP Cowpen 345kV Substation POIB 38044 (4 mile transmission line will connect POI at customer substation to POIB in the Cowpen substation) | Reeves | WEST | 2031-02-28 | GAS | CC | 1174.4 | FIS Request | 2026-06-15 | 2026-09-04 |  | 2026-09-01 |  |  |  | No | 2026-09-18
29INR0360 | Trumpet Solar | SS Completed, FIS Started, No IA | NextEra Energy Resources Interconnection Holdings LLC | tap 345kV 18723 Drylake_5 – 38125 TNFaulkner3 | Reeves | WEST | 2029-07-01 | SOL | PV | 533 | MW Size | 2026-06-17 | 2026-06-17 | 2026-09-11 | 2026-06-17 |  |  |  | No |  |  | Not Required
30INR0158 | Capshaw Solar | SS Started, FIS Started, No IA | NextEra Energy Resources Interconnection Holding, LLC | POIB: Tapping Drylake_5 (#18723) – TNFaulkner3 (#38125) 345 kV | Reeves | WEST | 2030-07-01 | SOL | PV | 450 |  | 2026-08-17 | 2026-08-25 |  | 2026-08-20 |  |  |  | No |  |  | Not Required
23INR0047 | Charger Solar | SS Completed, FIS Completed, IA | AP Solar 4, LLC | tap 345kV 8249 Angstrom – 5915 STP | Refugio | COASTAL | 2026-09-18 | SOL | PV | 397.15 |  | 2020-07-29 | 2020-06-19 | 2020-09-08 | 2020-06-07 | 2025-09-22 | No | 2021-06-05 | Yes | Not Required | Not Required | Not Required | 2022-04-04 | 2025-07-24 | 2026-01-27 |  |  | 2026-06-30 | 2026-07-17
26INR0155 | Ross Solar | SS Completed, FIS Started, IA | S&S Renewables, LLC | tap 345kV 8249 Angstrom – 8676 Static | Refugio | COASTAL | 2027-07-31 | SOL | PV | 1025.57 |  | 2023-07-17 | 2023-07-31 | 2023-10-27 | 2023-07-18 |  | Yes | 2024-06-27 | No |  |  | Not Required
26INR0156 | Ross Storage | SS Completed, FIS Started, IA | S&S Renewables, LLC | tap the 345 kV Angstrom (#8249) – Static (#8676) line; AEP | Refugio | COASTAL | 2027-07-31 | OTH | BA | 510.99 |  | 2023-07-21 | 2023-08-14 | 2023-11-03 | 2023-07-27 |  | Yes | 2024-06-27 | No
28INR0175 | Mobee Springs BESS | SS Completed, FIS Started, No IA | Mobee Springs, LLC | #8805 BONIVIEW2A 69kV | Refugio | COASTAL | 2028-03-31 | OTH | BA | 100.61 |  | 2025-04-29 | 2025-06-05 | 2025-09-02 | 2025-05-09 |  |  |  | No
29INR0341 | Pampa Natural Gas | SS Completed, FIS Started, No IA | IP Meitner Gas | CTT Ghost Town (#79008) | Roberts | PANHANDLE | 2030-01-01 | GAS | IC | 250.7 |  | 2026-06-11 | 2026-06-24 | 2026-09-19 | 2026-06-17 |  |  |  | No
22INR0503 | Tidwell Prairie II Batt | SS Completed, FIS Completed, IA | Tidwell Prairie IIA LLC | Tap 345kV 3400 Twin Oak - 39950 TNP One | Robertson | NORTH | 2026-12-03 | OTH | BA | 203.62 | COD | 2021-03-02 | 2021-03-16 | 2021-05-28 | 2021-02-17 | 2025-06-16 | No | 2025-01-13 | Yes |  |  |  | 2025-08-01 | 2025-08-01 | 2025-08-01
22INR0504 | Barton Branch IA | SS Completed, FIS Completed, IA | Barton Branch IA LLC | Tap 345kV 3400 Twin Oak - 39950 TNP One | Robertson | NORTH | 2026-10-01 | OTH | BA | 203.62 |  | 2021-03-02 | 2021-03-16 | 2021-05-28 | 2021-02-17 | 2025-06-16 | No | 2025-06-18 | Yes |  |  |  | 2025-08-01 | 2025-08-01 | 2025-08-01
23INR0421 | Bee Branch IA | SS Completed, FIS Completed, IA | Bee Branch IA LLCBee Branch IA LLC | Tap TNP ONE 39950 and Twin Oak 3400 | Robertson | NORTH | 2027-06-01 | OTH | BA | 203.75 |  | 2021-11-15 | 2021-11-15 | 2022-02-11 | 2021-11-09 | 2026-06-11 | No | 2026-03-13 | Yes |  |  |  | 2026-03-17 | 2026-08-03 | 2026-08-03
24INR0135 | BRP Mekong BESS | SS Completed, FIS Started, No IA | BRP Mekong BESS LLC | Tap 345 kV line from Twin Oak Switch (#3400) to TPN One Plant Switchyard (#39950) | Robertson | NORTH | 2027-12-01 | OTH | BA | 409.88 |  | 2021-12-15 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No
25INR0288 | Buffalo Prairie Storage | SS Completed, FIS Started, No IA | Buffalo Meadow Energy Center, LLC | Tap 345kV 975 Jack Creek - 3400 Twin Oak | Robertson | NORTH | 2028-09-30 | OTH | BA | 308.03 |  | 2022-12-30 | 2023-01-03 | 2023-03-29 | 2022-12-02 |  |  |  | No
25INR0331 | Buffalo Meadow Solar | SS Completed, FIS Started, No IA | Buffalo Meadow Energy Center, LLC | Tap Jack Creek (975) - Twin Oak (3400) 345kV line | Robertson | NORTH | 2028-09-30 | SOL | PV | 251.27 |  | 2023-02-15 | 2023-02-27 | 2023-05-26 | 2023-01-27 |  |  |  | No |  |  | Not Required
25INR0497 | Stegall Solar | SS Completed, FIS Completed, No IA | BT Martin Solar, LLC | Elliott (Bus #53) to Franklin (Bus #57) 69kV Transmission Line | Robertson | NORTH | 2027-05-30 | SOL | PV | 81.57 |  | 2023-08-15 | 2023-08-21 | 2023-11-06 | 2023-08-02 | 2025-08-06 | No |  | No |  |  | Not Required
25INR0498 | Stegall Storage | SS Completed, FIS Completed, No IA | BT Martin Solar, LLC | Tap connection to a new switching station on the Elliott (Bus #53) - Franklin (Bus #57) 69 kV Transmission Line | Robertson | NORTH | 2027-05-30 | OTH | BA | 50.47 |  | 2023-08-07 | 2023-08-21 | 2023-11-06 | 2023-08-15 | 2025-08-06 | No |  | No
26INR0431 | Big Rooter West Solar | SS Completed, FIS Started, IA | Big Rooter West, LLC | 39950# TNTNP_ONE_3 345 KV | Robertson | NORTH | 2028-05-31 | SOL | PV | 403.2 |  | 2024-02-26 | 2024-03-22 | 2024-06-19 | 2024-03-22 |  |  | 2025-02-18 | No | Not Required | Not Required | Not Required
26INR0432 | Big Rooter West Storage | SS Completed, FIS Started, No IA | Big Rooter West, LLC | 39950# TNTNP_ONE_3 345 KV | Robertson | NORTH | 2028-12-01 | OTH | BA | 201.08 |  | 2024-03-05 | 2024-03-22 | 2024-06-19 | 2024-03-22 |  |  |  | No | Not Required | Not Required
27INR0418 | Pioneer Path Energy Storage 1 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0423 | Pioneer Path Energy Storage 2 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0424 | Pioneer Path Energy Storage 3 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0425 | Pioneer Path Energy Storage 4 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0426 | Prairie Horizon Energy Storage 1 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0427 | Prairie Horizon Energy Storage 2 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0428 | Prairie Horizon Energy Storage 3 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
27INR0429 | Prairie Horizon Energy Storage 4 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap 345kV 39950 TNP ONE PLANT - 3400 TWIN OAK Ckt 2 | Robertson | NORTH | 2027-12-01 | OTH | BA | 102.14 |  | 2025-01-13 | 2025-02-03 | 2025-03-21 | 2025-01-13 |  |  |  | No
29INR0017 | Big Rooter East Solar | SS Completed, FIS Started, IA | Big Rooter East, LLC | 39950 TNP One Plant 345 kV | Robertson | NORTH | 2029-05-31 | SOL | PV | 554.7 |  | 2024-03-04 | 2024-03-22 | 2024-06-19 | 2024-03-22 |  |  | 2025-06-01 | No |  |  | Not Required
29INR0018 | Big Rooter East Storage | SS Completed, FIS Started, IA | Big Rooter East, LLC | 39950 TNP One Plant 345 kV | Robertson | NORTH | 2029-12-31 | OTH | BA | 201.03 |  | 2024-03-04 | 2024-03-22 | 2024-06-19 | 2024-03-22 |  |  | 2025-06-01 | No | Not Required | Not Required
26INR0418 | TE Smith Storage 2 | SS Completed, FIS Started, No IA | Smith II Battery Storage, LLC | 2478 Royse 345kV | Rockwall | NORTH | 2029-02-07 | OTH | BA | 125.32 | COD | 2024-12-09 | 2024-04-15 | 2024-07-12 | 2024-11-21 |  | No |  | No
19INR0035 | Norton Solar | SS Completed, FIS Completed, IA | TAI Norton Solar, LLC | 60451 Garnet 138kV | Runnels | WEST | 2025-11-24 | SOL | PV | 128.48 |  | 2017-11-08 | 2017-03-06 | 2017-04-20 | 2017-11-08 | 2024-10-29 | No | 2019-06-20 | Yes | Not Required | Not Required | Not Required | 2019-07-12 | 2023-05-30 | 2025-01-16 |  |  | 2025-07-24 | 2025-08-06
24INR0485 | Rutile BESS | SS Completed, FIS Completed, IA | Rutile BESS, LLC | Tap 138kV 6340 BALLINGER - 60399 WEISS | Runnels | WEST | 2028-03-31 | OTH | BA | 100.65 |  | 2023-05-10 | 2023-01-23 | 2023-04-22 | 2023-04-19 | 2025-10-20 | No | 2025-07-17 | Yes |  |  |  | 2025-08-05
28INR0198 | Winters Glow Solar | SS Completed, FIS Started, No IA | Winters Glow Solar, LLC | tap 345kV 1444 BROWN SWITCH - 11406 CENTRAL BLUFF | Runnels | WEST | 2029-04-17 | SOL | PV | 301.6 |  | 2024-10-21 | 2024-10-29 | 2024-01-06 | 2024-10-16 |  |  |  | No |  |  | Not Required
28INR0199 | Winters Glow Storage | SS Completed, FIS Started, No IA | Winters Glow Storage, LLC | tap 345kV 1444 BROWN SWITCH - 11406 CENTRAL BLUFF | Runnels | WEST | 2029-04-17 | OTH | BA | 155.2 |  | 2024-10-21 | 2024-10-29 | 2024-01-06 | 2024-10-21 |  |  |  | No
29INR0210 | Sawtooth Solar | SS Completed, FIS Started, No IA | Sawtooth Solar, LLC | Tap to the 345kV Odysseus (Bus#60072) to Bluff Creek (Bus #60040) line | Runnels | WEST | 2030-08-01 | SOL | PV | 201.36 |  | 2025-11-17 | 2025-11-24 | 2025-12-15 | 2025-11-18 |  | Yes |  | No | Not Required | Not Required | Not Required
30INR0076 | Zuma Solar | SS Completed, FIS Started, No IA | Zuma Solar, LLC | Tap 345kV 11263 Fisk Switch - 11406 Central Bluff Switch | Runnels | WEST | 2030-09-09 | SOL | PV | 201.37 |  | 2026-03-16 | 2026-04-02 | 2026-06-30 | 2026-03-26 |  |  |  | No | Not Required | Not Required | Not Required
30INR0088 | Mistflower Energy Center Solar | SS Completed, FIS Started, No IA | Mistflower Energy Center LLC | Tap 345kV 60072 ODYSSEUS7A– 60040 BLF_CRK7A | Runnels | WEST | 2030-06-01 | SOL | PV | 401.62 |  | 2026-02-18 | 2026-02-25 | 2026-03-23 | 2026-02-19 |  | Yes |  | No |  |  | Not Required
30INR0089 | Mistflower Energy Center Storage | SS Completed, FIS Started, No IA | Mistflower Energy Center LLC | Tap 345kV 60072 Odysseus – 60040 Bluff Creek | Runnels | WEST | 2030-06-01 | OTH | BA | 312.85 |  | 2026-02-18 | 2026-02-25 | 2026-03-23 | 2026-03-12 |  | Yes |  | No
22INR0332 | Brantley Branch Batt | SS Completed, FIS Started, No IA | Brantley Branch LLC | Mt. Enterprise (Bus # 3116) – Martin Lake 345kv Line (Bus # 3100 | Rusk | NORTH | 2029-02-01 | OTH | BA | 302.35 |  | 2020-12-07 | 2020-05-01 | 2020-07-15 | 2020-11-24 |  | No |  | No
23INR0286 | Dry Creek Solar I | SS Completed, FIS Completed, IA | OAK HILL SOLAR LLC | tap 345kV 3100 Martin Lake - 3105 Elkton (Dorsett 345kV Switching Station) | Rusk | NORTH | 2026-01-31 | SOL | PV | 201.06 |  | 2022-04-04 | 2021-08-18 | 2021-11-05 | 2022-03-30 | 2024-06-12 | No | 2023-11-02 | Yes | Not Required | Not Required | Not Required | 2024-10-29 | 2024-10-29 | 2024-10-29 |  |  | 2025-05-08 | 2025-05-19
25INR0590 | Zeus Rusk Solar | SS Completed, FIS Started, No IA | Rusk Solar, LLC | Tap 345kV 3109 Stryker to 3100 Martin Lake | Rusk | NORTH | 2027-09-01 | SOL | PV | 26.8 |  | 2025-09-05 | 2024-03-22 | 2024-06-19 | 2024-12-16 |  |  |  | No |  |  | Not Required |  |  |  | 2026-07-01 | 2027-04-29
25INR0591 | Zeus Rusk BESS | SS Completed, FIS Started, No IA | Rusk BESS, LLC | Tap 345kV 3109 Stryker to 3100 Martin Lake | Rusk | NORTH | 2027-09-01 | OTH | BA | 208.8 |  | 2024-12-30 | 2024-04-09 | 2024-06-19 | 2024-12-16 |  |  |  | No | [6 empty] | 2026-07-01 | 2027-04-29
27INR0488 | Dry Creek Solar II | SS Completed, FIS Completed, No IA | Oak Hill Solar II LLC | Dorsett 345 kV Switching Station(tap 345 kV 3100 Martin Lake - 3105 Elkton) | Rusk | NORTH | 2028-02-01 | SOL | PV | 201.28 | MW Size | 2025-06-02 | 2025-06-19 | 2025-09-16 | 2025-06-02 | 2026-09-15 | No |  | No |  |  | Not Required
22INR0392 | Kalina Solar | SS Completed, FIS Started, No IA | Aurora Solar LLC | 8606 Goddard 345kV | San Patricio | COASTAL | 2029-05-31 | SOL | PV | 120 |  | 2021-03-31 | 2020-08-04 | 2020-10-28 | 2021-03-29 |  | No |  | No | Not Required | Not Required | Not Required
22INR0443 | Bowstring BESS | SS Completed, FIS Completed, IA | Longbow Energy Storage, LLC | 138kV 8961 WHITEPT4A - 8418 RINCON4A | San Patricio | COASTAL | 2028-09-18 | OTH | BA | 155 |  | 2021-04-01 | 2020-11-18 | 2021-02-09 | 2021-03-24 | 2023-05-30 |  | 2025-09-09 | Yes | Not Required | Not Required | 2025-09-23
23INR0180 | Jackalope Solar | SS Completed, FIS Completed, IA | Peacock Energy Project, LLC | 8173 Gibbs 138kV | San Patricio | COASTAL | 2026-02-05 | SOL | PV | 155.68 |  | 2021-01-29 | 2021-02-09 | 2021-05-06 | 2021-02-02 | 2021-11-18 |  | 2021-09-30 | Yes | Not Required | Not Required | Not Required | 2021-10-18 | 2022-10-24 | 2023-10-19 |  |  | 2024-07-30 | 2024-09-19
25INR0052 | SanPat Solar II | SS Completed, FIS Completed, IA | CGRP 04, LLC | Tap 345kV 8249 Angstrom – 8659 Naismith | San Patricio | COASTAL | 2027-07-22 | SOL | PV | 256.23 |  | 2022-07-29 | 2022-02-28 | 2022-05-27 | 2022-07-15 | 2026-07-09 | Yes | 2023-10-18 | Yes |  |  | Not Required | 2025-02-13 | 2026-08-03 | 2026-08-03
25INR0081 | SanPat Solar I | SS Completed, FIS Completed, IA | Padre Solar LLC | Tap 345kV 8249 Angstrom – 8659 Naismith | San Patricio | COASTAL | 2027-07-08 | SOL | PV | 308.88 |  | 2022-07-29 | 2022-07-18 | 2022-10-12 | 2022-07-15 | 2026-07-09 | Yes | 2023-10-18 | Yes |  |  | Not Required | 2025-02-13 | 2026-08-03 | 2026-08-03
26INR0211 | Titus Low Carbon Ventures Solar 1 | SS Completed, FIS Started, IA | Vaquero Solar, LLC | Tap 345kV 8249 Angstrom - 8624 Grissom | San Patricio | COASTAL | 2028-10-16 | SOL | PV | 338.04 |  | 2023-08-21 | 2023-10-13 | 2024-01-10 | 2023-09-21 |  | Yes | 2026-05-26 | No |  |  | Not Required
26INR0306 | Nautilus Heavy Storage | SS Completed, FIS Started, No IA | Nautilus Heavy Storage, LLC | 8422 Dupont 138kV | San Patricio | COASTAL | 2030-01-30 | OTH | BA | 256.24 |  | 2023-12-11 | 2023-12-20 | 2024-03-15 | 2023-12-01 |  | No |  | No
26INR0428 | Diamond Cowboy Storage | SS Completed, FIS Started, IA | Diamond B Storage, LLC | Tap 345kV 8249 Angstrom - 8624 Grissom | San Patricio | COASTAL | 2028-10-16 | OTH | BA | 103.5 |  | 2024-04-03 | 2024-04-15 | 2024-07-12 | 2024-04-16 |  | Yes | 2026-05-26 | Yes
26INR0599 | Coda BESS | SS Completed, FIS Started, No IA | Coda BESS, LLC | (#80258) Mayo 138kV | San Patricio | COASTAL | 2028-07-31 | OTH | BA | 202 |  | 2025-01-16 | 2025-01-28 | 2025-04-08 | 2025-01-17 |  |  |  | No
27INR0132 | Palo Verde Wind | SS Completed, FIS Started, IA | RWE Clean Energy Development, LLC | Tap 345kV 8624 Grissom – 8455 Lon C Hill | San Patricio | COASTAL | 2029-07-22 | WIN | WT | 297.5 |  | 2024-04-01 | 2024-04-09 | 2024-07-05 | 2024-04-01 |  | Yes | 2025-12-19 | No |  |  | Not Required
27INR0227 | PALO VERDE BESS | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | Tap 345kV 8624 Grissom – 8455 Lon C Hill | San Patricio | COASTAL | 2029-07-22 | OTH | BA | 150 |  | 2024-04-01 | 2024-04-15 | 2024-07-05 | 2024-04-01 |  | Yes |  | No
27INR0492 | Gulf Gateway Solar One | SS Completed, FIS Started, No IA | Gulf Gateway Solar, LLC | Tap 345 kV 8249 Angstrom - 8624 Grissom | San Patricio | COASTAL | 2029-12-01 | SOL | PV | 301.4 |  | 2025-04-03 | 2025-04-21 | 2025-07-19 | 2025-04-03 |  |  |  | No |  |  | Not Required
27INR0524 | Portland Storage SLF | SS Completed, FIS Started, No IA | Convergent Energy Solutions LLC | 8566 HOT IRON 4A 138 kV 8569 HOT IRON 4B 138 kV (2) POIs will be used for this project because there are (2) 138 kV lines supplying the ArcelorMittal plant. Project physical connection will be 13.8 kV bus at ArcelorMittal. | San Patricio | COASTAL | 2028-01-03 | OTH | BA | 0 |  | 2025-06-30 | 2025-07-29 | 2025-10-06 | 2025-07-18 |  |  |  | No
27INR0556 | Gulf Gateway Storage One | SS Completed, FIS Started, No IA | Gulf Gateway Storage, LLC | Tap 345 kV 8249 Angstrom - 8624 Grissom | San Patricio | COASTAL | 2029-12-01 | OTH | BA | 301.4 |  | 2025-08-25 | 2025-08-26 | 2025-11-18 | 2025-08-21 |  |  |  | No
28INR0179 | Sunburst Solar | SS Completed, FIS Started, No IA | Indigo Solar, LLC | KATOEN (Bus#8579) | San Patricio | COASTAL | 2029-03-16 | SOL | PV | 301.6 |  | 2024-10-09 | 2024-10-10 | 2025-01-07 | 2024-10-23 |  |  |  | No |  |  | Not Required
28INR0181 | Sunburst BESS | SS Completed, FIS Started, No IA | Indigo Solar, LLC | KATOEN (Bus#8579) | San Patricio | COASTAL | 2029-03-16 | OTH | BA | 256.3 |  | 2024-10-09 | 2024-10-10 | 2025-01-07 | 2024-10-23 |  |  |  | No
28INR0223 | Bayou Creek Solar | SS Completed, FIS Started, IA | Bayou Creek Solar LLC | 8606 Goddard 345kV | San Patricio | COASTAL | 2028-09-25 | SOL | PV | 256.9 | MW Size | 2025-07-22 | 2024-12-19 | 2025-03-24 | 2025-09-17 |  |  | 2026-06-02 | Yes |  |  | Not Required
28INR0305 | Iron Cowboy Solar | SS Completed, FIS Started, IA | Vaquero II Solar LLC | Bus #8920 Haisley 4A 138 kV | San Patricio | COASTAL | 2029-07-10 | SOL | PV | 144.59 | COD SFS/NtP | 2025-04-25 | 2025-06-05 | 2025-09-02 | 2025-05-16 |  |  | 2026-08-10 | Yes |  |  | Not Required
28INR0306 | Iron Cowboy Storage | SS Completed, FIS Started, IA | Vaquero II Storage LLC | Bus #8920 Haisley 4A 138 kV | San Patricio | COASTAL | 2029-07-10 | OTH | BA | 63.27 | COD SFS/NtP | 2025-04-25 | 2025-06-05 | 2025-09-02 | 2025-05-16 |  |  | 2026-08-10 | Yes
28INR0484 | Pathfinder Energy Storage, LLC | SS Completed, FIS Started, No IA | Pathfinder Energy Storage, LLC | 8437 Rincon 138kV | San Patricio | COASTAL | 2029-12-28 | OTH | BA | 201.16 |  | 2026-01-23 | 2026-01-26 | 2026-04-17 | 2026-01-23 |  | No |  | No
28INR0496 | Blue Kite | SS Completed, FIS Started, No IA | RWE Clean Energy Development, LLC | <Bus#8956> <WHITEPOINT> <345KV> | San Patricio | COASTAL | 2030-08-29 | GAS | GT | 370.08 |  | 2026-03-09 | 2026-03-10 | 2026-06-04 | 2026-03-06 |  |  |  | No
29INR0068 | Gregory Power Development SLF | SS Completed, FIS Started, IA | Gregory Power Partners LLC | 8580 Resnick 138kV | San Patricio | COASTAL | 2028-12-19 | GAS | CC | 469.9 |  | 2025-04-15 | 2024-11-19 | 2025-02-20 | 2025-03-26 |  | No | 2026-07-01 | No | 2025-12-15 | 2025-12-15 | 2026-07-15
29INR0106 | Kalina Storage | SS Completed, FIS Started, No IA | Aurora Solar LLC | 8606 GODDARD 345kV | San Patricio | COASTAL | 2029-12-01 | OTH | BA | 104.56 |  | 2026-01-22 | 2025-04-21 | 2025-07-19 | 2026-01-15 |  | Yes |  | No | Not Required | Not Required
29INR0207 | Alila BESS II | SS Completed, FIS Started, No IA | Electra Energy Project, LLC | 8249 Angstrom 345kV | San Patricio | COASTAL | 2029-01-25 | OTH | BA | 205.71 |  | 2025-12-30 | 2026-01-13 | 2026-04-06 | 2025-12-12 |  |  |  | No
29INR0227 | San Patricio Energy Center BESS | SS Completed, FIS Started, No IA | Ferrovial Energy US 1 | 8606 Goddard 345kV | San Patricio | COASTAL | 2029-03-31 | OTH | BA | 300.84 |  | 2025-12-22 | 2026-01-13 | 2026-04-07 | 2025-12-31 |  | No |  | No
30INR0004 | Hecate Energy Arkansas Wind | SS Completed, FIS Started, No IA | Hecate Energy Gulf Wind LLC | 8659 Naismith 345kV | San Patricio | COASTAL | 2030-06-01 | WIN | WT | 1029.39 |  | 2024-05-15 | 2023-06-28 | 2023-09-22 | 2024-04-03 15:06 |  |  |  | No |  |  | Not Required
22INR0239 | Rockefeller Storage | SS Completed, FIS Started, IA | Mittel Rockefeller Storage LLC | 76003 Big Hill 345kV | Schleicher | WEST | 2027-06-01 | OTH | BA | 206.8 |  | 2020-08-20 | 2019-10-31 | 2020-01-24 | 2020-07-21 |  | No | 2024-09-23 | Yes | Not Required | Not Required |  | 2025-02-12
26INR0150 | Proving Ground Solar | SS Completed, FIS Started, No IA | Lantana Solar LLC | Tap 138 kV Live Oak (6500) - Santiago (6490) | Schleicher | WEST | 2028-06-30 | SOL | PV | 82.1 |  | 2024-01-30 | 2023-07-10 | 2023-10-05 | 2024-01-26 16:36 |  |  |  | No | Not Required | Not Required | Not Required
26INR0159 | Proving Ground BESS | SS Completed, FIS Started, No IA | Lantana Solar LLC | Tap 138kV 6500 Live Oak - 6490 Santiago | Schleicher | WEST | 2028-06-30 | OTH | BA | 51.4 |  | 2024-03-06 | 2023-07-10 | 2023-10-05 | 2024-01-26 16:41 |  |  |  | No
26INR0290 | Cold Creek Solar 2 | SS Completed, FIS Started, IA | Cold Creek Solar and Storage LLC | Tap 345kV line Big Hill (#76003) - Twin Buttes (#76009) | Schleicher | WEST | 2028-05-28 | SOL | PV | 431.87 |  | 2023-11-07 | 2023-12-18 | 2024-03-01 | 2023-11-07 |  |  | 2025-04-23 | No |  |  | Not Required
26INR0291 | Cold Creek Storage 2 | SS Completed, FIS Started, IA | Cold Creek Solar and Storage LLC | Tap 345kV line Big Hill (#76003) - Twin Buttes (#76009) | Schleicher | WEST | 2028-05-28 | OTH | BA | 171.75 |  | 2023-11-02 | 2023-12-04 | 2024-03-01 | 2023-11-02 |  |  | 2025-04-23 | No | Not Required | Not Required
27INR0231 | Easy Battery Energy Storage Center | SS Completed, FIS Started, No IA | Easy Wind Energy Center, LLC | Tap 345 kV 76003 Big Hill to 76005 Schneeman Draw | Schleicher | WEST | 2029-06-15 | OTH | BA | 200 |  | 2024-03-18 | 2024-03-29 | 2024-06-19 | 2024-03-20 |  |  |  | No
27INR0246 | Easy Wind Energy Center | SS Completed, FIS Started, No IA | Easy Wind Energy Center, LLC | Tap 345kV #76003 Big Hill - #76005 Schneeman Draw circuit #1 | Schleicher | WEST | 2029-06-15 | WIN | WT | 241.13 |  | 2024-05-01 | 2024-05-20 | 2024-08-16 | 2024-05-02 |  | No |  | No |  |  | Not Required
27INR0261 | Tipperary Solar | SS Completed, FIS Started, No IA | Tippsol | 6498 Live Oak AEP 69kV | Schleicher | WEST | 2028-03-15 | SOL | PV | 60.16 |  | 2024-05-10 | 2024-06-13 | 2024-09-10 | 2024-05-17 |  |  |  | No |  |  | Not Required
27INR0364 | Cashel BESS | SS Completed, FIS Started, No IA | TIPPSOL LLC | 6500 Live Oak AEP 138kV | Schleicher | WEST | 2028-03-15 | OTH | BA | 150.44 |  | 2024-10-22 | 2024-10-29 | 2025-01-26 | 2024-10-22 |  |  |  | No
28INR0280 | Live Oak Wind II | SS Completed, FIS Started, No IA | ENGIE IR Holdings LLC | #76003 Big Hill 345kV | Schleicher | WEST | 2028-09-29 | WIN | WT | 302.63 |  | 2025-03-21 | 2025-03-24 | 2025-06-09 | 2025-03-19 |  | No |  | No | Not Required | Not Required | Not Required
17INR0027b | Coyote Wind | SS Completed, FIS Completed, IA | Coyote Wind | 11305 Dermott 345kV | Scurry | WEST | 2026-08-28 | WIN | WT | 242.6 |  |  | 2015-04-22 | 2015-05-22 | 2015-06-11 | 2020-01-31 | No | 2016-08-09 | Yes | Not Required | Not Required | Not Required | 2016-08-09 | 2020-01-28 | 2020-01-31 |  |  | 2020-08-24 | 2020-11-25
21INR0532 | Brazos Wind Repower | SS Completed, FIS Completed, No IA | BRAZOS WIND VENTURES, LLC | 1064 Sun 138kV | Scurry | WEST | 2025-11-14 | WIN | WT | 22.4 |  | 2020-12-18 | 2020-12-22 | 2021-03-10 | 2020-11-30 | 2022-04-01 |  |  | Yes | Not Required | Not Required | Not Required | 2022-08-03 | 2022-10-21 | 2023-02-03 |  |  | 2023-04-25 | 2023-07-01
24INR0519 | Roost Energy Storage | SS Completed, FIS Started, No IA | Bluff Creek Energy Storage LLC | the Knapp Sub (bus# 1310) – Union Switch (bus# 18555) | Scurry | WEST | 2028-09-30 | OTH | BA | 102.36 |  | 2023-01-24 | 2023-01-30 | 2023-04-28 | 2023-01-21 |  | No |  | No
25INR0196 | Inadale Solar | SS Completed, FIS Completed, No IA | Inadale Solar, LLC | Tap 345 kV TONKAWAW_5 (11048) – SCURCNTYS_5 (11318) Circuit #2 | Scurry | WEST | 2029-03-02 | SOL | PV | 281.03 |  | 2023-02-17 | 2023-02-20 | 2023-05-19 | 2023-02-08 | 2026-08-03 | No |  | No |  |  | Not Required
25INR0197 | Inadale BESS | SS Completed, FIS Started, No IA | Inadale BESS, LLC | Tap 345 kV TONKAWAW_5 (11048) – SCURCNTYS_5 (11318) Circuit #2 | Scurry | WEST | 2029-03-02 | OTH | BA | 287.16 |  | 2023-02-17 | 2023-02-20 | 2023-05-19 | 2023-02-16 |  | No |  | No
25INR0287 | Hide Town Energy Storage | SS Completed, FIS Started, No IA | Hide Town Energy Storage LLC | 18555 Union Switch 138 kV | Scurry | WEST | 2029-10-11 | OTH | BA | 102.76 |  | 2025-04-24 | 2023-01-17 | 2023-04-14 | 2024-08-28 |  |  |  | No
25INR0400 | Maldives Solar | SS Completed, FIS Started, IA | Maldives Solar LLC | Galvani 345 kV station (Bus #59912) | Scurry | WEST | 2028-09-25 | SOL | PV | 181.3 | MW Size | 2023-07-08 | 2023-07-18 | 2023-10-15 | 2023-07-05 |  | Yes | 2023-12-01 | Yes |  |  | Not Required | 2024-07-17
27INR0192 | Cedar Draw Solar | SS Completed, FIS Completed, No IA | Cedar Draw Solar LLC | 60011 Nebula7A 345kV | Scurry | WEST | 2027-12-31 | SOL | PV | 451.4 |  |  | 2024-03-22 | 2024-06-19 | 2024-03-01 | 2026-09-24 |  |  | No |  |  | Not Required
27INR0193 | Cedar Draw BESS | SS Completed, FIS Completed, No IA | Cedar Draw Solar LLC | 60011 Nebula7A 345kV | Scurry | WEST | 2027-12-31 | OTH | BA | 225.7 |  | 2024-03-04 | 2024-03-22 | 2024-06-19 | 2024-02-20 | 2026-09-23 |  |  | No
27INR0529 | Zeus Scurry Solar | SS Completed, FIS Started, No IA | Scurry Solar, LLC | MHOS 345 kV Substation (#59911) | Scurry | WEST | 2028-10-01 | SOL | PV | 503.54 |  | 2025-05-28 | 2025-06-03 | 2025-08-29 | 2025-05-29 |  |  |  | No |  |  | Not Required
27INR0535 | Zeus Scurry BESS | SS Completed, FIS Started, No IA | Zeus Scurry BESS | MHOS 345 kV Substation (#59911) | Scurry | WEST | 2028-10-01 | OTH | BA | 1043.07 |  | 2025-06-02 | 2025-06-05 | 2025-08-29 | 2025-06-04 |  |  |  | No
27INR0623 | Helion Solar | SS Completed, FIS Started, No IA | Helion Solar LLC | 59912 GALVANI 345 | Scurry | WEST | 2027-10-22 | SOL | PV | 100 |  | 2026-03-30 | 2026-05-15 | 2026-08-12 | 2026-05-14 |  |  |  | No |  |  | Not Required
27INR0624 | Helion BESS | SS Completed, FIS Started, No IA | Helion BESS | 59912 GALVANI 345 | Scurry | WEST | 2027-09-16 | OTH | BA | 100 |  | 2026-03-30 | 2026-05-15 | 2026-08-12 | 2026-05-14 |  |  |  | No
28INR0202 | Fluvanna Max BESS SLF | SS Completed, FIS Started, No IA | Fluvanna Max Solar LLC | 11305 DERMOTT 345 kV | Scurry | WEST | 2029-09-14 | OTH | BA | 51.8 |  | 2024-11-04 | 2024-12-19 | 2025-03-10 | 2024-11-11 |  | No |  | No
28INR0486 | Spectra Solar | SS Completed, FIS Started, IA | SE DC Devco | 59912 Galvani 345KV | Scurry | WEST | 2028-11-16 | SOL | PV | 1200 |  | 2025-12-19 | 2025-12-23 | 2026-03-23 | 2025-12-19 |  |  | 2025-12-29 | Yes |  |  | Not Required
29INR0077 | Fluvanna Max Solar SLF | SS Completed, FIS Started, No IA | Fluvanna Max Solar LLC | 11305 DERMOTT 345 kV | Scurry | WEST | 2029-09-14 | SOL | PV | 152.7 |  | 2024-11-04 | 2024-12-19 | 2025-03-18 | 2024-11-11 |  | No |  | No |  |  | Not Required
26INR0500 | Shackleford BESS | SS Completed, FIS Started, No IA | Shackelford County BESS LLC | 1442 CFRSW 345kV | Shackelford | WEST | 2028-09-23 | OTH | BA | 206.5 |  | 2025-02-03 | 2024-12-19 | 2025-03-17 | 2025-01-31 |  |  |  | No
28INR0151 | Chimney Creek Solar | SS Completed, FIS Started, No IA | Chimney Creek Energy, LLC | Tap 345 kV 68000 West Shackelford – 60515 Clear Crossing Ckt 1 | Shackelford | WEST | 2030-05-30 | SOL | PV | 203.88 |  | 2025-11-17 | 2025-02-14 | 2025-05-12 |  |  |  |  | No |  |  | Not Required
27INR0354 | Cebocell BESS | SS Completed, FIS Started, No IA | Cebocell, LLC | 3137 BlackFork 138 KV | Smith | NORTH | 2028-10-31 | OTH | BA | 200.87 |  | 2024-08-20 | 2024-09-04 | 2024-11-13 | 2024-08-13 |  |  |  | No
21INR0520 | Yellow Viking Solar | SS Completed, FIS Completed, IA | Yellow Viking Development One, LLC | Tap 345kV 1900 Comanche Peak - 11886 Timberview Switch | Somervell | NORTH | 2027-07-13 | SOL | PV | 171.13 |  | 2020-10-09 | 2020-10-23 | 2021-01-12 | 2020-08-20 | 2026-09-17 |  | 2022-10-25 | Yes |  |  | Not Required
27INR0497 | Black Mountain Somervell Gas Combined | SS Completed, FIS Started, No IA | Fort Worth Power Core LLC | Dinosaur Switch (#15208) | Somervell | NORTH | 2029-09-28 | GAS | CC | 495.3 |  | 2025-04-11 | 2025-04-21 | 2025-07-19 | 2025-04-16 |  |  |  | No
16INR0081 | Mesteno Wind | SS Completed, FIS Completed, IA | Mesteno Windpower, LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2027-03-01 | WIN | WT | 201.6 |  | 2014-12-30 | 2014-12-30 | 2015-03-09 | 2014-12-30 | 2018-01-29 | No | 2018-04-25 | Yes | Not Required | Not Required | Not Required | 2018-04-25 | 2019-03-28 | 2019-04-01 |  |  | 2019-11-26 | 2019-12-12
20INR0162 | Diamondback solar | SS Completed, FIS Completed, IA | Diamondback Solar, LLC | 80355 Del Sol 345kV | Starr | SOUTH | 2028-04-29 | SOL | PV | 200.5 | MW Size COD |  | 2018-09-13 | 2018-12-06 | 2018-11-07 | 2026-06-30 | No | 2024-06-14 | Yes | Not Required | Not Required | Not Required | 2025-02-12
20INR0216 | Starr Solar Ranch | SS Completed, FIS Completed, IA | Starr Solar Ranch 1 LLC | 8795 Roma 138kV | Starr | SOUTH | 2025-08-14 | SOL | PV | 136.73 |  | 2018-11-07 | 2018-11-07 | 2018-12-14 | 2018-11-07 | 2024-01-26 | No | 2020-10-01 | Yes | Not Required | Not Required | Not Required | 2024-01-24 | 2024-01-24 | 2024-01-31 |  |  | 2024-10-09 | 2024-10-30
23INR0354 | Bordertown BESS | SS Completed, FIS Started, IA | Bordertown BESS LLC | 8796 Roma 138kV | Starr | SOUTH | 2028-12-01 | OTH | BA | 100 |  | 2021-08-17 | 2021-09-01 | 2021-11-22 | 2021-08-19 |  | No | 2022-10-12 | Yes | Not Required | Not Required | 2025-04-03 | 2025-02-13
23INR0455 | Bessie Storage | SS Completed, FIS Started, No IA | Bessie Energy Storage, LLC | Charly Egner Substation Tap 345kV 80355 Del Sol - 80368 LV4 Bridge | Starr | SOUTH | 2029-09-28 | OTH | BA | 210.8 |  | 2022-02-08 | 2022-02-21 | 2022-05-19 | 2022-02-07 |  | No |  | No | Not Required | Not Required
24INR0445 | PSE Flores TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | TAP 138KV 8793 RIO GRANDE CITY - 8798 LAGRULLA | Starr | SOUTH | 2028-06-30 | OTH | BA | 200 |  | 2023-10-01 | 2022-12-15 | 2023-03-13 | 2023-09-19 |  |  |  | No | Not Required | Not Required
24INR0446 | PSE Gongora Hill TX Storage | SS Completed, FIS Started, No IA | PureSky Development Inc | Tap 138kV 8796 Roma – 7870 Escobares | Starr | SOUTH | 2028-06-30 | OTH | BA | 200 |  | 2023-11-02 | 2023-02-27 | 2023-03-13 | 2022-11-22 |  |  |  | No | Not Required | Not Required
25INR0241 | Halcon Storage | SS Completed, FIS Started, No IA | TX BESS A LLC | Tap 138kV 8957 Central Lopeno - 80106 Falcon Dam | Starr | SOUTH | 2028-05-15 | OTH | BA | 132.65 |  | 2023-05-15 | 2023-05-22 | 2023-08-17 | 2023-04-24 |  |  |  | No
25INR0379 | Starr Storage | SS Completed, FIS Started, No IA | Falcon Lake Storage, LLC | 8795 Roma 138kV | Starr | SOUTH | 2028-03-29 | OTH | BA | 0 |  | 2023-04-03 | 2023-06-28 | 2023-09-22 | 2023-03-08 |  |  |  | No
26INR0445 | Sword Solar | SS Completed, FIS Started, No IA | Hidalgo Solar LLC | Tap 138 kV 8394 Liston - 8392 Bates | Starr | SOUTH | 2029-02-22 | SOL | PV | 137.18 |  | 2024-11-20 | 2024-03-22 | 2024-06-19 | 2024-11-12 |  | No |  | No |  |  | Not Required
26INR0446 | Sword BESS | SS Completed, FIS Started, No IA | Hidalgo Solar LLC | Tap 138 kV 8394 Liston - 8392 Bates | Starr | SOUTH | 2029-02-22 | OTH | BA | 40.1 |  | 2024-11-20 | 2024-03-22 | 2024-06-19 | 2024-11-12 |  | No |  | No
26INR0527 | Mandolin Solar SLF | SS Completed, FIS Started, No IA | Mandolin Energy Center I, LLC | Tap 345kV 80355 Del Sol - 80227 Rapido | Starr | SOUTH | 2029-06-15 | SOL | PV | 300 |  | 2024-07-09 | 2024-07-22 | 2024-10-17 | 2024-06-24 |  |  |  | No |  |  | Not Required
26INR0528 | Mandolin Storage SLF | SS Completed, FIS Started, No IA | Mandolin Energy Center I, LLC | Tap 345kV 80355 Del Sol - 80227 Rapido | Starr | SOUTH | 2029-06-15 | OTH | BA | 0 |  | 2024-07-09 | 2024-07-22 | 2024-10-17 | 2024-06-24 |  |  |  | No
27INR0222 | Fierce River BESS | SS Completed, FIS Started, No IA | Rio Grande Solar LLC | Tapping the 345 kV Line from Del Sol (Bus# 80355) to Frontera (Bus# 80119) ckt 1 | Starr | SOUTH | 2029-02-22 | OTH | BA | 284.49 |  | 2024-11-21 | 2024-03-22 | 2024-06-19 | 2024-11-12 |  | No |  | No
28INR0037 | Bullring Wind 1 | SS Completed, FIS Started, IA | Halcon Wind, LLC | Tap 345 kV 80355 DelSol7A - 80079 Cruce Ckt 1 | Starr | SOUTH | 2028-06-30 | WIN | WT | 303.5 |  | 2024-03-21 | 2024-05-09 | 2024-08-05 | 2024-04-30 |  | Yes | 2025-11-03 | Yes | Not Required | Not Required | Not Required | 2026-01-30
28INR0038 | Bullring Wind 2 | SS Completed, FIS Started, IA | Halcon Wind, LLC | Tap 345 kV 80355 DelSol7A - 80079 Cruce Ckt 1 | Starr | SOUTH | 2028-06-30 | WIN | WT | 303.8 |  | 2025-02-19 | 2024-05-09 | 2024-08-05 | 2024-04-30 |  | Yes | 2025-11-03 | Yes | Not Required | Not Required | Not Required | 2026-01-30
28INR0039 | Bullring Wind 3 | SS Completed, FIS Started, IA | Halcon Wind, LLC | Tap 345 kV 80355 DelSol7A - 80079 Cruce Ckt 1 | Starr | SOUTH | 2028-06-30 | WIN | WT | 190.4 |  | 2025-02-19 | 2024-05-09 | 2024-08-05 | 2024-04-29 |  | Yes | 2025-11-03 | Yes | Not Required | Not Required | Not Required | 2026-01-30
28INR0043 | Sendero Solar | SS Completed, FIS Started, No IA | ACE DevCo NC, LLC | Tap 345kV 80079 Cruce - 80355 Del Sol | Starr | SOUTH | 2029-05-15 | SOL | PV | 502.69 | Proj Name | 2025-07-22 | 2024-01-11 | 2024-04-09 |  |  |  |  | No |  |  | Not Required
28INR0127 | Half Moon Solar | SS Completed, FIS Started, IA | NextEra Energy Interconnection Holdings, LLC | #80231 Pronto 345kV | Starr | SOUTH | 2029-07-01 | SOL | PV | 512.5 |  | 2024-12-26 | 2025-01-13 | 2025-04-08 | 2024-12-23 |  |  | 2025-09-08 | Yes | Not Required | Not Required | Not Required | 2025-09-15
29INR0223 | Mandolin Solar II SLF | SS Completed, FIS Started, No IA | Mandolin Energy Center II, LLC | Tap 345kV 80355 Del Sol - 80227 Rapido | Starr | SOUTH | 2029-06-15 | SOL | PV | 304.4 |  | 2026-06-17 | 2026-07-23 | 2026-08-18 | 2026-06-17 |  |  |  | No |  |  | Not Required
29INR0224 | Mandolin Solar III SLF | SS Started, FIS Started, No IA | Mandolin Energy Center I, LLC | Tap 345kV 80355 Del Sol - 80227 Rapido | Starr | SOUTH | 2029-06-15 | SOL | PV | 250 |  | 2026-08-10 | 2026-09-04 |  | 2026-08-25 |  |  |  | No |  |  | Not Required
21INR0240 | La Casa Wind | SS Completed, FIS Completed, IA | LA CASA WIND, LLC | New switching station: 138kV Graham Plant Switch - Breckenridge - Leon Switch | Stephens | NORTH | 2026-11-30 | WIN | WT | 148.4 |  |  | 2018-12-28 | 2019-03-12 | 2018-12-29 | 2023-09-22 |  | 2023-09-07 | Yes | Not Required | Not Required | Not Required | 2024-01-04 | 2024-04-29 | 2024-04-29 |  |  | 2025-10-31 | 2025-11-14
26INR0600 | Crocus Solar | SS Completed, FIS Completed, IA | Crocus Solar, LLC | Tap 138 kV Gunsolas Creek Sub (1660) – Breckenridge Tap (1613) | Stephens | NORTH | 2028-07-01 | SOL | PV | 102 |  | 2025-01-27 | 2025-01-28 | 2025-04-08 | 2025-01-27 | 2026-09-01 | No | 2026-08-04 | No |  |  | Not Required
26INR0601 | Crocus Storage | SS Completed, FIS Completed, IA | Crocus Solar, LLC | Tap 138 kV Gunsolas Creek Sub (1660) – Breckenridge Tap (1613) | Stephens | NORTH | 2028-07-01 | OTH | BA | 51 |  | 2025-01-27 | 2025-01-28 | 2025-04-08 | 2025-01-27 | 2026-09-01 | No | 2026-08-04 | No
17INR0054 | Capricorn I & III repower | SS Completed, FIS Completed, IA | Nextera | 180757 Capricorn Ridge 3 138kV | Sterling | WEST | 2026-06-30 | WIN | WT | 32 |  | 2017-03-09 | 2017-03-09 | 2017-04-24 | 2017-03-09 | 2018-02-26 | No | 2006-11-14 | No | Not Required | Not Required | Not Required | 2021-02-28 | 2021-02-28 | 2021-02-28 |  |  |  | 2021-03-04
26INR0589 | Goat Mountain BESS | SS Completed, FIS Started, No IA | Clearway Energy Group LLC | 76030-Gasconades Creek 345 kV | Sterling | WEST | 2028-06-01 | OTH | BA | 201.1 |  | 2025-01-21 | 2025-01-28 | 2025-04-08 | 2025-01-17 |  |  |  | No
26INR0611 | Goat Mountain BESS 2 | SS Completed, FIS Started, No IA | Clearway Energy Group LLC | 76030-Gasconades Creek 345 kV | Sterling | WEST | 2028-06-01 | OTH | BA | 100.7 |  | 2025-01-21 | 2025-01-28 | 2025-04-08 | 2025-01-17 |  |  |  | No
27INR0076 | Bob Creek Wind | SS Completed, FIS Started, IA | NextEra Energy Interconnection Holdings, LLC | 59902 Sand Bluff 345kV | Sterling | WEST | 2028-07-01 | WIN | WT | 239.47 | MW Size | 2024-01-08 | 2024-01-11 | 2024-04-08 | 2024-01-09 |  | No | 2025-06-06 | Yes | Not Required | Not Required | Not Required | 2025-09-08
27INR0367 | Goat Mountain Wind-Repower | SS Completed, FIS Completed, IA | Goat Wind LLC | 76030 Gasconades Creek 345kV | Sterling | WEST | 2027-03-01 | WIN | WT | 303.2 |  | 2025-01-10 | 2025-01-13 | 2025-04-07 | 2024-12-13 | 2026-01-09 | No | 2026-02-20 | Yes | 2026-06-15 | Not Required | Not Required | 2026-06-18 | 2026-07-15 | 2026-08-05
29INR0185 | Roan Solar Phase 1 | SS Completed, FIS Started, No IA | Roan Solar, LLC | Divide (#76090) to Sand Bluff Wind Farm (#59902) 345 kV | Sterling | WEST | 2029-04-30 | SOL | PV | 205.9 |  |  | 2025-10-21 | 2025-12-12 | 2025-10-14 |  |  |  | No |  |  | Not Required
29INR0187 | Roan Solar Phase 2 | SS Completed, FIS Started, No IA | Roan Solar, LLC | Divide (#76090) to Sand Bluff Wind Farm (#59902) 345 kV | Sterling | WEST | 2029-12-15 | SOL | PV | 205.9 |  |  | 2025-10-21 | 2025-12-12 | 2025-10-14 |  |  |  | No |  |  | Not Required
26INR0269 | Moccasin Solar | SS Completed, FIS Completed, IA | Swenson Solar LLC | Tapping the 345 kV Line from Kirchhoff (Bus# 60707) to Clear Crossing (Bus# 60515) | Stonewall | WEST | 2027-07-06 | SOL | PV | 603.59 |  | 2023-08-30 | 2023-09-07 | 2023-12-06 | 2023-09-01 | 2026-01-08 | Yes | 2024-09-04 | Yes | Not Required | Not Required | Not Required | 2025-02-12 | 2026-04-21 | 2026-04-21
27INR0242 | Stonewall Solar | SS Completed, FIS Completed, No IA | Stonewall PV, LLC | Tap 69kV #755 BEPC Aspermont - #6156 AEP Aspermont | Stonewall | WEST | 2029-01-15 | SOL | PV | 60.2 |  | 2024-05-06 | 2024-05-09 | 2024-08-05 | 2024-05-01 | 2026-03-13 | No |  | No |  |  | Not Required
28INR0253 | Stonewall BESS | SS Completed, FIS Started, No IA | Stonewall ESS, LLC | tap 138kV 6150 SPUR4A - 6158 ASPM4A | Stonewall | WEST | 2028-12-29 | OTH | BA | 135 |  | 2025-02-17 | 2025-02-25 | 2025-05-20 | 2025-02-06 |  |  |  | No
27INR0236 | Atticus Energy Storage | SS Completed, FIS Started, No IA | Atticus Energy Storage | Tap 69 KV 6570 Bond Road - 6513 Sonora | Sutton | WEST | 2030-01-26 | OTH | BA | 102.98 |  | 2024-03-26 | 2024-03-29 | 2024-06-25 | 2024-03-29 |  |  |  | No
28INR0148 | Sonora High Noon BESS | SS Completed, FIS Started, No IA | Sonora High Noon, LLC | 60412 CARVER 138kV | Sutton | WEST | 2028-07-01 | OTH | BA | 204.08 |  | 2024-08-28 | 2024-09-04 | 2024-11-27 | 2024-09-03 |  |  |  | No
22INR0402 | Frye Storage | SS Completed, FIS Started, No IA | Hecate Energy Frye Storage LLC | new 345kV sub Kress connecting both 23912 Ogallala - 23914 Tule Canyon circuits | Swisher | PANHANDLE | 2028-12-01 | OTH | BA | 503.85 |  | 2020-08-26 | 2020-09-02 | 2020-11-19 | 2020-08-17 |  | No |  | No
24INR0003 | Stem Solar | SS Completed, FIS Started, No IA | Innovative Solar 134, LLC | tap 345kV 23914 Tule Canyon - 23912 Ogallala | Swisher | PANHANDLE | 2025-08-26 | SOL | PV | 200 |  | 2020-12-03 | 2020-02-04 | 2020-04-27 | 2020-10-22 |  |  |  | No |  |  | Not Required
25INR0282 | Hornet Solar II SLF | SS Completed, FIS Started, IA | Hornet Solar II LLC | Ozark Trail Switch 345kV substation (Bus #23901) | Swisher | PANHANDLE | 2028-07-31 | SOL | PV | 201.49 |  | 2022-12-20 | 2023-01-03 | 2023-03-29 | 2022-12-20 |  | No | 2024-08-21 | Yes |  |  | Not Required | 2025-02-12
25INR0283 | Hornet Storage II SLF | SS Completed, FIS Started, IA | Hornet Storage II LLC | Ozark Trail Switch 345kV substation (Bus # 23901) | Swisher | PANHANDLE | 2028-07-31 | OTH | BA | 0 |  | 2022-12-28 | 2023-01-03 | 2023-03-29 | 2022-12-20 |  | No | 2024-08-21 | Yes |  |  |  | 2025-02-12
27INR0625 | Hornet Energy Storage SLF | SS Completed, FIS Started, No IA | Hornet Energy Storage LLC | 23901 OZARKTRAIL_5 345kV | Swisher | PANHANDLE | 2029-09-30 | OTH | BA | 0 | COD | 2026-04-09 | 2026-04-22 | 2026-07-08 | 2026-04-09 |  |  |  | No
29INR0032 | Commodus 2 Solar | SS Completed, FIS Started, No IA | IP Blackwell II, LLC | Tapping the 345 kV Double-Circuit Line from Tule Canyon (Bus# 23914) to Alibates (Bus# 23900) | Swisher | PANHANDLE | 2029-07-30 | SOL | PV | 502.1 |  | 2025-02-25 | 2025-03-03 | 2025-06-03 | 2025-02-18 |  |  |  | No |  |  | Not Required
29INR0033 | Commodus 2 Wind | SS Completed, FIS Started, No IA | IP Blackwell II, LLC | Tapping the 345 kV Double-Circuit Line from Tule Canyon (Bus# 23914) to Alibates (Bus# 23900) | Swisher | PANHANDLE | 2029-07-30 | WIN | WT | 641.48 |  | 2025-02-24 | 2025-03-03 | 2025-06-03 | 2025-02-18 |  |  |  | No |  |  | Not Required
21INR0492 | Stockyard Grid Batt | SS Completed, FIS Completed, IA | Stockyard Grid, LLC | 2082 Hicks 138kV | Tarrant | NORTH | 2028-12-14 | OTH | BA | 150.6 |  | 2020-02-05 | 2020-01-13 | 2020-03-30 | 2020-01-13 | 2022-07-14 | No | 2022-10-26 | Yes | Not Required | Not Required |  | 2022-10-26 | 2022-10-26 | 2022-10-26
24INR0763 | Team Ranch Storage | SS Completed, FIS Started, No IA | BAF Storage, LLC | 1869 Benbrook Switch 345kV | Tarrant | NORTH | 2027-03-01 | OTH | BA | 307.2 |  | 2024-06-05 | 2024-06-13 | 2024-08-07 | 2024-06-05 |  |  |  | No
26INR0487 | Anglin BESS | SS Completed, FIS Started, No IA | Fort Worth BESS LLC | 1883 EVRSW 138kV | Tarrant | NORTH | 2028-09-30 | OTH | BA | 206 |  | 2024-11-11 | 2024-05-09 | 2024-08-06 | 2024-11-11 |  |  |  | No
28INR0116 | Salazar BESS | SS Completed, FIS Started, No IA | Salazar Energy Storage LLC | 2068 Rosen Heights 138kV | Tarrant | NORTH | 2028-07-11 | OTH | BA | 127.82 |  | 2024-09-10 | 2024-10-01 | 2024-12-09 | 2024-08-27 |  |  |  | No
17INR0052 | Horse13 CallD repower | SS Completed, FIS Completed, IA | Nextera | 6216 Bluff Creek 138kV | Taylor | WEST | 2027-03-31 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2018-04-10 | No | 2019-05-22 | Yes | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13 |  |  |  | 2021-03-16
17INR0053 | HHGT repower Horse13+CallD | SS Completed, FIS Completed, IA | Nextera | 7046 Kendal 345kV | Taylor | WEST | 2027-03-31 | WIN | WT | 44 |  | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | 2017-07-06 | No | 2009-06-26 | No | Not Required | Not Required | Not Required | 2020-04-13 | 2020-04-13 | 2020-04-13 |  |  |  | 2021-09-10
24INR0308 | Forts Trail Solar | SS Completed, FIS Started, No IA | JC Central Bluff, LLC | 11406 Central Bluff Switch 345kV | Taylor | WEST | 2029-03-02 | SOL | PV | 200.81 |  | 2022-06-07 | 2022-06-02 | 2022-08-30 | 2022-06-03 |  | No |  | No | Not Required | Not Required | Not Required
24INR0341 | Forts Trail BESS | SS Completed, FIS Started, No IA | JC Central Bluff, LLC | 11406 Central Bluff Switch 345kV | Taylor | WEST | 2029-03-02 | OTH | BA | 208.82 |  | 2022-06-06 | 2022-06-02 | 2022-08-30 | 2022-06-03 |  | No |  | No | Not Required | Not Required
24INR0488 | Forts Trail BESS 2 | SS Completed, FIS Started, No IA | JC Central Bluff, LLC | 11406 Central Bluff Switch 345 kV | Taylor | WEST | 2029-03-02 | OTH | BA | 205.54 |  | 2023-02-15 | 2023-02-20 | 2023-05-20 | 2023-02-01 |  | No |  | No | Not Required | Not Required
26INR0618 | Taylor County Paul Storage | SS Completed, FIS Completed, No IA | DM-TCP, LLC | 6260 Abilene South Substation 138kV | Taylor | WEST | 2029-12-30 | OTH | BA | 204.9 |  | 2024-12-05 | 2024-12-19 | 2025-02-20 | 2024-12-05 | 2026-04-09 | No |  | No
26INR0622 | Buffalo Gap 1 Wind Repower | SS Completed, FIS Completed, IA | Buffalo Gap Wind Farm, LLC | 6216 Bluff Creek Substation 138kV | Taylor | WEST | 2027-02-01 | WIN | WT | 120.23 |  | 2025-01-16 | 2025-01-28 | 2025-04-15 | 2025-01-10 | 2026-03-17 | No | 2005-02-28 | Yes | Not Required | Not Required | Not Required | 2026-03-25 | 2026-05-05 | 2026-05-05
26INR0626 | Buffalo Gap 3 Wind Repower | SS Completed, FIS Completed, IA | Buffalo Gap Wind Farm 3, LLC | 6216 Bluff_Creek 138kV | Taylor | WEST | 2027-02-01 | WIN | WT | 168.45 |  | 2024-11-26 | 2024-12-03 | 2025-02-18 | 2024-11-20 | 2026-03-17 | No | 2005-02-28 | Yes |  |  | Not Required | 2026-03-25 | 2026-05-05 | 2026-05-05
26INR0700 | Key City Battery Storage SLF | SS Completed, FIS Started, No IA | Key City Battery Storage LLC | 6235 Abilene Mulberry Creek 345 | Taylor | WEST | 2029-03-31 | OTH | BA | 1.9 |  | 2026-04-13 | 2025-07-07 | 2025-09-30 | 2026-03-31 |  |  |  | No
26INR0701 | Key City Solar SLF | SS Completed, FIS Started, No IA | Key City Solar LLC | 6235 Abilene Mulberry Creek 345 | Taylor | WEST | 2029-03-31 | SOL | PV | 989.1 |  | 2026-04-10 | 2025-07-07 | 2025-09-30 | 2026-03-31 |  |  |  | No |  |  | Not Required
27INR0503 | Dog Star Solar I | SS Completed, FIS Started, No IA | Dog Star Solar LLC | Bluff Creek (Bus #60040) to Mulberry Creek (Bus #6235) 345 kV | Taylor | WEST | 2027-12-31 | SOL | PV | 499.01 |  | 2025-06-25 | 2025-07-07 | 2025-09-16 | 2025-06-20 |  | Yes |  | No |  |  | Not Required
27INR0504 | Dog Star Solar II | SS Completed, FIS Started, No IA | Dog Star Solar LLC | Bluff Creek (Bus #60040) to Mulberry Creek (Bus #6235) 345 kV | Taylor | WEST | 2027-12-31 | SOL | PV | 499.01 |  | 2025-06-25 | 2025-07-02 | 2025-09-19 | 2025-06-20 |  | Yes |  | No |  |  | Not Required
28INR0156 | Chimney Rock BESS | SS Completed, FIS Started, No IA | Taylor ESS, LLC | Tap 138kV 76317 MOORE - 76318 BUTMAN | Taylor | WEST | 2028-04-10 | OTH | BA | 156 |  | 2024-12-11 | 2025-02-14 | 2025-05-12 | 2024-12-17 |  |  |  | No
28INR0254 | Summerhill BESS | SS Completed, FIS Started, No IA | Taylor ESS, LLC | Tap 138kv 6228 ABNTHWST4A - 6288 MULBERRY4D | Taylor | WEST | 2028-12-15 | OTH | BA | 143 |  | 2025-02-14 | 2025-02-14 | 2025-05-13 | 2025-02-06 |  |  |  | No
21INR0263 | Monarch Creek Wind | SS Completed, FIS Completed, IA | MONARCH CREEK WIND, LLC | 11419 Coody Crossing Switch 345kV | Throckmorton | WEST | 2027-09-17 | WIN | WT | 283.4 |  | 2019-10-28 | 2019-04-25 | 2019-07-19 | 2019-08-05 | 2025-11-05 | No | 2020-08-24 | Yes | Not Required | Not Required | Not Required | 2025-12-22 | 2026-01-26 | 2026-01-26
25INR0558 | Ayass BESS | SS Completed, FIS Started, No IA | Harvick BESS, LLC | 6206 Bush Knob 69kV | Throckmorton | WEST | 2028-12-30 | OTH | BA | 51.28 |  | 2023-11-27 | 2023-12-04 | 2024-03-01 | 2023-11-15 |  |  |  | No
26INR0327 | Sleepy Hollow BESS | SS Completed, FIS Completed, No IA | Sleepy Hollow BESS, LLC | Tap 138 kV 792 Murray - 6169 Paint Creek | Throckmorton | WEST | 2028-02-22 | OTH | BA | 123.1 |  | 2023-11-30 | 2023-11-30 | 2024-02-27 | 2023-11-15 | 2025-07-21 |  |  | No | Not Required | Not Required
30INR0123 | Sideoats Solar 1 | SS Started, FIS Started, No IA | Bush Knob Solar, LLC | DUSTYROAD_5 (11050) to GRHAMSES1 (1430) 345 kV | Throckmorton | WEST | 2031-03-31 | SOL | PV | 167.6 | FIS Request | 2026-08-26 | 2026-09-18 |  | 2026-09-15 |  |  |  | No |  |  | Not Required
30INR0124 | Sideoats Solar 2 | SS Started, FIS Started, No IA | Bush Knob Solar, LLC | DUSTYROAD_5 (11050) to GRHAMSES1 (1430) 345kV | Throckmorton | WEST | 2031-03-31 | SOL | PV | 167.6 | FIS Request | 2026-09-16 | 2026-09-18 |  | 2026-09-15 |  |  |  | No |  |  | Not Required
30INR0125 | Sideoats Solar 3 | SS Started, FIS Started, No IA | Bush Knob Solar, LLC | DUSTYROAD_5 (11050) to GRHAMSES1 (1430) 345kV | Throckmorton | WEST | 2031-03-31 | SOL | PV | 167.6 | FIS Request | 2026-08-26 | 2026-09-18 |  | 2026-09-15 |  |  |  | No |  |  | Not Required
20INR0247 | Water Valley Wind Energy | SS Completed, FIS Started, IA | Water Valley Wind Energy, LLC | 345 kV 76009 Twin Buttes to 76090 Divide Double Circuit | Tom Green | WEST | 2027-12-15 | WIN | WT | 180 |  | 2019-01-10 | 2019-01-15 | 2019-03-29 | 2019-01-10 |  |  | 2025-03-17 | Yes |  |  | Not Required
23INR0224 | Morning Glory Solar | SS Completed, FIS Started, No IA | Armadillo Solar, LLC | tap 345kV 7077 Amos Creek - 76009 Twin Buttes | Tom Green | WEST | 2028-11-30 | SOL | PV | 122.4 |  | 2022-05-31 | 2021-06-16 | 2021-09-07 | 2022-05-17 |  |  |  | No |  |  | Not Required
23INR0312 | Hofbrau BESS | SS Completed, FIS Started, No IA | Momentum Hofbrau LLC | 6442 Redcreek 138kV | Tom Green | WEST | 2028-07-01 | OTH | BA | 180.72 |  | 2021-09-22 | 2021-09-22 | 2021-12-09 | 2021-09-22 |  | No |  | No
25INR0339 | Fort Concho Energy storage | SS Completed, FIS Started, No IA | Rocky Mountain Energy Development, LLC | Tap 138 kV #76320 Schkade - #76011 Twin Buttes Line; LCRA | Tom Green | WEST | 2028-12-31 | OTH | BA | 251.15 |  | 2023-02-23 | 2023-01-30 | 2023-04-28 | 2023-02-17 |  |  |  | No
25INR0853 | Tango Lily BESS | SS Completed, FIS Started, No IA | Lightsource Renewable Energy Development LLC | Tap 138kV 60008 TRIBUTE4A - 6442 REDCREEK4A | Tom Green | WEST | 2029-12-22 | OTH | BA | 200.95 |  | 2026-01-09 | 2026-01-26 | 2026-04-17 | 2026-01-20 |  | No |  | No | Not Required | Not Required
26INR0083 | Zeppelin Energy Storage | SS Completed, FIS Started, No IA | ZEPPELIN ENERGY STORAGE LLC | 6464 San Angelo North | Tom Green | WEST | 2028-05-31 | OTH | BA | 163.93 |  | 2023-03-08 | 2023-01-30 | 2023-04-28 | 2023-02-17 19:02 |  |  |  | No
26INR0454 | Dove Creek Solar | SS Completed, FIS Started, No IA | Dove Creek Solar, LLC | Tap at Big Hill - Twin Buttes 345 kV line (76003 / 76009) | Tom Green | WEST | 2028-07-01 | SOL | PV | 163.6 |  | 2024-07-10 | 2024-07-22 | 2024-10-08 | 2024-06-25 |  |  |  | No | Not Required | Not Required | Not Required
26INR0455 | Dove Creek Storage | SS Completed, FIS Started, No IA | Dove Creek Solar, LLC | Tap at Big Hill - Twin Buttes 345 kV line (76003 / 76009) | Tom Green | WEST | 2028-07-01 | OTH | BA | 162.5 |  | 2024-07-10 | 2024-07-22 | 2024-10-08 | 2024-06-25 |  |  |  | No | Not Required |  | 2025-09-15
27INR0445 | Moon Chapel Wind | SS Completed, FIS Started, No IA | Orsted Onshore Development North America, LLC | Tap 345kV 76090 Divide - 76009 Twin Buttes Ckt 1 | Tom Green | WEST | 2028-10-01 | WIN | WT | 379.2 |  | 2025-02-07 | 2025-02-14 | 2025-05-12 | 2025-02-07 |  | No |  | No |  |  | Not Required
29INR0231 | Tango Lily Solar | SS Completed, FIS Started, No IA | Lightsource Renewable Energy Development LLC | Tap 138kV 60008 TRIBUTE4A - 6442 REDCREEK4A | Tom Green | WEST | 2029-12-21 | SOL | PV | 200.95 |  | 2026-01-20 | 2026-01-26 | 2026-04-17 | 2025-12-19 |  | No |  | No | Not Required | Not Required | Not Required
29INR0328 | Moon Chapel Solar | SS Completed, FIS Started, No IA | Orsted Onshore Development North America, LLC | Tap 345kV 76090 Divide – 76009 Twin Buttes Ckt 1 | Tom Green | WEST | 2029-12-31 | SOL | PV | 402.01 |  | 2026-07-15 | 2026-04-22 | 2026-07-07 |  |  |  |  | No |  |  | Not Required
29INR0365 | Silver Sky Solar | SS Started, FIS Started, No IA | Lightsource Renewable Energy Development LLC | 6444 Red Creek 345kV | Tom Green | WEST | 2029-12-13 | SOL | PV | 401.9 |  | 2026-08-10 | 2026-08-17 |  | 2026-08-12 |  |  |  | No |  |  | Not Required
29INR0376 | Silver Sky BESS | SS Started, FIS Started, No IA | Lightsource Renewable Energy Development LLC | 6444 Red Creek 345kV | Tom Green | WEST | 2029-12-13 | OTH | BA | 201.1 |  | 2026-08-10 | 2026-08-17 |  | 2026-08-12 |  |  |  | No
22INR0488 | Venture Hill Storage | SS Completed, FIS Started, No IA | KCE TX 24, LLC | 7336 Gilleland Creek 138kV | Travis | SOUTH | 2026-12-01 | OTH | BA | 70.44 |  | 2021-01-08 | 2021-02-09 | 2021-05-06 | 2020-12-29 |  |  |  | No
23INR0474 | AP Greenport | SS Completed, FIS Completed, No IA | AP Greenport | Austrop – Lost Pines 345 kV transmission line (Bus #7040 – 9041) | Travis | SOUTH | 2027-11-19 | OTH | BA | 100.45 |  | 2022-09-14 | 2022-06-10 | 2022-09-06 | 2022-06-24 | 2023-09-29 | No |  | No
24INR0372 | GIGA AUSTIN SOLAR | SS Completed, FIS Started, No IA | GIGA TEXAS ENERGY LLC | 7047 HORNSBY Substation 138kV | Travis | SOUTH | 2027-03-14 | SOL | PV | -53.3 |  | 2022-08-09 | 2022-07-18 | 2022-10-14 | 2022-07-26 |  |  |  | No |  |  | Not Required
25INR0266 | East Blackland Battery Storage SLF | SS Completed, FIS Started, No IA | DERIVA ENERGY STORAGE, LLC | 7337 Kimbro 138kV | Travis | SOUTH | 2028-05-27 | OTH | BA | 75 |  | 2022-11-17 | 2022-11-23 | 2023-02-17 | 2022-11-22 |  |  |  | No
25INR0688 | Giga Texas Data Center | SS Completed, FIS Completed, IA | Giga Texas Energy, LLC | HORNSBY Substation POIB# 7047 Site will be connected behind the meter at Medium Voltage 24.9 kV with non export controls GSU TRANSFORMER 80/106/133MVA 345kV DELTA PRIMARY 24.9kV WYE-G SECONDARY Z=XX%, 65DEG C RISE | Travis | SOUTH | 2025-12-15 | OTH | BA | 133 |  | 2024-08-15 | 2024-08-27 | 2024-11-25 | 2024-07-30 | 2025-03-17 |  | 2025-04-30 | No | Not Required | Not Required |  |  |  | 2025-05-01
27INR0485 | Blackland Prairie 1 Energy Storage | SS Completed, FIS Started, IA | Balcones Ridge Resiliency LLC | 9328 Austrop 138kV | Travis | SOUTH | 2027-12-01 | OTH | BA | 102.1 |  | 2025-02-24 | 2025-03-24 | 2025-06-09 | 2025-02-24 |  |  | 2026-04-10 | No
27INR0486 | Blackland Prairie 2 Energy Storage | SS Completed, FIS Started, No IA | Balcones Ridge Resiliency II LLC | 9328 Austrop 138kV | Travis | SOUTH | 2030-12-01 | OTH | BA | 102.1 | COD | 2025-02-24 | 2025-03-24 | 2025-06-09 | 2025-02-24 |  |  |  | No
27INR0487 | Blackland Prairie 3 Energy Storage | SS Completed, FIS Started, No IA | Balcones Ridge Resiliency II LLC | 9328 Austrop 138kV | Travis | SOUTH | 2030-12-01 | OTH | BA | 102.1 | COD | 2025-02-24 | 2025-03-24 | 2025-06-09 | 2025-02-24 |  |  |  | No
19INR0002 | Grandfalls Solar | SS Completed, FIS Completed, IA | King Mountain Solar, LLC | 842 King Mountain Station 345kV | Upton | WEST | 2026-11-25 | SOL | PV | 175.6 |  | 2016-05-24 | 2016-05-24 | 2016-06-06 | 2016-05-24 | 2025-12-17 | No | 2025-01-23 | Yes | Not Required | Not Required | Not Required | 2026-01-08 | 2026-01-26 | 2026-01-26 |  |  | 2026-06-24 | 2026-07-15
19INR0189 | SP TX-12B Phase III | SS Completed, FIS Started, No IA | ConEd Development | 76040 Castillo 138kV | Upton | WEST | 2025-12-02 | SOL | PV | 40 |  | 2019-01-29 | 2018-09-12 | 2018-10-03 |  |  | No |  | No | Not Required | Not Required | Not Required
21INR0006 | Giddings Wind | SS Completed, FIS Started, No IA | Pioneer Natural Resources | 71212 Upton 138kV | Upton | WEST | 2030-09-09 | WIN | WT | 240 |  | 2019-04-02 | 2017-09-06 | 2019-08-19 | 2020-01-15 |  |  |  | No | Not Required | Not Required | Not Required
21INR0262 | Grandfalls Storage SLF | SS Completed, FIS Started, No IA | King Mountain Storage LLC | tap 345kV 11028 Odessa - 76000 North McCamey | Upton | WEST | 2028-07-01 | OTH | BA | 175.6 |  | 2019-02-14 | 2019-03-25 | 2019-06-17 | 2019-02-14 |  |  |  | No |  |  | 2023-05-22
24INR0238 | Appaloosa Run BESS | SS Completed, FIS Started, No IA | APPALOOSA RUN STORAGE, LLC | New Palouse 138kV (#60278) | Upton | WEST | 2026-08-30 | OTH | BA | 103 |  | 2022-02-11 | 2022-03-07 | 2022-06-02 | 2022-03-01 |  |  |  | No |  |  | 2024-02-09
24INR0393 | ELECTRODE BESS | SS Completed, FIS Started, No IA | CED Development Inc. | 76040 Castillo 138kV | Upton | WEST | 2027-12-31 | OTH | BA | 150 |  | 2022-07-18 | 2022-07-25 | 2022-10-21 | 2022-07-12 |  |  |  | No | Not Required | Not Required
24INR0394 | CATHODE BESS | SS Completed, FIS Started, No IA | CED Development Inc. | 76635 King Mountain 138kV | Upton | WEST | 2027-12-31 | OTH | BA | 150 |  | 2022-07-25 | 2022-08-05 | 2022-11-01 | 2022-07-12 |  |  |  | No
24INR0404 | Tres Rios Ranch Solar | SS Completed, FIS Started, IA | LectricWind LLC | 76008 Twelvemile 345kV | Upton | WEST | 2027-12-31 | SOL | PV | 508 |  | 2023-05-04 | 2022-08-05 | 2022-11-01 | 2023-04-26 19:05 |  |  | 2025-12-30 | No |  |  | Not Required
25INR0207 | Shadow Ranch Solar | SS Completed, FIS Started, No IA | LectricWind LLC | 842 King Mountain 345kV | Upton | WEST | 2030-06-01 | SOL | PV | 807.61 |  | 2023-07-24 | 2022-09-27 | 2023-01-12 | 2023-07-11 |  |  |  | No |  |  | Not Required
25INR0417 | Mesa View Storage | SS Completed, FIS Completed, IA | Mesa View Storage, LLC | Tap 345 kV KINGMTSW (#842) to NORTMC (#76000) | Upton | WEST | 2027-07-15 | OTH | BA | 254.88 |  | 2023-04-11 | 2023-04-19 | 2023-07-12 | 2023-04-12 | 2026-06-11 | No | 2024-09-09 | Yes | Not Required | Not Required |  | 2026-07-29 | 2026-07-29 | 2026-07-29
25INR0451 | Tres Rios Ranch BESS | SS Completed, FIS Started, IA | LectricWind LLC | 76008 Twelvemile 345kV | Upton | WEST | 2027-12-31 | OTH | BA | 290 |  | 2023-05-22 | 2023-05-26 | 2023-08-22 | 2023-05-23 |  |  | 2025-12-30 | No
25INR0557 | McCamey's Castle Battery | SS Completed, FIS Started, IA | Castle Storage, LLC | 76597 Robbins Switch 138 kV | Upton | WEST | 2028-03-30 | OTH | BA | 409.6 |  | 2023-09-29 | 2023-10-13 | 2024-01-10 | 2023-10-09 |  |  | 2025-03-20 | Yes | Not Required | Not Required |  | 2025-03-20 |  |  | 2026-05-28 | 2027-03-31
28INR0057 | Windecker | SS Completed, FIS Started, No IA | Windecker Energy LLC | 10058 Catclaw Switch 138kV | Upton | WEST | 2028-04-17 | WIN | WT | 419.7 |  | 2024-03-13 | 2024-03-29 | 2024-06-19 | 2024-03-14 |  |  |  | No |  |  | Not Required
28INR0086 | West Royal Natural Gas (TEF-Due Diligence) | SS Completed, FIS Started, No IA | Invenergy Energy Transition Development LLC | Tap 345kV 76000 L_NORTMC5_1Y - 18668 ROCKDRAW_5 | Upton | WEST | 2030-06-01 | GAS | GT | 888 |  | 2025-01-13 | 2024-06-13 | 2024-09-10 | 2024-12-17 |  |  |  | No
28INR0212 | Badger Solar | SS Completed, FIS Started, No IA | 174 Power Global Properties, LLC | Tap 345kV 59903 Bearkat - 76000 L_NORTMC5_1Y | Upton | WEST | 2029-05-25 | SOL | PV | 280.46 | MW Size | 2025-02-05 | 2025-02-12 | 2025-04-22 | 2024-11-27 |  |  |  | No |  |  | Not Required
28INR0213 | Badger BESS | SS Completed, FIS Started, No IA | Greasewood BESS, LLC | Tap 345kV 59903 Bearkat - 76000 L_NORTMC5_1Y | Upton | WEST | 2029-05-25 | OTH | BA | 138.57 | MW Size | 2025-02-05 | 2025-02-12 | 2025-04-22 | 2024-11-27 |  |  |  | No
28INR0446 | Vista Bluff Wind I "Alternate POI" | SS Completed, FIS Started, No IA | Vista Bluff Windpower, LLC | tap 345 kV (76000) North McCamey - (59903) Bearkat (Benedum 345 kV station that LCRA will build part of 24RPG024). | Upton | WEST | 2029-12-31 | WIN | WT | 290.4 |  | 2025-09-16 | 2025-09-22 | 2025-12-12 | 2025-09-22 |  |  |  | No |  |  | Not Required
28INR0447 | Vista Bluff Wind II "Alternate POI" | SS Completed, FIS Started, No IA | Vista Bluff Windpower, LLC | tap 345 kV (76000) North McCamey - (59903) Bearkat (Benedum 345 kV station that LCRA will build part of 24RPG024). | Upton | WEST | 2029-12-31 | WIN | WT | 290.4 |  | 2025-09-16 | 2025-09-22 | 2025-12-12 | 2025-09-22 |  |  |  | No |  |  | Not Required
21INR0334 | Nightfall Solar | SS Completed, FIS Completed, IA | BDPU SOLAR NIGHTFALL, LLC | 138 kV Tap 8707 Dryfrio - 8234 Uvalde (new 138 kV Meil station) | Uvalde | SOUTH | 2026-12-31 | SOL | PV | 180.87 |  | 2020-09-24 | 2019-05-10 | 2019-07-31 | 2020-01-24 | 2025-12-17 |  | 2023-10-26 | Yes | Not Required | Not Required | Not Required | 2025-05-14 | 2026-01-29 | 2026-01-29 |  |  | 2026-09-22
28INR0188 | Ashra Solar SLF | SS Completed, FIS Started, No IA | Ashra Solar, LLC | Tap 69kV bus#5823 UVALDE Switch (UVALDESW9) to bus#5820 UVALDE SUB (UVALDESUB9) | Uvalde | SOUTH | 2028-06-14 | SOL | PV | 40.25 |  | 2025-03-30 | 2025-04-25 | 2025-07-22 | 2025-03-31 |  |  |  | No |  |  | Not Required
28INR0190 | Ashra Storage SLF | SS Completed, FIS Started, No IA | Ashra Solar, LLC | Tap 69kV 5823 UVALDE Switch - 5820 UVALDE SUB | Uvalde | SOUTH | 2028-06-14 | OTH | BA | 1.62 |  | 2025-03-30 | 2025-04-25 | 2025-07-22 | 2025-03-31 |  |  |  | No
25INR0546 | VISOL 1 SOLAR | SS Completed, FIS Started, No IA | VISOL 1 SOLAR, LLC | Tap 138kV 8683 Comstock - 60389 Corral | Val Verde | WEST | 2028-06-30 | SOL | PV | 94.78 |  | 2024-02-04 | 2023-10-25 | 2024-01-22 | 2024-01-24 |  | No |  | No | Not Required | Not Required | Not Required
26INR0260 | Evans Creek Energy Storage | SS Completed, FIS Started, No IA | Evans Creek Energy Storage LLC | Comstock 138kV Substation (PSSE Bus #8683) | Val Verde | WEST | 2028-04-01 | OTH | BA | 102.96 |  | 2023-09-13 | 2023-10-25 | 2024-01-22 | 2023-10-19 |  | No |  | No
26INR0419 | Lone Bow Solar | SS Completed, FIS Started, No IA | Greenalia Solar Power Lone Bow LLC | Tap 138 kV 8683 Comstock - 60389 Corral | Val Verde | WEST | 2030-06-15 | SOL | PV | 277.46 |  | 2024-01-22 | 2026-05-11 | 2026-08-06 | 2026-02-02 |  |  |  | No |  |  | Not Required
23INR0045 | Caney Creek Solar | SS Completed, FIS Started, IA | HEP Aquamarine Holdings LLC | Tap 138kV 6829 Glen Pine - 6833 Explorer | Van Zandt | NORTH | 2027-06-21 | SOL | PV | 121.04 |  | 2016-02-23 | 2020-09-25 | 2020-12-16 | 2021-02-22 |  | No | 2021-12-29 | Yes | Not Required | Not Required | Not Required | 2021-12-13
24INR0472 | Amador Storage | SS Completed, FIS Completed, IA | BT Amador Storage, LLC | 6833 Explorer Switching Station 138kV | Van Zandt | NORTH | 2027-04-08 | OTH | BA | 102.41 | COD | 2022-11-15 | 2022-11-23 | 2023-02-17 | 2022-11-18 | 2024-12-18 | No | 2023-11-02 | Yes |  |  |  | 2025-02-03 | 2025-02-03 | 2025-02-03
25INR0253 | Whiskey BESS | SS Completed, FIS Started, IA | Whiskey BESS LLC | 6828 Canton Tap 138 kV | Van Zandt | NORTH | 2027-07-31 | OTH | BA | 153.72 |  | 2023-05-04 | 2022-12-07 | 2023-03-06 | 2023-05-02 |  |  | 2025-03-28 | No | Not Required | Not Required
25INR0384 | Zorro BESS | SS Completed, FIS Completed, IA | ZORRO BESS LLC | 138 kV Ben Wheeler (Bus# 6852) | Van Zandt | NORTH | 2027-08-31 | OTH | BA | 153.69 |  | 2023-06-13 | 2023-03-27 | 2023-06-19 | 2023-06-02 | 2024-05-21 | No | 2025-03-28 | No | Not Required | Not Required
26INR0253 | Goldfinch Solar | SS Completed, FIS Started, No IA | BT DJ4M Solar, LLC | Tap Connection Bus 2485 Poetry Switch to 3103 Shamburger Switch | Van Zandt | NORTH | 2029-03-31 | SOL | PV | 150.77 |  | 2023-09-15 | 2023-09-22 | 2023-12-14 | 2023-09-15 |  | No |  | No | Not Required | Not Required | Not Required
26INR0254 | Goldfinch Storage | SS Completed, FIS Started, No IA | BT DJ4M Solar, LLC | Tap Connection Bus 2485 Poetry Switch – 3223 Shamburger Switch | Van Zandt | NORTH | 2030-03-31 | OTH | BA | 100.44 |  | 2023-09-26 | 2023-10-04 | 2023-12-14 | 2023-09-20 |  |  |  | No | Not Required | Not Required
27INR0317 | Edgewood BESS 1 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap Edgewood 138kV bus(3181) to CANTNSW_8 (3174) | Van Zandt | NORTH | 2028-03-01 | OTH | BA | 102.1 |  | 2024-10-16 | 2024-11-21 | 2025-02-18 | 2024-11-05 |  |  |  | No
27INR0413 | Edgewood BESS 2 | SS Completed, FIS Started, No IA | Tempus Power management LLC | Tap Edgewood 138kV bus(3181) to 3174 | Van Zandt | NORTH | 2028-03-01 | OTH | BA | 102.1 |  | 2024-10-24 | 2025-01-28 | 2025-04-21 | 2025-01-14 |  |  |  | No
23INR0090 | Iguala Solar | SS Completed, FIS Started, IA | Iguala Solar LLC | AEP South Texas Project (#5915) to Static (#8676) 345kV line | Victoria | SOUTH | 2029-02-01 | SOL | PV | 250 |  | 2021-06-11 | 2020-10-07 | 2020-12-28 | 2021-06-07 |  | Yes | 2025-07-29 | No |  |  | Not Required
23INR0342 | Brizo BESS | SS Completed, FIS Started, IA | BRP Brizo BESS LLC | 138 kV Loop 463 Substation (#5680) | Victoria | SOUTH | 2027-09-01 | OTH | BA | 144.22 |  | 2021-10-05 | 2021-10-05 | 2021-12-22 | 2021-09-24 |  |  | 2025-03-27 | No | Not Required | Not Required
24INR0168 | Tejano Storage | SS Completed, FIS Started, No IA | Tejano Storage, LLC | Tap 138kV 8125 Lolita - 8172 Victoria | Victoria | SOUTH | 2029-07-01 | OTH | BA | 152.31 |  | 2022-05-06 | 2022-03-30 | 2022-06-26 | 2022-04-18 |  | No |  | No
24INR0425 | Two Brothers ESS | SS Completed, FIS Started, IA | BRP Blue Topaz 2, LLC | 8911 BLKBYU4A 138kV | Victoria | SOUTH | 2028-02-29 | OTH | BA | 154.65 |  | 2022-09-13 | 2022-09-15 | 2022-12-13 | 2022-09-14 |  | No | 2024-04-22 | Yes | Not Required | Not Required |  | 2025-02-13
26INR0021 | Crossroads Wind | SS Completed, FIS Completed, IA | HyFuels Green Lake Wind LLC | 80090 Dokmai 138 KV | Victoria | SOUTH | 2028-02-28 | WIN | WT | 277.38 | MW Size COD | 2023-07-01 | 2022-09-27 | 2022-12-22 | 2023-06-16 | 2026-05-28 |  | 2024-07-24 | Yes | Not Required | Not Required | Not Required | 2025-09-10
26INR0028 | HyFuels Calhoun Solar | SS Completed, FIS Started, No IA | HyFuels Green Lake Solar LLC | Tap 345kV 8715 RADIANT7A - 8728 COBRA7A | Victoria | SOUTH | 2028-10-07 | SOL | PV | 301.82 |  | 2023-07-17 | 2022-10-18 | 2023-01-15 | 2023-07-07 |  | Yes |  | No |  |  | Not Required
26INR0505 | Goldhill Energy Storage | SS Completed, FIS Started, No IA | Goldhill Energy Storage LLC | Tap 138kV 8154 VISTRON4B – 8189 TUNGSTEN4A | Victoria | SOUTH | 2028-09-30 | OTH | BA | 200.58 |  | 2024-04-12 | 2024-04-15 | 2024-07-05 | 2024-04-15 |  |  |  | No
26INR0559 | Georgia-Lynn BESS | SS Completed, FIS Started, No IA | Georgia Lynn BESS LLC | 80064 CHOCBAYU4A 138 kV | Victoria | SOUTH | 2028-02-20 | OTH | BA | 108.7 |  | 2024-07-25 | 2024-07-30 | 2024-10-28 | 2024-07-25 |  |  |  | No
27INR0169 | Marcos Solar SLF | SS Completed, FIS Started, No IA | GRS BESS Texas Eight | To the 138 kV line from EDNA (#8118) to VICTORIA4A (#8172) | Victoria | SOUTH | 2028-08-15 | SOL | PV | 216.11 |  | 2024-01-06 | 2024-01-11 | 2024-04-08 | 2023-12-28 |  |  |  | No |  |  | Not Required
27INR0170 | Marcos BESS | SS Completed, FIS Started, No IA | GRS BESS Texas Eight LLC | To the 138 kV line from EDNA (#8118) to VICTORIA4A (#8172) | Victoria | SOUTH | 2027-08-15 | OTH | BA | 115.88 |  | 2024-01-17 | 2024-02-07 | 2024-04-30 | 2024-01-16 |  |  |  | No
27INR0224 | Leopard BESS | SS Completed, FIS Started, IA | Bobcat Energy Center, LLC | 8721 Beecher 138 kV | Victoria | SOUTH | 2029-02-28 | OTH | BA | 264.24 |  | 2024-04-22 | 2024-05-09 | 2024-08-05 | 2024-04-05 |  | No | 2025-06-09 | Yes | Not Required | Not Required | 2025-08-08 | 2025-08-08
27INR0382 | Calico BESS | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | Tap 138 kV 8723 CANGREJO4A - 8721 BEECHER4A | Victoria | SOUTH | 2028-06-01 | OTH | BA | 204.9 |  | 2024-10-28 | 2025-04-29 | 2025-07-26 | 2025-03-14 |  |  |  | No
28INR0356 | Arpeggio BESS | SS Completed, FIS Started, No IA | Arpeggio BESS, LLC | #80064 Chocolate Bayou 138kV | Victoria | SOUTH | 2029-09-30 | OTH | BA | 200.71 |  | 2025-06-17 | 2025-06-19 | 2025-09-17 | 2025-06-18 |  |  |  | No
29INR0243 | Oak Belt Solar | SS Completed, FIS Started, No IA | Oak Belt Solar, LLC | Tap 138 kV (Bus #5506) FURHMANSB8 - (Bus #5584) VANDERBLTSW8 | Victoria | SOUTH | 2030-03-31 | SOL | PV | 181 | COD | 2025-12-16 | 2025-12-23 | 2026-02-05 | 2025-12-17 |  |  |  | No | Not Required | Not Required | Not Required
29INR0244 | Oak Belt Storage | SS Completed, FIS Started, No IA | Oak Belt Storage, LLC | Tap 138 kV (Bus #5506) FURHMANSB8 - (Bus #5584) VANDERBLTSW8 | Victoria | SOUTH | 2030-03-31 | OTH | BA | 209.7 | COD | 2025-12-16 | 2025-12-23 | 2026-02-05 | 2025-12-17 |  |  |  | No | Not Required | Not Required
29INR0248 | Blue Energy Center - Phase 1b – Steam | SS Completed, FIS Started, No IA | Brother 1, LLC | Tap 345kV 80286 DULCE7A - 8676 STATIC7A | Victoria | SOUTH | 2031-10-17 | GAS | CC | 330 | Proj Name MW Size | 2025-12-22 | 2026-01-26 | 2026-04-24 | 2026-01-20 |  | No |  | No
30INR0150 | Blue Energy Center- Phase 1a - Gas | SS Started, FIS Started, No IA | Brother 1, LLC | Tap 345kV 80286 DULCE7A - 8676 STATIC7A | Victoria | SOUTH | 2030-05-02 | GAS | GT | 780 | FIS Request | 2026-09-04 | 2026-09-04 |  | 2026-09-04 |  |  |  | No
33INR0007 | Blue Energy Center - Phase 3 – Steam Stage 2 | SS Started, FIS Started, No IA | Sister 1, LLC | Tap 345kV 80286 DULCE7A - 8676 STATIC7A | Victoria | SOUTH | 2033-06-15 | NUC | ST | 1320 | FIS Request | 2026-09-04 | 2026-09-10 |  | 2026-09-04 |  |  |  | No
24INR0461 | Augie BESS | SS Completed, FIS Completed, No IA | BRP Blue Topaz 5, LLC | 46560 Waller 138kV | Waller | HOUSTON | 2027-12-17 | OTH | BA | 200.81 |  | 2022-12-01 | 2023-01-23 | 2023-04-22 | 2023-01-18 | 2024-01-24 | No |  | No
26INR0243 | Caladium BESS | SS Completed, FIS Started, No IA | Caladium Storage, LLC | 57664 Sunnyside 69kV | Waller | HOUSTON | 2027-11-30 | OTH | BA | 201.28 |  | 2024-09-09 | 2024-11-19 | 2025-02-18 | 2024-10-29 |  |  |  | No
26INR0425 | Twinwood Solar 1 | SS Completed, FIS Started, IA | Twinwood PV1, LLC | Tap 138kV 44750 FULSHR_S25_8 - 44860 TWINWD_S25_8 | Waller | HOUSTON | 2029-02-01 | SOL | PV | 358.06 |  | 2024-08-06 | 2024-03-22 | 2024-06-19 | 2024-07-20 |  |  | 2025-11-07 | Yes |  |  | Not Required | 2026-05-26
26INR0426 | Maderagemela BESS1 | SS Completed, FIS Started, IA | Twinwood ES1, LLC | Tap 138kV 44750 FULSHR_S25_8 to 44860 TWINWD_S25_8 | Waller | HOUSTON | 2029-02-01 | OTH | BA | 153.96 |  | 2024-07-31 | 2024-02-27 | 2024-05-24 | 2024-07-20 |  |  | 2025-11-07 | Yes |  |  |  | 2026-05-26
23INR0075 | BRP Rhine BESS | SS Completed, FIS Started, No IA | BRP Rhine BESS LLC | Tap 345kV 11188 QUARRYFLD - 11010 WOLF | Ward | WEST | 2028-12-01 | OTH | BA | 206.89 |  | 2020-09-22 | 2020-08-04 | 2020-11-02 | 2020-09-17 |  |  |  | No
23INR0094 | BRP Pyxis BESS | SS Completed, FIS Started, No IA | BRP Pyxis BESS LLC | tap 138kV 1009 Yucca - 11197 Sand Tank Pod | Ward | WEST | 2028-12-01 | OTH | BA | 206.87 |  | 2020-09-23 | 2020-09-25 | 2020-12-16 | 2020-09-11 |  |  |  | No
24INR0538 | FLIFER Solar I | SS Completed, FIS Started, No IA | FLIFER LLC | Tap 138 kV Yucca Drive Switch (bus# 1009) – Sand Tank (bus# 11197) | Ward | WEST | 2027-04-15 | SOL | PV | 84 |  | 2023-05-08 | 2023-03-08 | 2023-06-01 | 2023-04-26 |  |  |  | No |  |  | Not Required
25INR0008 | BasRanch (TEF - Due Diligence) | SS Completed, FIS Completed, IA | CPV Basin Ranch, LLC | tap 345kV Riverton Switch - Sand Lake Switch | Ward | WEST | 2028-12-01 | GAS | CC | 1350 |  | 2021-11-24 | 2020-08-04 | 2020-11-02 | 2021-10-28 | 2025-05-05 | Yes | 2025-07-16 | Yes | 2024-11-25 | 2024-11-25 | 2025-09-05 | 2025-09-08
25INR0606 | Proteus Thornton Ranch Solar SLF | SS Completed, FIS Started, No IA | Thornton Ranch Solar, LLC | 37990 TNSTAGHORN1 138kV | Ward | WEST | 2028-11-20 | SOL | PV | 180 |  | 2024-02-12 | 2024-02-26 | 2024-05-20 | 2024-02-12 |  | No |  | No | Not Required | Not Required | Not Required
25INR0607 | Proteus Thornton Ranch Storage SLF | SS Completed, FIS Started, No IA | Thornton Ranch Solar, LLC | 37990 TNSTAGHORN1 138kV | Ward | WEST | 2028-11-20 | OTH | BA | 0 |  | 2024-01-08 | 2024-03-22 | 2024-06-19 | 2024-03-11 |  | No |  | No
26INR0724 | Monahans Power Gas | SS Completed, FIS Started, No IA | Liberty Power Innovations LLC | Tap #1107 Monahans Tap 2 to #11117 Pecos Trail 138kV | Ward | WEST | 2030-04-16 | GAS | IC | 18.2 |  | 2026-05-29 | 2025-09-22 | 2025-12-02 | 2026-05-26 |  |  |  | No
27INR0202 | Shallow Valley Storage | SS Completed, FIS Completed, No IA | Shallow Valley Storage, LLC | Tap 138kV 1239 Coyanosa - 11238 Blair Lake Sub | Ward | WEST | 2029-04-19 | OTH | BA | 103.39 | Status Change INA-to-PLN | 2024-07-19 | 2024-07-22 | 2024-10-17 | 2024-07-19 | 2026-02-27 |  |  | No
27INR0255 | New Minglewood Energy Center | SS Completed, FIS Started, No IA | Nova Clean Energy LLC | #11098 Sand Lake Switch Station (SANDLAKE_5) 345kV | Ward | WEST | 2029-09-29 | OTH | BA | 208.3 |  | 2024-04-24 | 2024-05-09 | 2024-08-05 | 2024-04-29 |  | No |  | No
27INR0562 | Frizzle BESS | SS Completed, FIS Started, No IA | Frizzle BESS, L.L.C. | #38143, TNSLVRLEAF1, 138kV | Ward | WEST | 2027-10-18 | OTH | BA | 180.9 |  | 2025-09-10 | 2025-09-11 | 2025-11-11 | 2025-09-10 |  |  |  | No | Not Required | Not Required
28INR0105 | Vast Sands Power I (TEF -Due Diligence) | SS Completed, FIS Completed, IA | Permian Power I LLC | Tap 345kV 11010 Wolf Switch - 11188 Quarry Field Switch Ckt 2 | Ward | WEST | 2028-05-01 | GAS | GT | 440 |  | 2024-07-05 | 2024-07-22 | 2024-10-08 | 2024-07-05 | 2026-09-16 |  | 2025-10-31 | Yes | 2026-01-12 | 2026-02-10 | 2026-04-12 | 2026-02-10
28INR0109 | Vast Sands Power II (TEF-Due Diligence) | SS Completed, FIS Completed, IA | Permian Power I LLC | Tap 345kV 11010 Wolf Switch - 11188 Quarry Field Switch Ckt 2 | Ward | WEST | 2028-06-30 | GAS | GT | 440 |  | 2024-07-05 | 2024-07-22 | 2024-10-08 | 2024-07-03 | 2026-09-16 |  | 2025-10-31 | Yes | 2026-01-12 | 2025-09-24 | 2026-04-12 | 2026-04-21
20INR0047 | Siete | SS Completed, FIS Started, IA | Apex Clean Energy | 345kV 8718 Triada | Webb | SOUTH | 2029-03-31 | WIN | WT | 492.8 |  | 2019-06-13 | 2018-10-23 | 2018-12-11 | 2019-06-12 |  | No | 2022-06-30 | Yes | Not Required | Not Required | Not Required | 2022-07-19
22INR0257 | Corazon Solar Phase II | SS Completed, FIS Started, IA | BAYWA R.E. SOLAR PROJECTS | 80219 Lobo 345kV | Webb | SOUTH | 2028-06-01 | SOL | PV | 203.9 |  | 2019-12-16 | 2019-12-19 | 2020-03-12 | 2019-12-04 |  | No | 2020-08-04 | No | Not Required | Not Required | Not Required
23INR0183 | Pradera Storage | SS Completed, FIS Started, No IA | Pradera Storage, LLC | tap 345 kV Lobo 80219 - Fowlerton 5709 ckt #2 | Webb | SOUTH | 2029-06-23 | OTH | BA | 153.11 |  | 2021-10-18 | 2021-01-25 | 2021-04-16 | 2021-10-13 |  |  |  | No
23INR0209 | Outpost Storage | SS Completed, FIS Started, No IA | Hecate Energy Outpost Storage LLC | 345kv Avanzada7A (80235) | Webb | SOUTH | 2028-03-01 | OTH | BA | 508.1 |  | 2021-02-15 | 2021-03-01 | 2021-05-13 | 2021-02-15 |  |  |  | No
24INR0059 | Cuchillas Solar | SS Completed, FIS Completed, IA | Gransolar Texas Two, LLC | 80219 Lobo 345kV | Webb | SOUTH | 2028-12-15 | SOL | PV | 305.6 |  | 2022-02-24 | 2021-06-02 | 2021-08-18 | 2022-02-11 | 2025-05-27 | No | 2023-06-20 | Yes |  |  | Not Required | 2025-02-13
25INR0321 | El Molino Solar SLF | SS Completed, FIS Started, No IA | El Molino Solar, LLC | Tap 138kV 80439 LaQuinta - 8297 Bruni 8297 | Webb | SOUTH | 2029-09-01 | SOL | PV | 201.32 |  | 2023-01-16 | 2023-01-17 | 2023-04-14 | 2023-03-31 |  | No |  | No |  |  | Not Required
25INR0322 | El Molino Storage SLF | SS Completed, FIS Started, No IA | El Molino Solar, LLC | Tap 138kV 80439 LaQuinta - 8297 Bruni 8297 | Webb | SOUTH | 2029-09-01 | OTH | BA | 0 |  | 2023-01-16 | 2023-01-17 | 2023-04-14 | 2023-01-13 |  | No |  | No
26INR0024 | Becerra Creek Storage 1 | SS Completed, FIS Started, No IA | Bordas Renewable Energy, LLC | 345 kV Cenizo Substation (#80220) | Webb | SOUTH | 2027-12-01 | OTH | BA | 125.62 |  | 2022-09-19 | 2022-09-21 | 2022-12-19 | 2022-09-07 |  |  |  | No
27INR0003 | Becerra Creek Storage 2 | SS Completed, FIS Started, No IA | Bordas Renewable Energy, LLC | 345 kV Cenizo Substation (#80220) | Webb | SOUTH | 2027-12-01 | OTH | BA | 125.62 |  | 2022-09-19 | 2022-09-21 | 2022-12-19 | 2022-09-07 |  |  |  | No
27INR0077 | Cuchillas BESS | SS Completed, FIS Started, No IA | Gransolar Texas Two | 80219 Lobo 345kV | Webb | SOUTH | 2028-12-15 | OTH | BA | 306.94 |  | 2023-08-17 | 2023-09-26 | 2023-12-20 | 2023-08-17 |  |  |  | No
27INR0126 | Corvus Solar | SS Completed, FIS Completed, IA | Corvus Solar, LLC | Tap 345kV Cenzio (#80219) - Lobo (#80220) | Webb | SOUTH | 2028-11-12 | SOL | PV | 201.5 |  | 2024-01-16 | 2024-02-07 | 2024-04-30 | 2024-01-16 | 2026-08-31 | No | 2025-07-31 | Yes | Not Required | Not Required | Not Required | 2025-08-04
27INR0390 | Diamond Sage Solar 1 | SS Completed, FIS Started, No IA | DGC Renewables, LLC | tap 345kV 80219 LOBO7A - 5709 FOWLER TONSW5 CKT2 | Webb | SOUTH | 2028-10-01 | SOL | PV | 213.96 |  | 2024-01-28 | 2025-01-28 | 2025-04-15 | 2025-01-27 |  | Yes |  | No |  |  | Not Required
27INR0395 | Diamond Sage Solar 2 | SS Completed, FIS Started, No IA | DGC Renewables, LLC | Tap 345kV LOBO7A (80219) - FOWLERTONSW5 (5709) | Webb | SOUTH | 2028-10-01 | SOL | PV | 213.96 |  | 2025-01-24 | 2025-01-28 | 2025-04-21 | 2025-01-27 |  | Yes |  | No |  |  | Not Required
27INR0398 | Bravo BESS | SS Completed, FIS Started, No IA | Bravo BESS LLC | Tap 345kV 80220 CENIZO7A - 80224 TIEMPO7A | Webb | SOUTH | 2027-12-12 | OTH | BA | 207.38 |  | 2024-11-20 | 2024-11-26 | 2025-02-18 | 2024-11-21 |  | No |  | No
27INR0414 | Diamond Sage BESS 1 | SS Completed, FIS Started, No IA | DGC Renewables, LLC | tap 345kV 80219 LOBO7A - 5709 FOWLERTONSW5 CKT2 | Webb | SOUTH | 2028-10-01 | OTH | BA | 103.5 |  | 2024-01-28 | 2025-01-28 | 2025-04-15 | 2025-01-27 |  | Yes |  | No
27INR0444 | Diamond Sage BESS 2 | SS Completed, FIS Started, No IA | DGC Renewables, LLC | Tap 345kV LOBO7A (80219) - FOWLERTONSW5 (5709) | Webb | SOUTH | 2028-10-01 | OTH | BA | 103.5 |  | 2025-01-24 | 2025-01-28 | 2025-04-21 | 2025-01-27 |  | Yes |  | No
27INR0536 | Siete Wind | SS Completed, FIS Started, No IA | Siete Wind, LLC | 345kV 8718 Triada | Webb | SOUTH | 2028-01-03 | WIN | WT | 492.8 |  | 2025-06-12 | 2025-07-07 | 2025-09-25 | 2025-06-24 |  |  |  | No |  |  | Not Required
29INR0219 | Cenizo Solar | SS Completed, FIS Started, IA | Cenizo Energy Center LLC | Tap 345 kV 80220 Cenizo - 80079 Cruce Ckt 2 | Webb | SOUTH | 2029-12-31 | SOL | PV | 301.39 |  | 2025-11-20 | 2025-11-24 | 2025-12-19 | 2025-11-20 |  | No | 2026-09-28 | No |  |  | Not Required
20INR0069 | Danish Fields Solar | SS Completed, FIS Completed, IA | Danish Fields Solar, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2026-08-29 | SOL | PV | 602.8 |  | 2023-03-20 | 2018-04-12 | 2018-06-05 | 2018-08-21 | 2022-07-25 | No | 2020-02-24 | Yes | Not Required | Not Required | Not Required | 2022-07-28 | 2022-07-28 | 2022-07-28 |  |  | 2023-03-27 | 2023-05-04
20INR0238 | Voyager Storage | SS Completed, FIS Started, No IA | EDF Renewables Development, Inc. | 44200 Hillje 345kV | Wharton | SOUTH | 2028-04-08 | OTH | BA | 50.14 |  | 2019-04-30 | 2019-01-14 | 2019-03-19 | 2019-04-26 |  |  |  | No | Not Required | Not Required
21INR0220 | Maleza Solar | SS Completed, FIS Not Started, IA | Brush Solar LLC | tap Blue – Hillje 345 kv Ckt.#27 | Wharton | SOUTH | 2028-12-31 | SOL | PV | 254.94 |  | 2019-03-07 | 2018-12-06 | 2019-01-18 |  |  | No | 2021-01-13 | Yes |  |  | Not Required | 2022-12-08
21INR0341 | Space City Solar | SS Completed, FIS Started, IA | Apollo Solar Ranch, LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2027-06-01 | SOL | PV | 366 |  | 2019-10-28 | 2019-11-01 | 2020-03-06 | 2019-10-15 |  |  | 2025-12-11 | Yes | Not Required | Not Required | Not Required | 2021-01-11
21INR0456 | Maleza Storage | SS Completed, FIS Started, No IA | Brush Storage, LLC | tap Blue – Hillje 345 kv Ckt.#27 | Wharton | SOUTH | 2028-12-31 | OTH | BA | 150.83 |  | 2020-08-24 | 2019-10-31 | 2020-01-24 | 2020-08-18 |  |  |  | No
21INR0505 | Ramsey Storage | SS Completed, FIS Started, IA | Hecate Energy Ramsey Storage LLC | 44200 Hillje 345kV | Wharton | SOUTH | 2028-06-30 | OTH | BA | 500 |  | 2021-01-20 | 2020-05-20 | 2020-07-30 | 2020-12-23 |  | No | 2022-08-11 | Yes |  |  |  | 2023-08-18 | 2024-01-02
22INR0205 | Sbranch Solar | SS Completed, FIS Completed, IA | Bernard Creek Solar, LLC | Tap 138kV 44190 East Bernard - 44130 Caney | Wharton | SOUTH | 2026-10-31 | SOL | PV | 233.52 |  | 2019-04-01 | 2019-01-03 | 2019-03-13 | 2019-03-29 | 2021-07-29 | No | 2020-07-26 | Yes | Not Required | Not Required | Not Required | 2020-10-07 | 2021-07-06 | 2021-07-29 |  |  | 2022-09-12 | 2023-11-21
22INR0517 | Lane City Wind | SS Completed, FIS Completed, IA | RWE Clean Energy, LLC | 44040 Bailey 345kV | Wharton | SOUTH | 2026-12-31 | WIN | WT | 199.5 |  | 2021-05-05 | 2021-04-26 | 2021-07-28 | 2021-04-26 | 2024-07-18 | No | 2022-05-13 | Yes | Not Required | Not Required | Not Required | 2024-08-01 | 2024-08-01 | 2024-08-01 |  |  | 2025-06-12 | 2025-07-28
23INR0058 | Erin Solar | SS Completed, FIS Started, IA | Erin Solar LLC | 44040 Bailey 345 kV | Wharton | SOUTH | 2029-12-31 | SOL | PV | 208.34 |  | 2021-02-15 | 2020-07-24 | 2020-10-08 | 2021-01-26 |  | No | 2023-03-22 | No | Not Required | Not Required | Not Required
23INR0111 | PHOTON SOLAR 3 SLF | SS Completed, FIS Completed, IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2026-05-11 | SOL | PV | 109.99 |  | 2020-12-03 | 2020-10-23 | 2021-02-02 | 2020-11-24 | 2022-11-28 | No | 2021-10-01 | Yes | Not Required | Not Required | Not Required | 2021-11-05 | 2023-01-27 | 2023-01-27 |  |  | 2024-05-17 | 2024-10-02
23INR0137 | Diran BESS | SS Completed, FIS Completed, IA | BRP Diran BESS LLC | 43190 South Lane City 138kV | Wharton | SOUTH | 2028-01-31 | OTH | BA | 103 |  | 2020-11-30 | 2020-12-03 | 2021-02-18 | 2020-11-25 | 2025-10-03 | No | 2025-01-07 | Yes | Not Required | Not Required |  | 2025-07-21
23INR0227 | Maleza Solar II | SS Completed, FIS Started, No IA | Brush Solar, LLC | tap Blue – Hillje 345 kv Ckt.#27 | Wharton | SOUTH | 2028-12-31 | SOL | PV | 254.94 |  | 2021-05-24 | 2021-04-06 | 2021-06-24 | 2021-05-19 |  |  |  | No |  |  | Not Required
24INR0167 | OCI SunRoper | SS Completed, FIS Completed, IA | OCI SunRoper LLC | tap138kV #43190 South Lane City to #42985 Dyann CKT#60 | Wharton | SOUTH | 2027-10-01 | SOL | PV | 265.1 |  | 2021-11-18 | 2021-11-24 | 2022-02-19 | 2021-11-23 | 2026-04-17 | No | 2025-07-10 | Yes | Not Required | Not Required | Not Required | 2026-04-17
24INR0210 | Raven Storage | SS Completed, FIS Completed, IA | Raven Storage, LLC | Tap 138kV 44740 Wallis - 44190 East Bernard CKT#65 | Wharton | SOUTH | 2027-02-01 | OTH | BA | 103.53 |  | 2022-11-01 | 2022-01-28 | 2022-04-26 | 2022-10-18 | 2025-09-16 | No | 2024-06-04 | Yes | Not Required | Not Required |  | 2025-10-28 | 2025-10-29 | 2025-10-30
24INR0569 | Hadrian Energy Storage | SS Completed, FIS Completed, No IA | Hadrian Energy Storage, LLC | Line Tap 138kV #43012 NEWGLF60T3_8 - #43190 S_LANE_B138 | Wharton | SOUTH | 2028-12-31 | OTH | BA | 101.2 |  | 2023-11-07 | 2023-05-15 | 2023-08-11 | 2023-10-24 | 2025-02-12 |  |  | No
24INR0576 | Boling Generation (TEF-Due Diligience) | SS Completed, FIS Completed, No IA | Boling Generation | 43340 Gulftie 138kV | Wharton | SOUTH | 2028-12-16 | GAS | GT | 400 |  | 2023-10-11 | 2023-12-04 | 2024-03-01 | 2023-11-02 | 2025-08-20 | No |  | No
24INR0605 | TEXAS GULF SULPHUR REPOWER | SS Completed, FIS Completed, IA | Wharton County Generation, LLC | 43340 Gulftie 138 kV | Wharton | SOUTH | 2025-03-27 | GAS | GT | 16.1 |  | 2023-07-22 | 2023-07-31 | 2023-10-27 | 2023-07-27 | 2024-02-01 |  | 2022-03-01 | Yes | 2025-06-03 |  | 2024-01-30 | 2024-01-31 | 2024-01-31 | 2024-02-01 |  |  |  | 2025-02-17
25INR0293 | TOCE BESS 1 | SS Completed, FIS Completed, IA | TOCE BESS 1, LLC | 138 kV Danevang Switching Station (Bus# 5546) | Wharton | SOUTH | 2028-12-31 | OTH | BA | 205.2 | COD | 2023-10-02 | 2023-10-13 | 2024-01-10 | 2023-09-22 | 2024-11-07 |  | 2024-12-30 | No | Not Required | Not Required
25INR0319 | Northington Solar | SS Completed, FIS Started, IA | Northington Solar, LLC | The 138 kV El Campo (#8102) - Pulsar (#8192) Line; AEP. | Wharton | SOUTH | 2028-03-14 | SOL | PV | 125.9 |  | 2023-02-17 | 2023-02-20 | 2023-05-19 | 2023-02-02 |  | No | 2024-10-02 | Yes | Not Required |  | Not Required | 2025-02-12
25INR0493 | PHOTON SOLAR 1 2 SLF | SS Completed, FIS Completed, IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2026-05-11 | SOL | PV | 235.66 |  | 2024-08-28 | 2024-09-02 | 2021-02-02 | 2024-08-28 | 2022-11-28 |  | 2021-10-01 | Yes |  |  | Not Required | 2021-11-05 | 2021-11-05 | 2023-01-27 |  |  | 2024-10-15 | 2024-10-31
25INR0542 | Hynes Bay Energy Storage | SS Completed, FIS Started, No IA | Hynes Bay Energy Storage, LLC | Tap 138kV 5546 DANEVANG SW - 8121 BLESSING | Wharton | SOUTH | 2027-12-31 | OTH | BA | 101.2 |  | 2023-10-16 | 2023-10-25 | 2024-01-22 | 2023-10-16 |  |  |  | No | Not Required | Not Required
25INR0545 | Blue Creek Energy Storage | SS Completed, FIS Started, No IA | Blue Creek Energy Storage, LLC | Tap 138kV 42985 DYANN_POI8 - 43190 S_LANE_B138 Ckt 60 | Wharton | SOUTH | 2028-12-31 | OTH | BA | 101.2 |  | 2023-10-11 | 2023-10-13 | 2024-01-10 | 2023-10-11 |  | No |  | No | Not Required | Not Required
25INR0582 | Maleza Storage II | SS Completed, FIS Started, No IA | Brush Storage, LLC | 44220 Julia 345kV | Wharton | SOUTH | 2028-12-31 | OTH | BA | 256.1 |  | 2024-02-10 | 2024-02-27 | 2024-05-24 | 2024-02-20 |  | No |  | No
25INR0673 | PHOTON SOLAR 4 SLF | SS Completed, FIS Completed, No IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2026-05-11 | SOL | PV | 105.98 |  | 2024-08-28 | 2024-09-04 | 2021-02-02 | 2024-08-21 | 2022-11-28 |  |  | Yes | Not Required | Not Required | Not Required | 2021-11-05 | 2023-01-27 | 2023-01-27 |  |  | 2024-06-25 | 2024-11-04
26INR0144 | Wittig Solar | SS Completed, FIS Started, No IA | Greenalia Solar Power Wittig LLC | 138 kV Gulftie (#43340) – San Bernard (#43110) | Wharton | SOUTH | 2028-10-30 | SOL | PV | 106.9 |  | 2024-02-05 | 2024-02-27 | 2024-05-24 | 2024-01-18 |  | No |  | No | Not Required | Not Required | Not Required
26INR0474 | Sorghum BESS | SS Completed, FIS Completed, IA | Blue Creek BESS, LLC | #44060 Blue Substation 345kV | Wharton | SOUTH | 2027-12-01 | OTH | BA | 208.9 |  | 2024-04-18 | 2024-04-15 | 2024-07-05 | 2024-04-18 | 2024-11-13 | No | 2025-01-08 | No | Not Required | Not Required
26INR0718 | PHOTON SOLAR REPOWERING | SS Completed, FIS Completed, IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2027-08-17 | SOL | PV | 0 |  | 2025-09-30 | 2025-10-13 | 2025-12-23 | 2025-10-02 | 2026-09-23 | No | 2021-02-25 | No |  |  | Not Required
26INR0725 | PHOTON BESS REPOWERING | SS Completed, FIS Completed, No IA | GulfStar Power, LLC | 44880 Waterh_POI_5 345kV | Wharton | SOUTH | 2027-08-17 | OTH | BA | 305.48 |  | 2025-10-21 | 2025-11-05 | 2025-12-23 | 2025-10-07 | 2026-09-23 | No |  | No
27INR0102 | Cottonseed Energy Storage | SS Completed, FIS Completed, No IA | Cottonseed Energy Storage LLC | South Lane City and PSEE # is 43190 | Wharton | SOUTH | 2027-04-20 | OTH | BA | 207.6 |  | 2023-11-01 | 2023-11-14 | 2024-01-08 | 2023-11-02 | 2024-08-23 |  |  | No
27INR0111 | Malachite Solar | SS Completed, FIS Completed, IA | Malachite Solar LLC | The 345 kV Hillje (#44200) – Holman (#9073) Line; AEN. | Wharton | SOUTH | 2032-04-30 | SOL | PV | 184.55 |  | 2024-01-31 | 2024-02-27 | 2024-05-22 | 2024-01-25 | 2025-11-04 | Yes | 2025-12-26 | No |  |  | Not Required
27INR0112 | Malachite BESS | SS Completed, FIS Completed, IA | Malachite Storage LLC | Tap 345 kV 44200 Hillje – 9073 Holman | Wharton | SOUTH | 2032-04-30 | OTH | BA | 191.12 |  | 2024-05-15 | 2024-05-20 | 2024-07-22 | 2024-05-15 | 2025-11-04 | Yes | 2025-12-26 | No
27INR0392 | Cernan BESS | SS Completed, FIS Completed, IA | Cernan BESS LLC | Hillje 345kV (#44200) | Wharton | SOUTH | 2028-10-02 | OTH | BA | 10.04 | COD | 2024-12-23 | 2025-02-14 | 2025-04-22 | 2025-01-30 | 2025-10-31 | No | 2025-12-30 | No
28INR0030 | Brela BESS LLC | SS Completed, FIS Started, No IA | Brela BESS LLC | 44040 Bailey SW 345 kV | Wharton | SOUTH | 2028-05-29 | OTH | BA | 251.3 |  | 2024-06-26 | 2024-01-11 | 2024-04-08 | 2024-06-13 08:58 |  |  |  | No
28INR0068 | Alpujarra Solar | SS Completed, FIS Started, No IA | Greening USA Corp. | 5521 GALOW 138 KV | Wharton | SOUTH | 2028-05-01 | SOL | PV | 112.5 |  | 2024-08-23 | 2024-09-04 | 2024-11-27 | 2024-08-12 |  |  |  | No |  |  | Not Required
28INR0090 | EmberGreen | SS Completed, FIS Completed, IA | EmberGreen Energy Center | Tap 138kV 48050 Caney - 44150 Hungerford | Wharton | SOUTH | 2028-01-01 | GAS | GT | 1036 |  | 2024-06-28 | 2024-06-13 | 2024-09-10 | 2024-12-18 | 2026-04-21 | Yes | 2026-08-04 | No
28INR0160 | Neal Solar | SS Completed, FIS Started, No IA | CH Neal Solar LLC | tap of 138kV 8750 Chalmers - 8127 Lane City | Wharton | SOUTH | 2029-04-03 | SOL | PV | 146.6 |  | 2025-05-14 | 2025-05-27 | 2025-08-23 | 2025-05-14 |  |  |  | No |  |  | Not Required
28INR0452 | Neal Battery | SS Completed, FIS Started, No IA | CH Neal Battery LLC | tap of 138kV 8750 Chalmers - 8127 Lane City | Wharton | SOUTH | 2029-04-03 | OTH | BA | 120.52 |  | 2025-10-10 | 2025-10-21 | 2026-01-06 | 2025-10-14 |  |  |  | No
29INR0082 | Peach Creek Solar | SS Completed, FIS Started, No IA | AEUG Peach Creek Solar LLC | 44040 Bailey 345 kV | Wharton | SOUTH | 2029-09-30 | SOL | PV | 300 |  | 2025-12-10 | 2024-12-19 | 2025-04-08 | 2025-12-05 |  |  |  | No |  |  | Not Required
29INR0197 | Zora Solar | SS Completed, FIS Started, No IA | Zora Solar, LLC | 46650 Athena 138 kV | Wharton | SOUTH | 2029-10-15 | SOL | PV | 250.8 |  | 2026-04-27 | 2026-05-13 | 2026-08-10 | 2026-05-12 |  |  |  | No |  |  | Not Required
30INR0133 | Starfield Energy Storage | SS Started, FIS Started, No IA | Starfield Energy Storage, LLC | Tap 138kV 44150 Hungerford - 44190 East Bernard | Wharton | SOUTH | 2030-12-31 | OTH | BA | 122.2 |  | 2026-09-01 | 2026-09-04 |  | 2026-08-19 |  |  |  | No
30INR0077 | Moon Hammer | SS Completed, FIS Started, IA | Moon Hammer LLC | tap 345 kV line between Tesla & Grey | Wheeler | PANHANDLE | 2030-11-30 | GAS | GT | 1300 |  | 2025-12-29 | 2026-01-13 | 2026-02-17 | 2025-12-10 |  |  | 2025-12-19 | No
24INR0201 | Short Creek Solar | SS Completed, FIS Completed, IA | Wichita Solar I, LLC | Tap 345kV 6101 Riley - 1425 Fisher Road Switch Ckt 1 | Wichita | WEST | 2027-12-17 | SOL | PV | 627.81 |  | 2022-10-17 | 2022-01-20 | 2022-04-18 | 2022-10-12 | 2026-09-09 | No | 2024-10-02 | Yes | Not Required |  | Not Required | 2025-02-12
25INR0154 | Nymphaea Solar | SS Completed, FIS Started, IA | Nymphaea Solar, LLC | Tap 345kV 1730 Krum West Swtich - 6111 Riley7B | Wichita | WEST | 2028-07-01 | SOL | PV | 120.9 |  | 2023-01-06 | 2022-09-21 | 2022-12-19 | 2022-12-23 |  | No | 2026-05-18 | Yes | Not Required |  | Not Required | 2026-06-04
25INR0155 | Nymphaea Storage | SS Completed, FIS Started, IA | Nymphaea Solar, LLC | Tap 345kV 1730 Krum West Swtich - 6111 Riley7B | Wichita | WEST | 2028-07-01 | OTH | BA | 61 |  | 2023-01-13 | 2022-09-21 | 2022-12-19 | 2022-12-23 |  | No | 2026-05-18 | Yes | Not Required |  |  | 2026-06-04
26INR0280 | Pethrus BESS | SS Completed, FIS Completed, No IA | Pethrus BESS, LLC | Tap Wichita Falls Switch (#1464) – North Star (#1467) 138 kV Line | Wichita | WEST | 2029-03-03 | OTH | BA | 174.08 |  | 2023-09-15 | 2023-09-23 | 2023-12-20 | 2023-08-30 | 2025-03-18 | No |  | No | Not Required | Not Required
26INR0472 | Bologna BESS | SS Completed, FIS Completed, No IA | MALONEY BESS LLC | Tap 138kV #1450 Pleasant Valley Switch - #1492 Wichita Falls Riverbend | Wichita | WEST | 2028-04-19 | OTH | BA | 202.56 |  | 2024-03-26 | 2024-03-29 | 2024-06-25 | 2024-03-20 | 2025-03-25 | No |  | No
26INR0613 | Wichita County Mawson Storage | SS Completed, FIS Started, No IA | DM-WCM, LLC | Tap 345kV Fisher Road Switch (#1425) – Riley (#6101) Line | Wichita | WEST | 2029-04-16 | OTH | BA | 153.62 |  | 2024-12-13 | 2024-12-19 | 2025-02-20 | 2024-12-13 |  |  |  | No
27INR0029 | Short Creek BESS | SS Completed, FIS Started, No IA | Wichita Solar I, LLC | Tap 345kV 6101 Riley - 1425 Fisher Road Switch Ckt 1 | Wichita | WEST | 2028-07-01 | OTH | BA | 155.66 |  | 2023-04-12 | 2023-04-19 | 2023-07-14 | 2023-04-12 |  |  |  | Yes | Not Required | Not Required |  | 2026-05-07
27INR0412 | Spinosa BESS | SS Completed, FIS Started, No IA | Spinosa Energy Center, LLC | Tap 138 kV Wichita Falls Cogen (#1498) – Pleasant Valley Switch (#1450) | Wichita | WEST | 2030-05-08 | OTH | BA | 201.2 |  | 2025-04-28 | 2025-04-29 | 2025-07-23 | 2025-04-29 |  |  |  | No
28INR0118 | Copperleaf Energy Storage | SS Completed, FIS Started, No IA | Copperleaf Energy Storage, LLC | Tap 345kV Fisher Road Switch (#1425) – Riley (#6101) | Wichita | WEST | 2029-09-25 | OTH | BA | 305.63 | COD | 2024-11-04 | 2024-11-19 | 2025-02-18 | 2024-10-16 |  |  |  | No
28INR0221 | Rio Star Energy Storage | SS Completed, FIS Started, No IA | Rio Star Energy Storage, LLC | Tap 1464 Wichita Falls South Switch – 1474 Scotland 138 kV | Wichita | WEST | 2029-04-20 | OTH | BA | 142.58 |  | 2025-02-03 | 2025-02-14 | 2025-05-12 | 2025-02-04 |  | No |  | No
28INR0377 | Wichita Creek Solar | SS Completed, FIS Started, No IA | Wichita Solar II, LLC | Tap 345 kV 6111 RILEY - 1730 KRUM WEST Ckt 1 | Wichita | WEST | 2030-04-15 | SOL | PV | 3.43 | COD | 2026-06-12 | 2026-06-17 | 2026-09-14 | 2026-06-12 |  | No |  | No |  |  | Not Required
28INR0378 | Wichita Creek Storage | SS Completed, FIS Started, No IA | Wichita Solar II, LLC | Tap 345 kV 6111 RILEY - 1730 KRUM WEST Ckt 1 | Wichita | WEST | 2030-04-15 | OTH | BA | 300 | COD | 2026-08-14 | 2026-08-21 | 2026-09-14 | 2026-08-13 |  | No |  | No
21INR0210 | Adamstown Solar | SS Completed, FIS Completed, IA | Adams Creek Solar Project, LLC | tap 345kV 1730 West Krum - 6111 Riley Ckt 2 | Wilbarger | WEST | 2027-08-31 | SOL | PV | 250.88 |  | 2019-05-22 | 2018-11-20 | 2019-02-04 | 2019-05-16 | 2026-02-25 | No | 2024-12-04 | Yes |  |  | Not Required | 2025-12-19 | 2026-07-17 | 2026-07-17
22INR0209 | Felix North Solar | SS Completed, FIS Started, IA | Crescent Solar, LLC | 6101 Riley 345kV | Wilbarger | WEST | 2028-12-31 | SOL | PV | 200.98 |  | 2019-09-23 | 2019-01-17 | 2019-04-02 | 2019-09-20 |  | Yes | 2025-02-21 | Yes | Not Required | Not Required | Not Required | 2025-04-03
22INR0497 | TEXPO | SS Completed, FIS Started, No IA | Oklaunion Power Station, LLC | 6101 Riley 345 kV | Wilbarger | WEST | 2027-10-31 | GAS | ST | 680 |  | 2021-11-30 | 2021-03-16 | 2021-05-28 | 2021-11-23 |  | No |  | No | Not Required | Not Required | 2022-05-02
23INR0273 | Poco Trail Solar | SS Completed, FIS Started, No IA | Eastern Trail Solar Center, LLC | Tap 345kV 6101 Riley - 1422 Bowman Byrd Road Switch | Wilbarger | WEST | 2029-04-02 | SOL | PV | 438.75 |  | 2021-06-02 | 2021-09-14 | 2021-11-30 | 2021-07-12 |  | No |  | No | Not Required | Not Required | Not Required
25INR0377 | Proteus Vernon Solar SLF | SS Completed, FIS Started, No IA | Vernon Solar and Storage LLC (a Delaware LLC) | 6060 Vernon 138kV | Wilbarger | WEST | 2029-02-18 | SOL | PV | 75 |  | 2023-07-17 | 2023-03-27 | 2023-06-19 | 2023-07-03 |  |  |  | No |  |  | Not Required
25INR0416 | Proteus Vernon Storage SLF | SS Completed, FIS Started, No IA | Vernon Solar and Storage LLC (a Delaware LLC) | 6060 Vernon 138kV | Wilbarger | WEST | 2029-02-18 | OTH | BA | 0 |  | 2023-07-13 | 2023-03-27 | 2023-06-19 | 2023-07-03 |  |  |  | No
25INR0492 | Blue Summit Energy Storage | SS Completed, FIS Completed, IA | NextEra Energy Interconnection Holdings, LLC | 61001 JIM TREECE 345kV | Wilbarger | WEST | 2026-07-31 | OTH | BA | 100 |  | 2023-08-28 | 2023-10-20 | 2024-01-16 | 2023-10-18 | 2025-05-08 | No | 2012-02-22 | Yes | Not Required | Not Required | 2023-10-26 | 2025-02-13 | 2025-07-28 | 2025-07-28 |  |  | 2025-12-17 | 2026-02-03
27INR0004 | Dundee West Wind | SS Completed, FIS Started, IA | Felix 2, LLC | 345 kV Riley Substation (#6101); AEP | Wilbarger | WEST | 2027-12-31 | WIN | WT | 146.49 |  | 2022-12-28 | 2023-01-03 | 2023-03-30 | 2022-12-28 |  | Yes | 2025-02-21 | Yes | Not Required |  | Not Required | 2025-04-03
27INR0007 | Felix East Solar | SS Completed, FIS Started, IA | Felix 1, LLC | The 345 kV Riley Substation (#6101); AEP | Wilbarger | WEST | 2028-12-31 | SOL | PV | 200.92 |  | 2022-12-28 | 2023-01-03 | 2023-03-30 | 2022-12-22 |  | Yes | 2025-02-21 | Yes | Not Required |  | Not Required | 2025-04-03
27INR0009 | Felix Storage | SS Completed, FIS Started, No IA | Felix 1, LLC | The 345 kV Riley Substation (#6101); AEP | Wilbarger | WEST | 2027-07-31 | OTH | BA | 100.54 |  | 2022-12-28 | 2023-01-03 | 2023-03-30 | 2022-12-22 |  | No |  | No
27INR0012 | Felix West Solar | SS Completed, FIS Started, IA | Felix 1, LLC | 6101 Riley 345 kV | Wilbarger | WEST | 2028-12-31 | SOL | PV | 200.95 |  | 2023-01-06 | 2023-01-17 | 2023-04-14 | 2023-01-03 |  | Yes | 2025-02-21 | Yes | Not Required |  | Not Required | 2025-04-03
27INR0207 | Wander Waters BESS | SS Completed, FIS Completed, No IA | Wander Waters BESS LLC | 61001 JIMTREEC7A 345kV | Wilbarger | WEST | 2027-10-31 | OTH | BA | 303.5 |  | 2024-03-11 | 2024-03-22 | 2024-06-19 | 2024-03-12 | 2025-11-14 |  |  | No
27INR0332 | White Wing Solar | SS Completed, FIS Started, No IA | White Wing Solar, LLC | Tap 345 kV (#60504) Tesla - (#6111) Riley | Wilbarger | WEST | 2028-07-01 | SOL | PV | 127.4 |  | 2025-07-24 | 2025-08-13 | 2025-10-13 | 2025-08-01 |  | Yes |  | No | Not Required | Not Required | Not Required
27INR0333 | White Wing Storage | SS Completed, FIS Started, No IA | White Wing Solar, LLC | Tap 345 kV (#60504) Tesla - (#6111) Riley | Wilbarger | WEST | 2028-07-01 | OTH | BA | 130.4 |  | 2025-07-24 | 2025-08-13 | 2025-10-13 | 2025-08-01 |  |  |  | No | Not Required | Not Required | 2026-01-12
27INR0581 | Limitless Energy Hub I | SS Completed, FIS Started, IA | Limitless Energy Hub I LLC | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B. | Wilbarger | WEST | 2028-12-01 | GAS | CC | 1238.25 |  | 2025-11-04 | 2025-11-05 | 2026-01-12 | 2025-10-31 |  |  | 2025-12-31 | No
27INR0582 | Limitless Energy Hub II | SS Completed, FIS Started, IA | Limitless Energy Hub II LLC | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B. | Wilbarger | WEST | 2028-12-01 | GAS | CC | 1238.25 |  | 2025-11-04 | 2025-11-05 | 2026-01-12 | 2025-10-31 |  |  | 2025-12-31 | Yes
28INR0332 | Reunion Solar | SS Completed, FIS Started, No IA | Reunion Solar, LLC | Tap 345kV #60504 Tesla Road to #6111 Riley | Wilbarger | WEST | 2028-07-01 | SOL | PV | 600.9 |  | 2025-10-06 | 2025-03-24 | 2025-06-19 | 2025-09-11 |  |  |  | No |  |  | Not Required
28INR0333 | Reunion Storage | SS Completed, FIS Started, No IA | Reunion Solar, LLC | Tap 345kV #60504 Tesla Road to #6111 Riley | Wilbarger | WEST | 2028-07-01 | OTH | BA | 200.3 |  | 2025-10-06 | 2025-03-24 | 2025-06-19 | 2025-09-11 |  |  |  | No
28INR0464 | Grayback Solar | SS Completed, FIS Started, No IA | Grayback Solar, LLC | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B | Wilbarger | WEST | 2029-09-01 | SOL | PV | 221.81 |  | 2025-10-31 | 2025-11-05 | 2026-01-12 | 2025-10-14 |  | No |  | No |  |  | Not Required
32INR0006 | H&C WILBARGER POWER I | SS Started, FIS Started, No IA | H&C WILBARGER POWER I | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B | Wilbarger | WEST | 2032-02-27 | GAS | CC | 1025.55 |  | 2026-08-06 | 2026-08-11 |  | 2026-08-06 |  |  |  | No
32INR0008 | H&C WILBARGER POWER II | SS Started, FIS Started, No IA | H&C WILBARGER POWER I | Tap 345kV 6101 RILEY7A - 60505 EDITHCLA7B | Wilbarger | WEST | 2032-02-27 | GAS | CC | 1025.55 |  | 2026-08-06 | 2026-08-11 |  | 2026-08-07 |  |  |  | No
19INR0023 | Monte Alto 2 Wind | SS Completed, FIS Started, IA | Monte Alto Windpower, LLC | tap 345kV 8318 Rio Hondo - 8383 N Edinburg | Willacy | COASTAL | 2028-12-31 | WIN | WT | 199.2 |  |  | 2016-11-04 | 2017-01-10 | 2017-03-23 |  | No | 2022-03-22 | Yes | Not Required | Not Required | Not Required | 2025-02-12
20INR0097 | El Sauz Ranch | SS Completed, FIS Completed, IA | El Sauz Ranch Wind, LLC | 8663 EL SAUZ POI 345kV | Willacy | COASTAL | 2026-12-01 | WIN | WT | 301.5 | COD | 2019-02-01 | 2018-06-19 | 2018-08-22 | 2019-01-31 | 2021-10-29 |  | 2021-01-27 | Yes | Not Required | Not Required | Not Required | 2021-10-14 | 2022-01-26 | 2022-01-26 |  |  | 2022-09-28 | 2023-02-28
24INR0534 | Lyford Energy | SS Completed, FIS Started, No IA | Lyford Energy, LLC | 5745 E Raymondville 138kV | Willacy | COASTAL | 2027-09-02 | OTH | BA | 101.2 |  | 2023-11-07 | 2023-03-08 | 2023-06-05 | 2023-10-24 |  |  |  | No
26INR0507 | Los Vientos IB Repower | SS Completed, FIS Started, No IA | Los Vientos Windpower IB, LLC | #8319 RIOHONDO 138 kV | Willacy | COASTAL | 2029-03-01 | WIN | WT | 184.8 |  | 2024-07-17 | 2024-07-22 | 2024-10-07 | 2024-07-12 |  |  |  | No |  |  | Not Required
27INR0606 | Big Watt Mustang Power | SS Completed, FIS Started, No IA | Big Watt Power Mustang LLC | Tapping the 138 kV line from Taylor (Bus#3658) to Thorndale North (Bus#3659) | Williamson | SOUTH | 2028-12-15 | GAS | CC | 448.98 | COD | 2026-03-13 | 2026-03-16 | 2026-06-05 | 2026-03-02 |  |  |  | No
23INR0027 | Clear Fork Creek Solar | SS Completed, FIS Completed, IA | Clear Fork Creek Solar LLC | Tap 345KV 5133 Elm Creek - 5323 Old Hickory | Wilson | SOUTH | 2027-04-29 | SOL | PV | 602.02 |  | 2020-08-19 | 2020-05-01 | 2020-07-13 | 2020-08-17 | 2026-06-17 | No | 2021-11-23 | Yes | Not Required | Not Required | Not Required | 2021-11-29 | 2026-07-28 | 2026-07-28
23INR0077 | Cachena Storage SLF | SS Completed, FIS Started, No IA | Clear Fork Creek Solar LLC | Tap 345KV 5133 Elmcreek - 5323 Old Hickory | Wilson | SOUTH | 2027-04-29 | OTH | BA | 0 |  | 2020-08-21 | 2020-08-21 | 2020-10-16 | 2020-08-17 |  |  |  | No | Not Required | Not Required
23INR0318 | Marcelina Storage | SS Completed, FIS Completed, No IA | Marcelina Solar, LLC | Tap 345 kV 5133 Elm Creek - 5901 San Miguel | Wilson | SOUTH | 2026-12-18 | OTH | BA | 203.21 |  | 2022-05-03 | 2021-08-09 | 2021-10-29 | 2022-04-22 | 2024-01-23 |  |  | No
24INR0156 | Moonstone Solar Project | SS Completed, FIS Completed, IA | Moon Stone Solar Farm, LLC | Tap 138kV Eagle Creek (5132) to Floresville (5155) | Wilson | SOUTH | 2029-03-31 | SOL | PV | 174.97 |  | 2022-06-20 | 2021-10-27 | 2022-01-24 | 2022-06-07 | 2024-01-18 |  | 2025-02-17 | No |  |  | Not Required
24INR0160 | Huisache Solar | SS Completed, FIS Started, IA | Huisache Solar, LLC | Tapping the Elm Creek to Shaula circuit 1 | Wilson | SOUTH | 2029-06-30 | SOL | PV | 125.59 | SFS/NtP | 2022-07-11 | 2021-12-03 | 2022-03-01 | 2022-06-22 |  |  | 2025-08-12 | Yes | Not Required | Not Required | Not Required | 2026-09-09
24INR0376 | Huisache BESS | SS Completed, FIS Started, IA | Huisache Solar, LLC | Tapping the Elm Creek to Shaula circuit 1 | Wilson | SOUTH | 2029-06-30 | OTH | BA | 100.67 | SFS/NtP | 2023-01-11 | 2022-08-05 | 2022-11-01 | 2022-11-07 |  |  | 2025-08-12 | Yes |  |  |  | 2026-09-10
25INR0248 | Strawberry Acres Storage | SS Completed, FIS Completed, No IA | Strawberry Acres Energy Center, LLC | 5132 Eagle Creek Substation 138kV | Wilson | SOUTH | 2028-09-30 | OTH | BA | 156.73 |  | 2022-11-11 | 2022-11-23 | 2023-02-17 | 2022-11-15 | 2025-10-27 | No |  | No
26INR0074 | Anila Solar | SS Completed, FIS Completed, IA | Alina Energy LLC | Tap 345kV 5133 Elm Creek - 5901 San Miguel Gen Ckt 1 | Wilson | SOUTH | 2028-09-30 | SOL | PV | 200.8 |  | 2023-01-23 | 2023-01-30 | 2023-04-28 | 2023-01-20 | 2024-07-10 |  | 2025-03-06 | Yes | Not Required | Not Required | Not Required | 2026-03-04
26INR0077 | Anila BESS | SS Completed, FIS Completed, IA | Alina Energy LLC | Tap of 345 kV Elm Creek (Bus# 5133) - San Miguel Gen (Bus# 5901) Transmission Line Ckt 1 | Wilson | SOUTH | 2028-09-30 | OTH | BA | 209 |  | 2023-06-01 | 2023-02-20 | 2023-05-20 | 2023-05-25 | 2024-07-10 |  | 2025-03-06 | Yes | Not Required | Not Required |  | 2026-03-04
28INR0250 | Mojo Solar | SS Completed, FIS Started, No IA | Power Synergy | Tap 345 kV 5133 Elm Creek - 5901 San Miguel CKT 1 & 2 | Wilson | SOUTH | 2028-06-30 | SOL | PV | 527.94 |  | 2025-02-26 | 2025-03-03 | 2025-05-19 | 2025-02-12 |  |  |  | No |  |  | Not Required
28INR0299 | Moon Stone BESS | SS Completed, FIS Started, No IA | Moon Stone Battery Facility LLC | Tap 138kV Eagle Creek (5132) to Floresville (5155) | Wilson | SOUTH | 2029-03-31 | OTH | BA | 200.8 |  | 2026-01-12 | 2025-02-14 | 2025-05-14 |  |  |  |  | No
28INR0494 | Wilson Gas Plant | SS Completed, FIS Started, No IA | Misae Gas Power | Tap 345 kV 5133 ELMCREEK - 5901 MIGUEL5 CKT 1 Tap 345 kV 5133 ELMCREEK - 5901 MIGUEL5 CKT 2 | Wilson | SOUTH | 2028-06-30 | GAS | IC | 402.88 |  | 2026-02-23 | 2026-03-10 | 2026-06-04 | 2026-03-24 |  |  |  | No
29INR0318 | Nockenut Springs Storage 1 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | Tap the 345 kV Elm Creek (#5133) - Shaula (#5380) Line, CPS | Wilson | SOUTH | 2029-06-05 | OTH | BA | 209.36 |  | 2026-03-31 | 2026-04-22 | 2026-07-08 | 2026-04-01 |  |  |  | No
29INR0319 | Nockenut Springs Storage 2 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | Tap the 345 kV Elm Creek (#5133) - Shaula (#5380) Line, CPS | Wilson | SOUTH | 2029-06-05 | OTH | BA | 209.38 |  | 2026-03-31 | 2026-04-22 | 2026-07-08 | 2026-04-01 |  |  |  | No
29INR0320 | Nockenut Springs Storage 3 | SS Completed, FIS Started, No IA | Pecan Springs Energy, LLC | Tap the 345 kV Elm Creek (#5133) - Shaula (#5380) Line, CPS | Wilson | SOUTH | 2029-06-05 | OTH | BA | 209.38 |  | 2026-03-31 | 2026-04-22 | 2026-07-08 | 2026-04-01 |  |  |  | No
23INR0071 | BRP Volans BESS | SS Completed, FIS Started, No IA | BRP Volans BESS LLC | 11189 Quarry Field SW - 1074 Wink 138kV | Winkler | WEST | 2027-12-01 | OTH | BA | 206.88 |  | 2020-08-26 | 2020-08-04 | 2020-10-28 | 2020-08-24 |  | No |  | No
30INR0128 | Horizon Ridge Wind | SS Started, FIS Started, No IA | CPV Horizon Ridge Wind, LLC | POIB is 131853 NOTSW_1_8 - the Notrees SW Substation - Project includes property in Ector, Andrews, and Winkler counties. | Winkler | WEST | 2030-04-23 | WIN | WT | 406.55 | FIS Request |  | 2026-09-10 |  | 2026-09-03 |  |  |  | No |  |  | Not Required
20INR0286 | Wise County Power Repower (CT1, CT2) | SS Completed, FIS Completed, IA | Wise County Power Company LLC | 1421 Willow Creek 345kV | Wise | NORTH | 2026-12-19 | GAS | CC | 21 |  | 2019-07-15 | 2019-07-25 | 2019-10-23 | 2019-07-16 | 2019-10-23 | No | 2001-03-19 | Yes | 2020-01-21 | Not Required | 2019-12-05 | 2020-01-22 | 2020-01-27 | 2020-01-27
25INR0184 | Legato BESS | SS Completed, FIS Completed, No IA | Legato Storage, LLC | 138kV #608 Crafton Substation - #620 Bowie Substation | Wise | NORTH | 2028-04-24 | OTH | BA | 202.65 |  | 2023-01-20 | 2022-09-27 | 2022-12-21 | 2023-02-09 01:23 | 2024-09-12 | No |  | No
25INR0466 | Yooperlite Storage | SS Completed, FIS Completed, No IA | BT Yooperlite Storage, LLC | Tap 138 kV 580 Westbrook Switch - 588 Willow | Wise | NORTH | 2028-05-31 | OTH | BA | 175.65 |  | 2023-06-13 | 2023-06-28 | 2023-09-20 | 2023-06-06 | 2025-05-19 | No |  | No
25INR0656 | Gilleys Energy Storage | SS Completed, FIS Completed, No IA | Gilleys Energy Storage, LLC | Tap 345 kV 1730 West Krum - 6111 Riley CKT 2 | Wise | NORTH | 2028-04-21 | OTH | BA | 306.4 |  | 2024-05-03 | 2024-06-03 | 2024-08-27 | 2024-05-06 | 2026-01-05 | No |  | No
26INR0318 | Sandford Solar | SS Completed, FIS Started, No IA | BT Sandford Solar, LLC | Tap 345kV Bird Dog (Bus #11736) - Jacksboro (Bus #1429) | Wise | NORTH | 2029-01-30 | SOL | PV | 126.18 |  | 2023-12-20 | 2024-01-03 | 2024-03-29 | 2023-12-12 |  | No |  | No | Not Required | Not Required | Not Required
26INR0319 | Sandford Storage | SS Completed, FIS Started, No IA | BT Sandford Solar, LLC | Tap 345kV Bird Dog (Bus #11736) - Jacksboro (Bus #1429) | Wise | NORTH | 2029-01-30 | OTH | BA | 100.93 |  | 2023-12-18 | 2024-01-03 | 2024-03-29 | 2023-12-12 |  | No |  | No | Not Required | Not Required
26INR0329 | Pianissimo BESS II | SS Completed, FIS Started, No IA | Pianissimo Storage, LLC | Tap 138kV 685 LEO - 587 GREENWOOD | Wise | NORTH | 2027-12-31 | OTH | BA | 202 |  | 2024-10-07 | 2024-11-19 | 2025-02-18 | 2024-10-29 |  |  |  | No
27INR0040 | Solar Star Rhome Storage | SS Completed, FIS Completed, No IA | Solar Star Rhome Storage | 576 RHOME 138kV | Wise | NORTH | 2029-09-27 | OTH | BA | 226.24 |  | 2023-08-17 | 2023-04-19 | 2023-07-12 | 2023-08-04 | 2025-07-21 |  |  | No
27INR0618 | Prairie Point Energy Storage I | SS Completed, FIS Started, No IA | Prairie Point LLC | RAMHORNH 5 - 31875 | Wise | NORTH | 2027-12-31 | OTH | BA | 1000 |  | 2026-05-13 | 2026-05-13 | 2026-08-07 | 2026-04-30 |  |  |  | No
27INR0619 | Prairie Point Energy Storage II | SS Completed, FIS Started, No IA | Prairie Point LLC | RAMHORNH 5 - 31875 | Wise | NORTH | 2027-12-31 | OTH | BA | 1000 |  | 2026-05-13 | 2026-05-13 | 2026-08-07 | 2026-04-30 |  |  |  | No
28INR0278 | Spur Energy Storage | SS Completed, FIS Started, No IA | Spur Energy Storage, LLC | Tap 345kV (1429) JACKSBRO_5 - (11736) BIRDDOG_5 | Wise | NORTH | 2029-09-15 | OTH | BA | 612.62 |  | 2025-01-28 | 2025-02-25 | 2025-05-20 | 2025-01-30 |  |  |  | No
20INR0019 | Trinity Hills Wind repower | SS Completed, FIS Completed, IA | Trinity Hills Wind Farm LLC | 17002 Garvey Rd 345kV | Young | WEST | 2026-12-31 | WIN | WT | -27 | COD | 2017-09-21 | 2017-07-20 | 2017-09-08 | 2017-09-21 | 2018-08-02 | No | 2018-10-17 | No | Not Required | Not Required | Not Required | 2019-10-29 | 2019-10-29 | 2019-10-29 |  |  |  | 2020-05-22
25INR0306 | Red Top Solar I | SS Completed, FIS Completed, No IA | Cat Red Top Solar, LLC | Tap 138kV 1431 Graham SES - Short Grass 11525 | Young | WEST | 2029-04-20 | SOL | PV | 200.59 |  | 2023-10-24 | 2023-01-17 | 2023-04-14 | 2023-10-12 | 2026-01-07 |  |  | No | Not Required | Not Required | Not Required
26INR0302 | Young County Energy Storage | SS Completed, FIS Completed, No IA | Young County Energy Storage LLC | TAP 138 KV BUS AND CREAT NEW BUS BETWEEN MURRAY (792) AND GRAHAM SES (1431) COUNTY : YOUNG | Young | WEST | 2028-08-01 | OTH | BA | 104.5 |  | 2024-01-02 | 2024-02-27 | 2024-05-20 | 2024-02-12 | 2026-07-13 |  |  | No | Not Required | Not Required
29INR0084 | Jolly Rock Storage Center | SS Completed, FIS Started, No IA | Jolly Rock Storage Center LLC | Tap 138kV 1431 GRAHAM Plant Switch - 11525 Short Grass Circuit 1. | Young | WEST | 2029-05-16 | OTH | BA | 208.57 |  | 2025-04-29 | 2024-12-19 | 2025-03-18 | 2025-04-23 |  |  |  | No
29INR0171 | Sweetheart Solar | SS Completed, FIS Started, No IA | Sweetheart Energy, LLC | Tap 345kV #1430 GRAHAM SES - # 17002 GARVEY ROAD SWITCH | Young | WEST | 2029-12-01 | SOL | PV | 301.14 |  | 2025-08-25 | 2025-08-26 | 2025-11-18 | 2025-08-11 |  |  |  | No |  |  | Not Required
29INR0172 | Sweetheart BESS | SS Completed, FIS Started, No IA | Sweetheart Energy, LLC | Tap 345kV #1430 GRAHAM SES - # 17002 GARVEY ROAD SWITCH | Young | WEST | 2029-12-01 | OTH | BA | 310.16 |  | 2025-08-25 | 2025-08-26 | 2025-11-18 | 2025-08-11 |  |  |  | No
29INR0203 | Miller Bend Energy Solar | SS Completed, FIS Started, No IA | Miller Bend Energy, LLC | Tap 345kV (Bus1#1430) Graham SES to (Bus2#11050) Dusty Road | Young | WEST | 2029-12-01 | SOL | PV | 531.84 |  | 2025-12-08 | 2025-12-17 | 2026-02-04 | 2025-11-25 |  | No |  | No |  |  | Not Required
29INR0204 | Miller Bend Energy BESS | SS Completed, FIS Started, No IA | Miller Bend Energy , LLC | Tap 345kV (Bus1#1430) Graham SES to (Bus2#11050) Dusty Road | Young | WEST | 2029-12-01 | OTH | BA | 547.65 |  | 2025-12-08 | 2025-12-17 | 2026-02-05 | 2025-11-25 |  | No |  | No
17INR0043 | Vaquero 1 Wind | SS Completed, FIS Started, No IA | Enerverse | tap 345kV 8905 N Edinb - 8455 Lon Hill | Zapata | SOUTH | 2027-01-15 | WIN | WT | 400 |  | 2016-04-01 | 2016-04-01 | 2016-05-10 | 2016-04-01 |  |  |  | No | Not Required | Not Required | Not Required
23INR0006 | Sierra Madre Solar | SS Completed, FIS Started, No IA | Sierra Madre Solar LLC | tap 345kV 80307 Del Sol - 80225 Cenizo | Zapata | SOUTH | 2027-12-01 | SOL | PV | 255.15 |  | 2020-10-07 | 2020-01-22 | 2020-04-08 | 2020-10-05 |  | No |  | No |  |  | Not Required
23INR0215 | Big River Solar | SS Completed, FIS Started, No IA | Rio Grande River Solar LLC | tap 138kV 8299 Zapata - 8957 Lopeno4A | Zapata | SOUTH | 2028-12-31 | SOL | PV | 104.35 |  | 2021-04-09 | 2021-05-04 | 2021-07-27 | 2021-04-15 |  |  |  | No |  |  | Not Required
23INR0237 | Big River BESS | SS Completed, FIS Started, No IA | Rio Grande River Solar LLC | tap 138kV 8299 Zapata - 8957 Lopeno4A | Zapata | SOUTH | 2028-12-31 | OTH | BA | 51.26 |  | 2021-04-09 | 2021-05-04 | 2021-07-27 | 2021-04-15 |  |  |  | No
23INR0561 | Cascabel Wind 2 | SS Completed, FIS Started, IA | Vaquero Wind Energy, LLC | 345 kV Rapido Substation (New ETT Substation) tapping the existing 345 kV Line from CENIZO7C (#80225) to DELSOL7C (#80307). | Zapata | SOUTH | 2027-12-01 | WIN | WT | 197.75 |  | 2023-03-08 | 2023-03-13 | 2023-06-09 | 2023-02-15 |  |  | 2025-05-23 | Yes | Not Required |  | Not Required | 2025-09-24
24INR0077 | Quarter Ranch Solar | SS Completed, FIS Started, No IA | Gransolar Texas Three LLC | 80223 Cenizo Substation 345kV | Zapata | SOUTH | 2028-10-15 | SOL | PV | 154.12 |  | 2022-03-28 | 2021-07-13 | 2021-09-28 | 2022-03-23 |  | No |  | No |  |  | Not Required
24INR0131 | Zelus BESS | SS Completed, FIS Started, No IA | BRP Zelus BESS LLC | the 138 kV Zapata Substation (#8299; AEP) | Zapata | SOUTH | 2027-12-01 | OTH | BA | 201.03 |  | 2021-12-15 | 2021-12-20 | 2022-03-16 | 2021-12-03 |  |  |  | No
24INR0184 | Slate Solar Project | SS Completed, FIS Started, No IA | Ignis TX Solar Three LLC | Tap 138kV 8646 Rio Bravo - 8985 San Ygancio | Zapata | SOUTH | 2030-01-15 | SOL | PV | 104.89 | COD | 2022-08-03 | 2021-12-20 | 2022-03-10 | 2022-07-13 |  | No |  | No |  |  | Not Required
24INR0424 | Cascabel Wind 1 | SS Completed, FIS Started, IA | Vaquero Wind Energy, LLC | 345 kV Rapido Substation (New ETT Substation) tapping the existing 345 kV Line from CENIZO7C (#80225) to DELSOL7C (#80307) | Zapata | SOUTH | 2027-12-01 | WIN | WT | 197.75 |  | 2023-03-08 | 2023-03-13 | 2023-06-09 | 2023-02-15 |  |  | 2025-05-23 | Yes | Not Required |  | Not Required | 2025-09-24
24INR0505 | Corralitos Wind 1 | SS Completed, FIS Started, IA | Vaquero Wind Energy, LLC | Tap 345kV 80225 CENIZO7C - 80307 DELSOL7C (New ETT Tiempo Substation) | Zapata | SOUTH | 2027-12-01 | WIN | WT | 196.1 |  | 2023-01-24 | 2023-01-30 | 2023-04-28 | 2023-01-19 |  |  | 2025-06-19 | Yes |  |  | Not Required
24INR0506 | Corralitos Wind 2 | SS Completed, FIS Started, IA | Vaquero Wind Energy, LLC | Tap 345kV 80225 CENIZO7C - 80307 DELSOL7C (New ETT Tiempo Substation) | Zapata | SOUTH | 2027-12-31 | WIN | WT | 195.4 |  | 2023-01-24 | 2023-01-30 | 2023-04-28 | 2023-01-19 |  |  | 2025-06-19 | Yes |  |  | Not Required
26INR0107 | Freedom Falcon BESS | SS Completed, FIS Started, No IA | Falcon BESS, LLC | Tap 345kV #80224 Tiempo - #80227 Rapido | Zapata | SOUTH | 2028-08-11 | OTH | BA | 501.9 |  | 2023-04-26 | 2023-06-28 | 2023-09-22 | 2023-06-14 |  | Yes |  | No
26INR0116 | Falcon Zapata Storage 138 | SS Completed, FIS Started, IA | Falcon BESS, LLC | Tap 138kV 8299 Zapata - 8957 Lopeno | Zapata | SOUTH | 2028-03-11 | OTH | BA | 200.79 |  | 2023-04-28 | 2023-05-15 | 2023-08-11 | 2023-05-08 |  | No | 2026-02-03 | Yes |  |  |  | 2026-03-27
28INR0005 | Tetris Solar | SS Completed, FIS Started, No IA | NextEra Energy Interconnection Holdings LLC | TAP 345kV 80307 Del Sol 7C - 80225 Cenizo 7C | Zapata | SOUTH | 2029-07-01 | SOL | PV | 359 |  | 2023-06-15 | 2023-07-28 | 2023-10-23 | 2023-07-21 |  |  |  | No |  |  | Not Required
28INR0317 | Falcon Solar | SS Completed, FIS Started, No IA | Falcon Energy Project, LLC | Tap 345kV #80225 Cenizo7C to #80307 Del Sol7C | Zapata | SOUTH | 2029-12-01 | SOL | PV | 501.96 |  | 2025-10-29 | 2025-10-28 | 2026-01-12 |  |  |  |  | No | Not Required | Not Required | Not Required
28INR0337 | Barrosos Creek Wind 3 | SS Completed, FIS Started, No IA | Cascabel Wind Energy, LLC | #80227 Rapido 345 kV | Zapata | SOUTH | 2028-05-31 | WIN | WT | 197.75 |  | 2025-07-30 | 2025-08-18 | 2025-10-13 | 2025-07-30 |  | No |  | No |  |  | Not Required
28INR0338 | Barrosos Creek Wind 4 | SS Completed, FIS Started, No IA | Cascabel Wind Energy, LLC | #80227 Rapido 345 kV | Zapata | SOUTH | 2028-05-31 | WIN | WT | 197.75 |  | 2025-07-30 | 2025-08-18 | 2025-10-13 | 2025-07-30 |  | No |  | No |  |  | Not Required
28INR0339 | Corralitos Wind 3 | SS Completed, FIS Started, No IA | Las Crestas Wind Energy, LLC | ETT 345 kV Tiempo #80224 Substation (Tap on 345kV 80225 CENIZO7C - 80307 DELSOL7C) | Zapata | SOUTH | 2028-05-31 | WIN | WT | 196.1 |  | 2025-06-11 | 2025-06-13 | 2025-09-11 | 2025-06-24 |  |  |  | No |  |  | Not Required
28INR0340 | Corralitos Wind 4 | SS Completed, FIS Started, No IA | Las Crestas Wind Energy, LLC | ETT 345 kV Tiempo #80224 Substation (Tap on 345kV 80225 CENIZO7C - 80307 DELSOL7C) | Zapata | SOUTH | 2028-05-31 | WIN | WT | 195.4 |  | 2025-06-11 | 2025-06-13 | 2025-09-11 | 2025-06-24 |  |  |  | No |  |  | Not Required
28INR0482 | Falcon II Solar | SS Completed, FIS Started, No IA | Falcon Energy Project | 8004 Revilla 138 kV | Zapata | SOUTH | 2032-02-16 | SOL | PV | 100.32 |  | 2026-03-05 | 2026-03-29 | 2026-06-17 | 2026-03-20 |  | No |  | No |  |  | Not Required
28INR0483 | Falcon II BESS | SS Completed, FIS Started, No IA | Falcon Energy Project | 8004 Revilla 138 kV | Zapata | SOUTH | 2032-02-16 | OTH | BA | 103.3 |  | 2026-03-05 | 2026-03-29 | 2026-06-17 | 2026-03-16 |  | No |  | No
28INR0503 | Rancho Grande Solar | SS Completed, FIS Started, No IA | Bordas Renewable Energy, LLC | 345 kV Tiempo Substation #80224 | Zapata | SOUTH | 2028-05-09 | SOL | PV | 251.58 |  | 2026-03-30 | 2026-04-02 | 2026-06-30 | 2026-03-27 |  |  |  | No |  |  | Not Required
29INR0169 | Falcon BESS | SS Completed, FIS Started, No IA | Falcon Energy Project, LLC | Tap 345kV #80225 CENIZO to #80307 DEL SOL | Zapata | SOUTH | 2029-12-01 | OTH | BA | 516.72 |  | 2025-08-25 | 2025-09-09 | 2025-10-28 | 2025-08-28 |  |  |  | No
30INR0042 | La Morena Energy Center BESS | SS Completed, FIS Started, No IA | Adapture Solar Development | Tap 345 kV 80225 CENIZO7C - 80307 DELSOL7C | Zapata | SOUTH | 2029-05-07 | OTH | BA | 250 |  | 2026-01-23 | 2025-06-12 | 2025-09-04 |  |  | Yes |  | No
30INR0043 | La Morena Energy Center Solar | SS Completed, FIS Started, No IA | Adapture Solar Development | Tap 345 kV (80225) CENIZO7C - (80307) DELSOL7C | Zapata | SOUTH | 2029-05-07 | SOL | PV | 250 |  | 2026-01-27 | 2025-06-12 | 2025-09-04 |  |  | Yes |  | No |  |  | Not Required
30INR0092 | Wallflower Solar | SS Completed, FIS Started, No IA | Wallflower Solar, LLC | Tap the 345 kV Cenizo (#80225) - Del Sol (#80307) line. | Zapata | SOUTH | 2029-12-30 | SOL | PV | 201.15 |  | 2026-02-16 | 2026-03-10 | 2026-06-04 | 2026-03-05 |  | Yes |  | No | Not Required | Not Required | Not Required
30INR0093 | Wallflower Energy Storage | SS Completed, FIS Started, No IA | Wallflower Energy Storage | Tap the 345 kV Cenizo (#80225) - Del Sol (#80307) line | Zapata | SOUTH | 2029-12-30 | OTH | BA | 209.16 |  | 2026-02-16 | 2026-02-25 | 2026-05-21 | 2026-02-19 |  | Yes |  | No | Not Required | Not Required
25INR0304 | Flying Kite Solar | SS Completed, FIS Started, IA | FLYING KITE SOLAR LLC | Tap the 138 kV La Pryor (#8008) - Poblano (#8009) | Zavala | SOUTH | 2027-12-30 | SOL | PV | 80.38 |  | 2023-03-31 | 2023-04-07 | 2023-07-05 | 2023-03-17 |  |  | 2024-10-02 | No |  |  | Not Required
26INR0120 | Bramble Energy Center | SS Completed, FIS Started, No IA | Bramble Energy Center, LLC | 8236 West Batesville 138kV | Zavala | SOUTH | 2028-12-22 | OTH | BA | 225.1 |  | 2023-08-23 | 2023-09-08 | 2023-12-04 | 2023-08-15 |  |  |  | No | Not Required | Not Required
26INR0179 | SunShiner ESS | SS Completed, FIS Started, No IA | SunShiner ESS LLC | 8008 La Pryor4A | Zavala | SOUTH | 2029-05-11 | OTH | BA | 200 |  | 2023-09-20 | 2023-09-25 | 2023-12-21 | 2023-09-20 |  | No |  | No
27INR0274 | Flying Kite Bess | SS Completed, FIS Started, No IA | Flying Kite BESS, LLC | Tap the 138 kV La Pryor (#8008) - Poblano (#8009) | Zavala | SOUTH | 2027-12-30 | OTH | BA | 104.93 |  | 2024-07-10 | 2024-07-30 | 2024-10-28 | 2024-07-22 |  |  |  | No
27INR0380 | La Mancha Solar SLF | SS Completed, FIS Started, No IA | La Mancha Solar, LLC | Tap 69kV 5836 NBatesville - 5822 Leona | Zavala | SOUTH | 2028-10-10 | SOL | PV | 40.9 |  | 2024-11-07 | 2024-11-19 | 2025-02-14 | 2024-11-07 |  |  |  | No |  |  | Not Required
27INR0381 | La Mancha Storage SLF | SS Completed, FIS Started, No IA | La Mancha Storage, LLC | Tap 69kV 5836 NBatesville - 5822 Leona | Zavala | SOUTH | 2028-10-10 | OTH | BA | 40.9 |  | 2024-11-07 | 2024-11-19 | 2025-02-14 | 2024-11-07 |  |  |  | No

## Project Details - Small Gen
GIM Project Details - Small Generators
NOTES:
Due to Protocol confidentiality provisions, only those Small Generator projects are included for which ERCOT has (1) received written Notice from Interconnecting Entities (IE) that authorize the project
information to be made public, or (2) approved the IE's completed Resource Registration form as indicated by assignment of a “Model Ready Date".
Excludes projects that have a status of Inactive (status = INA).
INR | Project Name | Model Ready Date | Interconnecting Entity | POI Location | County | CDR Reporting Zone | Projected COD | Fuel | Technology | Capacity (MW) | Change indicators: Proj Name, MW | IA Signed | Financial Security | Approved for Energization | Approved for Synchronization | Comment
[11 empty] | Size, COD, SFS. |  | Required to fund
[11 empty] | Status Change INA-to-PLN |  | Dist. Upgrades
22INR0596 | Grizzly Ridge BESS SLF | 2022-09-01 | Grizzly Ridge Solar LLC | Pottsville Switching Substation (Bus# 178) | Hamilton | NORTH | 2030-07-01 | OTH | BA | 0 |  | 2021-10-18 | Yes | 2023-02-10
23INR0483 | Rio Nogales CT1 Rotor Replacement | 2023-04-12 | CPS Energy | Rio Nogales Substation 5362 RIONOG 345kV | Guadalupe | SOUTH | 2026-08-07 | GAS | CC | 3.1 |  | 2023-01-20 | Yes |  | 2023-04-27
23INR0529 | Torrecillas BESS | 2024-09-05 | Torrecillas Interconnect, LLC | 161257 Torrecillas 345kV Station code: TORR | Webb | SOUTH | 2026-12-31 | OTH | BA | 9.9 |  | 2015-01-30 | Yes | 2025-06-25 | 2025-07-01
23INR0548 | Leakey BESS | 2026-06-03 | Regis Leaky LLC | Station Name (TDSP Station Code): LEAKEY; Load/Load Transformer Name: L_LEAKEY9_1Y; PTI BUS Name: 7426; Voltage in kV (Transmission Level): 69kV Transformers: 3x 4000kVA 800VAC Δ - 24.9kVA Υ 12,000 MVA connected, Running load limited to 9.99 MW | Real | SOUTH | 2026-11-13 | OTH | BA | 9.9 |  | 2023-01-18 | Yes | 2026-07-02 | 2026-07-10
23INR0556 | IEP Orchard BESS | 2024-01-04 | IEP Tejas Verde LLC | Station Name (TDSP Station Code): OR Load/Load Transformer Name :TR1 PTI BUS number: 44541 Voltage in kV (Transmission Level): 138 kV Project Size: 9.99 MW battery energy storage (BESS) system; 50 MWh connecting on CNP 34.5kV Distribution System. | Fort Bend | HOUSTON | 2027-12-31 | OTH | BA | 9.99 | COD | 2023-08-09 | Yes | 2024-11-12 | 2024-12-06
23INR0603 | Damon BESS 2 | 2024-07-03 | PR DAMON, LLC | 9.99 MW 50 MWh battery energy storage project connecting at 12.47kV Damon (DA) substation. Station Name (TDSP Station Code): DA Load/Load Transformer Name: TR2 PTI BUS number: 42370 Voltage in kV (Transmission Level): 138 kV | Brazoria | COASTAL | 2027-08-21 | OTH | BA | 9.99 |  | 2023-10-06 | Yes
23INR0790 | DAMON BESS3 | 2025-09-04 | BarBar Storage LLC | Station Name: DAMON TSP Station Code: DA Load/Load Transformer Name: TR2 PTI BUS number: 42370 Voltage in kV (Transmission Level): 138 kV Node (associated w/ load/load XFRM in NMMS): TR2 | Brazoria | COASTAL | 2025-12-01 | OTH | BA | 9.96 |  | 2024-01-30 | Yes | 2025-09-29 | 2026-03-04
24INR0481 | Little York BESS | 2026-02-04 | ESTX-PLD-HOUSTON5, LLC | Station Name (TDSP Station Code): Little York (LK) Load/Load Transformer Name: TR3 PTI BUS number: 45995 Voltage in kV (Transmission Level): 138kV Node (associated w/ load/load XFMR in NMMS): TR3 | Harris | HOUSTON | 2026-11-12 | OTH | BA | 9.96 | COD | 2025-08-20 | Yes | 2026-06-05 | 2026-06-15
24INR0502 | Medina City BESS | 2026-06-03 | Regis Medina, LLC | Station Name (TDSP Station Code): MEDINA; Load/Load Transformer Name: L_MEDICI9_1Y; PTI BUS number: 7430; Voltage in kV (Transmission Level): 69kV Transformers: 3x 4000kVA 800VAC Δ - 12.47kVA Υ 12,000 MVA connected, Running load limited to 9.99 MW | Bandera | SOUTH | 2026-11-26 | OTH | BA | 9.99 |  | 2023-01-18 | Yes | 2026-07-16 | 2026-07-29
24INR0602 | CPS Rio Nogales CT301 Rotor Replacement | 2024-04-29 | CPS Energy | 5362 RIONOG 345kV | Guadalupe | SOUTH | 2026-08-07 | GAS | CC | 3.1 |  | 2023-11-10 | Yes |  | 2024-04-03
24INR0645 | COYOTE SPRINGS AGR1 | 2024-06-05 | HEN INFRASTRUCTURE, LLC 1 | Station Name: COYOTSPR Load Name: COYOTE_1 Bus#: 38113 Voltage: 138 kV DAC: COYOTSPR_LD8 COYOTSPR/COYOTE_1/38113/COYOTSPR_LD8 | Reeves | WEST | 2026-06-23 | OIL | OT | 9.95 |  | 2023-10-16 | Yes
24INR0646 | SADDLEBACK AGR1 | 2024-06-05 | HEN INFRASTRUCTURE, LLC 1 | SADLBACK/SADLBK_1/38058/SADLBACK_LD8 | Reeves | WEST | 2026-06-23 | OIL | OT | 9.95 |  | 2023-10-16 | Yes
24INR0712 | Byrd Ranch Repower | 2026-04-15 | Byrd Ranch Storage LLC | 39700 SWEENY 138kV | Brazoria | COASTAL | 2027-01-22 | OTH | BA | 5.5 |  | 2020-12-14 | No
25INR0601 | East Bernard BESS | 2026-09-02 | Regis East Bernard LLC | Station Name: East Bernard Station Code: EB ERCOT Load Name: TR2 ERCOT BUS #: 44190 Voltage (Transmission level kV): 138 Node associated with load XFMR: 8045 CNP 5-Digit Code: E_BERN Short Code: EB TR2 Feeder: EB-81 CNP XFMR #: EB TR2 | Wharton | SOUTH | 2026-11-04 | OTH | BA | 9.5 |  | 2024-04-29 | Yes
25INR0602 | Hockley BESS | 2027-01-06 | Regis Hockley LLC | 30.021619, -95.846315 Station Name (Station Code): Hockley (HK) LONG CODE: HOCKLY Short Code: HK TR5 ERCOT Bus Name: Hockley Feeder: HK-91 ERCOT Load Name: TR5 CNP XFMR #: HK TR5 ERCOT Bus #: 45880 Node: 0101 | Harris | HOUSTON | 2027-03-01 | OTH | BA | 9.99 |  | 2024-04-29 | Yes
25INR0604 | Pledger BESS | 2026-09-02 | Regis Pledger LLC | 29.188382, -95.911558 CNP Pledger Substation LONG Name: PLEDGER Short Name: PG ERCOT Bus #: 43120 ERCOT Load Name: TR2 Connectivity Node: TR2 | Matagorda | COASTAL | 2026-11-04 | OTH | BA | 9.5 |  | 2024-04-29 | Yes
25INR0665 | CPS Rio Nogales CT201 Rotor Replacement | 2025-04-02 | CPS Energy | 5362 RIONOG 345kV | Guadalupe | SOUTH | 2026-08-07 | GAS | CC | 3.1 |  | 2025-02-07 | Yes |  | 2025-04-02
25INR0711 | Coyanosa Gas | 2025-10-27 | RPC Merchant, LLC | Station Name: COYANOSA Load Name: COYAN_2 TNMP Transformer Name: Xfmr T-2 (25kV) Bus#: 38380 Transmission Voltage: 138kV Node: 0033 | Winkler | WEST | 2026-12-17 | GAS | IC | 9.9 |  | 2025-03-13 | Yes
25INR0741 | Hollywood Solar Repower | 2025-12-17 | RED TAILED HAWK SOLAR LLC | 44060 BLU 345kV | Wharton | SOUTH | 2026-09-30 | SOL | PV | 9.9 |  | 2025-10-21 | Yes
25INR0747 | Knapp BESS | 2025-09-04 | Knapp ESS Assets, LLC | Station Name: KNAPP Station Code: KNAPP Station Bus Number: #1310 Station Transmission Voltage: 138 kV Load/Load Transformer Name: LDLXFMR2 Distribution Voltage: 12.47 kV | Scurry | WEST | 2026-10-24 | OTH | BA | 9.95 |  | 2025-03-13 | Yes | 2025-11-05 | 2025-11-24
25INR0768 | Stafford Hill BESS | 2026-10-01 | Colorado Clean Energy Center, LLC | New DESR on the coordinates above tie at 12.47kV to: TSP Station Name: Stafford Hill TSP Station Code: STAFHI Load Name: LOAD1 Bus #: PTI Bus Number: 78520 Voltage (Transmission level kV): 138kV Node (load/load XFMR in NMMS), Tranformer: LD01 | Colorado | SOUTH | 2026-11-14 | OTH | BA | 9.9 |  | 2026-05-28 | Yes
25INR0769 | Kleimann BESS | 2026-09-02 | Columbus Clean Energy Center, LLC | New DESR on the coordinates above tie at 12.47kV to: TSP Station Name: Kleimann TSP Station Code: KLEIMA Load Name: LOAD1 Bus #: PTI Bus Number: 78115 Voltage (Transmission level kV): 138kV Node (load/load XFMR in NMMS), Tranformer: LD01 | Colorado | SOUTH | 2026-12-08 | OTH | BA | 9.9 | COD | 2025-03-31 | Yes
26INR0574 | Apple BESS | 2025-12-10 | Apple Infra LLC | Station Name - Apple Oncor 5-digit code - APPLE Oncor XFMR # - 1 ERCOT Bus Name - APPLE_9 ERCOT Bus # 1276 EROCT Load Name - LDLXFMR1 Substation Transmission kV - 138 | Ector | WEST | 2026-11-27 | OTH | BA | 9.9 | COD | 2025-04-03 | Yes | 2026-08-04
26INR0682 | North Edinburg BESS 1 | 2025-10-01 | Edinburg ESS Assets LLC | TSP Station Name: North Edinburg TSP Station Code: NEDIN Load Name / Load Transformer Name: LOAD3 Bus #: PTI Bus Number: 8380 Voltage (Transmission level kV): 138 kV Node (associated w/ load/load XFMR in NMMS): LD03 | Hidalgo | SOUTH | 2026-08-21 | OTH | BA | 9.99 |  | 2025-06-10 | Yes | 2026-05-05 | 2026-08-10
26INR0691 | Harlingen #1 BESS 1 | 2025-10-01 | Harlingen ESS Assets LLC | TSP Station Name: Harlingen #1 TSP Station Code: HARLIN_1 • Load Name / Load Transformer Name: 69_12_1 Bus #: PTI Bus Number:8321 Voltage (Transmission level kV):69kV Node (associated w/ load/load XFMR in NMMS): Transformer 1 | Cameron | COASTAL | 2026-08-21 | OTH | BA | 9.99 |  | 2025-06-18 | Yes | 2026-07-14 | 2026-08-10
26INR0698 | Staghorn Gas | 2026-02-04 | RPC Merchant LLC | STATION NAME: STAGHORN LOAD NAME: STGHRN_3 TNMP TRANSFORMER NAME: T3 BUS #: 37990 TRANSMISSION VOLTAGE: 138KV NODE: 9984 | Ward | WEST | 2026-10-29 | GAS | IC | 9.99 |  | 2025-05-30 | Yes | 2026-09-02 | 2026-09-18
26INR0702 | Bexar Martinez BESS | 2026-07-01 | Bexar Martinez LLC | TSP Station Name: Martinez TSP Station Code: C5 Load Name / Load Transformer Name: T3 Bus #: PTI Bus Number: 5294 Voltage (Transmission level kV): 138 Node (associated w/ load/load XFMR in NMMS): 0120 | Bexar | SOUTH | 2027-01-23 | OTH | BA | 9.99 | COD | 2026-02-03 | Yes | 2026-09-15
26INR0714 | Pavlov BESS2 | 2026-08-05 | Matagorda Clean Energy Center, LLC | New DESR on the coordinates above tie at 12.47kV to: TSP Station Name: Pavlov TSP Station Code: PAVLOV Load Name: 138_13_1 Bus #: PTI Bus Number: 8608 Voltage (Transmission level kV): 138kV Node (load/load XFMR in NMMS), Tranformer: LD01 | Matagorda | COASTAL | 2026-12-13 | OTH | BA | 9.99 | COD | 2025-06-18 | Yes
26INR0734 | Alamo Street BESS2 | 2026-12-02 | Momentum Pilsner, LLC | TSP Station Name: Alamo Street Sub TNP TSP Station Code: ALAMO_ST Load Name / Load Transformer Name: ALAMO_2 Bus #: PTI Bus Number: 38331 Voltage (Transmission level kV): 138 Node (associated w/ load/load XFMR in NMMS): 9631 | Pecos | WEST | 2027-03-30 | OTH | BA | 9.99 |  | 2023-02-01 | Yes
26INR0773 | Seaway BESS | 2026-12-02 | Mount Whitney Energy Storage LLC | TSP Substation Name - Seaway TSP Substation Code - Seaway Load Name/Load Transformer Name - LOAD_T-4 Bus # / PTI Bus Number: 57670 Voltage (Transmission level Kv) - 138kV Node (associated w/ load/load XFMR in NMMS) - 0009 | Waller | HOUSTON | 2027-02-22 | OTH | BA | 9.9 |  | 2024-12-11 | Yes
26INR0774 | Wallis BESS2 | 2026-12-02 | Denali Energy Storage LLC | TSP Substation Name - Wallis TSP Substation Code - WA Load Name/Load Transformer Name - TR4 Bus # / PTI Bus Number: 44740 Voltage (Transmission level kV) - 138 kV Node (associated w/ load/load XFMR in NMMS) - TR4 | Austin | SOUTH | 2027-02-22 | OTH | BA | 9.9 |  | 2024-12-11 | Yes

## GIM Trends
GIM Trends
Reflects all Large Generator projects for which a Security Screening Study has been requested. The third table reflects all Small Generator projects whose GIM applications have been approved.
Excludes projects that have a status of Inactive (status = INA).
Nameplate capacity will change across time due to additional projects, cancelations, expirations, adjustments from study results, and projects being placed into service.
| Year | Month | Total Projects |  |  | Project Count | [5 empty] | Project Capacity (MW)
[6 empty] | GIM milestones | [5 empty] | Fuel Type
|  |  |  | Small Generator Not Model Ready | Small Generator Model Ready | Initial Screening Study | Screening Study Complete | In Full Study | Completed Full Study | Signed Interconnection Agreement | Cancelled | Wind | Solar | Gas | Nuclear | Coal | Biomass | Battery | Other
| 2023 | Sep | 1580 | 40 | 32 | 43 | 102 | 924 | 93 | 346 | 15 | 31639.72 | 141315.27 | 11383.73 | 0 | 0 | 53 | 114563.15 | 2235.03
| 2023 | Oct | 1628 | 41 | 32 | 49 | 102 | 952 | 99 | 353 | 16 | 31915.72 | 143221.48 | 13637.63 | 0 | 0 | 53 | 120534.12 | 2235.03
| 2023 | Nov | 1656 | 44 | 30 | 55 | 99 | 961 | 92 | 375 | 10 | 32509.57 | 142605.97 | 15457.28 | 0 | 0 | 53 | 124941.16 | 2385.03
| 2023 | Dec | 1671 | 41 | 28 | 39 | 116 | 974 | 92 | 381 | 12 | 34590.95 | 145654.02 | 15482.78 | 0 | 0 | 53 | 127067.73 | 2367
| 2024 | Jan | 1731 | 42 | 29 | 35 | 133 | 1011 | 95 | 386 | 12 | 36260.89 | 148135.32 | 15546.14 | 0 | 0 | 53 | 133592.45 | 2246.85
| 2024 | Feb | 1783 | 43 | 27 | 65 | 132 | 1023 | 102 | 391 | 13 | 37214.97 | 152097.86 | 16022.14 | 0 | 0 | 0 | 140219.15 | 2966.85
| 2024 | Mar | 1775 | 39 | 29 | 80 | 100 | 1035 | 101 | 391 | 64 | 35119.62 | 155272.52 | 15428.85 | 0 | 0 | 0 | 141483.67 | 2331.85
| 2024 | Apr | 1780 | 42 | 33 | 58 | 115 | 1025 | 112 | 395 | 15 | 32956.29 | 152916.51 | 15572.93 | 0 | 0 | 0 | 145000.4 | 2331.85
| 2024 | May | 1813 | 39 | 41 | 48 | 129 | 1023 | 125 | 408 | 9 | 33886.77 | 154225.29 | 15937.93 | 0 | 0 | 0 | 149001.55 | 2331.85
| 2024 | Jun | 1812 | 34 | 44 | 20 | 137 | 1023 | 140 | 414 | 27 | 31452.23 | 152433.39 | 17088.71 | 0 | 0 | 0 | 147743.45 | 2331.85
| 2024 | Jul | 1858 | 31 | 46 | 27 | 136 | 1033 | 158 | 427 | 5 | 33731.45 | 154407.17 | 22159.93 | 0 | 0 | 0 | 151810.97 | 2561.85
| 2024 | Aug | 1886 | 27 | 49 | 24 | 140 | 1057 | 152 | 437 | 8 | 33853.45 | 154770.45 | 25327.99 | 0 | 0 | 0 | 154799.02 | 2561.85
| 2024 | Sep | 1881 | 29 | 48 | 21 | 140 | 1050 | 158 | 435 | 19 | 34838.55 | 153658.25 | 25966.99 | 0 | 0 | 0 | 154264.31 | 2960.85
| 2024 | Oct | 1872 | 35 | 44 | 28 | 127 | 1039 | 159 | 440 | 29 | 33467.14 | 154860.41 | 25953.73 | 0 | 0 | 0 | 152579.89 | 3712.85
| 2024 | Nov | 1903 | 33 | 48 | 21 | 126 | 1070 | 156 | 449 | 11 | 35307.35 | 155675.7 | 27159.53 | 0 | 0 | 0 | 156529.81 | 3113.15
| 2024 | Dec | 1917 | 32 | 46 | 22 | 120 | 1103 | 147 | 447 | 14 | 34449.55 | 154487.12 | 27577.52 | 0 | 0 | 0 | 160043.38 | 2912.85
| 2025 | Jan | 1952 | 30 | 46 | 16 | 119 | 1163 | 133 | 445 | 17 | 38223.03 | 153607.1 | 28773.88 | 0 | 0 | 0 | 165932.71 | 2780.85
| 2025 | Feb | 1987 | 24 | 50 | 19 | 113 | 1200 | 121 | 460 | 16 | 39892.87 | 155989.52 | 32190.19 | 0 | 0 | 0 | 168836 | 2780.85
| 2025 | Mar | 2018 | 26 | 50 | 19 | 113 | 1207 | 112 | 491 | 18 | 39795.14 | 156685.43 | 33578.49 | 600 | 0 | 0 | 171592.01 | 2912.85
| 2025 | Apr | 2037 | 32 | 50 | 29 | 102 | 1212 | 105 | 507 | 38 | 42483.35 | 159425.81 | 33583.05 | 600 | 0 | 0 | 172485.62 | 3062.85
| 2025 | May | 2031 | 31 | 50 | 21 | 89 | 1223 | 106 | 511 | 26 | 40885.47 | 158490.36 | 32489.82 | 600 | 0 | 0 | 173996.86 | 3208.4
| 2025 | Jun | 2054 | 28 | 50 | 27 | 88 | 1237 | 114 | 510 | 17 | 41414.07 | 161676.74 | 35260.07 | 600 | 0 | 0 | 177928.6 | 3501.35
| 2025 | Jul | 2066 | 23 | 52 | 27 | 86 | 1242 | 119 | 517 | 21 | 45048.33 | 162702.67 | 39557.68 | 600 | 0 | 0 | 181393.77 | 3501.35
| 2025 | Aug | 2041 | 23 | 56 | 33 | 82 | 1201 | 111 | 535 | 30 | 44648.55 | 160192 | 39402.77 | 600 | 0 | 0 | 179838.35 | 3501.35
| 2025 | Sep | 2042 | 29 | 54 | 20 | 94 | 1196 | 117 | 532 | 25 | 46093.45 | 159931.82 | 43695.24 | 600 | 0 | 0 | 178052.76 | 3562.45
| 2025 | Oct | 1999 | 28 | 56 | 11 | 94 | 1164 | 116 | 530 | 51 | 46422.28 | 158150.64 | 47848.45 | 600 | 0 | 0 | 175579.1 | 3384.45
| 2025 | Nov | 1994 | 28 | 57 | 9 | 91 | 1159 | 122 | 528 | 13 | 44785.68 | 159536.96 | 52655.95 | 600 | 0 | 0 | 174369.01 | 3257.94
| 2025 | Dec | 1984 | 25 | 54 | 5 | 90 | 1150 | 121 | 539 | 17 | 46190.94 | 161807.24 | 53716.05 | 600 | 0 | 0 | 175459.01 | 3257.94
| 2026 | Jan | 2008 | 31 | 50 | 17 | 79 | 1136 | 121 | 574 | 20 | 47960.85 | 162066.76 | 57403.35 | 600 | 0 | 0 | 178702.75 | 3572.5
| 2026 | Feb | 2008 | 31 | 42 | 25 | 78 | 1134 | 122 | 576 | 21 | 47792.98 | 162926.73 | 60714.87 | 600 | 0 | 0 | 177641.92 | 3885.35
| 2026 | Mar | 2013 | 28 | 43 | 19 | 77 | 1135 | 128 | 583 | 15 | 48088.84 | 165251.35 | 63899.87 | 600 | 0 | 0 | 176745.04 | 3571.28
| 2026 | Apr | 1965 | 26 | 36 | 9 | 85 | 1115 | 116 | 578 | 43 | 48349.17 | 163479.1 | 64745.63 | 1936.52 | 0 | 0 | 171105.76 | 3551.34
| 2026 | May | 1960 | 28 | 37 | 4 | 89 | 1120 | 113 | 569 | 13 | 48274.67 | 163091.35 | 70678.69 | 1936.52 | 0 | 0 | 171566.82 | 2752.53
| 2026 | Jun | 1949 | 32 | 35 | 4 | 85 | 1109 | 115 | 569 | 22 | 47990.56 | 161554.14 | 77606.59 | 1936.52 | 0 | 0 | 170944.95 | 2752.53
| 2026 | Jul | 1906 | 33 | 30 | 5 | 41 | 1122 | 112 | 563 | 56 | 48781.67 | 157952.59 | 80180.06 | 1936.52 | 0 | 0 | 165734.07 | 1993.53
| 2026 | Aug | 1890 | 35 | 32 | 4 | 41 | 1092 | 106 | 580 | 21 | 48130.76 | 156289.37 | 81703.96 | 1936.52 | 0 | 0 | 164416.98 | 1993.53
| 2026 | Sep | 1874 | 36 | 31 | 8 | 41 | 1059 | 110 | 589 | 26 | 49746.02 | 155122.86 | 81033.87 | 3256.52 | 0 | 0 | 162579.61 | 2043.53
Note: Other contains all Fuel and Technology Types not in the Solar, Wind, Gas or Battery categories.

## data_GIM Trends_1 (hidden)
| # Signed Interconnect Agreement | # Completed Full Study | # in Full Study | # Screening Study Complete | # Initial Screening study | GW Capacity
Sep-25 | 532 | 117 | 1196 | 94 | 20 | 431.1647
Oct-25 | 530 | 116 | 1164 | 94 | 11 | 431.2039
Nov-25 | 528 | 122 | 1159 | 91 | 9 | 434.4146
Dec-25 | 539 | 121 | 1150 | 90 | 5 | 440.2987
Jan-26 | 574 | 121 | 1136 | 79 | 17 | 449.5541
Feb-26 | 576 | 122 | 1134 | 78 | 25 | 452.8891
Mar-26 | 583 | 128 | 1135 | 77 | 19 | 457.5034
Apr-26 | 578 | 116 | 1115 | 85 | 9 | 452.6039
May-26 | 569 | 113 | 1120 | 89 | 4 | 457.707
Jun-26 | 569 | 115 | 1109 | 85 | 4 | 462.1715
Jul-26 | 563 | 112 | 1122 | 41 | 5 | 456.0041
Aug-26 | 580 | 106 | 1092 | 41 | 4 | 453.8673
Sep-26 | 589 | 110 | 1059 | 41 | 8 | 453.1668

## data_GIM Trends_2 (hidden)
| Natural Gas | Nuclear | Coal | Wind | Solar | Biomass | Battery | Other | Total Project Count | Cancelled Project Count
Sep-25 | 43.6952 | 0.6 | 0 | 46.0934 | 159.9318 | 0 | 178.0528 | 3.5625 | 2042 | 25
Oct-25 | 47.8484 | 0.6 | 0 | 46.4223 | 158.1506 | 0 | 175.5791 | 3.3845 | 1999 | 51
Nov-25 | 52.6559 | 0.6 | 0 | 44.7857 | 159.537 | 0 | 174.369 | 3.2579 | 1994 | 13
Dec-25 | 53.7161 | 0.6 | 0 | 46.1909 | 161.8072 | 0 | 175.459 | 3.2579 | 1984 | 17
Jan-26 | 57.4034 | 0.6 | 0 | 47.9609 | 162.0668 | 0 | 178.7028 | 3.5725 | 2008 | 20
Feb-26 | 60.7149 | 0.6 | 0 | 47.793 | 162.9267 | 0 | 177.6419 | 3.8853 | 2008 | 21
Mar-26 | 63.8999 | 0.6 | 0 | 48.0888 | 165.2514 | 0 | 176.745 | 3.5713 | 2013 | 15
Apr-26 | 64.7456 | 1.9365 | 0 | 48.3492 | 163.4791 | 0 | 171.1058 | 3.5513 | 1965 | 43
May-26 | 70.6787 | 1.9365 | 0 | 48.2747 | 163.0914 | 0 | 171.5668 | 2.7525 | 1960 | 13
Jun-26 | 77.6066 | 1.9365 | 0 | 47.9906 | 161.5541 | 0 | 170.945 | 2.7525 | 1949 | 22
Jul-26 | 80.1801 | 1.9365 | 0 | 48.7817 | 157.9526 | 0 | 165.7341 | 1.9935 | 1906 | 56
Aug-26 | 81.704 | 1.9365 | 0 | 48.1308 | 156.2894 | 0 | 164.417 | 1.9935 | 1890 | 21
Sep-26 | 81.0339 | 3.2565 | 0 | 49.746 | 155.1229 | 0 | 162.5796 | 2.0435 | 1874 | 26

## data_GIM Trends_3 (hidden)
| # Not Model Ready | # Model Ready | MW Capacity
Sep-25 | 29 | 54 | 770.99
Oct-25 | 28 | 56 | 780.98
Nov-25 | 28 | 57 | 790.97
Dec-25 | 25 | 54 | 732.45
Jan-26 | 31 | 50 | 752.12
Feb-26 | 31 | 42 | 672.74
Mar-26 | 28 | 43 | 653.03
Apr-26 | 26 | 36 | 563.57
May-26 | 28 | 37 | 593.55
Jun-26 | 32 | 35 | 613.76
Jul-26 | 33 | 30 | 574.29
Aug-26 | 35 | 32 | 603.87
Sep-26 | 36 | 31 | 615.62

## data_GIM Trends_4 (hidden)
|  | Gas | Wind | Solar | Battery | Other
COASTAL | 2025 |  |  | 0.1002 | 0.00996
| 2026 |  | 0.5427 | 1.564 | 0.57959
| 2027 | 1.8474 | 0.20233 | 4.2964 | 4.2001 | 1.3865
| 2028 | 0.4699 | 0.1992 | 3.7313 | 6.4077 | 0.07963
| 2029 | 0.55611 | 1.0051 | 2.3173 | 3.669
| 2030 | 0.68108 | 2.8714 | 0.6036 | 0.25624
HOUSTON | 2025 | 0.014 |  |  |  | 0.05
| 2026 | 0.03 |  |  | 1.6126
| 2027 | 0.0354 |  | 0.05042 | 4.0045
| 2028 | 1.142 |  |  | 2.766 | 0.05
| 2029 |  |  | 0.35806 | 2.5315
| 2030 | 1.471 | 1.0294 |  | 0.20305 |  | 1.298 | 2.769
WEST | 2023 |  | 0.0072
| 2024 |  | 0.0103
| 2025 |  | 0.0224 | 0.16848 | 0.20246
| 2026 | 0.01989 | 1.9505 | 2.3304 | 1.5844 | 0.0199
| 2027 | 3.6342 | 3.2869 | 9.9406 | 6.7154
| 2028 | 6.184 | 6.0725 | 15.6269 | 14.6954 | 0.18
| 2029 | 1.1658 | 4.96 | 24.287 | 13.6888 | 0.732
| 2030 | 9.0002 | 7.6913 | 11.3035 | 3.4285
| 2031 | 1.3367 |  | 0.5028
| 2032 | 2.0511
NORTH | 2025 |  | 0.016 | 0.31573 |  | 0.1
| 2026 | 0.021 | 1.5156 | 4.7013 | 1.3455
| 2027 | 1.7246 | 0.56652 | 9.2134 | 9.3
| 2028 | 3.0036 | 1.3256 | 10.9607 | 18.9858 | 0.15 | 0.166 | 3.1696
| 2029 | 6.3367 | 0.1987 | 8.0993 | 14.7638
| 2030 | 6.2562 |  | 0.57141 | 2.3378 | 1.232
| 2031 | 2.5358
| 2032 | 6.9864
PANHANDLE | 2025 |  |  | 0.38
| 2026 |  |  | 0.252 | 0
| 2027 | 0.21 | 0.5136 | 1.7792 | 1.6542
| 2028 |  | 3.1343 | 5.3332 | 2.713
| 2029 | 1.0683 | 3.8454 | 2.141 | 0.81
| 2030 | 3.8163 | 1.0973 | 0.4454 | 1.6312
| 2031 |  |  | 1.0041 | 0.3717
SOUTH | 2025 | 0.0161 |  | 0.34193 | 0.133
| 2026 | 0.6988 | 0.66471 | 3.6777 | 2.0965
| 2027 | 1.2258 | 1.3886 | 3.8975 | 7.063
| 2028 | 5.9751 | 4.5349 | 9.4218 | 16.2093
| 2029 | 3.157 | 1.0938 | 13.7468 | 11.7916
| 2030 | 4.7951 |  | 1.1738 | 4.3223
| 2031 | 0.95613 |  | 0.20086 | 0.20127
| 2032 | 0.62614 |  | 0.28487 | 0.29442
| 2033 | 1.986 |  |  |  | 1.32

## Commissioning Update
Commissioning Approvals during September 2026
Commissioning Category | INR | Size Category | Project Name | Fuel | County | Approval Date * | MW **
Commercial Operation Approved by ERCOT* | 22INR0363 | Large | Hayhurst Texas Solar | Solar | Culberson | 2026-09-16 | 24.76
Commercial Operation Approved by ERCOT* | 20INR0091 | Large | Fagus Solar Park 1 SLF | Solar | Childress | 2026-09-11 | 166.42
Commercial Operation Approved by ERCOT* | 23INR0501 | Large | Soda Lake BESS 1 | Battery Storage | Crane | 2026-09-04 | 203.87
Commercial Operation Approved by ERCOT* | 21INR0469 | Large | Big Star Storage | Battery Storage | Bastrop | 2026-09-25 | 80
Commercial Operation Approved by ERCOT* | 21INR0413 | Large | Big Star Solar | Solar | Bastrop | 2026-09-25 | 203.1
Commercial Operation Approved by ERCOT* | 24INR0302 | Large | Pintail Pass BESS | Battery Storage | San Patricio | 2026-09-01 | 207.25
Commercial Operation Approved by ERCOT* | 26INR0736 | Small | Hovey Solar 2 | Solar | Pecos | 2026-09-22 | 8.05
Commercial Operation Approved by ERCOT* | 25INR0055 | Large | Three W Solar | Solar | Hill | 2026-09-23 | 110.89
Commercial Operation Approved by ERCOT* | 25INR0706 | Large | Bocanova Power II | Battery Storage | Brazoria | 2026-09-17 | 150.46
Commercial Operation Approved by ERCOT* | 25INR0672 | Large | Fagus Solar Park 2 SLF | Solar | Childress | 2026-09-11 | 166.57
Commercial Operation Approved by ERCOT* | 26INR0333 | Large | VERTUS ENERGY STORAGE | Battery Storage | Galveston | 2026-09-28 | 207.3
Commercial Operation Approved by ERCOT* | 25INR0766 | Small | Mesquite BESS2 | Battery Storage | Cameron | 2026-09-02 | 9.99
Synchronization Approved by ERCOT | 24INR0491 | Large | Gunnar BESS | Battery Storage | Hidalgo | 2026-09-08 | 154.75
Synchronization Approved by ERCOT | 20INR0236 | Large | New Hickory Solar | Solar | Jackson | 2026-09-15 | 209.15
Synchronization Approved by ERCOT | 24INR0313 | Large | Backbone Creek BESS | Battery Storage | Burnet | 2026-09-21 | 124.1
Synchronization Approved by ERCOT | 26INR0698 | Small | Staghorn Gas | Gas | Ward | 2026-09-18 | 9.99
Synchronization Approved by ERCOT | 23INR0249 | Large | Limewood Solar | Solar | Bell | 2026-09-15 | 204.6
Energization Approved by ERCOT | 26INR0702 | Small | Bexar Martinez BESS | Battery Storage | Bexar | 2026-09-15 | 9.99
Energization Approved by ERCOT | 21INR0362 | Large | Oystercatcher Solar | Solar | Ellis | 2026-09-02 | 198.43
Energization Approved by ERCOT | 24INR0313 | Large | Backbone Creek BESS | Battery Storage | Burnet | 2026-09-04 | 124.1
Energization Approved by ERCOT | 21INR0334 | Large | Nightfall Solar | Solar | Uvalde | 2026-09-22 | 180.87
Energization Approved by ERCOT | 21INR0253 | Large | Ulysses Solar | Solar | Coke | 2026-09-18 | 151.2
Energization Approved by ERCOT | 25INR0231 | Large | Apache Hill BESS | Battery Storage | Hood | 2026-09-18 | 201.15
* For projects approved for commercial operations, the approval date is the Resource Commissioning Date defined in Section 2 of the ERCOT Nodal Protocols: The date on which ERCOT declares that a
Resource has completed all qualification testing administered by ERCOT as part of the Resource Interconnection process so that a Resource is approved for participation in ERCOT market operations.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may have zero or negative
values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW available to the grid.

## Inactive Projects
Inactive Projects as of end of September 2026*
INR | Size Category | Project Name | Fuel | County | Inactive Date | MW **
13INR0010a | Large | Mariah Del Este Wind | Wind | Parmer | 2019-09-09 10:19 | 152.5
20INR0025 | Large | Spinel Solar | Solar | Medina | 2019-09-10 14:02 | 30
20INR0024 | Large | Fluorite Solar | Solar | Uvalde | 2019-09-11 13:32 | 25
17INR0036 | Large | Grandview 4 Phase A Wind | Wind | Carson | 2019-10-31 10:59 | 200.5
20INR0096 | Large | Desert Rose Solar | Solar | Andrews | 2019-11-12 13:44 | 200
19INR0031 | Large | Bestla Solar | Solar | Winkler | 2020-03-04 16:50 | 180
20INR0023 | Large | Agate Solar | Solar | Ellis | 2020-05-22 15:12 | 60
19INR0101 | Large | Tehuacana Wind | Wind | Limestone | 2020-05-28 10:23 | 600
21INR0503 | Large | Celeste Energy Storage | Battery Storage | Pecos | 2020-06-03 10:35 | 60.89
20INR0299 | Large | Sparkl BESS | Battery Storage | Guadalupe | 2020-09-16 12:30 | 20
19INR0161 | Large | Pierce Wind | Wind | Wharton | 2021-03-16 10:13 | 300
20INR0267 | Large | Greens Bayou Expansion | Gas | Harris | 2021-04-17 01:08 | 140
18INR0072 | Large | Blue Summit repower | Wind | Wilbarger | 2021-04-28 15:42 | 9.9
20INR0013 | Large | Basalt Solar | Solar | Uvalde | 2021-08-16 09:22 | 20
23INR0152 | Large | Madrone Energy Storage | Battery Storage | Comal | 2021-08-20 09:03 | 102.49
22INR0548 | Large | Fighting Jays Battery | Battery Storage | Fort Bend | 2022-02-25 17:43 | 53.2
19INR0099b | Large | Kontiki 2 Wind (ERNEST) | Wind | Glasscock | 2022-03-10 15:42 | 250.1
19INR0099a | Large | Kontiki 1 Wind (ERIK) | Wind | Glasscock | 2022-03-10 15:46 | 250.1
19INR0017 | Large | Tri-County Solar | Solar | Crane | 2022-09-21 15:00 | 177.75
16INR0033 | Large | Hart Wind (Old POI) | Wind | Castro | 2022-10-13 14:42 | 165
20INR0202 | Large | Rueter Solar | Solar | Bosque | 2022-11-01 16:15 | 200
21INR0486 | Large | Pandora Solar | Solar | Wilson | 2022-11-14 14:50 | 252
23INR0210 | Large | Cornwall Solar | Solar | Williamson | 2023-01-19 21:20 | 204.5
23INR0192 | Large | Utica Solar | Solar | Guadalupe | 2023-04-25 09:22 | 204.5
17INR0022 | Large | MIRAGE | Gas | Harris | 2023-05-31 11:28 | 11
24INR0400 | Large | Bora Bora Solar | Solar | Wichita | 2023-06-05 16:38 | 233.35
25INR0243 | Large | CLUTCH CITY STORAGE I SLF | Battery Storage | Galveston | 2023-06-28 17:51 | 16.63
25INR0332 | Large | Clutch City Storage II SLF | Battery Storage | Brazoria | 2023-06-28 17:51 | 11.3
25INR0095 | Large | Brittlebush BESS | Battery Storage | Henderson | 2023-07-05 22:58 | 597.08
25INR0094 | Large | Brittlebush Solar | Solar | Henderson | 2023-07-05 22:58 | 594.01
25INR0089 | Large | Tempesta | Solar | Kaufman | 2023-08-11 14:22 | 443
25INR0090 | Large | Tempesta BESS | Battery Storage | Kaufman | 2023-08-11 14:23 | 600
22INR0275 | Large | Coleto Creek ESS Addition | Battery Storage | Goliad | 2023-09-18 12:23 | 100.1
24INR0428 | Large | Pioneer Hutt Solar | Solar | Midland | 2023-10-05 23:23 | 116
24INR0241 | Large | Utica BESS | Battery Storage | Guadalupe | 2024-01-23 11:46 | 203.9
24INR0244 | Large | Cornwall BESS | Battery Storage | Williamson | 2024-01-23 11:47 | 203.8
24INR0248 | Large | Half Moon 2 BESS | Battery Storage | Hidalgo | 2024-01-23 11:48 | 102
24INR0292 | Large | Urca Solar | Solar | Live Oak | 2024-01-23 11:50 | 204.1
25INR0234 | Large | Maldives Solar (Oncor POI) | Solar | Scurry | 2024-01-31 14:57 | 184
24INR0290 | Large | Rubicon Echo Wind | Wind | Haskell | 2024-02-05 09:51 | 228.4
28INR0012 | Large | Shamrock II Wind | Wind | Crockett | 2024-02-07 09:24 | 256.62
22INR0362 | Large | Pluto Solar | Solar | Webb | 2024-03-08 09:48 | 228
20INR0135 | Large | Half Moon Battery | Battery Storage | Hidalgo | 2024-03-08 10:09 | 30.2
24INR0402 | Large | Inertia BESS 3 | Battery Storage | Jones | 2024-03-11 11:38 | 108.44
25INR0151 | Large | Academy Wind | Wind | Dickens | 2024-03-12 06:59 | 304.56
21INR0363 | Large | Carol Battery | Battery Storage | Potter | 2024-03-13 09:42 | 168
25INR0179 | Large | Triangle Ranch Charlie | Wind | Cottle | 2024-03-14 10:30 | 200.22
25INR0180 | Large | Triangle Ranch Delta | Wind | Cottle | 2024-03-14 10:31 | 101.52
25INR0181 | Large | Triangle Ranch Echo | Wind | Cottle | 2024-03-14 10:32 | 100.52
25INR0182 | Large | Triangle Ranch Fox | Wind | Cottle | 2024-03-14 10:34 | 100.52
24INR0390 | Large | Long Point Solar II | Solar | Brazoria | 2024-03-21 08:36 | 100.9
24INR0398 | Large | Lake Henry Wind | Wind | Kent | 2024-03-29 12:37 | 305
25INR0398 | Large | Pumpville Ranch 1 | Solar | Val Verde | 2024-04-17 15:33 | 1000
24INR0242 | Large | Stockdale BESS | Battery Storage | Wilson | 2024-04-19 09:08 | 203.9
26INR0100 | Large | Wishbone Storage (SLF) | Battery Storage | Hidalgo | 2024-05-16 12:10 | 90
25INR0012 | Large | Alamosa Solar | Solar | Wilbarger | 2024-05-20 17:03 | 209.48
25INR0022 | Large | Alamosa Storage | Battery Storage | Wilbarger | 2024-05-20 17:03 | 207.21
25INR0079 | Large | Sunlight Solar | Solar | Ector | 2024-06-27 14:12 | 203
23INR0526 | Large | Canyon Wind Alternative | Wind | Scurry | 2024-07-05 09:42 | 311.6
25INR0516 | Large | Collier Ranch Solar | Solar | Motley | 2024-07-05 09:43 | 253
25INR0485 | Large | Diver Energy Storage SLF | Battery Storage | Limestone | 2024-07-05 09:53 | 0
24INR0348 | Large | Best Southwest BESS | Battery Storage | Dallas | 2024-07-15 13:53 | 241.32
21INR0201 | Large | Brandon | Gas | Lubbock | 2024-07-25 16:08 | 21
21INR0202 | Large | R Massengale | Gas | Lubbock | 2024-07-25 16:54 | 58
21INR0506 | Large | Ty Cooke | Gas | Lubbock | 2024-07-25 16:54 | 33
25INR0087 | Large | Capoterra | Solar | Milam | 2024-08-12 15:18 | 598
25INR0088 | Large | Capoterra BESS | Battery Storage | Milam | 2024-08-12 15:18 | 600
24INR0432 | Large | HGP Pacesetter BESS | Battery Storage | Dallas | 2024-08-26 13:39 | 200.83
22INR0238 | Large | Rockefeller Solar | Solar | Schleicher | 2024-09-05 09:05 | 207.48
26INR0316 | Large | Lonesome Dove BESS | Battery Storage | Throckmorton | 2024-09-11 13:41 | 256.1
26INR0282 | Large | Haute Stockage | Battery Storage | Shackelford | 2024-09-19 11:33 | 307.32
26INR0325 | Large | Reynolds Park BESS | Battery Storage | Wichita | 2024-09-19 11:36 | 204.8
26INR0286 | Large | Beaujolais BESS | Battery Storage | Lamar | 2024-09-19 13:50 | 307.2
24INR0259 | Large | Zeissel Storage SLF | Battery Storage | Knox | 2024-09-27 10:22 | 0
26INR0492 | Large | Horse Hollow BESS III SLF | Battery Storage | Nolan | 2024-10-01 11:28 | 0
25INR0049 | Large | Point Mountain Solar | Solar | Upton | 2024-10-07 09:40 | 514
26INR0055 | Large | Point Mountain Storage | Battery Storage | Upton | 2024-10-07 09:41 | 507.2
20INR0146 | Large | Angus Storage | Battery Storage | Bosque | 2024-10-08 10:44 | 63
23INR0193 | Large | Stockdale Solar | Solar | Wilson | 2024-10-17 10:52 | 152.5
27INR0052 | Large | Aquilla Lake 3 Wind (Alternative POI Oncor 138KV) | Wind | Hill | 2024-10-17 15:14 | 225.62
27INR0053 | Large | Aquilla Lake 3 Wind ( Alternative POI Oncor 345kV) | Wind | Hill | 2024-10-18 10:25 | 225.62
23INR0189 | Large | Bayside Solar | Solar | Victoria | 2024-10-18 10:27 | 508.9
23INR0282 | Large | BAYSIDE II SOLAR | Solar | DeWitt | 2024-10-18 10:27 | 252.8
24INR0236 | Large | Bayside 2 BESS | Battery Storage | DeWitt | 2024-10-18 14:30 | 252.3
24INR0237 | Large | Bayside BESS | Battery Storage | Victoria | 2024-10-18 14:30 | 507.8
21INR0274 | Large | Carol Solar | Solar | Potter | 2024-10-21 11:26 | 223.2
23INR0245 | Large | Tiger Storage | Battery Storage | Jones | 2024-10-24 15:35 | 251.04
24INR0439 | Large | Citrus Grove Energy Storage | Battery Storage | Hidalgo | 2024-12-05 09:53 | 204.93
19INR0175 | Large | Shifting Gale Wind | Wind | Castro | 2025-01-28 11:14 | 289
20INR0271 | Large | Blue Hills Wind | Wind | Val Verde | 2025-02-05 12:34 | 276
22INR0276 | Large | Trinidad ESS Addition | Battery Storage | Henderson | 2025-02-11 13:20 | 110
24INR0507 | Large | Young Wind II SLF | Wind | Young | 2025-05-08 07:46 | 152.28
23INR0117 | Large | Cantaloupe Storage | Battery Storage | Reeves | 2025-05-08 07:47 | 251.05
25INR0128 | Large | Fiji Solar | Solar | Limestone | 2025-05-08 07:48 | 202.7
28INR0018 | Large | Channing Wind | Wind | Oldham | 2025-05-08 07:48 | 360.5
24INR0245 | Large | Diamondback BESS | Battery Storage | Starr | 2025-05-08 07:49 | 203.8
28INR0033 | Large | Corvette Wind | Wind | Carson | 2025-05-08 07:49 | 1200
22INR0375 | Large | Inertia BESS 2 | Battery Storage | Haskell | 2025-05-08 07:50 | 100.77
26INR0344 | Large | Kendall BESS | Battery Storage | Kendall | 2025-05-08 07:50 | 0
24INR0246 | Large | Sultan BESS | Battery Storage | Bosque | 2025-05-08 07:51 | 203.8
23INR0295 | Large | Sultan Solar | Solar | Bosque | 2025-05-08 07:51 | 206.11
28INR0007 | Large | Tetris Solar (Alternative POI) | Solar | Zapata | 2025-05-08 07:52 | 359
27INR0065 | Large | Funston Solar (AEP POI) | Solar | Jones | 2025-05-16 14:58 | 355.22
26INR0577 | Large | Pine Forest BESS 2 | Battery Storage | Hopkins | 2025-05-21 13:44 | 201.1
24INR0177 | Large | Mitchell Plant Road Solar | Solar | Pecos | 2025-07-09 15:27 | 201.5
24INR0255 | Large | Mitchell Plant Road Storage | Battery Storage | Pecos | 2025-07-09 15:27 | 201.6
25INR0431 | Large | Millennium Energy Storage | Battery Storage | Martin | 2025-07-18 10:56 | 102.59
25INR0073 | Large | Saltillo Storage | Battery Storage | Bastrop | 2025-07-25 09:47 | 101
26INR0539 | Large | Jade Thunder Storage | Battery Storage | Scurry | 2025-08-13 13:50 | 320
26INR0540 | Large | Andromeda Storage IIB | Battery Storage | Scurry | 2025-08-14 08:58 | 320
26INR0541 | Large | Radian Storage IIB | Battery Storage | Brown | 2025-08-15 11:19 | 320
26INR0178 | Large | Alliance Solar | Solar | Navarro | 2025-08-19 13:30 | 180.25
25INR0171 | Large | Pinewood BESS | Battery Storage | Brazoria | 2025-08-20 17:00 | 100.9
25INR0167 | Large | Padrino BESS | Battery Storage | Hill | 2025-09-18 09:00 | 100.77
25INR0313 | Large | Staked Plains BESS | Battery Storage | Lubbock | 2025-09-18 09:11 | 254.8
27INR0415 | Large | Ulysses Crossing Storage | Battery Storage | Coleman | 2025-09-22 16:45 | 150.8
27INR0370 | Large | Ulysses Crossing Solar | Solar | Coleman | 2025-09-22 16:46 | 405.4
26INR0473 | Large | Canyon BESS SLF | Battery Storage | Scurry | 2025-09-25 09:46 | 0
27INR0378 | Large | Vista Bluff Wind 2 | Wind | Upton | 2025-10-01 10:42 | 290.4
26INR0279 | Large | Firebird Solar | Solar | Ector | 2025-10-03 14:16 | 100.42
21INR0432 | Large | Diversion Wind | Wind | Baylor | 2025-10-06 14:51 | 300
27INR0377 | Large | Vista Bluff Wind 1 | Wind | Upton | 2025-10-06 15:04 | 290.4
25INR0475 | Large | Castle Corral BESS | Battery Storage | Mills | 2025-10-08 10:17 | 200.9
26INR0326 | Large | Leaning Tree BESS | Battery Storage | Throckmorton | 2025-10-17 09:24 | 256.1
20INR0217 | Large | CAROL wind | Wind | Potter | 2025-10-20 09:33 | 165.42
25INR0459 | Large | Old Sorrell Energy Storage | Battery Storage | Concho | 2025-10-22 10:45 | 43.1
26INR0517 | Large | Andromeda Storage II | Battery Storage | Scurry | 2025-12-03 08:42 | 320
26INR0516 | Large | Jade Flash Storage | Battery Storage | Scurry | 2025-12-03 10:20 | 320
26INR0518 | Large | Radian Storage II | Battery Storage | Brown | 2025-12-03 10:51 | 320
25INR0284 | Large | Railway BESS | Battery Storage | Rusk | 2025-12-04 16:58 | 254.8
20INR0043 | Large | Gulf Wind 2 | Wind | Kenedy | 2025-12-22 15:29 | 226.5
29INR0091 | Large | Bandana Storage SLF | Battery Storage | Jim Wells | 2026-01-02 13:48 | 0
29INR0090 | Large | Bandana Solar SLF | Solar | Jim Wells | 2026-01-20 11:40 | 86.9
27INR0080 | Large | Pecos Storage Center | Battery Storage | Pecos | 2026-02-09 14:06 | 200.8
24INR0249 | Large | Hickerson BESS | Battery Storage | Bosque | 2026-02-26 10:52 | 0
24INR0109 | Large | Oriana BESS | Battery Storage | Victoria | 2026-03-06 14:38 | 60.3
23INR0093 | Large | Alila Solar | Solar | San Patricio | 2026-03-13 09:14 | 256.5
23INR0261 | Large | Dodd Solar I | Solar | Henderson | 2026-04-17 09:41 | 201.8
29INR0151 | Large | Juanita Creek BESS | Battery Storage | Matagorda | 2026-04-21 10:12 | 303.6
28INR0194 | Large | Tapaderos Solar | Solar | Young | 2026-04-23 15:14 | 301.6
28INR0196 | Large | Tapaderos Storage | Battery Storage | Young | 2026-04-23 15:14 | 207
27INR0087 | Large | Tumbleweed Storage | Battery Storage | Borden | 2026-05-01 11:30 | 507.2
27INR0086 | Large | Tumbleweed Solar | Solar | Borden | 2026-05-01 11:30 | 613.89
24INR0247 | Large | Lacy Creek Energy Storage SLF | Battery Storage | Glasscock | 2026-05-07 14:56 | 0
28INR0132 | Large | River Boat Solar | Solar | Mitchell | 2026-05-14 16:28 | 502.2
23INR0187 | Large | Leitrim 1 Solar | Solar | Hill | 2026-05-20 13:51 | 98.44
29INR0122 | Large | Sundance Solar | Solar | Knox | 2026-05-21 16:29 | 301
25INR0109 | Large | Sun Cactus Solar | Solar | Duval | 2026-05-26 08:51 | 120.63
21INR0326 | Large | Dove Run Solar | Solar | Duval | 2026-05-28 17:16 | 120.86
27INR0516 | Large | Paolo Sole Hamilton Solar | Solar | Hamilton | 2026-06-02 08:54 | 40.63
27INR0515 | Large | Paolo Sole Gustine Solar | Solar | Comanche | 2026-06-02 08:54 | 40.34
23INR0211 | Large | Rosscommon Solar | Solar | Lamar | 2026-06-02 11:07 | 91
28INR0351 | Large | River Boat Power Gas Plant | Gas | Mitchell | 2026-06-04 17:49 | 334.36
25INR0134 | Large | Hoskins Solar | Solar | Lamar | 2026-06-11 13:37 | 204.12
28INR0133 | Large | River Boat Storage | Battery Storage | Mitchell | 2026-06-29 09:45 | 207.02
27INR0519 | Large | Wagyu BESS SLF | Battery Storage | Brazoria | 2026-07-10 12:37 | 120.55
24INR0182 | Large | DeSpain Solar Project | Solar | Kinney | 2026-08-03 09:30 | 236.17
26INR0543 | Large | Three Canes Solar | Solar | Navarro | 2026-08-03 10:15 | 334.5
21INR0414 | Large | Jayhawk Solar | Solar | Mitchell | 2026-08-07 09:07 | 101.5
28INR0240 | Large | Dahlia Solar | Solar | La Salle | 2026-08-10 10:09 | 200.98
28INR0241 | Large | Dahlia BESS | Battery Storage | La Salle | 2026-08-10 10:10 | 102.77
28INR0293 | Large | Dart Energy Storage A1 | Battery Storage | Taylor | 2026-08-13 10:44 | 50
27INR0350 | Large | Saddle Horn Station BESS SLF | Battery Storage | Comanche | 2026-09-04 13:57 | 177.41
27INR0351 | Large | Saddle Horn Station Solar SLF | Solar | Comanche | 2026-09-04 13:59 | 174.64
27INR0228 | Large | Sunlit Pines BESS SLF | Battery Storage | Nacogdoches | 2026-09-08 09:35 | 208.12
27INR0226 | Large | Sunlit Pines Solar SLF | Solar | Nacogdoches | 2026-09-08 09:35 | 206.71
25INR0555 | Large | Stargazer Solar | Solar | Brazoria | 2026-09-14 13:07 | 157.7
25INR0556 | Large | Stargazer BESS | Battery Storage | Brazoria | 2026-09-14 13:07 | 104.5
26INR0196 | Large | Realitos Solar SLF | Solar | Duval | 2026-09-24 10:14 | 150.49
26INR0195 | Large | Realitos Storage SLF | Battery Storage | Duval | 2026-09-24 10:15 | 0
28INR0101 | Large | Vazlon Solar SLF | Solar | La Salle | 2026-09-29 09:50 | 211.41
28INR0104 | Large | Vazlon BESS SLF | Battery Storage | La Salle | 2026-09-29 09:50 | 0
26INR0544 | Large | Signal Hill BESS I | Battery Storage | Wichita | 2026-09-30 13:35 | 122.78
27INR0118 | Large | Grapefruit Solar | Solar | Hidalgo | 2026-09-30 14:59 | 291.4
29INR0026 | Large | Skeeter Solar | Solar | Jones | 2026-09-30 15:03 | 251
* Includes only those projects designated as Inactive by ERCOT or the project developer after the developer makes a Full Interconnection Study (FIS) request, or
in the case of Small Generators, after their Resource Registrations have been approved.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.

## Cancellation Update
Projects Cancelled by the Developer during September 2026*
INR | Size Category | Project Name | Fuel | County | Cancel Date | MW **
24INR0459 | Large | Exodus BESS | Battery Storage | Caldwell | 2026-09-01 10:18 | 201.36
27INR0272 | Large | EMPower Odessa (TEF - Due Diligence) | Gas | Ector | 2026-09-03 | 122.8
29INR0162 | Large | Wolf Bone North Energy Center (OLD) | Gas | Reeves | 2026-09-04 14:38 | 1204
20INR0029 | Large | Lutum Wind | Wind | Clay | 2026-09-14 | 241.5
23INR0204 | Large | GALVANIC BESS | Battery Storage | Kinney | 2026-09-14 14:31 | 100
24INR0121 | Large | PHOTO BESS 1 | Battery Storage | Uvalde | 2026-09-14 14:32 | 75
24INR0122 | Large | PHOTO BESS 2 | Battery Storage | Uvalde | 2026-09-14 14:32 | 150
24INR0380 | Large | Photo BESS 3 | Battery Storage | Uvalde | 2026-09-14 14:33 | 100
23INR0206 | Large | PEREGRINE BESS | Battery Storage | Goliad | 2026-09-14 14:33 | 150
25INR0078 | Large | Peregrine BESS 2 | Battery Storage | Goliad | 2026-09-14 14:33 | 150
25INR0194 | Large | Photo Solar 1 | Solar | Uvalde | 2026-09-14 14:34 | 150
25INR0195 | Large | Photo Solar 2 | Solar | Uvalde | 2026-09-14 14:34 | 300
23INR0205 | Large | SUNSETTER BESS | Battery Storage | Uvalde | 2026-09-14 16:27 | 100
21INR0380 | Large | Charolais Solar | Solar | Matagorda | 2026-09-14 16:27 | 261.63
23INR0168 | Large | Charolais Storage | Battery Storage | Matagorda | 2026-09-14 16:28 | 150
22INR0266 | Large | Creekfield Solar | Solar | Fort Bend | 2026-09-14 16:28 | 161.34
22INR0379 | Large | Creekfield Storage | Battery Storage | Fort Bend | 2026-09-14 16:28 | 69
21INR0349 | Large | Pearl Crescent Solar | Solar | Colorado | 2026-09-14 16:28 | 208.35
21INR0470 | Large | Pearl Crescent Storage | Battery Storage | Colorado | 2026-09-14 16:28 | 50.26
22INR0244 | Large | Razorbill Solar | Solar | Matagorda | 2026-09-14 16:29 | 240
22INR0382 | Large | Razorbill Storage | Battery Storage | Matagorda | 2026-09-14 16:29 | 120
28INR0113 | Large | Axis Ridge Wind | Wind | Sutton | 2026-09-16 13:27 | 392
25INR0057 | Large | Sombrero Solar | Solar | Schleicher | 2026-09-17 | 351.85
24INR0381 | Large | Alexandrite Storage | Battery Storage | Cameron | 2026-09-23 14:14 | 203
30INR0163 | Large | Starlight Storage 2 | Battery Storage | Mills | 2026-09-25 | 104.3
23INR0181 | Large | Starling Storage | Battery Storage | Gonzales | 2026-09-25 10:47 | 63.6
* Includes only those projects cancelled by the developer after it makes a Full Interconnection Study (FIS) request, or in the case of Small Generators, after the Resource Registrations have been approved.
** The megawatt capacities for projects identified as repowering are reported on a net change basis with respect to the original capacity amount, and thus may
have zero or negative values. For projects where increased self-serve load is part of the interconnection studies, the reported capacity is the maximum net MW
available to the grid.